Terms of Reference 
UN Sustainable Development Cooperation Framework 2022-2026 in Thailand

Evaluation
(Updated 14 May 2025)

# 1. Introduction

The United Nations Sustainable Development Cooperation Framework 2022–2026 is the central instrument guiding the collaboration between the United Nations Country Team (UNCT) and Thailand. As a key mechanism for advancing the 2030 Agenda for Sustainable Development, the Cooperation Framework represents a collective commitment to supporting Thailand’s efforts to address its development challenges while ensuring inclusivity and sustainability.

In line with international evaluation norms, including the United Nations Evaluation Group (UNEG) Guidelines for the Evaluation of the United Nations Sustainable Development Cooperation Framework, this final evaluation will review the framework's implementation progress, effectiveness, efficiency and alignment with national priorities. The evaluation will assess the Cooperation Framework’s contributions to Thailand’s strategic goals and identify lessons learned to inform future programming and partnerships.

This evaluation will be participatory and consultative, involving stakeholders at all levels—government agencies, civil society, the private sector, and beneficiaries. Through this inclusive process, the evaluation aims to provide actionable insights, foster transparency, and promote learning among key stakeholders, ensuring the UN’s continued relevance and impact.

## 1.1 Background on Country Development Context

Thailand, an upper-middle-income country, has made significant strides in its development but continues to face challenges that require sustained attention. Its economy, driven by tourism, exports, and agriculture, has shown resilience, but vulnerabilities such as high household debt, declining exports, and global uncertainties remain of concern. Economic growth, projected to average 2.8% in 2025, reflects a slowing pace.

### 1.1.1 Social Development and Inequality

Thailand has made progress in advancing social inclusion, as evidenced by the legal recognition of marriage equality in 2025, making it the first country in Southeast Asia to achieve this milestone. However, social inequality remains a challenge, with disparities in income distribution and access to opportunities between urban and rural areas. Thailand also grapples with relatively low education performance compared to regional peers, impacting its human capital development and competitiveness. Efforts to improve equitable access to quality education, essential health services, and reduce the urban-rural divide are key areas for ongoing intervention

### 1.1.2 Environmental Sustainability

Thailand faces environmental challenges related to climate change, air quality, and plastic waste. The impacts of climate change, including rising temperatures, extreme weather events, and flooding, posing risks to the country’s agriculture, infrastructure, and livelihoods. Air pollution, especially particulate matter (PM 2.5), remains an issue in urban centers and northern regions during the burning season, affecting public health. Additionally, the country generates large quantities of plastic waste, with inadequate recycling infrastructure exacerbating pollution in rivers and coastal areas. Addressing these challenges requires climate adaptation measures, improved air quality management, and promoting sustainable waste management practices to support long-term environmental resilience.

### 1.1.3 Governance & Fiscal Challenges

Thailand faces governance and fiscal challenges that impact its development trajectory. A key issue is fiscal stress, driven by a relatively low tax-to-GDP ratio, which remains below the regional average. This limits the government’s capacity to fund some public services and invest in infrastructure and human capital. Addressing inefficiencies in tax revenue collection, including broadening the tax base and tackling tax evasion, would support fiscal sustainability and enhancing public sector resources.

Malpractice continues to be a challenge, undermining public trust, weakening governance effectiveness, and deterring investment. Strengthening transparency, enforcing anti-corruption measures, and improving accountability would bolster institutional credibility and foster inclusive development.

## 1.2 Background

The Cooperation Framework 2022–2026 outlines the UN’s strategic partnership with the government to support the country’s sustainable development priorities. It is aligned with the 20-Year National Strategy (2018–2037), the 13th National Economic and Social Development Plan (NESDP), and the Sustainable Development Goals (SDGs). This evaluation aims to assess the progress, achievements, and lessons learned from the Cooperation Framework’s implementation, ensuring accountability, and providing strategic insights for future programming.

The Cooperation Framework is focused on priority areas that contribute to the long-term vision of Thailand becoming a high-income, sustainable, and resilient nation. It was developed through extensive stakeholder consultations, ensuring that diverse voices—including those of civil society, academia, the private sector, and vulnerable groups—were represented. The Cooperation Framework emphasizes the UN’s guiding principles of leaving no one behind, the human rights-based approach, gender equality, sustainability, and resilience.

It is structured around three Strategic Outcomes and six Outputs (focus areas), where the UN has a comparative advantage in supporting development efforts.

### 1.2.1 Strategic Outcomes

- Green, Inclusive Economy
Accelerate Thailand’s transformation into a green, resilient, low-carbon economy by promoting sustainable growth, fostering innovation, and enhancing climate resilience.

- Human Capital Development and Digital Transformation
Strengthen human capital through improved access to quality education, healthcare, and social protection, while fostering digital transformation to promote inclusive participation in the digital economy.

- Good Governance and Leaving No One Behind
Promote good governance, transparency, and the rule of law, while ensuring that marginalized and vulnerable populations are empowered to participate in and benefit from development.

### 1.2.2 Cooperation Framework Outputs (Focus Areas)

- Inclusive and Sustainable Economic Growth
Support Thailand’s transition to a high-value, green economy by fostering innovation, sustainable production, and responsible investment aligned with the Bio-Circular-Green Economy model.

- Climate Action and Disaster Resilience
Strengthen national capacities for climate mitigation, adaptation, and disaster resilience, ensuring environmental sustainability and biodiversity conservation.

- Improved Quality of Public Services
Enhance access to and quality of public services—including healthcare, education, and social protection—ensuring responsiveness to the needs of all, particularly vulnerable populations.

- Digital Transformation and Inclusion
Promote digital literacy, infrastructure development, and technological innovation to bridge the digital divide and foster inclusive participation in the digital economy.

- Enhanced Social Protection and Equality
Expand social protection systems and address inequalities by focusing on vulnerable groups, including women, children, the elderly, and migrant populations.

- Strengthened Governance and Rule of Law
Foster good governance by strengthening institutions, promoting human rights, enhancing transparency and accountability, and supporting inclusive, participatory decision-making.

These strategic outcomes and outputs support Thailand in its ambition to become a high-income, inclusive, and sustainable nation. The framework is being implemented through collaborative efforts with government and development partners, ensuring that effective monitoring and accountability mechanisms are in place.

More detailed information on the Cooperation Framework’s implementation are the Cooperation Framework 2022-2026, Annual Results Reports 2022-2024 found at this link, and the Joint Work Plan and Funding Framework on the UNINFO website

# 3. Purpose and Objectives of the Evaluation

## 3.1 Purpose

An external final evaluation will be conducted through an independent consultancy during its penultimate year of implementation. The evaluation will assess the relevance, coherence, effectiveness, efficiency, orientation towards impact, and sustainability while ensuring alignment with the principles of Human Rights, Gender Equality, and Leaving No One Behind (LNOB).

The evaluation serves two primary purposes:

- Promote greater learning and operational improvement: The evaluation will identify areas for enhancing programming and delivering results in the country. Findings will inform planning and decision-making for the next programming cycle and strengthen UN coordination. This process will provide valuable lessons learned, which can also be shared with the Development Coordination Office to benefit other countries.

- Support greater UNCT accountability: By providing objective evidence of results achieved within the Cooperation Framework assessing the effectiveness of strategies and interventions, the evaluation will enhance accountability to key stakeholders, including the government, national counterparts, and development partners.

The evaluation will move beyond a narrow focus on programmatic outputs and outcomes to assess the broader performance of the Cooperation Framework in addressing complex development challenges. This considers systemic, strategic, and contextual factors, enabling the evaluation to analyze critical aspects such as system-wide UN coordination, long-term impacts on resilience and sustainability, and alignment with national priorities, regional frameworks, and SDG commitments.

A system-level analysis ensures actionable and relevant lessons that inform the Cooperation Framework, foster innovation, and strengthen alignment with the evolving development needs. By focusing on the interconnectedness of interventions and their long-term impacts, the evaluation will generate meaningful insights to enhance the effectiveness, coherence, relevance and sustainability of UN contributions.

## 3.2 Objectives

The evaluation will focus on the following key objectives:

- Assess the Contribution of the Cooperation Framework to National Development Results through Evidence-Based Judgments
Evaluate the extent to which the Cooperation Framework contributed towards national development priorities and SDG commitments, using evaluation criteria of relevance, coherence, effectiveness, efficiency, sustainability, and orientation toward impact. This assessment will also consider cross-cutting issues, such as gender equality, human rights, and non-discrimination, including disability inclusion, and LNOB.

- Identify Factors Affecting the Cooperation Framework Contribution
Examine the key factors—such as institutional, operational, financial, and contextual elements—that have influenced the achievement of results. The evaluation will explore why performance unfolded as it did, highlighting systemic enablers, bottlenecks, and opportunities for improvement.

- Draw Conclusions on the UN’s Contributions to National Development
Synthesize the evaluation findings to provide clear, evidence-based conclusions about the collective contributions of the UN development system. This includes evaluating the overall coherence and added value of the UN’s efforts in addressing development challenges.

- Provide Actionable Recommendations for Future Programming
Generate actionable recommendations to inform the design and implementation of the next programming cycle. These recommendations will incorporate lessons learned to improve coordination, enhance systemic impacts, and address evolving development needs.

# 4. Scope of the Evaluation

## 4.1 Focus of the Evaluation

The evaluation will cover all UNCT programmes implemented in Thailand during the Cooperation Framework 2022–2026. The evaluation will focus on assessing the collective contributions of the UN system to the Cooperation Framework Outcomes, emphasizing relevance, coherence, efficiency, effectiveness, impact, and sustainability.

The evaluation will not assess individual programs or activities of UN agencies. The evaluation team may propose specific thematic areas for deeper analysis based on consultations with stakeholders. It will also examine how evaluated programs contribute to advancing Thailand’s SDG targets, with a focus on cross-cutting issues such as i.e. gender equality and women’s empowerment, human rights and non-discrimination, disability inclusion and environmental sustainability, among others.

The evaluation will explore humanitarian actions undertaken during the review period, with a focus on COVID-19 responses, disaster risk reduction activities, and humanitarian support for refugees, displaced persons, and children on the move. Efforts to ensure their protection, access to vital services, and integration into development frameworks will be examined. The assessment will also review contributions from signatory agencies without formal country programs, non-resident agencies, and initiatives under global or regional programmes, while incorporating an analysis of regional and cross-border elements.

## 4.2 Priority Outputs and Activities

The Evaluation Manager and Independent External Evaluators, in consultation with the Evaluation Steering Committee, may prioritize specific outputs and activities. This prioritization will ensure a balanced assessment of the breadth and depth of UN contributions, considering the scope of work, data availability, and the overall development landscape.

## 4.3 Geographic Scope

UN agencies operate across all regions of the country. The evaluation will take a national perspective while considering geographic representation, focusing on areas where UN support has a significant presence. Budgetary considerations and data availability will guide the selection of focus areas for geographic analysis during the inception phase.

## 4.4 Timeframe

The evaluation will cover the period of 2022–2026, with a focus on activities conducted between January 2022 and Q1 2025.

## 4.5 Key Users and Intended Use

The primary users of the evaluation include the UNCT, the Government, and key development partners. Secondary users include line ministries, civil society organizations, and other stakeholders. The evaluation findings will be used to:

- Establish accountability and learning from the Cooperation Framework 2022–2026 to inform the new Framework for 2027–2031.

- Strengthen UN coordination and strategic alignment with development priorities.

- Provide evidence-based recommendations to guide the design of new UN programs and strategies.

# 5. Evaluation Criteria and Questions

The evaluation will apply the following criteria, with additional emphasis on coordination. Below are brief definitions of the criteria:

- Relevance and Adaptability: Assesses the extent to which the Cooperation Framework aligns with  national priorities, policies, and needs, including the SDGs, and whether it addresses emerging challenges and opportunities.

- Coherence: Examines the consistency and compatibility of Cooperation Framework objectives and interventions with other development efforts, including the alignment between UN agencies, national partners, and other stakeholders.

- Effectiveness: Evaluates the extent to which the strategic outcomes and outputs have been achieved and identifies the factors contributing to or hindering success.

- Efficiency: Analyzes the extent to which resources (human, financial, and technical) have been used in the most cost-effective way to deliver results.

- Orientation Towards Impact: Measures the significant, longer-term changes—positive or negative—that can be attributed to Cooperation Framework interventions, particularly for marginalized and vulnerable populations.

- Sustainability: Assesses the likelihood that the benefits and results of the Cooperation Framework will continue after the framework's conclusion, examining institutional, financial, and community-level mechanisms for maintaining progress.

- Coordination: Focuses on how effectively UN agencies have collaborated and coordinated their efforts with each other, the Government, and other partners to achieve joint results and maximize efficiency.

The Independent External Evaluators may adapt the evaluation criteria, questions, and matrix upon agreement with the Evaluation Manager and the Evaluation Steering Committee. The final evaluation questions and evaluation matrix will be finalized in the inception report, incorporating feedback from the Evaluation Manager and the Evaluation Steering Committee. The list of indicative evaluation questions based on evaluation criteria can be found below.

| Relevance | - To what extent is the Cooperation Framework aligned with national priorities, including the 20-Year National Strategy and the NESDP? - Are the objectives and activities responsive to the evolving needs and priorities of vulnerable populations, including women, children, youth, persons with disabilities, migrants, refugees, ethnic minorities, People Living with HIV, LGBTIQ, and other LNOB groups? |
| --- | --- |
| Coherence (mandatory) | - Post UN reform, to what extent have UN agency programs and work plans been effectively and meaningfully derived from the CF both in design and implementation? For agencies with existing programming instruments, assess the type of derivation applied amongst the 3 Options for country programming instrument derivation . - To what extent are the UN’s interventions coherent with the efforts of the Government and other stakeholders, such as civil society, academia, and the private sector? - How effectively does the Cooperation Framework leverage partnerships to promote integrated sustainable development? |
| Effectiveness | - To what extent the CF interventions contributed to, or is likely to contribute to, the CF outcomes and outputs? - How effectively has the UN system addressed cross-cutting issues, such as inclusive participation of women, LGBTI individuals, persons with disabilities, ethnic minorities, and other vulnerable groups? |
| Efficiency | - To what extent have coordination mechanisms helped reduce inefficiencies and improved resource utilization? - Are there specific processes or practices that could enhance the cost-effectiveness of implementation? |
| Orientation Towards Impact | - What significant changes have resulted from Cooperation Framework interventions, especially for the most vulnerable populations? - How have the UN’s actions influenced policy or structural changes in Thailand that support sustainable development? |
| Sustainability | - Are there mechanisms in place to ensure the continuation and scaling of successful initiatives? - How well does the Cooperation Framework promote local ownership and capacity-building to ensure long-term sustainability? |
| Coordination (mandatory) | - To what extent did the post reform Resident Coordinator office’s roles and responsibilities enable positive UNCT’s joint convening power and better coherence of the country team? - Is innovation applied to coordination that could enhance the impact of the Cooperation Framework? |

# 6. Evaluation Methodology

The evaluation will employ a rigorous methodology to assess the Cooperation Framework’s relevance, coherence, effectiveness, efficiency, sustainability, and impact. The methodology will be based on a mixed-methods, integrating quantitative and qualitative data collection and analysis to ensure a thorough and balanced assessment of Cooperation Framework performance and contributions. This will provide evidence-based insights to inform decision-making and enhance future Cooperation Frameworks.

The Evaluation Team will develop the methodology to collect appropriate disaggregated data and information as strong, evidence-based answers to the overall evaluation questions. The methodology will account for the needs of the evaluation’s different socio-economic groups of beneficiaries. The methodological design will include sampling, participation and inclusion strategies, theory of change analysis and reconstruction, data collection tools, the evaluation matrix, data collection strategy, data quality assurance (control and validation), data analysis, and reporting, including data provided via UN Info.

This methodology is designed to be participatory, inclusive, and gender-responsive, adhering with UNEG Norms and Standards for Evaluation and the Guidelines for the Evaluation of the United Nations Sustainable Development Cooperation Framework.

In addition, the evaluation will adhere to:

- the UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluations (2014),

- the UN Women Evaluation Handbook on How to Manage Gender-Responsive Evaluation (2015),

- the UN-SWAP 2.0 Framework and Technical Guidance (2023),

- the Guidance on Integrating Disability Inclusion in Evaluations and Reporting on the UNDIS Entity Accountability Framework Evaluation Indicator, and

- the UNEG Good Practices for Integrating Gender Equality and Human Rights in Evaluation (2017).

## 6.1 Evaluation Matrix

The evaluation will utilize an evaluation matrix to systematically align key questions with criteria, data sources, and methods of analysis. The matrix will serve as a guiding framework to ensure consistency and rigor. It will be finalized during the inception phase through consultation with stakeholders. The matrix will include key evaluation questions, indicators to assess progress and effectiveness, data sources such as documents, interviews, surveys, and methods for data collection and analysis.

## 6.2 Conceptual and Analytical Framework

The Theory of Change will guide the analysis of how UN interventions align with and contribute to national development priorities and SDGs. If necessary, the Theory of Change will be reconstructed to reflect changes or adaptations made during the implementation period.

The analysis will focus on the following:

- Descriptive Analysis: Summarizing key findings to provide clear narratives of performance and outcomes.

- Contribution Analysis: Assessing the plausible  contribution of interventions to observed outcomes.

- Triangulation: Cross-verifying data from multiple sources to enhance reliability and validity.

## 6.3 Data Collection

The evaluation will integrate a variety of data collection methods to capture both quantitative and qualitative information. Data collection and analysis methods will be human rights based and gender sensitive. Key methods will include:

- Document Review: This will involve analyzing Joint Work Plans, progress reports, evaluations, and national strategies to gain an understanding of the interventions’ context and objectives.

- Key Informant Interviews (KIIs): Semi-structured interviews will be conducted with government representatives, UN agencies, development partners, and civil society stakeholders to gather contextual and nuanced insights.

- Focus Group Discussions (FGDs): Discussions will be held with targeted beneficiary groups, especially marginalized populations, to capture diverse perspectives on the impact and relevance of the interventions.

- Surveys: Structured surveys will be used to gather quantitative data and broader stakeholder feedback on performance and outcomes.

- Field Visits: On-site observations in selected areas will validate findings and contextualize implementation challenges, providing a direct understanding of local realities.

- Case Studies: In-depth case studies of selected interventions to highlight best practices and lessons learned.

- Secondary Data Analysis: Statistical and programmatic data from existing sources will be reviewed to complement primary data collection efforts, e.g. project evaluations, agency-specific evaluations, CF mid-term review, etc.

This mixed-methods ensures that the evaluation captures diverse perspectives and provides a holistic understanding of the Cooperation Framework’s performance.

## 6.4 Sampling

A purposive sampling will be used to select programs and stakeholders for inclusion in the evaluation. This will ensure that interventions with significant transformational intent, maturity, and diversity are captured. The sampling criteria and process will be clearly outlined, addressing any potential biases, and ensuring adequate representation of stakeholders.

## 6.5 Participation and Inclusion

The evaluation will be participatory and inclusive, ensuring that diverse voices are represented, particularly those of marginalized and vulnerable groups. Stakeholder mapping will identify key actors, including UN agencies, national government representatives, civil society organizations, and beneficiaries, to ensure that the evaluation reflects a wide range of perspectives. This includes systematically disaggregated by sex and age and, to the extent possible, by geographical region, ethnicity, disability, migratory status and other contextually relevant markers of equity.

## 6.6 Quality Assurance

Rigorous quality assurance will be applied to ensure reliability of findings. Triangulation will be used to cross-verify data from multiple sources, and the evaluation team will maintain close communication with UNCT implementation entities at the country level to validate data and insights.

## 6.7 Limitations

While the evaluation methodology is designed to be robust, certain limitations are anticipated. These include potential data gaps due to limited availability or access to program-specific information, challenges in conducting extensive field visits or stakeholder engagements due to time and logistical constraints, and difficulties in isolating the effects of interventions from other influencing factors.

To address these challenges, the evaluation will use triangulation to validate findings across multiple sources, prioritize data collection methods that are efficient and accessible, and maintain a clear focus on assessing contributions rather than attempting to establish direct attribution. These measures will help ensure the credibility and reliability of the evaluation findings while remaining practical and actionable.

# 7. Governance and Evaluation Management

## The key governance bodies of the CF Evaluation consist of the following:

- Evaluation Steering Committee (ESC)

- Resident Coordinator (RC)

- Evaluation Manager (EM)

- Evaluation Management Technical Team (EMTT)

- Resident Coordinator’s Office (RCO)

- Evaluation Team (ET)

- Development Coordination Office (DCO)

- UN Evaluation Group (UNEG)

- United Nations Evaluation Development Group (UNEDAP)

## 7.1 Governance and Evaluation Management Mechanism key functions

The Evaluation Steering Committee (ESC) is made up of the Heads of UNDP, UNFPA and UNICEF (as CPD UN entities), in consultation with the Ministry of Foreign Affairs and the Office of the National Economic and Social Development Council (Planning Ministry). It will ensure that the evaluation remains aligned with national development priorities and the objectives. The Evaluation Steering Committee will:

- Approve the evaluation’s terms of reference, inception report, and final report.

- Provide high-level oversight and guidance to ensure the evaluation’s relevance and quality.

- Facilitate stakeholder engagement and ensure alignment with national and UN priorities.

- Support the dissemination and use of evaluation findings and recommendations.

Resident Coordinator (RC) commissions the CF evaluation, designates the Evaluation Manager, supports all processes, provides comments to key products, and leads the preparation of the management response document. The RC is supported by the RCO and works in coordination with the UNCT when necessary.

Evaluation Manager (EM) oversees the entire process of the evaluation, from its preparation to the dissemination and use of the final evaluation report, providing quality assurance for all evaluation outputs, ensuring adherence to UNEG norms and standards.

Evaluation Management Technical Team (EMTT) consists of the UNCT designated focal points, including from the Data & Results Reporting Group and other programme technical experts to provide routine day-to-day technical support to the EM and ensures sound technical review for all the evaluation deliverables.

Resident Coordinator’s Office (RCO): The RCO is Data Management Officer (DMO) serving as the focal point for the CF Evaluation, delivers technical and coordination support to the RC and EM in their evaluation roles. The RCO will facilitate communication and data sharing between the evaluation team and the Evaluation Steering Committee. It will organize stakeholder consultations and validation workshops to foster inclusivity and engagement across the UNCT and partners.

Evaluation Team (ET) comprises independent external evaluators to conduct the CF Evaluation. The CF Evaluation Team will consist of 2 consultants (1 International and 1 National evaluator). The ET abides by the UNEG Code of Conduct for carrying out the evaluations. See Section 7.2 Composition of the Evaluation Team for further details on the evaluation team.

Development Coordination Office (DCO-HQ) oversees and supports the CF Evaluation process, approves the evaluation TOR and the selection of Evaluation Team, as well as backstops the Evaluation Manager when necessary.

UN Evaluation Development for Asia and the Pacific (UNEDAP) provides technical advice to the CF evaluation and facilitates the coordination of agency evaluations and joint evaluations, to the extent possible, as inputs to the CF evaluations.

## 7.2 Composition of the Evaluation Team

The evaluation team will comprise of one international and one national evaluator, and in alignment with the Assessment tool for I&N Consultants_CF_Evaluation.xlsx. The international evaluator should possess the following qualifications:

| Education | - Advanced university degree in political science, economics, public administration, development studies, or another relevant field. |
| --- | --- |
| Experience | - At least 10 years of proven experience in leading complex evaluations at the international level, including evaluations of UNDAF/ Cooperation Framework’s or UN agency country programs. - Strong expertise in SDGs and UN programming principles, including Leave No One Behind, the human-rights-based approach to development, gender equality and women’s empowerment, disability inclusion, meaningful youth engagement, environmental sustainability, and resilience. - Demonstrated experience in designing and implementing evaluations using mixed methods (quantitative and qualitative). - Solid understanding of political economy, financing for development, and socio-economic and geopolitical analysis. - Previous experience in facilitating multi-stakeholder consultations, including government, civil society, and development partners. - Knowledge of the UN reform process and UN programming at the country level. |
| Competencies | - Excellent analytical and problem-solving skills with the ability to synthesize complex information. - Demonstrated managerial competence and experience in organizing, leading, and coordinating evaluation teams. - Strong communication and facilitation skills, with cultural, gender, religion, race, nationality, and age sensitivity. - Proven ability to deliver high-quality reports on time. |
| Language Requirements | - Excellent command of English. |

The national evaluator should possess the following qualifications:

| Education | - Advanced university degree in political science, economics, public administration, development studies, or another relevant field. |
| --- | --- |
| Experience | - At least 5 years of proven experience in supporting or leading research or evaluations, with a strong preference for experience in evaluating UNDAF/ Cooperation Framework or UN agency country programs. - In-depth knowledge of SDGs and UN programming principles, including LNOB, the human-rights-based approach, gender equality, disability inclusion, youth engagement, environmental sustainability, and resilience. - Proven ability to collect and analyze data using appropriate methods and tools, including qualitative and quantitative techniques. - Track record of research and analysis related to the country’s socio-economic development, geopolitical context, and environmental challenges. - Experience in facilitating stakeholder engagement, including organizing workshops and meetings. |
| Competencies | - Strong process management and organizational skills. - Technical competence in conducting complex research or evaluations using mixed-methods. - Excellent time management skills and ability to deliver high-quality outputs on schedule. - Knowledge of the UN role, UN reform process, and UN programming at the country level. |
| Language Requirements | - Excellent command of English and Thai. |

Drawing on their comprehensive knowledge of the local context, the National Evaluator plays a key role in the evaluation process by conducting data collection and analysis, including desk reviews, interviews, and field visits. The National Evaluator is required to be physically present in the country throughout the entire evaluation process. Their responsibilities include providing substantive contributions to the inception report, presenting preliminary findings, and supporting the preparation of both the draft and final evaluation reports.

# 7.3 Selection process

The evaluator selection process will follow the procurement rules and regulations of the contracting entity. To ensure independence, value for money and transparency, the process must follow the principle of open and competitive recruitment. Contracts should be based on level of effort. The selection panel should include the DCO Evaluation Advisor, RC, and two Heads of Agencies.

# 7.4 Sources of recruitment

To enhance fairness and demonstrate transparency, multiple channels will be used to disseminate the recruitment call, such as the UN Evaluation Group, the Development Evaluation Association (IDEAS), the International Organization for Cooperation in Evaluation (IOCE), etc.

# 8. Deliverables

- Inception Report and Presentation: Outlining the evaluation methodology, and work plan.

- Preliminary Findings Presentation: A briefing to present initial findings and gather feedback.

- Draft Evaluation Report: A comprehensive report detailing findings, conclusions, and recommendations.

- Final Evaluation Report: Incorporating feedback from stakeholders.

- Evaluation Brief: A summary of key findings and recommendations.

# 9. Timeline

The evaluation will follow an indicative timeline to ensure the systematic progression of activities, from recruitment to final report submission. The timeline outlines the key phases of the evaluation process:

| Activity | Timeline |
| --- | --- |
| Recruitment of Evaluation Team | May - June 2025 |
| Inception Phase | June 2025 |
| Data Collection | June - July 2025 |
| Analysis and Draft Report | August - Sept 2025 |
| Validation Workshop | Sept 2025 |
| Final Report Submission | Sept 2025 |

# 10. Payment

Payment will be linked to the successful completion and approval of deliverables as outlined below. Payments will be made upon submission of deliverables, approval by the Evaluation Steering Committee, and verification of the quality and completeness of the outputs.

| No. | Deliverables/Outputs | Target Due Dates | Payment |
| --- | --- | --- | --- |
| 1 | Approval of the inception report | TBC | 20% |
| 3 | Approval of the preliminary evaluation report, including an executive summary, infographics, and an evaluation brief | TBC | 40% |
| 4 | Approval of the final evaluation report, including an executive summary, infographics for publication, an evaluation brief, and a PowerPoint presentation for stakeholder dissemination | TBC | 40% |

#### Additional Information

- The Level of Effort for the Team Leader will be 35 days, and for the National Consultant it will be 25 days.

- This is calculated based on actual days worked and is not equivalent to calendar days. The contract will be based on payment against approved deliverables.

- The evaluation is expected to commence in Q1 2025 and conclude within six months, including the submission of the final report. Timely submission of high-quality outputs will be prioritized, with the final proofread and fully formatted report to be completed within one month after the draft report is finalized and approved.

All deliverables must meet UNEG norms and standards, ensuring clarity, accuracy, and usefulness. Adjustments to timelines or payments may be considered based on unforeseen circumstances, subject to approval by the Evaluation Steering Committee.

# 11. Application

Interested candidates are invited to submit documents demonstrating their qualifications for this assignment. These should include:

| International Team Leader | - Latest CV: A detailed and updated CV highlighting relevant experience. - Sample of Previous Work: Examples of completed evaluations or other relevant outputs. - Statement of Suitability for the Assignment: A brief outline of strengths and expertise, highlighting directly relevant experiences to the assignment, including familiarity with the UN programming principles Leave No One Behind, human rights, gender equality and women’s empowerment (GEWE), environmental sustainability and resilience, and accountability). - Approach to Work/Suggested Methodology and Work Plan: A brief description of the proposed evaluation methodology and a clear work plan. - Financial Proposal: Inclusive of all costs related to the assignment, such as travel and daily subsistence allowance (DSA) for data collection within Thailand. |
| --- | --- |
| National Team Member | - Latest CV: A detailed and updated CV highlighting relevant experience. - Sample of Previous Work: Examples of completed evaluations or other relevant outputs. - Statement of Suitability for the Assignment: A brief outline of strengths and expertise, highlighting directly relevant experiences to the assignment, including familiarity with the UN programming principles (LNOB, human rights, GEWE, environmental sustainability and resilience, and accountability). - Physical Presence: Confirmation of availability to be physically present in Thailand throughout the evaluation process. - Financial Proposal: Inclusive of all costs related to the assignment. |

# 12. Administrative Issues

The consultants will be responsible for arranging their own travel within Thailand, including any associated costs. Any additional expenses beyond the scope of these Terms of Reference will not be covered. Consultants are expected to provide their own laptops and any other technical equipment necessary to complete the assignment.

All documents and outputs produced under these Terms of Reference will be treated as strictly confidential. The UN holds exclusive rights to distribute, publish, and share these documents.

# 13. Ethical Considerations

The evaluation will adhere to the UNEG ethical guidelines, ensuring respect for participants, informed consent, confidentiality, and impartiality.