## Sheet1
Country _Eswatini: UNSDCF 2021 - 2025 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Evaluation of the United Nations Sustainable Development Cooperation Framework (UNSDCF) between the Government of Eswatini and the United Nations (2021 - 2025) • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RCO, PPSG and Data & M and E team • Frequency of monitoring and updating: Bi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Foster strong ownership and buy-in for the UNSDCF by actively involving stakeholders, including government counterparts, CSOs, and other partners, from the design stage to ensure alignment with national priorities and shared accountability for its implementation.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Ensure that UNSDCF M&E framework is aligned with the national M&E and reporting structures (based on outcomes). This alignment will create a sense of ownership among government counterparts, enhancing their commitment to implementation and mutual accountability. | Quarterly | RCO, PPSG M&E Group | Quartely joint reviews with MEPD (M & E Team) | ongoing as expected | June | 2025
1.2 | Strengthen the capacity of external stakeholders to enhance their roles as co-leads and alternates of RGs. This will encourage greater ownership and engagement from external stakeholders. | Contineous | RCO, RGs Coleads | UN coleads to intentionally work with their alternates | delayed | June | 2025
Recommendation 2: Develop a comprehensive Contingency Plan to proactively address potential risks and unforeseen challenges that could disrupt the implementation of the UNSDCF, ensuring continuity and adaptability in achieving its objectives
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Conduct a comprehensive risk assessment and early warning systems to identify potential internal and external risks that could affect the successful implementation of the UNSDCF. | Contineous | DEMT | These key action to be implemented with support from OCHA, DPPA | ongoing as expected | June | 2025
Recommendation 3: Enhance the effectiveness and sustainability of the UNSDCF by ensuring that interventions are impactful, efficient, and aligned with the long-term development priorities and aspirations of the country and its people.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Strengthen collaboration with government, CSOs, private sector, and other stakeholders to ensure local ownership and alignment with national priorities, fostering sustainable change through capacity-building and integrated development approaches through periodic engagement. | Bi annually | RCO, Results Groups | This will be organised through a mid-year stakeholder engagement | ongoing as expected | June | 2025
3.2 | Focus on cost-effectiveness and impact measurement, along with regular financial reviews, to maximize outcomes and ensure efficient resource allocation in line with sustainable development goals. | Quarterly | RCO, PPSG M&E Group, Results Group Co-leads |  | ongoing as expected | June | 2025
3.4 | Enhance the M&E framework to enable course corrections, align interventions with evolving needs, and inform future programming, thus enhancing impact through continuous review and learning | Quaterly | RCO, PPSG M&E Group |  | ongoing as expected | June | 2025
RECOMMENDATIONS TO IMPROVE GOVERNANCE AND COORDINATION
Recommendation 4: Strengthen coordination mechanisms and Delivering as One (DaO) principles to ensure the effective implementation of the UNSDCF, promoting alignment, efficiency, and collaboration across stakeholders
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.2 | Clearly define the coordination roles and responsibilities of the RCO, each Results Group (RG), UN agencies and government counterparts in relation to the UNSDCF. This will reduce overlap, confusion and promote ownership. | 2025 | RCO | This has to be endorsed by UNCT | ongoing as expected | June | 2025
Recommendation 5: Strengthen the governance structures of the Cooperation Framework (CF) to ensure clear roles, accountability, and efficient decision-making processes, enhancing the overall effectiveness of CF implementation and fostering stronger collaboration among stakeholders
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Provide targeted training and capacity-building for the RCO, co-leads, and alternates of the Results Groups (RGs) and subgroups (both UN and government counterparts). This training should focus on strengthening their understanding of the UNSDCF’s strategic objectives and clarifying their roles and responsibilities in coordinating and monitoring its implementation. | Twice every year | DCO, RCO | This will based on agreed ToRs for RCO,MEPD,Co-leadand sub group chairs | delayed | June | 2025
Recommendation 6: Address the coordination gaps and challenges between the UN and government that have hindered the effectiveness and efficiency of the CF by enhancing coordination, streamlining processes, improving communication, and strengthening collaboration among key stakeholders to achieve more effective implementation.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Develop robust communication channels to facilitate regular consultations between the UN and government. Schedule periodic coordination meetings with clear agendas and action points to keep all partners informed of progress and challenges. | Quarterly | RG coleads | This can be done through analysis and feedback of RG plans and reports | ongoing as expected | June | 2025
RECOMMENDATIONS ON FINANCING
Recommendation 7: Establish a sustainable and transparent financing mechanism for the implementation of the UNSDCF, ensuring adequate resource mobilization, efficient allocation, and financial accountability to support long-term development goals and outcomes
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Develop and implement a funding framework and resource mobilization strategy to provide a structured approach to mobilizing and allocating financial resources necessary for the successful implementation of the CF. | 1st quarter of 2025 | RCO,UNCT,PPSG |  | delayed | June | 2025
RECOMMENDTAION ON RESULTS MONITORING
Recommendation 8: Strengthen Monitoring, Evaluation, and Learning (MEL) mechanisms for UNSDCF implementation by establishing robust systems to track progress, assess impact, and incorporate lessons learned. This will enhance accountability, improve decision-making, and ensure adaptive management of the Framework's interventions
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Develop a Comprehensive MEL Framework that includes a results and resources framework with SMART performance indicators, clearly defined roles and responsibilities for M&E, reporting mechanisms, timelines, and resources to ensure timely and consistent data collection, analysis, and dissemination across all UNSDCF results groups. | 1st quarter of 2025 | RCO, PPSG,M and E,Results Groups | Currently working on this | ongoing as expected | June | 2025
RECOMMENDATION ON DATA AND EVIDENCED - BASED DECISION MAKING
Recommendation 9: Enhance UNSDCF data and knowledge management systems by developing comprehensive frameworks for data collection, analysis, and sharing. This will ensure timely access to accurate information, improve decision-making, and facilitate better coordination and collaboration among stakeholders for effective implementation of the Framework
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Strengthen documentation and reporting processes to ensure that all relevant information is systematically captured and shared. | 1st quarter of 2025 | PPSG M&E Group | UNINFO | ongoing as expected | June | 2025
9.2 | Establish a repository at the RCO that consolidates all UNSDCF-related data, reports, research, and lessons learned. This platform should be accessible to all UN agencies, fostering a centralized knowledge base for easy reference and collaboration. | 2nd quarter of 2025 | RCO,UNCT,PPSG | Budget required | delayed | June | 2025
9.3 | Implement standardized data collection and reporting templates across all RGs and agencies involved in the UNSDCF. This will ensure consistency and comparability of data, improving the quality of analysis and allowing for a more accurate assessment of progress toward UNSDCF objectives. | 1st quarter of 2025 | RCO,PPSG,M & E | Standard template distributed to RCOs | completed | June | 2025
9.4 | Provide training and capacity building for M&E focal points and other key stakeholders on effective data management, analysis, and knowledge sharing to enhance the overall quality and impact of data-driven decision-making. | 2nd quarter of 2025 | RCO, PPSG M&E Group | Budget required | delayed | June | 2025

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030