## Sheet1
Country __Ukraine____________; UNPF 2018 - 2022 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Mid-term evaluation/ 2021 • Preparation of the management response: UNCT • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: UNCT and the Joint Steering Committee • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Invest in further developing RBM skills and knowledge in particular in terms of formulating results framework and identifying relevant indicators or other means of verification
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Organize RBM training for UNCT programme managers and M&E specialists as a part of the new CF development | Q2 2022 | RCO
1.2 | 18-19 January RBM/Theory of Change workshop with UNCT for CF design | Q1 2021 | UNCT, RCO
1.3 | Targeted training of RCO staff on RBM | Q1 2022 | RCO
Recommendation 2: Review the Results Framework and incorporate intermediate outcomes as the essential changes expected to be achieved at country level during the UNSDCF timeframe
Management response - Accepted/Partially Accepted/rejected : Partially Accepted
If rejected or partially accepted, please provide an explanation: UNCT to fully incorporate recommendation in next Results Framework
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | New CF to incorporate intermediate results, attribuable to UN | Q1 2022 | PMT, RCO
2.2 | Align CF intermediate results of the new CF to national/global SDG indicators | Q2 2022 | PMT, RCO
…
Recommendation 3: Keep the UNSDCF short and simple with clear definitions of the key terms used and focus on the expected programmatic outcomes
Management response - Accepted/Partially Accepted/rejected : Accepted.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Provide the consultant with examples of the UNSDCFs | q1 2022 | RCO
3.2 | Constant review of the draft CFs | q1-q2 2022 | RCO
3.3 | RBM review of the draft CF by PMT/M&E group | Q1 2022 | PMT, RCO
Recommendation 4: Consider an extended Steering Committee with GoU, development partners and possibly CSO partners that meet once a year to review and steer progress of the UNSDCF implementation
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Include relevat provision to the UNSDCF and ToR of the UNSDCF Steering Committee | 2023-2027 | RCO
4.2 | Invite CSOs and DPs to the 2022 UN-GoU Steering Committee | Q1 2022 | UNCT
Recommendation 5: Build on existing successes (gender, human rights, East) as entry points for the next UNPF
Management response - Accepted/Partially Accepted/rejected : Accepted.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Develop UNSDCF outcomes, outputs and indicators considering the main achivement of the UNPF identified by the evaluation | Q2 2022
5.2 | Integrate gender, human rights and HDPN as cross-cutting elements of all future CF outcomes | Q1 2022
…
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 6: Invest in more area-based integrated joint programmes where different actors can support a common outcome from different interventions
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Establish an indicator (per cent of JP among all CF programms) for Joint Programmes in the next UNSDCF cycle | Q4 2022 | UNCT
6.2 | Operationalise HDPN on the local level | 2022-2027
6.3
Recommendation 7: Ensure improved Information Management System (IMS) is in place with proper mapping to better inform about the collective UN achievements and support a solid communication strategy on the work of the UN in Ukraine
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Constant and accurate inputs into UN Info for joint planning and monitoring | ongoing | UNCT; Results Groups
7.2 | Develop a long-term communacation strategy for the new CF cycle | Q4 2022 | UN GAC
7.3 | Develop a partnership startegy for the new CF | 2022 | UNCT, RCO
Recommendation 8: Move from narrative and descriptive reporting (e.g., what the UN does) to what changes have or are being achieved (e.g., RBM reporting from outcome level analysis) amongst the GoU institutions and for the people of Ukraine
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Implement recommendation during development of the annual results report | annually | UNCT; Results Groups
8.2 | RBM review of the draft Report 2021 by PMT/M&E group | Q2 2022
…
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 9: Define the primary use(s) of the next UNSDCF during the upcoming retreat in November 2021 amongst UNCT
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Define the primary use(s) of the next UNSDCF during the upcoming retreat in November 2021 amongst UNCT [done] | 2021 | UNCT; PMT
9.2
…
Recommendation 10: Obtain the support of the UN regional and HQ to pilot an innovative UNSDCF based on a different architecture as suggested in this report
Management response - Accepted/Partially Accepted/rejected : Partially accepted
If rejected or partially accepted, please provide an explanation: the recommendation has been partially accepted, where it does not contradict the global CF guidance. Alternative: UNCT to attempt gaining support of regional offices and HQ to pilot an innovative UNSDCF, in line with global CF guidance.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Involve Regional DCO in CF planning reatreat [done] | 2021
10.2 | Review of the draft CF outcomes and Results framework by Peer Support Group | Q1 2022
…
Recommendation 11: Assume a risk-taking scenario where the next UNPF is more programmatically anchored on 3 or 4 key programming areas (e.g., based on existing key achievements in Ukraine), with the specific commitment and ownership from the GoU (e.g., indicating its resource commitment) and involving the development partners in supporting and funding the 3 or 4 key programming areas that are the main thrust of the UN collective contribution (but obviously not exclusive of other interventions and/or programmes)
Management response - Accepted/Partially Accepted/rejected : Partially accepted
If rejected or partially accepted, please provide an explanation: the recommendation has been partially accepted, i.e. new CF will be closely anchored on a substantive and UN-specific contribution of UNCT to Ukraine's development, without limiting the scope of engagement of specific agencies, keeping the CF as much focused as possible
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
11.1 | CF prioritisation retreat [done] | 2022
11.2 | 18-19 January RBM/Theory of Change workshop with UNCT for CF design
…
Recommendation 12: Include a narrative ToC together with the ToC diagram to explain how and under what assumptions the changes will take place
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
12.1 | Conduct ToC session led by CF consultant, UNCT and PMT | Q1 2022 | UNCT; PMT; RCO
12.2 | Include a narrative ToC together with the ToC diagram to the UNSDCF
…
Recommendation 13: Clearly define the UN position in Ukraine regarding humanitarian aid (HA), peace building (PB), the Nexus, the assistance policy in NGCA, again in order to support coherent positioning and communication to national stakeholders
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
13.1 | Use the HDPN paper for further communication related with the Government and developmen partners | ongoing | UNCT/HCT
13.2 | Integrate gender, human rights and HDPN as cross-cutting elements of all future CF outcomes | 2022 | UNCT,PMT
…
Recommendation 14: Enhance linkages between HRP and UNSDCF, to ensure that CF outcomes support the HRP strategy (particularly the international humanitarian exit strategy)
Management response - Accepted/Partially Accepted/rejected : Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
14.1 | Enhance linkages between HRP and UNSDCF, to ensure that CF outcomes support the HRP strategy (particularly the international humanitarian exit strategy) | Q2 2022 | UNCT/HCT
14.2
…

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030