## Recommendations_Proposed action
Country ______ZIMBABWE________; ZUNSDCF/ CF 2022 - 2026 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: -Evaluation of the ZUNSDCF /December 2025 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: UNRCO • Frequency of monitoring and updating: Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: It is recommended that the UNCT should rebalance the next CF portfolio to prioritize concrete actions that advance structural economic transformation, market development, governance reforms, and macro-level resilience
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Include in the new CF mechanisms/ strategies for establishing/institutionalise dialogue between UN( +IFIs)–Government(+private sector, CSOs) on Structural Transformation, Formalisation & Jobs Strategy. 2026 Deliverable(s): CA, CF and Report of Dialogue Outcomes. | 2026-12-31 | Lead: RCO(TPA), ILO: Agencies: UNWOMEN, UNESCO, UNDP, UNIDO) | Action is being implemented through the on-going CF development process | ongoing as expected | December | 2026
1.2 | Integrate employment and decent work, sustainable enterprise development, and digital inclusion as cross-cutting policy and programme priorities in all pillars with LNOB (youths, women, PWDs, informal workers(creatives)) considerations. | 2026-12-31 | Lead Agency: ILO, Agencies: UNESCO, UNWOMEN, UNFPA, ITU, UNFPA, IOM, UNICEF, UNDP…. | Action is being implemented through the on-going CF development process | ongoing as expected | December | 2026
1.3 | Leverage the Partnerships and Development Financing Taskforce to bring together UN-Government, Private Sector on Innovative Financing to address the country’s financing gaps in productive sectors with the highest potential for creation of jobs and socio-economic transformation. 2026 Deliverable(s): Employment Public Expenditure Mapping/Review. | 2026-12-31 | Lead Agency: RCO(TPA), ILO: Agencies: UNDP, IOM, UNWOMEN, UNICEF, UNESCO, UNFPA… |  | ongoing as expected | December | 2026
Recommendation 2: It is recommended that the UN should advocate for and support the national government in strengthening devolution [drawn from Conclusions 5 and 6].
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Establish a joint Devolution Capacity Strengthening initiative to enhance institutional, fiscal, and administrative capacities at provincial and district levels, enabling subnational authorities to effectively plan, budget, implement, and monitor development interventions in line with constitutional devolution provisions and national priorities. | 2026-12-31 | Lead: UNDP¦ Agencies: All Agencies |  | ongoing as expected | December | 2026
2.2 | Develop and roll out a Joint UN Subnational Integrated Multi Sector Convergence Initiative that supports the national devolution agenda by bundling infrastructure, services, livelihoods, climate resilience, and local governance interventions in selected high vulnerability districts (Q2–Q4 2026). | 2026-12-31 | . Lead: UNDP¦ Agencies: All Agencies |  | ongoing as expected | December | 2026
…
Recommendation 3:It is recommended that The UNCT should strengthen strategic adaptability by embedding adaptive management practices within the CF, using evidence and results data to enable timely course correction [drawn from Conclusions 1 and 3].
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Improve the End‑of‑Year Review Guidelines by integrating an adaptive management component that requires systematic review of key assumptions and risks, including analysis of how these factors enabled or hindered delivery of expected CF results | 2026-12-01 | UNCT M&E team, Result Groups Technical leads |  | ongoing as expected | December | 2026
3.2 | Map all UN agencies’, partners’, and Government M&E capacity‑building initiatives and consolidate them into a unified UN Capacity‑Building Plan, and deliver a joint training programme on Results-Based Management (RBM), risk-informed management, and adaptive decision‑making for UN, Government, and implementing partners | 31 Decmber 2026 | UNCT M&E team, Result Groups Technical leads |  | ongoing as expected | December | 2026
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: :In line with UN reforms, it is recommended that the Results Groups should consolidate joint programming as the default modality for UN cooperation, with support from the PMT [drawn from Conclusions 2 and 5]
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Use existing UN INFO agency programmes and sub output data to identify areas of overlap and complementarity across agencies and develop a consolidated Joint Programming Opportunities Matrix for each Result Group, establishing joint programming as the default modality for UN cooperation | 2026-12-01 | Lead- RCO Agencies: M & E team and PMT | Agencies are updating their UN info data | ongoing as expected | December | 2026
4.2 | Strengthen implementation of a unified UN visibility and resource mobilization framework that sets common branding, joint messaging, and collective fundraising protocols, and introduces incentives that recognize and reward cross-agency collaboration, co-financing, and equitable participation in joint programmes. | 2026-12-01 | Lead: UNIC/WFP Comms Agencies: Comms Team | UN Comms are jointing developing visibility materials | ongoing as expected | December | 2026
Recommendation 5: It is recommended for the UNCT to enhance coherence and synergy across the CF pillars and invest in the RCO capacity and resourcing to strengthen CF coordination, implementation and monitoring [drawn from Conclusions 2 and 5]
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We concur that the UNCT should strengthen coherence and synergies across the CF pillar, as highlighted in the first part of the recommendation. However, regarding the proposed enhancement of RCO capacities and resources, the evaluation report does not provide sufficient analytical grounding such as a functional review or an assessment of coordination needs and existing capacities to justify this recommendation.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | PMT to establish cross-pillar task forces on shared priorities (e.g., climate-smart livelihoods, governance and resilience, digital inclusion) as part of the design of the new CF, promoting multi-sectoral programming through incentives (shared funding windows, integrated workplans). | 375105 | PMT |  | ongoing as expected | December | 2026
5.2 | Establish a dedicated secretariat for the Joint SDGs and ZUNSDCF steering committee to be domiciled in the RCO or OPC, but with representation from the UN and government, and covering all the four pillars. | 2026-12-01 | RCO |  | ongoing as expected | December | 2026
Recommendation 6: It is recommended for the UNCT to systematize knowledge management and lesson learning in the next CF. [drawn from Conclusions 5 and 6].
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Develop and operationalize an Integrated Knowledge Management and Shared Learning Strategy that connects the work of the UN M&E, Data for Development, Innovation, and Communications groups and Government M & E teams. | 2026-12-01 | Lead: RCO M&E/Comms/OPC ; Agencies: Result Groups Technical Leads, M & E teams, DfDI Group and Comms Team. |  | ongoing as expected | December | 2026
Recommendation 7: Enhance sustainability through national institutionalisation and diversified financing models [drawn from Conclusions 4, 6 and 7].
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Strengthen UNCT Learning and Collaboration on Sustainability: Organize and deliver a dedicated PMT session focused on programme sustainability, capturing lessons learned and best practices from the 2022–2025 cycle. | 2026-12-01 | PMT |  | ongoing as expected | December | 2026
7.2 | High-Level Strategic Dialogue with Government: Facilitate a strategic dialogue led by the RC with senior government officials on institutionalisation and sustainability of UN-supported programmes. | 2026-12-01 | PMT |  | ongoing as expected | December | 2026

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030