# Management Response to

# Evaluation of United Nations Cooperation Framework by

# United Nations Country Team in Georgia

# December 2019

| Recommendation 1 The next UNSDCF should be based on a robust, participatory CCA, that will identify SDGs priorities where the UN has a collective added value. The CCA should also provide the evidence to build a shared ToC based on which the UN will identify how each relevant UN entity can contribute based on its comparative advantages | Accepted |  |  |
| --- | --- | --- | --- |
| Explanation [in case of rejection or partial acceptance] |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| New CCA preparation was ongoing in parallel with the UNPSD evaluation. New CCA document will be made available in the first quarter of 2020 and be used as a basis for elaboration of UNSDCF ToC. |  |  |  |
| - Finalization of the CCA | RCO, UNCT | January 2020 |  |
| - Elaboration of the UNSDCF ToC and full participation of UNCT in the Prioritization process | RCO, UNCT | February 2020 |  |
| Recommendation 2 During the planning stage the UNCT should avail itself of RBM and M&E experts leveraging resources from the regional tier of the UN, if necessary. It would be useful to set up a small M&E group at the country level, coordinated by the RCO and comprising UNCT’s M&E specialists (where present). This group should provide quality assurance for the design of the M&E framework of the UNSDCF. | Partially Accepted |  |  |
| Explanation Prioritization process will be organized by RCO which will involve UNCT management, programme staff and M&E focal points where available. M&E group will be established to follow up on coordinated monitoring of CF implementation and M&E Framework elaboration. M&E Group will become operational after CF is approved. |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - Establishment of the Monitoring, Learning and Evaluation (MEL) Group within the UNCT | RCO, UNCT | July 2020 |  |
| Recommendation 3 Subject to the outcomes of the CCA process, consider the framing of the UNSDCF outcomes around concrete, cross-sectoral, SDGs game-changer issues that would require the active collaboration across agencies and sectors. These would possibly determine the set-up of results groups that are motivated to proceed with joint planning and monitoring as overall result will depend upon each agency’s interdependent contributions. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT, with overall coordination by RCO will organize a prioritization workshop during which Overarching priority and UNSDCF pillar directions will be identified and agreed | RCO, UNCT | February 2020 |  |
| - Formulation of Working Groups within UNCT, that will follow up on subsequent formulation of Outcome and Outputs of the UNSCF Results Framework | RCO, UNCT | February 2020 |  |
| Recommendation 4 Explore at the planning stage potential synergies and complementarities across agencies and sectors, this should be part and parcel of recommendations 1 and 3 and is based on the findings related to potential synergies in particular between working on decentralization and aiming at enhancing specific social services given Georgia’s decentralization process (see Chapter 2). | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT with overall coordination of RCO will form up UNSDCF elaboration working groups. Groups will involve UNCT program staff to ensure CF RF elaboration is carried out in full compliance with the recommendation | RCO, UNCT | February -July 2020 |  |
| Recommendation 5 Consider how regional and sub-regional issues can be incorporated in the next CCA/UNSDCF. This is in line with the new UNSDG guidelines and also resonate well with what the evaluators learned in the process: not only there are a number of international development partners that cover, out of the same office, Georgia and other Caucasus’ countries with whom it would be useful to cooperate, but also it would be important to explore possible synergies for sustainable development across the borders (in consultation with neighbouring UNCTs). | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - The next CCA will include a chapter on the sub-regional issues and will thus guide the development of UNSCDCF - RCO will promote UNCT Georgia engagement with other UNCTs in South Caucasus and broader region, as well as regional economic commissions and other entities to continuously explore opportunities for synergies | RCO/UNCT RCO | February 2020 2021-2025 |  |
| Recommendation 6 It is recommended that in the future programme cycle, as minimum, results groups meet for annual or biannual joint planning also with relevant main government and non-governmental partners, to agree on collective outputs that will contribute the UNSDCF outcome. This should be an opportunity to review the initial ToC, question its validity in light of results achieved and observed, and readjust it as needed. Methodology for such planning should be as a participatory workshop rather than round-the-table sharing of information. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNSDCF Results Groups will be established upon the adoption of the new UNSDCF | RCO/UNCT | By the end of 2020 |  |
| - Consultations will be organized to support UNSDCF programming to involve external partners, including Government, NGOs/CSOs, Private Sector, Academia, etc. | RCO/UNCT | Regularly in 2021-2025 |  |
| Recommendation 7 Further strengthen the collaboration with the AoG’s Donor Coordination Unit and Policy Unit as the main counterpart to the UN as a whole, in order to ensure ownership of UN programming processes. Explore how the UNRCO can further support DCU’s coordination efforts as well as the AoG’s SDGs architecture. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT through RCO will strengthen cooperation with the DCU under AoG throughout the UNSDCF Elaboration and implementation | UNCT/RCO | 2020-2025 |  |
| - UNCT/RCO will be represented at various thematic groups’ discussions organized by the DCU under AoG that relate to SDG implementation | UNCT/RCO | 2020-2025 |  |
| - Steering Committee will be established to jointly monitor implementation of the CF | UNCT/RCO | 2021-2025 |  |
| Recommendation 8 Streamline the JWPs approval process. This should be handled at results groups’ level, involving the relevant line ministries and, if feasible, directly also DCU. The RCO should not act as a gate keeper, but facilitate government’s and UN’s participation and contribution to the results groups. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| Results Groups established with the purpose of coordinated implementation of the UNSDCF will invite/involve representatives of the Government/ DCU as appropriate | UNCT/RCO | 2021-2025 |  |
| Recommendation 9 UN staff’s contribution to joint UN work should be acknowledged and appraised. Achievements reached by staff participation and/or chairing of UN results groups, contributing to the CF implementation, should be included in their agency’s annual performance appraisal systems and planning. | Partially accepted |  |  |
| Explanation The final result will depend on each agency’s commitment to prioritize contribution to joint processes, and technical capabilities of each performance appraisal system |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| RCO will regularly share updates on UN staff contributions to joint UN Work in the monthly UNCT meetings and bilaterally in engagements with Heads of Agencies, and encourage inclusion of these roles in the respective annual performance appraisal system and planning | RCO/UNCT | 2020-2025 |  |
| Recommendation 10 As per UNSDG guidelines, the UN needs to move from a concept of funding UN programmes to one of Financing the SDGs in Georgia. This requires a radical shift from the concept of resource mobilization to fund specific projects to one of considering how to mobilise financial resources to reach the SDGs in the country together with all other partners. It is recommended in particular to explore opportunities for innovative financing, including green bonds, public-private partnerships, private sector-led initiatives, crowd-funding, etc. This should be explored in parallel with the formulation of the CCA (or as part of the same as recommended in the guidelines) and incorporated in the next framework document. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| RCO in coordination with UNCT will undertake annual reviews of SDG financing landscape in Georgia and use data to inform and advocate for Georgia to initiate steps towards INFF | RCO/UNCT | 2021-2025 |  |
| Recommendation 11 In line with recommendation 2 above, it is recommended that the overall results culture in Georgia’s UN system is further enhanced. The suggested M&E group should be involved in the design, monitoring and reporting of the next UNSDCF, ensuring that these are meaningful and feed into each other. The UNCT should be held squarely accountable for the delivery of the results and possibly have the implementation of the UNSDCF as an outstanding agenda item of its regular meetings to ensure leadership and ownership at the highest level. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT will establish its permanent Monitoring, Evaluation and Learning Group (MEL Group), which will work under the overall supervision of the UNCT and be guided by the RCO. It will provide advice and technical support during the implementation and evaluations of the CF; MEL group will also facilitate coordination of technical support to national entities in the collection, quality control and dissemination of statistical data. | RCO/UNCT | 2020 |  |
| Recommendation 12 Annual reviews should take place with national counterparts, building on outcome level reviews with partners in the context of the results groups. These should propose to the JSC changes and adjustments to the collective outputs, as well as workplans for their achievements in line with results reached thus far and the evolving context. The JSC will have oversight function as well as accountability (through the UNCT) to ensure effective interlinkages across results areas. | Accepted |  |  |
| Exp |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - CF results review will take place as part of the UNCT annual report preparation process within the UNCT and with overall coordination of the RCO | RCO/UNCT | 2021-2025 |  |
| - Periodic review/update of the CCA will provide updated information about overall country context and its’ status of priorities. | RCO/UNCT | 2021-2025 |  |
| - Annual presentation of the results achieved will take place according to the corporate guidance before the end of March | RCO/UNCT | 2021-2025 |  |
| - UNSDCF Steering Committee will meet and have focused discussion over annual results and Joint Workplans for the subsequent period | RCO/UNCT | 2021-2025 |  |
| Recommendation 13 Building on the good practices of the UNCG and the experience of the joint SDGs communication strategy, develop common messages and advocacy tools on key cross-cutting or cutting-edge issues that will emerge from the CCA and will be prioritised for the next programming framework. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT Communications Group, with overall coordination from RCO Communications officer will elaborate and periodically review/update the UNCT Communications Strategy, which will serve as a guidance document for building up communication campaign of the UNCT | RCO/UNCG | 2021-2025 |  |
| Recommendation 14 Engage the UNCG in the preparation of next UNSDCF and allocate budget for joint communication to raise awareness on the key issues that the UN will be addressing in the next few years. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - UNCT Communications Group, with overall coordination from RCO Communications officer will elaborate and periodically review/update the UNCT Communications Strategy, which will serve as a guidance document for building up communication campaign of the UNCT | RCO/UNCG | 2021-2025 |  |
| Recommendation 15 UNCG to consider partnering with government and private sector for joint communication efforts around the 2030 agenda and prioritised SDGs. This should include engaging media outlets to raise general public’s awareness as well as partnering with banks and businesses to leverage their resources and outreach potentials. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - Communication strategy will foresee concrete actions and identify/recommend on potential partners for targeted communication campaigns | RCO/UNCG | 2021-2025 |  |
| Recommendation 16 A private sector partnership strategy should be developed by the UNCT, mapping potential partners (business associations, large companies, like-minded business-persons, chambers of commerce, etc.), consult them in the CCA/UNSDCF process, and identifying potential areas for collaboration | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| - RCO will work with the UNCT to integrate private sector engagement into the UN in Georgia partnerships strategy and its implementation - Private sector entities will be consulted in the process of UNSDCF elaboration | RCO/UNCT RCO/UNCT | 2021-2025 2020 |  |
| Recommendation 17 Partnership with the IFIs needs to be strengthened. IFIs are a crucial development partner to Georgia, which relies mainly on loans as part of its ODA. On the other hand, UN ‘soft’ interventions run the risk of being unsustainable if policies and strategies are not supported by a financed-implementation plan. There is a potential for close, mutually beneficial collaboration in this regard that should be explored from the onset of the planning cycle. | Accepted |  |  |
| Explanation |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| Closer coordination and operational synergies with IFIs will be promoted, including building on the membership of the WB and IMF in UNCT Georgia, exchanges within the IFI-inclusive development partner working group, bilateral and issue-based engagements | RCO/UNCT | 2020-2025 |  |
| Recommendation 18 Likewise, it is important that the UN develops a clear Innovation strategy, i.e. on how innovation can be streamlined in all results areas to make them more effective, efficient and ultimately sustainable. Innovation based on digital solutions have huge potential in Georgia and this should be explored across the system (not only at agency level). The UN should position itself as the centre of innovation for sustainable development, bringing ideas and experiences from other countries as well as sharing those of Georgia | Partially accepted |  |  |
| Explanation While innovation will be promoted, the need for a dedicated strategy will be assessed by the UNCT |  |  |  |
| Actions to be taken | Responsible entities | Timeframe | Resource implication |
| RCO will facilitate regular exchanges on innovation within the UNCT and explore relevant programming and operational improvements, including within UNSDCF Results Groups and the OMT | RCO/UNCT | 2021-2025 |  |