## Sheet1
Country __The Gambia; UNDAF 2017 - 2021 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: -----EVALUATION OF THE UNITED NATIONS DEVELOPMENT ASSISTANCE FRAMEWORK (2017-2021)------------ / 2022 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: ----------------------- • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: It is recommended that the planning cycle of the new Cooperation Framework be better aligned to the NDP planning cycle to enhance UNs continued relevance and contribution to the attainment of national priorities. Also, the government and other relevant stakeholders should actively participate in the CF formulation process to ensure ownership. Given the high vulnerability of the economy to shocks, it is recommended that the new CF takes into account such vulnerabilities and possible resilience measures from the design stage. Based on the experience of the UNDAF implementation, the new CF should anticipate the various socio-economic and environmental risks that may likely affect its implementation and provide possible mitigation measures.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | The recommendation is accepted given that the UNDAF was formulated prior to the formulation the NDP 2018-2021. As a result, some of the key areas of the NDP (such as migration were not adequately captured in the UNDAF documernt
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The roadmap of the new CF should factor the completion of the NDP | 2022-12-31 | RCO |  | completed | June | 2023
1.2 | The prioritization for the CF should be inclusive and participatory | 2023-03-31 | RCO |  | completed | June | 2023
1.3 | The new Cooperation Framework (2024-2028) should develop a comprehensive risk analysis and possible mitigation measures | 2023-09-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  | ongoing as expected | December | 2023
Recommendation 2: For the new Cooperation Framework, it is recommended that a robust and comprehensive TOC be developed, with clear pathways describing how interventions are linked to outcomes and priorities, and the accompanying assumptions and risks. This will enhance the degree to which UN contribution can be attributed to changes in the desired outcomes of the new CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is accepted because the current UNDAF did not have a Theory of Change to elaborate the change pathways. As a result, it is difficult to attribute change in outcomes to UNDAF interventions
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.2 | Develop a robust TOC as part of the CF process | 2023-04-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  | ongoing as expected | June | 2023
…
Recommendation 3: For the new CF, it is recommended that it is monitored by a holistic and robust results matrix with smart, realistic and adequate indicators. It is further recommended that respective UN agencies support special surveys to fill the data gaps as a number of indicators were without current data.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is accepted because the UNDAF results measurement framework was not robust enough. This has resulted in low assessment of some of the outcomes. The indicators for some outcomes were not adequate to track progress in the outcomes
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | The Results Measurement Framework for the new CF should be developed in a participatory manner | 2023-05-31 | M&E working group, RCO, UNCT |  | ongoing as expected | June | 2023
3.2
…
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: To avoid duplication of efforts and ensure coherence in UN interventions, it is recommended that the UNCT intensify joint planning, programming, and delivery. The use of joint programmes will avoid gaps and overlaps and ensure judicious use of resources.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted as the UN has been implementing joint pogrammes. Through the Peace Building Fund for instance, the UNCT has implemented several joint programmes that have supported the government’s transitional justice programme
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Partnerships and resource monilisation strategy | 2023-06-30 | RCO |  |  | June | 2023
| Endorsement of partnerships and resource monilisation strategy | 2023-11-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  |  | December | 2023
1.2 | Training on joint programming | 2023-11-30 | RCO |  | ongoing as expected | December | 2023
…
Recommendation 5: It is recommended that UNCT together with GoTG work to strengthen representation and involvement of the stakeholders in the UNDAF Joint National/UN Steering Committee. Also, it is recommended to ensure its strategic involvement and guidance for UNDAF implementation, through regular meetings and involvement of senior level representatives from the Government, UN and CSOs in all governance structures.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is accepted because the UNDAF coordination could be improved. The Joint National-UN steering committee only meet once a year and the representation of government officials at senior level could be improved. Other structures such as Results Groups, and M&E groups were not meeting regularly
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | To include CSOs and the private sector as part of the Joint national UN Steering Committee. The committee should meet at least twice a year | 2023-09-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  | ongoing as expected | June | 2023
1.2 | Ensure that Results Groups for the new CF meet regularly. The RGs should comprise of UN, government and CSOs | 2023-09-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  | ongoing as expected | December | 2023
… | Harmonize the CF implemtation structures with the NDP to reduce multiplicity of committees | 2023-09-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS |  | ongoing as expected | December | 2023
Recommendation 6: To ensure sustainability of the CF interventions, participation of all stakeholders, especially the most vulnerable and stakeholders at the grassroots level should be ensured. Also, it is recommended that exit or sustainability plans are developed in consultation with the beneficiaries at the planning stage of the interventions. For projects and interventions that require technical capacities, the UN should provide the needed transfer of skills to ensure continuity after the intervention.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This is how the UN has been working in the past (consultative processes). However, there is room for improvement on exit strategies
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The new Cooperation Framework will highlight sustainability and exit strategy for UN interventions / projects | 2023-09-30 | RCO, UNDP, UNICEF, WFP, FAO, UNFPA, IOM, ITC, UNCDF, UNODC, UNAIDS | This action will start with the implementation of the new CF (after 2023) | ongoing as expected | December | 2023
1.2
…

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030