## Sheet1
Country RWANDA UNDAF / CF 2018 - 2024 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: 2024 / YYYY • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: ----------------------- • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Develop a unified and inclusive framework that seamlessly incorporates stakeholder priorities, cross-cutting concerns, and emerging issues across all levels of program planning, budgeting, policy development, capacity building, stakeholder engagement, monitoring, evaluation, and other relevant activities. This approach will ensure that guiding principles such as gender equality and women empowerment (GEWE), leaving no one behind (LNOB), and human rights are consistently integrated into program design and implementation, ultimately fostering more effective and equitable results. Explanation The CF needs to respond more directly to the identified needs and priorities of both the country and program development partners . While alignment and to some extent adaptation measures exist, further integration of cross-cutting and mechanisms for adapting to emerging issues is essential.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The UNCT will ensure stakeholder engagement during the development of the CF at all stages starting from the conceptual framework till the final endorsement of the CF. This will be done through planned consultative meetings and virtual engagements. | Ongoing | UNRCO, UN Agencies, PMT, Task Teams (TTs), Government Partners, Development Partners
1.2 | The UNCT will ensure utilization of relevant checklists of cross cutting issues e.g. gender and where required involvement of relevant experts to undertake specialized audits to ensure mainstreaming of cross-cutting issues across the CF. Moreover, the UNCT support mainstream of gender, HR and other cross cutting issues into Results Groups by having focal points in all groups. | Ongoing | UNRCO, UN Agencies, PMT, TTs
| The UNCT will ensure that UNSDCF and joint work plans are in line with and advance UN strategies and action plans applicable to UNCTs, including on disability inclusion, gender, and youth. |  | UNRCO, UN Agencies, PMT, TTs
| The UNCT commits to ensure through its Programme management Team and relevant task teams the continued and systemic involvement of relevant experts within UN Rwanda, beyond the development of the CF, across all levels of program planning, budgeting, policy development, capacity building, stakeholder engagement, monitoring, evaluation, and other relevant activities. Moreover, The UNCT will support capacity building initiatives for relevant staff and stakeholders on GEWE, LNOB, and human rights principles. | 6 months | UNRCO, UN Agencies, PMT, TTs
… | Strengthen the incorporation of gender and human rights markers into the program’s M&E systems. Regularly plan, monitor, and report on these markers in UNINFO to ensure continuous adherence to these principles. |  | UNRCO, UN Agencies, PMT, TTs
Recommendation 2: To enhance program coherence, it is crucial to foster regular communication, leverage best practices, reinforce accountability mechanisms, and optimize operational workflows. This can be achieved by establishing knowledge-sharing platforms and streamlining operations. Additionally, collaborative planning, assessments, and the development of integrated programs are essential for maximizing operational effectiveness. Explanation With a wide array of stakeholders engaged in the program, such as development partners, UN agencies, and government partners, there's a pressing need to establish clear channels for knowledge sharing and communication. Additionally, enhancing adaptive programming and operational processes is crucial. Given the program's complexity and the involvement of various stakeholders, more efficient coordination is necessary to optimize resource allocation and minimize duplication of efforts. However, several coordination mechanisms and knowledge sharing efforts have been put in place in the past and therefore the focus will be more in re-assessing the value of the efforts, re-shaping the systems established and enhancing ‘what works’ prior to initiating new systems/initiatives. This will allow UNCT to optimize what already in place while channeling energy and resources – including human resources – specifically in areas identified as gaps.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | The UNCT through the UN Communications Team, will assess current communications channels accessible to all stakeholders (e.g., email, online platforms, in-person meetings,brown bags, town-halls, policy dialogues ) and agree on which ones need to be strengthen or on new ones to be established – which are agile and cost-effective. | 6 months | UNCT, PMT, UNRCO, UN Communications Team
| While UN joint learning opportunities have been ongoing in many areas of work and particularly in relation to cross-cutting matters. The UNCT will initiate a survey to further assess the learning needs of staff and the preferred delivery methods with the intent of facilitating peer-to-peer learning opportunities (e.g., workshops, webinars, site visits) to share lessons learned and best practices. | 6 months and throughout the implementation of the new CF | UNCT, PMT, UNRCO, UN Communications Team
| A mapping of UNCT partners will be undertaken with expected roles and responsibilities and communicated accordingly also ensuring cross fertilization on JPs when required. | 6 months and throughout the implementation of the new CF | UNCT, PMT, UNRCO, UN Communications TeamJPs focal points/leads, M&E FTT,
| The M&E task team with support from UNRCO will be strengthened and the use of UNINFO will be further enhanced – including routine data collection to ensure compliance, programme monitoring, transparency and accountability. | 6 months and throughout the implementation of the new CF | UNRCO, M&E TT, PMT
| The UNCT – at the beginning of the new CF as well as yearly – will mandate relevant JPs leads to engage stakeholders in joint planning processes to ensure buy-in and alignment. This will be done systematically, and SOPs will be issued to ensure harmonization and compliance. | As part of the co-creation of JPs – from inception as well as yearly | UNRCO, JPs Chairs, PMT, stakeholders
Recommendation 3: To maximize effectiveness while implementing the CF, it is recommended that the UN adopts a multi-faceted approach to address challenges related to Joint Programs (JPs) as follows: 1. Implement activity/time tracking tools to ensure sufficient time, human and financial resources’ capacity for successful JPs’ outcomes. This reduces the risk of delays affecting human resources capacity, misuse of time available and sub-optimization of financial resources. 2.Standardize operational procedures, fostering cross-functional collaboration, and conducting regular reviews towards the harmonized processes across results groups. 3.Strengthening M&E mechanisms through a robust framework, data sharing, regular reporting, and data-driven decision-making is crucial. Explanation To maximize the impact of program interventions, there is a need to address challenges related to sufficient time and continual resourcing for (JP) activities, harmonizing operational processes, and strengthening monitoring and evaluation mechanisms across results groups. However, there is a need to first assess all the systems already in place and agree on what needs to be improved and when/if new systems may be required in the spirit of agility and adaptability.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | The UNCT will ensure that the available monitoring systems (UNINFO) are utilized effectively and monitored on a quarterly basis. Additionally, the UNCT/PMT will focus on strengthening leadership, accountability and optimization of the tools already in place. | 6 months | UNCT, UNRCO, PMT and M&E TT
3.2 | The UN System has adopted several standardized procedures including HACT and will soon pilot the other joint practices e.g. joint fleet to foster a culture of cost-effectiveness and efficiency. The same principles will be applied to programming and new standardized procedures will be explored e.g. recommendation 2, point e). | 6 months | UNRCO, JPs Chairs, PMT, stakeholders
| M&E mechanisms will be strengthened as per recommendation 2, point d). | 6 months and throughout the implementation of the new CF | UNRCO, M&E TT, PMT
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: To strengthen the impact orientation of the Cooperation Framework CF in Rwanda, it is recommended to ensure that the activities outlined in the Joint Programmes (JPs) directly contribute to the strategic realization of the CF outcomes, as detailed in the Theory of Change (ToC). Explanation While there is a focus on achieving meaningful impact and transformative change, there is a need to prioritize quality data collection, support private sector an CSO engagement, and strengthen monitoring for gender-related initiatives.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The UNCT commits to ensure through the PMT that all the JPs will be designed through inclusive and consultative processes within and outside the United Nations in Rwanda. Beyond the UN guidelines on JPs development – the UNCT will task the PMT to develop a checklist that clearly highlights the relevant steps to be followed to ensure inclusiveness. | 6 months | UNCT, PMT, JPs Chairs and stakeholders
1.2 | In relation to the M&E system refer to Recommendation 2 point (d) | 6 months and throughout the implementation of the new CF
| RGs Annual review meetings will be called by the PMT with the participation of relevant TTs and JPs chairs to assess progress of the CF and where necessary recommend amendments to the UNCT to remain agile and adaptive to evolving needs. | Yearly – throughout the CF implementation timeframe | UNCT, PMT, JPs Chairs, RGs
Recommendation 5: To promote the sustainability of CF interventions, it is recommended to: (a) Engage partners in resource mobilization efforts (b) Involve partners in results-based management and improve knowledge sharing (c) Enhance coordination mechanisms Integrate key sustainability principles such as environmental integrity, social equity and economic viability and others. Explanation To ensure the long-term success and impact of program interventions, there is a need to engage partners in resource mobilization efforts, involve partners in results-based management, and incorporate sustainability principles into interventions.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The UNCT will commit to the development of a UN Rwanda Strategy of engagement with strategic partners including development partners and private sector in line with the CF and its established JDs. A team – led by UNRCO – will be established to ensure coordination and compliance. | 6 months | UNRCO, PMT, UN tech experts, development partners and private sector
| Specifically for resource mobilization purposes -the UNCT will commit to develop a resource mobilization and financing strategy to guide a “One UN” approach to RM and financing/leveraging models. | 12 months | UNRCO, PMT, UNCDF, other UN agencies, technical experts.
| Existing coordination mechanisms within the UN and outside the UN – within which the UN have a chairing or co-chairing role, will be assessed and modalities of engagement may be steered to ensure better coordinated efforts. | 12 months | UNRCO, DPs, PMT, M&E TTs and Communications Team
| The integration across the JPs of Sustainability principles will be ensured using the proposed intervention as per Recommendation 4, point a) | 6 months | UNCT, PMT, JPs Chairs and stakeholders
1.2
…

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030