## Management Response
MANAGEMENT RESPONSE TO EVALUATION OF ONE STRATEGIC PLAN 2017-2021
Evaluation Title/Year: Evaluation of One Strategic Plan 2017-2021 / 2020-2021 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: OSP Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RC/UNCT and GOVN/MPI • Frequency of monitoring and updating: Every 6 months. Report made to JSC.
RESPONSES TO RECOMMENDATIONS
Recommendation 1: The UNCT, in consultation with the GOVN, social partners and other relevant stakeholders, should develop the next UN – GOVN Cooperation Framework (CF) based on a well-reasoned and robust Theory of Change. It is strongly recommended to adhere to the UNSDG guidance to formulate structured multi-layer outcomes and outputs during the Cooperation Framework design stage to ensure a clear logic in the TOC and the related results matrix. Developing a more accurate and robust TOC in line with the requirements set out in the UNSDG guidance will enable UN agencies to be more selective about their respective areas of focus and contribute to greater accountability and transparency of UN system interventions. Particular attention should be paid to formulation of immediate and intermediate outcomes in order to enable monitoring of progress and evaluation of the UN contribution to high level outcomes. The next CF should be based on a realistic overall budget envelope with maximized core and secured resources. |  |  |  | Partially Accepted
Explaination of rejection or partially acceptance The UNCT agrees the CF should be developed with a robust TOC, resulting from inclusive consultation with the GOVN and all other relevant stakeholders, based on realistic resources, and in line with UNSDG guidance. In the curent CF guidance, immediate and intermediate outcomes are not part of the CF structure (rather outcomes and outputs are). The regional DCO and PSG strongly suggested including only outcomes in the CF results framework and the UNCT endorsed this in May 2021.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
1.1 | Develop 2022-2026 CF in line with the UNSDG guidance with robust TOC and results framework which enable more strategic and selective UN interventions, and greater accoutanbility and transparency of the UN system in Viet Nam | UNCT (with support of RCO, Outcome Groups, PMT, MSRWG) and GOVN | Feb - Jul 2021 | 30000 | 1
1.2 | Set up relevant mechanisms (GOVN-UN taskforce, multis-stakeholder workshop and consultation) to ensure inclusive consultation with government, NGOs, mass organizations, DPs, and other stakeholders during CF development | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Jun - Jul 2021 | 5000 | 2
Recommendation 2: The UNCT in consultation with the GOVN should take extra care for proper identification and definition of Outcome Indicators and their target values and strengthen the use of effective monitoring tools to ensure timely and effective monitoring of progress at both Output and Outcome levels. The monitoring of the next CF will benefit from active involvement of the GOVN as the latter is holder of data and information needed to assess progress towards achieving target values of the CF results indicators. The number of Outcome Indicators should be kept realistic to enable tracking of progress. Active involvement of GOVN agencies should optimally include use of national evaluation systems in the monitoring of progress that will further strengthen national data and information systems as well as national monitoring and evaluation capacities. In particular, the UNCT should develop and use indicators of progress that reflect immediate and intermediate results that are more closely linked with UN interventions and can therefore better define and measure the UN contribution to progress towards the achievement of high-level Outcomes within the duration of a single programme cycle. To the extent possible, UN entities should undertake efforts towards synchronization of their individual systems of monitoring for development results with the monitoring and evaluation system of the next CF. |  |  |  | Accepted with the important caveat stated below
Explaination of rejection or partially acceptance The recommendation on synchronization of individual agency systems of monitoring of results goes well beyond the country level and cannot be made a country level Agency responsibility. Both UN agencies (at country level), RCO and UNRC will continue to raise this with Agency at HQ level and DCO headquarters.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
2.1 | Select robust Outcome indicators as part of CF Results Framework which link with national SDG indicator framework and output areas to reflect UN contribution. Outcome indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | UNCT (through Outcome Groups with support of MSRWG) and GOVN | Jun - Jul 2021 |  | 3
2.2 | Select robust Output indicators as part of CF Joint Work Plans which reflect UN specific contribution as results of UN interventions. Output indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | Outcome Groups (with support of MSRWG) | Aug - Oct 2021 |  | 4
2.3 | Develop the UNCT Monitoring, Evaluation, and Learning Plan, including a clear guidance on JWP planning, monitoring, review and reporting | MSRWG | Aug - Oct 2021 |  | 5
2.4 | Improve the UNInfo database (through sufficient data entry) and its use for monitoring of CF progress and UN contribution (both programmatically and financially) to SDGs and as a basis for UN discussion and identification of possible joint interventions | RGs and MSRWG | Aug - Oct 2021 |  | 6
Recommendation 3: The UNCT in consultation with the GOVN should carefully revise the coordinating role of the Joint Steering Committee (JSC) in order to ensure a meaningful and active participation of the GOVN and its representatives. A stronger role of the GOVN and key social partners identified for joint contributions to national priorities in the JSC will enhance the national commitment to and responsibility for the next CF as well as accountability for its implementation. By the same token, it will increase the GOVN and key social partners’ buy-in and ownership of the next CF and ensure that relevant national authorities will take resolute steps to ensure timely and effective implementation of CF interventions in line with the plans of the UN agencies and expectations of donors. |  |  |  | Accepted Please note the RC/UNCT has already advocated this for some time. Action is needed by the GOVN
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
3.1 | Revise the JSC TOR to strengthen JSC’s coordination towards strategic discussions and more active GOVN participation, especially for the new CF. | UNCT and GOVN (through JSC) | Aug - Oct 2021 |  | 7
3.2 | Implement the JSC TOR as designed and revise when necessary | JSC | Oct 2021 - End 2026 |  | 8
3.3 | Ensure meaningful and active GOVN contribution to the CF development | UNCT and GOVN (through JSC) | Feb - Jul 2021 |  | 9
Recommendation 4: In line with the UNSDG guidance and based on the experience from implementation of the OSP, the UNCT should carefully revise and optimize the current coordination mechanism for the next CF, in particular to strengthen the strategic position of the Results Groups in the CF coordination architecture and ensure alignment of the Results Groups with existing equivalent GOVN-led working structures. The Results Groups should be aligned with relevant GOVN-led sector structures (such as working groups, clusters) to ensure contribution of the UN RGs to such external mechanisms. Where equivalent GOVN-led structures do not exist, the RGs should incorporate representatives of relevant line ministries and key national partners. This arrangement will ensure a more coherent UN system-wide approach to CF strategic priorities and will be more inclusive through establishing linkages to the CF priority sectors. The extended RGs should meet at regular pre-established intervals in line with the UNSDG guidance. |  |  |  | Partially accepted
Explaination of rejection or partially acceptance It's agreed that Results Groups (RGs) need to play a more important and active role in implementing the CF as well as to have more interactions among and within Results Groups. This has always been the intention but results in different groups have been mixed and there is room for improvement. While it is important to ensure the linkage between Results Groups and the existing GOVN sectoral/thematic coordination structure to ensure meaningful contribution and alignment of the RGs to GOVN work, and also important to maximize maximize GOVN participation in RGs activities to the extent possible, the RG mechanism should be viewed as an independent internal UN mechanism and GOVN should not be included as members but should be invited as and when required. This is the common practice for other such independent development partner mechanisms (e.g. DPG) and is the appropriate approach.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
4.1 | Establish UN-internal CF Governance and Management Structure to ensure RG strategic position | UNCT | Aug - Oct 2021 |  | 10
4.2 | Develop (and implement at later stage) RG TOR to ensure RG strategic position, more frequent interaction within RGs, linkage with GOVN sectoral/thematical coordination structures, and maximized GOVN participation in RGs (including in the development of joint programmes) to extent possible | Results Groups for UNCT approval | Oct - Nov 2021 |  | 11
4.3 | Implement the CF Government and Management Structure and RG TORs as designed and revise when neccesary | Results Groups for UNCT approval | Oct 2021 - End 2026 |  | 12
Recommendation 5: The UNCT should undertake a more systematic approach towards joint programming as a foundation for a more coordinated approach to implementation of the next CF. Under each CF Outcome, the UNCT should identify areas for collaborative work and develop a framework for collaborative efforts based on comparative advantages and complementarity of individual agencies. Such framework should provide substantive details of collaborative work of individual agencies, in accordance with their respective mandates, and building on their respective strengths. Existence of the framework will shorten time needed for preparation of Joint Programmes and facilitate thus timely and effective submission of the JPs for consideration of donors. The UNCT should also ensure collection of good practices and lessons learned for future joint programming |  |  |  | Accepted Results Group Joint Programme target (of at least one JP per RG per year) already exists and has been achieved, but should be strengthened
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
5.1 | RGs to discuss and identify areas for collective efforts and potential joint programmes annually during the JWP planning | Results Groups | Nov - Jan, annually |  | 13
5.2 | Collect and review good practices and lessons learned on joint programming and joint programme during annual review/reporting period. Report to UNCT for strategic discussion for improvement of joint programming. | Results Groups and UNCT | Nov - March, annually |  | 14
Recommendation 6: For formulation of the next CF, the UNCT should introduce indicators and target values that will enable systematic tracking of progress on mainstreaming of cross-cutting themes into the CF implementation. Mainstreaming od cross-cutting topics in development cooperation is a process that requires changes in awareness, attitudes, plans and programme implementation. There are some examples of approaches, tools and practices for mainstreaming the most common cross-cutting themes as well as tracking the progress and achievements. The challenge is to use them systematically and consistently in the project or programme cycle to enable monitoring of progress in their mainstreaming into the OSP implementation. |  |  |  | Accepted
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
6.1 | Identify cross-cutting priorities and LNOB in CF document | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Feb - Jul 2021 |  | 15
6.2 | Mainstream cross-cutting priorities and LNOB into CF indicator frameworks (in the CF documents, JWPs, and MEL plan) to extent possible in line with relevant UNCT action plans (e.g. SWAP and UNDIS action plans) | UNCT (with support of MSRWG, GTG, etc.) and GOVN | Jun 2021 - Mar 2022 |  | 16
Recommendation 7: The UNCT should conduct analysis of the various reporting levels of the UN agencies and harmonize the reporting format under the OSP with the reporting requirements of the UN agencies and main donors. Despite the differences in reporting practices across UN agencies and donors, there is a commonality in the information requested. It would be advisable to adjust the format for reporting of the UN agencies to the RGs according to the common information/reporting requirements of the UN agencies and donors. |  |  |  | Rejected
Explaination of rejection or partially acceptance The recommendation on OSP reporting is relevant, but requires a decision and harmonisation at HQ level, not country-level. In the earlier stage of OSP implementation, a review of reporting requirements of both individual agencies and DCO was conducted. However, this did not add much value to a more harmonized reporting system at country level since the requirements are mandatory and kept changing from the HQ level. Relevant feedback on double reporting, its burden and discrepancies have been provided to the HQ level repeatedly. The UNCT will continue to advocate with Headquarters and harmonize some internal formats at the national level to the extent possible but this recommendation needs to be addressed by HQ and cannot be addressed sufficiently at the country level.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
Recommendation 8: The UNCT needs to enhance the modality of coordination and support for non-resident agencies in collaboration with GOVN agencies. There remains an issue of delay process and less effectiveness of the collaboration between UN non-resident agencies and GOVN due to obstacles in direct communication and discussion. As a result, the formulated activities could be slow and even cancelled. The UNCT/RCO should take a more active role in support the discussion and approval process on behalf of non-resident agencies to increase the effectiveness of the cooperation via an effectively and timely implementation process and better communication. |  |  |  | Partially accepted
Explaination of rejection or partially acceptance The recommendation is relevant in the sense that it's necessary to enhance the coordination with non-resident agencies (NRAs) regarding collaboration with GOVN agencies. The RC/O has gone out of its way to do this over the years with mixed results based on NRA response and active interest. It's also important for strengthening UN-internal collaboration through NRAs' active sharing information of their activities, participation and presentation in and contribution to the UNCT, RGs, and other inter-agency coordination mechanisms; however this effort needs to be made by NRAs and DCO needs to provide more clear guidance on NRA participation in UNCTs and how this can be realized in practice given the existing significant structural constraints to enabling this.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
8.1 | UNCT/RCO to continue to support non-resident agencies in collaborating with GOVN agencies and other stakeholder to extent possible, and to consistently engage non-resident agencies in relevant groups/tasks/communication | UNCT/RCO | from now forward |  | 17
8.2 | Non-resident agencies to be more active in sharing information of their activities, participating, presentating and contributing to the UNCT, RGs, and other inter-agency coordination mechanisms (including CF and JWP planning, implementation, monitoring and reporting) | Non-resident agencies | from now forward |  | 18
Recommendation 9: The UN in Viet Nam should make assessment of sustainability of the Viet Nam SDG Fund and its potential for prioritization and mobilization of donor financing for the next CF. Although the current SDG Fund for Viet Nam was established in 2018, there has been very little success in mobilizing funds through this financial mechanism due to concerns about monitoring and reporting for accountability of the UN to donors. The UNCT should make reassessment of the country-level SDG Fund situation in comparison with other options, in particular with funds mobilization through joint programming through the Global SDG Fund. |  |  |  | Accepted
Explaination of rejection or partially acceptance It's agreed that a decision needs to be made on whether the VN SDG Fund should be kept for the future given the existing joint global fund and GOVN procedures and given that we may still get some funds through this country-level mechanism in the future. Nevertheless, it should be noted that at present, GOVN agencies have reservations about the SDGF TOR; thus it is not functional owing more to administrative reasons and Viet Nam's fast reducing ODA given its changing status to lower middle income country, and the creation of the Global SDG Fund which we have used more.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
9.1 | UNCT and GOVN to make a decision on whether we should keep the VN SDG Fund for the future given the existing joint global fund and GOVN procedures and given that we may still get some funds through this country-level mechanism in the future | UNCT and GOVN (through JSC) | Now - Aug 2021 |  | 19
9.2 | If the decision is yes (for Action 9.1) then JSC to agree on the SDGF TOR | JSC | Aug - Dec 2021 |  | 20
Recommendation 10: The UNCT should put emphasis on interventions related to the normative, capacity building and awareness raising mandates of the UN agencies that constitute major comparative advantages of the UN system. In this regard, the next CF should extend support and technical assistance to the GOVN for better understanding of international norms and standards, their integration into formulation of national policies and legislation as well as for effective implementation of the policies, strategies and action plans in line with international norms, standards, and conventions. The increased emphasis on the normative agenda and capacity building will propagate mainstreaming of the cross-cutting topics of data for development as well as learning and innovation. For field engagements not directly linked to the normative agenda, UNCT should look for opportunities for partnerships with organizations in the field such as local government organizations or NGOs. |  |  |  | Partially Accepted
Explaination of rejection or partially acceptance In fact, the UNCT emphasis on interventions related to UN normative and capacity building mandates is more or less in place. The more relevant issue is that the UN agencies are still working in a compartmentalized manner and there are inadequate global HQ-level corporate strategies to deliver the UN mandates in a more harmonized and effective manner and there is a need to discuss concretely how this will be addressed at global HQ level.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
10.1 | Discuss and identify directions/ways to enhance UNCT collective strategy and common messages on UN normative agenda | UNCT | from now forward |  | 21
10.2 | Implement UNCT directions to enhance UNCT collective strategy and common messages on UN normative agenda, including through join workplanning, join programming, and UN joint messages | UNCT | from now forward |  | 22
10.3 | Improve the UN joint communication for advocating UN normative agenda and common strategic messages through UNCT website and other media tools | UN Comms Group | from now forward | 3000 | 23
Recommendation 11: The GOVN agencies should be engaged in designing the joint programmes with the UN agencies to ensure full partnership, commitment, and co-financing in the implementation of the next CF. The GOVN agencies have been positioned by the UNCT as partner rather than beneficiaries or implementers of activities. This best reflects the switch of the UNCT from donor to partner, from development assistance to partnership. Engagement of the GOVN agencies in designing the joint programmes will ensure commitments, ownership, and co-financing sources from the GOVN agencies for the implementation of the next CF. Given the uncertainty of global economic recovery, it is reasonable to anticipate a tightening financing prospect for the next CF and therefore, mobilizing counterpart contribution from the GOVN is also important in financial terms. |  |  |  | Accepted
Explaination of rejection or partially acceptance This has always been the intention and is often the case. National ownership is the key principle of 2030 Agenda and for UN operations. GOVN agencies, as one of the most important owners of UN support, have been engaged in JP design. The UN and GOVN will further engage GOVN agencies for more meaningful and timely contribution to JP design, approval and implementation. However, global joint fund short deadlines and some current requirements make this difficult to do sometimes, so there needs to be change in the global joint fund guidelines to more actively facilitate or allow this.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
11.1 | Strengthen GOVN engagement in designing joint programmes from the beginning and through out the whole JP development process | Relevant UNCT groups and GOVN agencies | from now forward |  | 24

## Management Response (monitorin)
MANAGEMENT RESPONSE TO EVALUATION OF ONE STRATEGIC PLAN 2017-2021
Evaluation Title/Year: Evaluation of One Strategic Plan 2017-2021 / 2020-2021 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: OSP Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RC/UNCT and GOVN/MPI • Frequency of monitoring and updating: Every 6 months. Report made to JSC.
RESPONSES TO RECOMMENDATIONS
Recommendation 1: The UNCT, in consultation with the GOVN, social partners and other relevant stakeholders, should develop the next UN – GOVN Cooperation Framework (CF) based on a well-reasoned and robust Theory of Change. It is strongly recommended to adhere to the UNSDG guidance to formulate structured multi-layer outcomes and outputs during the Cooperation Framework design stage to ensure a clear logic in the TOC and the related results matrix. Developing a more accurate and robust TOC in line with the requirements set out in the UNSDG guidance will enable UN agencies to be more selective about their respective areas of focus and contribute to greater accountability and transparency of UN system interventions. Particular attention should be paid to formulation of immediate and intermediate outcomes in order to enable monitoring of progress and evaluation of the UN contribution to high level outcomes. The next CF should be based on a realistic overall budget envelope with maximized core and secured resources. |  |  |  | Partially Accepted
Explaination of rejection or partially acceptance The UNCT agrees the CF should be developed with a robust TOC, resulting from inclusive consultation with the GOVN and all other relevant stakeholders, based on realistic resources, and in line with UNSDG guidance. In the curent CF guidance, immediate and intermediate outcomes are not part of the CF structure (rather outcomes and outputs are). The regional DCO and PSG strongly suggested including only outcomes in the CF results framework and the UNCT endorsed this in May 2021.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any) |  | Status of Implementation | Status of Implementation by 2022 end
1.1 | Develop 2022-2026 CF in line with the UNSDG guidance with robust TOC and results framework which enable more strategic and selective UN interventions, and greater accoutanbility and transparency of the UN system in Viet Nam | UNCT (with support of RCO, Outcome Groups, PMT, MSRWG) and GOVN | Feb - Jul 2021 | 30000 | 1 | completed | completed
1.2 | Set up relevant mechanisms (GOVN-UN taskforce, multis-stakeholder workshop and consultation) to ensure inclusive consultation with government, NGOs, mass organizations, DPs, and other stakeholders during CF development | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Jun - Jul 2021 | 5000 | 2 | completed | completed
Recommendation 2: The UNCT in consultation with the GOVN should take extra care for proper identification and definition of Outcome Indicators and their target values and strengthen the use of effective monitoring tools to ensure timely and effective monitoring of progress at both Output and Outcome levels. The monitoring of the next CF will benefit from active involvement of the GOVN as the latter is holder of data and information needed to assess progress towards achieving target values of the CF results indicators. The number of Outcome Indicators should be kept realistic to enable tracking of progress. Active involvement of GOVN agencies should optimally include use of national evaluation systems in the monitoring of progress that will further strengthen national data and information systems as well as national monitoring and evaluation capacities. In particular, the UNCT should develop and use indicators of progress that reflect immediate and intermediate results that are more closely linked with UN interventions and can therefore better define and measure the UN contribution to progress towards the achievement of high-level Outcomes within the duration of a single programme cycle. To the extent possible, UN entities should undertake efforts towards synchronization of their individual systems of monitoring for development results with the monitoring and evaluation system of the next CF. |  |  |  | Accepted with the important caveat stated below
Explaination of rejection or partially acceptance The recommendation on synchronization of individual agency systems of monitoring of results goes well beyond the country level and cannot be made a country level Agency responsibility. Both UN agencies (at country level), RCO and UNRC will continue to raise this with Agency at HQ level and DCO headquarters.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
2.1 | Select robust Outcome indicators as part of CF Results Framework which link with national SDG indicator framework and output areas to reflect UN contribution. Outcome indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | UNCT (through Outcome Groups with support of MSRWG) and GOVN | Jun - Jul 2021 |  | 3 | completed | completed
2.2 | Select robust Output indicators as part of CF Joint Work Plans which reflect UN specific contribution as results of UN interventions. Output indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | Outcome Groups (with support of MSRWG) | Aug - Oct 2021 |  | 4 | delayed | completed
2.3 | Develop the UNCT Monitoring, Evaluation, and Learning Plan, including a clear guidance on JWP planning, monitoring, review and reporting | MSRWG | Aug - Oct 2021 |  | 5 | delayed | completed
2.4 | Improve the UNInfo database (through sufficient data entry) and its use for monitoring of CF progress and UN contribution (both programmatically and financially) to SDGs and as a basis for UN discussion and identification of possible joint interventions | RGs and MSRWG | Aug - Oct 2021 |  | 6 | delayed | completed
Recommendation 3: The UNCT in consultation with the GOVN should carefully revise the coordinating role of the Joint Steering Committee (JSC) in order to ensure a meaningful and active participation of the GOVN and its representatives. A stronger role of the GOVN and key social partners identified for joint contributions to national priorities in the JSC will enhance the national commitment to and responsibility for the next CF as well as accountability for its implementation. By the same token, it will increase the GOVN and key social partners’ buy-in and ownership of the next CF and ensure that relevant national authorities will take resolute steps to ensure timely and effective implementation of CF interventions in line with the plans of the UN agencies and expectations of donors. |  |  |  | Accepted Please note the RC/UNCT has already advocated this for some time. Action is needed by the GOVN
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
3.1 | Revise the JSC TOR to strengthen JSC’s coordination towards strategic discussions and more active GOVN participation, especially for the new CF. | UNCT and GOVN (through JSC) | Aug - Oct 2021 |  | 7 | delayed | completed
3.2 | Implement the JSC TOR as designed and revise when necessary | JSC | Oct 2021 - End 2026 |  | 8 | delayed | ongoing as expected
3.3 | Ensure meaningful and active GOVN contribution to the CF development | UNCT and GOVN (through JSC) | Feb - Jul 2021 |  | 9 | completed | completed
Recommendation 4: In line with the UNSDG guidance and based on the experience from implementation of the OSP, the UNCT should carefully revise and optimize the current coordination mechanism for the next CF, in particular to strengthen the strategic position of the Results Groups in the CF coordination architecture and ensure alignment of the Results Groups with existing equivalent GOVN-led working structures. The Results Groups should be aligned with relevant GOVN-led sector structures (such as working groups, clusters) to ensure contribution of the UN RGs to such external mechanisms. Where equivalent GOVN-led structures do not exist, the RGs should incorporate representatives of relevant line ministries and key national partners. This arrangement will ensure a more coherent UN system-wide approach to CF strategic priorities and will be more inclusive through establishing linkages to the CF priority sectors. The extended RGs should meet at regular pre-established intervals in line with the UNSDG guidance. |  |  |  | Partially accepted
Explaination of rejection or partially acceptance It's agreed that Results Groups (RGs) need to play a more important and active role in implementing the CF as well as to have more interactions among and within Results Groups. This has always been the intention but results in different groups have been mixed and there is room for improvement. While it is important to ensure the linkage between Results Groups and the existing GOVN sectoral/thematic coordination structure to ensure meaningful contribution and alignment of the RGs to GOVN work, and also important to maximize maximize GOVN participation in RGs activities to the extent possible, the RG mechanism should be viewed as an independent internal UN mechanism and GOVN should not be included as members but should be invited as and when required. This is the common practice for other such independent development partner mechanisms (e.g. DPG) and is the appropriate approach.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
4.1 | Establish UN-internal CF Governance and Management Structure to ensure RG strategic position | UNCT | Aug - Oct 2021 |  | 10 | delayed | completed
4.2 | Develop (and implement at later stage) RG TOR to ensure RG strategic position, more frequent interaction within RGs, linkage with GOVN sectoral/thematical coordination structures, and maximized GOVN participation in RGs (including in the development of joint programmes) to extent possible | Results Groups for UNCT approval | Oct - Nov 2021 |  | 11 | delayed | completed
4.3 | Implement the CF Government and Management Structure and RG TORs as designed and revise when neccesary | Results Groups for UNCT approval | Oct 2021 - End 2026 |  | 12 | delayed | ongoing as expected
Recommendation 5: The UNCT should undertake a more systematic approach towards joint programming as a foundation for a more coordinated approach to implementation of the next CF. Under each CF Outcome, the UNCT should identify areas for collaborative work and develop a framework for collaborative efforts based on comparative advantages and complementarity of individual agencies. Such framework should provide substantive details of collaborative work of individual agencies, in accordance with their respective mandates, and building on their respective strengths. Existence of the framework will shorten time needed for preparation of Joint Programmes and facilitate thus timely and effective submission of the JPs for consideration of donors. The UNCT should also ensure collection of good practices and lessons learned for future joint programming |  |  |  | Accepted Results Group Joint Programme target (of at least one JP per RG per year) already exists and has been achieved, but should be strengthened
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
5.1 | RGs to discuss and identify areas for collective efforts and potential joint programmes annually during the JWP planning | Results Groups | Nov - Jan, annually |  | 13 | ongoing as expected | ongoing as expected
5.2 | Collect and review good practices and lessons learned on joint programming and joint programme during annual review/reporting period. Report to UNCT for strategic discussion for improvement of joint programming. | Results Groups and UNCT | Nov - March, annually |  | 14 | ongoing as expected | ongoing as expected
Recommendation 6: For formulation of the next CF, the UNCT should introduce indicators and target values that will enable systematic tracking of progress on mainstreaming of cross-cutting themes into the CF implementation. Mainstreaming od cross-cutting topics in development cooperation is a process that requires changes in awareness, attitudes, plans and programme implementation. There are some examples of approaches, tools and practices for mainstreaming the most common cross-cutting themes as well as tracking the progress and achievements. The challenge is to use them systematically and consistently in the project or programme cycle to enable monitoring of progress in their mainstreaming into the OSP implementation. |  |  |  | Accepted
Explaination of rejection or partially acceptance
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
6.1 | Identify cross-cutting priorities and LNOB in CF document | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Feb - Jul 2021 |  | 15 | completed | completed
6.2 | Mainstream cross-cutting priorities and LNOB into CF indicator frameworks (in the CF documents, JWPs, and MEL plan) to extent possible in line with relevant UNCT action plans (e.g. SWAP and UNDIS action plans) | UNCT (with support of MSRWG, GTG, etc.) and GOVN | Jun 2021 - Mar 2022 |  | 16 | ongoing as expected | ongoing as expected
Recommendation 7: The UNCT should conduct analysis of the various reporting levels of the UN agencies and harmonize the reporting format under the OSP with the reporting requirements of the UN agencies and main donors. Despite the differences in reporting practices across UN agencies and donors, there is a commonality in the information requested. It would be advisable to adjust the format for reporting of the UN agencies to the RGs according to the common information/reporting requirements of the UN agencies and donors. |  |  |  | Rejected
Explaination of rejection or partially acceptance The recommendation on OSP reporting is relevant, but requires a decision and harmonisation at HQ level, not country-level. In the earlier stage of OSP implementation, a review of reporting requirements of both individual agencies and DCO was conducted. However, this did not add much value to a more harmonized reporting system at country level since the requirements are mandatory and kept changing from the HQ level. Relevant feedback on double reporting, its burden and discrepancies have been provided to the HQ level repeatedly. The UNCT will continue to advocate with Headquarters and harmonize some internal formats at the national level to the extent possible but this recommendation needs to be addressed by HQ and cannot be addressed sufficiently at the country level.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
Recommendation 8: The UNCT needs to enhance the modality of coordination and support for non-resident agencies in collaboration with GOVN agencies. There remains an issue of delay process and less effectiveness of the collaboration between UN non-resident agencies and GOVN due to obstacles in direct communication and discussion. As a result, the formulated activities could be slow and even cancelled. The UNCT/RCO should take a more active role in support the discussion and approval process on behalf of non-resident agencies to increase the effectiveness of the cooperation via an effectively and timely implementation process and better communication. |  |  |  | Partially accepted
Explaination of rejection or partially acceptance The recommendation is relevant in the sense that it's necessary to enhance the coordination with non-resident agencies (NRAs) regarding collaboration with GOVN agencies. The RC/O has gone out of its way to do this over the years with mixed results based on NRA response and active interest. It's also important for strengthening UN-internal collaboration through NRAs' active sharing information of their activities, participation and presentation in and contribution to the UNCT, RGs, and other inter-agency coordination mechanisms; however this effort needs to be made by NRAs and DCO needs to provide more clear guidance on NRA participation in UNCTs and how this can be realized in practice given the existing significant structural constraints to enabling this.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
8.1 | UNCT/RCO to continue to support non-resident agencies in collaborating with GOVN agencies and other stakeholder to extent possible, and to consistently engage non-resident agencies in relevant groups/tasks/communication | UNCT/RCO | from now forward |  | 17 | completed | completed
8.2 | Non-resident agencies to be more active in sharing information of their activities, participating, presentating and contributing to the UNCT, RGs, and other inter-agency coordination mechanisms (including CF and JWP planning, implementation, monitoring and reporting) | Non-resident agencies | from now forward |  | 18 | completed | completed
Recommendation 9: The UN in Viet Nam should make assessment of sustainability of the Viet Nam SDG Fund and its potential for prioritization and mobilization of donor financing for the next CF. Although the current SDG Fund for Viet Nam was established in 2018, there has been very little success in mobilizing funds through this financial mechanism due to concerns about monitoring and reporting for accountability of the UN to donors. The UNCT should make reassessment of the country-level SDG Fund situation in comparison with other options, in particular with funds mobilization through joint programming through the Global SDG Fund. |  |  |  | Accepted
Explaination of rejection or partially acceptance It's agreed that a decision needs to be made on whether the VN SDG Fund should be kept for the future given the existing joint global fund and GOVN procedures and given that we may still get some funds through this country-level mechanism in the future. Nevertheless, it should be noted that at present, GOVN agencies have reservations about the SDGF TOR; thus it is not functional owing more to administrative reasons and Viet Nam's fast reducing ODA given its changing status to lower middle income country, and the creation of the Global SDG Fund which we have used more.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
9.1 | UNCT and GOVN to make a decision on whether we should keep the VN SDG Fund for the future given the existing joint global fund and GOVN procedures and given that we may still get some funds through this country-level mechanism in the future | UNCT and GOVN (through JSC) | Now - Aug 2021 |  | 19 | delayed | delayed
9.2 | If the decision is yes (for Action 9.1) then JSC to agree on the SDGF TOR | JSC | Aug - Dec 2021 |  | 20 | delayed | delayed
Recommendation 10: The UNCT should put emphasis on interventions related to the normative, capacity building and awareness raising mandates of the UN agencies that constitute major comparative advantages of the UN system. In this regard, the next CF should extend support and technical assistance to the GOVN for better understanding of international norms and standards, their integration into formulation of national policies and legislation as well as for effective implementation of the policies, strategies and action plans in line with international norms, standards, and conventions. The increased emphasis on the normative agenda and capacity building will propagate mainstreaming of the cross-cutting topics of data for development as well as learning and innovation. For field engagements not directly linked to the normative agenda, UNCT should look for opportunities for partnerships with organizations in the field such as local government organizations or NGOs. |  |  |  | Partially Accepted
Explaination of rejection or partially acceptance In fact, the UNCT emphasis on interventions related to UN normative and capacity building mandates is more or less in place. The more relevant issue is that the UN agencies are still working in a compartmentalized manner and there are inadequate global HQ-level corporate strategies to deliver the UN mandates in a more harmonized and effective manner and there is a need to discuss concretely how this will be addressed at global HQ level.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
10.1 | Discuss and identify directions/ways to enhance UNCT collective strategy and common messages on UN normative agenda | UNCT | from now forward |  | 21 | ongoing as expected | ongoing as expected
10.2 | Implement UNCT directions to enhance UNCT collective strategy and common messages on UN normative agenda, including through join workplanning, join programming, and UN joint messages | UNCT | from now forward |  | 22 | ongoing as expected | ongoing as expected
10.3 | Improve the UN joint communication for advocating UN normative agenda and common strategic messages through UNCT website and other media tools | UN Comms Group | from now forward | 3000 | 23 | ongoing as expected | ongoing as expected
Recommendation 11: The GOVN agencies should be engaged in designing the joint programmes with the UN agencies to ensure full partnership, commitment, and co-financing in the implementation of the next CF. The GOVN agencies have been positioned by the UNCT as partner rather than beneficiaries or implementers of activities. This best reflects the switch of the UNCT from donor to partner, from development assistance to partnership. Engagement of the GOVN agencies in designing the joint programmes will ensure commitments, ownership, and co-financing sources from the GOVN agencies for the implementation of the next CF. Given the uncertainty of global economic recovery, it is reasonable to anticipate a tightening financing prospect for the next CF and therefore, mobilizing counterpart contribution from the GOVN is also important in financial terms. |  |  |  | Accepted
Explaination of rejection or partially acceptance This has always been the intention and is often the case. National ownership is the key principle of 2030 Agenda and for UN operations. GOVN agencies, as one of the most important owners of UN support, have been engaged in JP design. The UN and GOVN will further engage GOVN agencies for more meaningful and timely contribution to JP design, approval and implementation. However, global joint fund short deadlines and some current requirements make this difficult to do sometimes, so there needs to be change in the global joint fund guidelines to more actively facilitate or allow this.
Actions to be taken |  | Responsible entities | Timeframe | Resource implication (if any)
11.1 | Strengthen GOVN engagement in designing joint programmes from the beginning and through out the whole JP development process | Relevant UNCT groups and GOVN agencies | from now forward |  | 24 | ongoing as expected | ongoing as expected

## Management Response (monito (2)
MANAGEMENT RESPONSE TO EVALUATION OF ONE STRATEGIC PLAN 2017-2021
Evaluation Title/Year: Evaluation of One Strategic Plan 2017-2021 / 2020-2021 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: OSP Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RC/UNCT and GOVN/MPI • Frequency of monitoring and updating: Every 6 months. Report made to JSC.
RESPONSES TO RECOMMENDATIONS
Recommendation 1: The UNCT, in consultation with the GOVN, social partners and other relevant stakeholders, should develop the next UN – GOVN Cooperation Framework (CF) based on a well-reasoned and robust Theory of Change. It is strongly recommended to adhere to the UNSDG guidance to formulate structured multi-layer outcomes and outputs during the Cooperation Framework design stage to ensure a clear logic in the TOC and the related results matrix. Developing a more accurate and robust TOC in line with the requirements set out in the UNSDG guidance will enable UN agencies to be more selective about their respective areas of focus and contribute to greater accountability and transparency of UN system interventions. Particular attention should be paid to formulation of immediate and intermediate outcomes in order to enable monitoring of progress and evaluation of the UN contribution to high level outcomes. The next CF should be based on a realistic overall budget envelope with maximized core and secured resources.
Explaination of rejection or partially acceptance The UNCT agrees the CF should be developed with a robust TOC, resulting from inclusive consultation with the GOVN and all other relevant stakeholders, based on realistic resources, and in line with UNSDG guidance. In the curent CF guidance, immediate and intermediate outcomes are not part of the CF structure (rather outcomes and outputs are). The regional DCO and PSG strongly suggested including only outcomes in the CF results framework and the UNCT endorsed this in May 2021.
Actions to be taken |  | Responsible entities | Timeframe |  | Status of Implementation | Status by end 2022
1.1 | Develop 2022-2026 CF in line with the UNSDG guidance with robust TOC and results framework which enable more strategic and selective UN interventions, and greater accoutanbility and transparency of the UN system in Viet Nam | UNCT (with support of RCO, Outcome Groups, PMT, MSRWG) and GOVN | Feb - Jul 2021 | 1 | completed | completed
1.2 | Set up relevant mechanisms (GOVN-UN taskforce, multis-stakeholder workshop and consultation) to ensure inclusive consultation with government, NGOs, mass organizations, DPs, and other stakeholders during CF development | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Jun - Jul 2021 | 2 | completed | completed
2.1 | Select robust Outcome indicators as part of CF Results Framework which link with national SDG indicator framework and output areas to reflect UN contribution. Outcome indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | UNCT (through Outcome Groups with support of MSRWG) and GOVN | Jun - Jul 2021 | 3 | completed | completed
2.2 | Select robust Output indicators as part of CF Joint Work Plans which reflect UN specific contribution as results of UN interventions. Output indicators are measurable and realistic in number, with available baseline and targets, with clear date sources, and with identification of UN agencies in charge of data reporting. | Outcome Groups (with support of MSRWG) | Aug - Oct 2021 | 4 | delayed | completed
2.3 | Develop the UNCT Monitoring, Evaluation, and Learning Plan, including a clear guidance on JWP planning, monitoring, review and reporting | MSRWG | Aug - Oct 2021 | 5 | delayed | completed
2.4 | Improve the UNInfo database (through sufficient data entry) and its use for monitoring of CF progress and UN contribution (both programmatically and financially) to SDGs and as a basis for UN discussion and identification of possible joint interventions | RGs and MSRWG | Aug - Oct 2021 | 6 | delayed | completed
3.1 | Revise the JSC TOR to strengthen JSC’s coordination towards strategic discussions and more active GOVN participation, especially for the new CF. | UNCT and GOVN (through JSC) | Aug - Oct 2021 | 7 | delayed | delayed
3.2 | Implement the JSC TOR as designed and revise when necessary | JSC | Oct 2021 - End 2026 | 8 | delayed | ongoing, need attention
3.3 | Ensure meaningful and active GOVN contribution to the CF development | UNCT and GOVN (through JSC) | Feb - Jul 2021 | 9 | completed | completed
4.1 | Establish UN-internal CF Governance and Management Structure to ensure RG strategic position | UNCT | Aug - Oct 2021 | 10 | delayed | completed
4.2 | Develop (and implement at later stage) RG TOR to ensure RG strategic position, more frequent interaction within RGs, linkage with GOVN sectoral/thematical coordination structures, and maximized GOVN participation in RGs (including in the development of joint programmes) to extent possible | Results Groups for UNCT approval | Oct - Nov 2021 | 11 | delayed | completed
4.3 | Implement the CF Government and Management Structure and RG TORs as designed and revise when neccesary | Results Groups for UNCT approval | Oct 2021 - End 2026 | 12 | delayed | ongoing as expected
5.1 | RGs to discuss and identify areas for collective efforts and potential joint programmes annually during the JWP planning | Results Groups | Nov - Jan, annually | 13 | ongoing as expected | ongoing, need attention
5.2 | Collect and review good practices and lessons learned on joint programming and joint programme during annual review/reporting period. Report to UNCT for strategic discussion for improvement of joint programming. | Results Groups and UNCT | Nov - March, annually | 14 | ongoing as expected | ongoing, need attention
6.1 | Identify cross-cutting priorities and LNOB in CF document | UNCT (with support of RCO, Outcome Groups, PMT) and GOVN | Feb - Jul 2021 | 15 | completed | completed
6.2 | Mainstream cross-cutting priorities and LNOB into CF indicator frameworks (in the CF documents, JWPs, and MEL plan) to extent possible in line with relevant UNCT action plans (e.g. SWAP and UNDIS action plans) | UNCT (with support of MSRWG, GTG, etc.) and GOVN | Jun 2021 - Mar 2022 | 16 | ongoing as expected | ongoing as expected
8.1 | UNCT/RCO to continue to support non-resident agencies in collaborating with GOVN agencies and other stakeholder to extent possible, and to consistently engage non-resident agencies in relevant groups/tasks/communication | UNCT/RCO | from now forward | 17 | completed | completed
8.2 | Non-resident agencies to be more active in sharing information of their activities, participating, presentating and contributing to the UNCT, RGs, and other inter-agency coordination mechanisms (including CF and JWP planning, implementation, monitoring and reporting) | Non-resident agencies | from now forward | 18 | completed | completed
9.1 | UNCT and GOVN to make a decision on whether we should keep the VN SDG Fund for the future given the existing joint global fund and GOVN procedures and given that we may still get some funds through this country-level mechanism in the future | UNCT and GOVN (through JSC) | Now - Aug 2021 | 19 | delayed | delayed
9.2 | If the decision is yes (for Action 9.1) then JSC to agree on the SDGF TOR | JSC | Aug - Dec 2021 | 20 | delayed | delayed
10.1 | Discuss and identify directions/ways to enhance UNCT collective strategy and common messages on UN normative agenda | UNCT | from now forward | 21 | ongoing as expected | ongoing as expected
10.2 | Implement UNCT directions to enhance UNCT collective strategy and common messages on UN normative agenda, including through join workplanning, join programming, and UN joint messages | UNCT | from now forward | 22 | ongoing as expected | ongoing as expected
10.3 | Improve the UN joint communication for advocating UN normative agenda and common strategic messages through UNCT website and other media tools | UN Comms Group | from now forward | 23 | ongoing as expected | ongoing as expected
11.1 | Strengthen GOVN engagement in designing joint programmes from the beginning and through out the whole JP development process | Relevant UNCT groups and GOVN agencies | from now forward | 24 | ongoing as expected | ongoing as expected

## Sheet2
cancelled | June | 2022
delayed | December | 2023
ongoing as expected |  | 2024
ongoing, need attention |  | 2025
completed |  | 2026
2027
2028
2029
2030