UGANDA UN COUNTRY TEAM WORKPLAN

JUNE 2024 - DECEMBER 2025

1.0 Background

The UN Country Team (UNCT) in Uganda is committed to accelerating the achievement of the Sustainable Development Goals (SDGs) through strategic initiatives and enhanced coordination. In line with the priorities outlined during the recent UNCT Retreat, this workplan for 2024-2025 focuses on supporting the six transitions for SDG acceleration, strengthening coordination at central and regional levels, enhancing UN coherence through joint programmes and initiatives, improving staff welfare and wellbeing, and designing a new cooperation framework. This period is crucial for planning as the new cooperation framework and agency country programmes are being designed.

2.0 Purpose and Objectives

The purpose of this workplan is to provide a structured approach for the UNCT in Uganda to achieve its strategic objectives over the next two years. The key objectives are:

- Support the six transitions for SDG acceleration.

- Strengthen coordination mechanisms at both central and regional levels.

- Enhance UN coherence and impact through the lenses of the UN Reform.

- Improve staff welfare and wellbeing to ensure a motivated and productive team.

- Design and implement a new Cooperation Framework that is aligned with national priorities and the 2030 Agenda.

3.0 Management Arrangement

The implementation of this workplan will be overseen by the UN Resident Coordinator supported closely by each Head of Agency and the team in the Resident Coordinator’s Office (RCO) in Uganda. Heads of agencies are expected to demonstrate leadership and accountability on task assigned, with required status updates provided to the RC and UNCT as and when required. The Head of RCO will lead a dedicated coordination team to facilitate the execution of activities, ensure effective communication among UN agencies, and facilitate stakeholder engagement.

4.0 Monitoring and Reporting

Monitoring and reporting will be integral to the implementation of this workplan. Regular progress reviews will be conducted to ensure activities are on track and outputs are being achieved. Quarterly briefing will be provided in the UNCT monthly meeting to update on progress, review and address challenges and make decision where required. Semi-annual or annual reports will be prepared, highlighting progress, challenges, and lessons. Key performance indicators as listed in the document will be used to measure success and obtain feedback from the UNCT and staff which will be incorporated to enhance the effectiveness of current and future interventions.

5.0 UNCT Workplan Matrix:

| Outcome: There is increased collaboration and common approaches among the UNCT in Uganda that are fostering programmatic and operational impact in the implementation of the UN Reform and achievement of the goals in the 2030 Agenda for sustainable development. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Subject | Output and output indicator | Activities | Responsible Party | Timeline | Budget (USD) |
| Supporting key national processes integrating the six transitions for SDG Acceleration | UN contribution and support to NDP III and IV and the Parish Development Model are harmonized and enhanced. Output Indicator: Proportion of initiatives linked to this workplan supported by the UN (Total number of initiatives/total number of those supported) Target: At least 0.8 | Define a clear role for the UN in the upcoming elections | RCO | Q4 2024 | TBD |
|  |  | Ensure the UNCT is supporting the NDP IV process | UNDP | Q2 2024 | TBD |
|  |  | Streamline UN support to the Parish Development Model | UNDP | Continuous | TBD |
|  |  | Coordinate UN support to other government related processes such as VNR, national SDG conference, Census 2024 and | RCO | Continuous | TBD |
|  |  | Advocate and support the development of bankable projects linked to the six transitions | Agency leads | Q2 2025 | TBD |
|  |  | Support the National Partnership Forum and its annual engagement with partners | RCO | Q4 2024 | TBD |
|  |  | Coordinate UN support to the Summit of the Future | RCO | Q3 2025 | TBD |
|  |  | Ensure an annual dialogue meeting between the UNCT and the Presidency. | RCO | Q4 2024 and Q4 2025 | - |
|  |  | Aid national initiatives aimed at enhancing domestic financing and revenue mobilization and Uganda’s 10-fold growth aspiration. | UNDP | Continuous | TBD |
|  |  | Review and discuss the completed vulnerability assessment to understand structural factors contributing to vulnerability in Uganda. | UNAIDS and UN WOMEN | Q2 2024 | - |
| Implementation of the UN reform initiatives | Results of the UN reform implementation in Uganda are consolidated and sustained. Indicator: Number of existing and new activities linked to UN reform under implementation. Target: All UN reform related actions are undertaken by December 2025. | Participate in regular coordination meetings such as the monthly UNCT Meeting, HCT-Light and other Heads of Agencies related meetings | UNCT | Continuous | - |
|  |  | Capacitate and strengthen the role of UNACs and ensure their effective participation in UNCT functions | UNCT | Continuous | 10,000 |
|  |  | Provide leadership for UN coordination groups to ensure effective accountability | UNCT | Continuous | - |
|  |  | Oversee the effective implementation of the flagship joint programmes – Youth, Data and Statistics, gender-based violence, etc. | UNCT | Continuous | 5,000 |
|  |  | Ensure the effective functioning of the groups your agency is leading (results groups and functional groups such as Partnership and Communication, RBM, SDG, Gender and Human Rights, Humanitarian, and PSEA). | UNCT | Continuous | 20,000 |
|  |  | Encourage and facilitate participation of agency staff in CF related processes such as monthly and quarterly meetings, data collection through UN INFO, annual reviews, and reporting. | UNCT | Continuous | - |
|  |  | Chairs of Strategic Priorities lead dialogue and discussion on priority areas of the CF with government and other national stakeholders. | UNCT | Q3 2024 and Q3 2025 | 20,000 |
|  |  | Collaborate in the UN efficiency agenda through the Business Operations Strategy, common premises, and other efficiency initiatives | UNCT | Continuous | 80,000 |
|  |  | Explore the feasibility and viability of a Common Back Office or Local Shared Service Centre in Uganda | RCO | Q4 2024 | 5,000 |
| Promoting UN Coherence and impact on the ground | UN coherence is increased through joint advocacy, resource mobilization, joint programmes, and communication. Indicator: Per cent of UN collaboration demonstrating UN coherence and collective impact on the ground Target: At least 90% All planned coherence activities are undertaken by December 2025 | Develop and implement a comprehensive UNCT advocacy agenda. | HoAs (volunteers) | Q2 2024 | 5,000 |
|  |  | Coordinate and undertake actions to implement the UN Common Pledge for refugees | RCO and UNHCR | Continuous | - |
|  |  | Harmonize UN work on PSEA, non-discrimination and other relevant normative agenda | RCO | Continuous | 50,000 |
|  |  | Organise one UNCT Retreat per annum. | RCO | Q1 2025 | 15,000 |
|  |  | Convene regular dialogue with government and non-government development partners on issues of common interest as part of the rollout of the advocacy agenda. | Chair of SPs | Q3 2024 and Q3 2025 | 30,000 |
|  |  | Expand and continue strategic dialogue with partners at core. | RCO | Continuous | 10,000 |
|  |  | Undertake more thematic UNCT dialogues as part of an integrated approach. | Chair of RGs | Quarterly | 5,000 |
|  |  | Ensure the National Joint Steering Committee on the CF is held annually | RCO | Q2 2024 and Q1 2025 | 15,000 |
|  |  | Develop and implement a robust UN visibility action plan to tell the world more about UN in Uganda. | UN Communications Working Group | Q3 2024 | 30,000 |
|  |  | Develop and monitor a comprehensive programme and workplan on UN in Karamoja. | UN Deputies | Continuous | 10,000 |
|  |  | Strengthen engagement with the private sector and revive the private sector platform. | UN partnership Working Group | Continuous | 10,000 |
|  |  | Develop and adopt a harmonized approach to funding joint programmes and initiatives in Uganda i.e. MPTF, local cost-share budgets, or basket funds, etc. | Chair of UN Partnership Working Group | Continuous | 10,000 |
| Enhancing Staff welfare and wellbeing | Expected Output: UN Uganda international and national staff welfare and wellbeing are improved. Indicator: Number of welfare and wellbeing initiatives implemented. Target: 10 initiatives by December 2025 All proposed staff welfare and wellbeing initiatives completed by December 2025 | Ensure adequate security and safety of all UN premises, personnel, and assets. | UNDSS | Continuous | - |
|  |  | Establish a functional occupation hazard and safety committee for Uganda (OSH). | OMT and UNDSS | Q3 2024 | 5,000 |
|  |  | Ensure corporate processes linked to staff welfare and wellbeing are properly streamlined and managed i.e. salary surveys, post adjustments, DSA surveys, and other related exercises. | OMT | Continuous | 5,000 |
|  |  | Work with staff association to resolve the problem of the UN clinic. | UN Clinic Committee | Q2 2024 | - |
|  |  | Ensure efficient medical service provision to all staff including those in the fields | HoA | Continuous | - |
|  |  | Implement health and wellness programmes for staff in collaboration with staff association. | UN Wellness Group | Continuous | 50,000 |
|  |  | Celebrate UN Day and other important global holidays with all staff (estimated budget per annum) | RCO | Q4 2024 and Q4 2025 | 50,000 |
|  |  | Facilitate access to mental health support services to staff | UN Wellness Group | Continuous | TBD |
|  |  | Support the organization of annual all-staff team-building event – annual staff get-together (estimated contribution per annum) | RCO and Staff Association | Continuous | 30,000 |
|  |  | Organise townhalls for all-staff | RCO | Q2 2024, Q4 2024, Q2, 2025 and Q4 2025 | 5,000 |
|  |  | Work with staff association to provide professional development opportunities to all staff. | Staff Association | Continuous | 5,000 |
| Ensuring effectiveness and compliance in the design of a new Cooperation Framework | Expected Output: New CF Cooperation Framework completed by signed by September 2025 Indicator: Approval of the new Cooperation Framework. Yes/No Target: Yes, by September 2025 | Ensure the evaluation of the cooperation framework is completed on time. | UNCT | Q3 2024 | 70,000 |
|  |  | Provide oversight in the Common Country Analysis (CCA) process. | UNCT | Q3 2024 | 40,000 |
|  |  | Ensure stakeholders are consulted in the CF processes as outlined in the CF Roadmap. | UNCT | Continuous | 100,000 |
|  |  | Review and refine draft Cooperation Framework with stakeholders. | UNCT | Q1 2025 | 10,000 |
|  |  | Ensure the CF results framework aligns Cooperation Framework with NDP IV | UNCT | Q1 2025 | - |
|  |  | Provide quality assurance in the drafting and finalization of the Cooperation Framework. | UNCT | Q2 2025 | - |
|  |  | Support the dissemination of the final Cooperation Framework. | UNCT | Q3 2025 | 15,000 |

6.0 Budget

The total budget for the implementation of this workplan is USD 715,000. This budget will cover activities related to supporting national processes for SDG acceleration, strengthening coordination mechanisms, enhancing UN coherence, improving staff welfare, and designing a new cooperation framework. Detailed budget allocations have been made for each output and activity to ensure clear linkage between activities, resources, and results. Total resources available (from the RCO core budget and UNCT 2024 Cost-share budget) for some of these activities in 2024 is USD 75,000 with a further USD 50,000 committed by the DCO Regional Office for Africa for 2025. A total of USD 590,000 is required for 2025, which is expected to be funded through a UNCT cost-share.

Budget Breakdown

|  | Amount (in $) | Source | Coverage (activities) |
| --- | --- | --- | --- |
| Available Resources | 75,000 | RCO core budget – USD 75,000 | CF evaluation, Common Country Analysis |
|  |  | UNCT Cost-share budget | The CSB has covered activities related to UN wellness, OMT Officer position, PSEA and related activities and UN Day in 2024. The budgeted amounts above are for 2025. |
| Commitment for 2025 | 50,000 | RCO core budget | CF design and consultation with partners |
| To be funded by the UNCT | 590,000 | 2025 Cost share budget | All remaining activities in this workplan |
| Total Required Budget | 715, 000 | All agencies | All activities in this workplan |

The exact budget or cost of these activity will be determined when the time is right.

The agency leads in the provision of the support and RCO coordinates any UN system-wide support required for the activity.

Lead agencies are based on the roles assigned to agencies on the ‘Six Transitions’ during the February 2024 UNCT Retreat at Protea, Entebbe.

The listed agencies will cover the cost of these initiatives.

Cost for this is usually borne by the hosting UN entity.

UNCT here refers only to Heads of Agencies or their assigned representative.

This budget line is linked to the OMT post and related workshops for BOS.

The cost for this activity is in the UN Common Pledge

Estimate for this is provided as part of the security budget.

No further contribution is required in 2024. Similar activities in this workplan are already covered in the UNCT 2024 cost-share budget. The above amount is for 2025.