## Sheet1
Country: Tajikistan; UNDAF / CF 2016 - 2022 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Tajikistan UNDAF Evaluation report / 2021 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RCO • Frequency of monitoring and updating: Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: UNCT should remain flexible and responsive to the needs of the citizens and priorities defined in the national strategic documents in Tajikistan and continue with the activities and the efforts under the ISEF strategic areas.
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation:
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | *Conduct prioritization process for new CF design in consultation with stakeholders (Gov.entities and CSOs to extent possible) to define and agree upon national priorities in alignment with SDGs | 2022-03-01 | UNCT/RCO | CF design has been initiated | ongoing as expected | December | 2022
Recommendation 2: UN Agencies in Tajikistan should prioritize long-term interventions, clearly linked to SDGs and national priorities, with explicitly set results and focus on sustainability. The inclusion of vulnerable groups should be considered as a programming principle, linking them with comparative advantages of UN Agencies in Tajikistan.
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Update the Vulnerability ATLAS and use it for policy making and implementation | Sept 2021 - Jun 2023 | UNCT | Request letter received from the GoT | not started | June | 2023
2.2 | Support the GoT to revive the National Poverty Council (NPC) | Sept 2021 - Jun 2023 | UNCT | NPC has new composition; Preliminary discussion held with MEDT/WB | not started | June | 2023
Recommendation 3: UN Agencies/ UNCT together with GoT should work to strengthen functioning of the UNDAF Joint Steering Committee and ensure its strategic guidance for UNDAF implementation, through regular meetings and involvement of senior level representatives.
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: |  | UNDAF JSC and RGs is functioning with some limitations during 2020 due to the pandemic situation. UNCT agrees the GoT and Non Got stakeholders should be more actively engaged in the work of both JSC and RGs
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Involve GoT partners and CSOs more actively and meaningfully into the new CF planning, implementation and reporting processes (including JWPs) | September 2021 - June 2023 | UNCT | CF is under development | ongoing as expected | June | 2023
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: UNCT should intensify its normative work as one of UN comparative advantages and further strengthen gender mainstreaming across UNDAF outcomes.
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: |  | UNCT has been active in normative work jointly and within UN Agencies' mandates. However UNCT agrees to the recommendation to mainstream gender equality and empowerment of women in all activities and initiatives across all UNDAF outcomes and focus areas.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Develop a costed gender strategy and action plan for UNCT Tajikistan in alignment with UNCT SWAP scorecard and UNDAF/CF priorities and the “Women and Men in Tajikistan” statistical publication | September 2021 - June 2023 | UNCT/UN GTG | Comprehensive UN SWAP has been initiated in 2021 | not started | June | 2023
4.2 | Intensify the work of UN GTG in UNDAF/CF planning, implementation and reporting processes | September 2021 - June 2023 | UN GTG | UN GTG is in place | ongoing as expected | June | 2023
Recommendation 5: The UN Agencies should explore and work on new partnerships and diversification of funding opportunities.
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation:
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Involve donors and potential partners into CF planning and reporting processes to increase shared vision of development goals and transparency (including through DCC platform) | September 2021 - June 2023 | UNCT/RCO | Active DCC groups | ongoing as expected | June | 2023
5.2 | Use the CF to promote joint programming including for resource mobilization | September 2021 - June 2023 | UNCT/RCO | Experienced in conducting joint programmes. Repository of joint proposals | ongoing as expected | June | 2023
5.3 | Develop UNCT partnership strategy to diversify funding opportunity and to engage partners into implementation of CF | September 2021 - June 2023 | UNCT/RCO | N/A | not started | June | 2023
Recommendation 6: UNCT in partnership with the national stakeholders should prepare clear and practical sustainability strategy under all outcomes and perform regular analysis of risks and assumptions The FET recommends to develop a sound approach to measure capacity development across all priority areas and assess impact of these enhanced capacities. At the current stage of development of systems, structures and capacities of the authorities within three branches of power, it is important to consider and provide a longer-term and needs-based capacity development assistance. Especially important remains to continue work on the development of capacity for policy making and implementation in Tajikistan. The role of the national stakeholders in the implementation of UNDAF could not be overstated- it is recommended to enhance and ensure genuine involvement of national partners in all activities, from planning to implementation of interventions within UNDAF. The FET recommends UNCT to expand its partnership with CSOs, to strengthen their capacities across main functional areas, while engaging them in policy-making processes and delivery of public services. Also, it is recommended to strengthen the watchdog role of the CSOs for competent monitoring of development processes, policies, and strategies thus competently involve in the implementation of the SDG related priorities. (linked to the Conclusion 2, Conclusion 7, also other conclusions could be relevant)
Management response - Accepted/Partially Accepted/Rejected |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation:
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT/RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Develop a sustainability strategy for the new CF based on the analyses of risks and assumptions, stakeholder engagement and existing governance and implementation mechanisms | September 2021 - June 2023 | UNCT/RCO | N/A | not started | June | 2023
6.2 | Engage CSOs across main functional areas to support their role in policy-making processes and delivery of public services (eg., dialogue platforms, capacity building interventions and involvement in CF processes). | September 2021 - June 2023 | UNCT | Fragmented invovlement of CSOs | ongoing as expected | June | 2023

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030