1. Recommendation:

1. The UNCT and Government are called to improve the strategic positioning of the next UNDAF  (strategic focus versus inclusiveness)

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| UNDAF 2016-2020 has been aligned with NDS 2016-2030, MTDP 2016-2020 [Added: 2019/07/04] | UNCT | 2015/12 | Completed |  |  |

2. Recommendation:

2. The UNCT and Government could look into the possibility of developing an UNDAF Action Plan

##### Management Response: [Added: 2019/07/04]

no longer applicable

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| no longer applicable [Added: 2019/07/04] | no longer applicable | 2015/12 | No Longer Applicable | [Justification: no longer applicable ] |  |

3. Recommendation:

3. The UNCT and Government should ensure the continued relevance of the UNDAF

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| To conduct UNDAF Mid-Term review [Added: 2019/07/04] | UNCT | 2018/08 | Completed |  |  |

4. Recommendation:

4. The Government should strengthen their ownership and coordination of the UNDAF, and the UNCT and Government should encourage the involvement of NGOs and CSOs at a more strategic level

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| Joint Steering Committee/Annual review meetings with the engagement of CSOs are regularly conducted [Added: 2019/07/04] | UNCT | 2021/12 | Initiated |  |  |

5. Recommendation:

5. The UNCT and Government should maintain a geographical targeting in the UNDAF implementation

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| no longer applicable [Added: 2019/07/04] | no longer applicable | 2021/12 | No Longer Applicable | [Justification: no longer applicable] |  |

6. Recommendation:

6. The UNCT and Government should enhance the effectiveness of the UNDAF

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| Joint UN/Government Result Groups have been established with clear roles from both sides. UNDAF Coordination and M&E Group has been established to support UNCT in UNDAF coordination, M&E and reporting. [Added: 2019/07/04] | RCO | 2016/02 | Completed |  |  |

7. Recommendation:

7. The UNCT is invited to strengthen joint programming and implement targeted joint programmes

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| For the period of 2016-2019, UNCT initiated 5 joint programmes in areas of cross border cooperation, health, and vulnerability [Added: 2019/07/04] | UN Agencies | 2021/12 | Initiated | on-going |  |

8. Recommendation:

8. The UNCT should strengthen the UN’s strategic positioning in the Development Coordination Council and other coordination mechanisms

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| UN Agencies are the members of DCC and advocate UN values and programmes [Added: 2019/07/04] | UN Agencies | 2021/12 | Initiated | on-going |  |

9. Recommendation:

9. UN agencies are called to increase their cooperation, and the UNCT and Government should put in place Results/Outcome Groups, and Thematic Groups, raise their profile, and use them to manage the UNDAF strategically

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| 8 Result Groups for 6 UNDAF Outcomes have been established. To support UNDAF implementation and advise UNCT on various development areas following thematic groups were established: Gender, Youth, HIV. [Added: 2019/07/04] | UNCT | 2021/12 | Initiated |  |  |

10. Recommendation:

10. The UNCT should ensure a better resource mobilization around the UNDAF strategic goals

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| Resource mobilization is a high priority of UNCT and # of concept notes and proposals have been prepared to tackle future financing opportunities [Added: 2019/07/04] | UNCT | 2021/12 | Initiated | on-going |  |

11. Recommendation:

11. The UNCT and Government should strengthen their use of effective RBM and M&E systems to monitor and manage the UNDAF strategically

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| 1. UNCT and Government conducted RBM workshop to strengthen the capacity in UNDAF implementation, monitoring and reporting. 2. As per MTR recommendations, UNDAF RRF was updated and validated by both parties. 3. UNDAF was extended until 2021 to ensure that the new UNDAF is better aligned with the national priorities and SDG agenda. [Added: 2019/07/04] | UNCT & UNDAF Coordination and M&E | 2016/12 | Completed |  |  |

12. Recommendation:

12. The UNCT should produce high quality annual reviews and a Progress Report at mid-term, together with a final evaluation

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| Annual Results Reports and MTR report have been developed and shared with UNDAF partners [Added: 2019/07/04] | RCO | 2021/12 | Initiated |  |  |

13. Recommendation:

13. The UNCT should ensure a greater mainstreaming of cross-cutting issues and the five UNDAF programming principles in the UNDAF

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| UNCT conducted UN SWAP in 2017 and implemented review of UNDAF from gender perspectives in 2018. As per MTR WASH and Migration were integrated into the UNDAF. [Added: 2019/07/04] | UNCT | 2019/04 | Completed |  |  |

14. Recommendation:

14. The UNCT and Government should use the UNDAF to strengthen the efficiency of the UN system and implementing partners

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| UNCT follows the requirements of Delivering as One SOP and implements separate elements of DaO. As such majority of requirements have been implemented and reported. [Added: 2019/07/04] | UNCT | 2021/12 | Initiated | on-going |  |

15. Recommendation:

15. The UNCT should increasingly “communicate as one”

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| UNCT established UN Communication Group to strengthen one UN communication and to support UNDAF reporting and further advocacy. The UNCG keeps functioning hitherto [Added: 2019/07/04] | UNCG | 2021/12 | Initiated |  |  |

16. Recommendation:

16. The UN system in Tajikistan should continue its efforts to Deliver as One

##### Management Response: [Added: 2019/07/04]

Agree

##### Key Actions:

| Key Action | Responsible | DueDate | Status | Comments | Documents |
| --- | --- | --- | --- | --- | --- |
| as per action plan provided under recommendation #14 [Added: 2019/07/04] | UNCT | 2021/12 | Initiated | on-going |  |