## Sheet1
Evaluation Recommendations Tracking Matrix
| Evaluation Title: | The evaluation of the United Nations Strategic Framework for Libya (2019-2022)
| Office\Region: | Resident Coordinator Office / Libya
| Year of the Report: | July - October 2021
| Overall Response to the evaluation: | Overall, the UNSF evaluation was a useful exercise to consolidate the lessons learned across the UN system, government counterpart, donors, and other stakeholders, with a view to improving the UN's positive impact and delivery of services to the people in need. Its findings aim to inform the formulation and implementation of the new UNSDCF (2023-2025), in line with the UNDS reform requirements.
| Planned use of the evaluation | It will guide the revision of the UNSF revision in line with its extension, as well as the design and implementation of the next Cooperation Framework.
| Important Annexes | The UNSF evaluation report
Evaluation Recommendations Tracking Matrix for Strategic Framework Evaluation
# | MANAGEMENT RESPONSE TO EVALUATION RECOMMENDATIONS | [7 empty] | IMPLEMENTATION TRACKING
| Evaluation Finding Number | Recommendation Number | Evaluation Recommendation | Management Response | Management Response summary | Actions to be taken | Action By | Implementation timeframe | Status | Implementation remarks/ narrative | Last update
| (as per the evaluation report)+B10:K11 | (as per final published evaluation report) | (as per final published evaluation report) | (Is recommendation Accepted, partially accepted or not accepted) |  | (Briefly state what actions will be taken to address the recommendation) | [specify the responsible team within RCO/ UNCT / Country Offices, HQ or, External Stakeholders | [Month, Year] | [Not started] [In progress] [ On hold] [Completed] | (brief on action taken if status is completed, or ongoing actions is status is in progress, or reasons why actions are on hold or not started)
1 | 2 | 1 | The UNCT to reduce the next CF document size and to focus on the ToC and RF | Accepted | Informed by the UNSF evaluation findings and a new CCA, a new UNSDCF for Libya aims to be a strategic framework of the UN's actions with clear priorities. The RCO already convened a CCA and a UNSDCF workshop on 29 Nov - 1 Dec 2021, where CCA findings were presented and endorsed and the key thematic/priority work areas of the UNSDCF were agreed on. This exercise will be the start to a number of actions that feed into fulfilling this recommendation. | 1.Endorse CCA findings and which reflect the demands mapped on the ground. 2. Agree on the main priority areas for the UNSDCF and which shall be targeted and realistic. 3. Develop strategic objectives and outcomes: a.Heavily informed by the CCA findings and using the theory of Change, strategic/thematic objectives and outcomes should be developed in coordination with the UN system in Libya, the government, and other stakeholders. b.UN agencies to then commence developing their CPDs. 4.Elaborating the UNSDCF results framework, informed by the SF evaluation and the CCA including data collected as part of the CCA exercise. | UNCT, RCO | Nov 2021 – May 2022
2 | 2 | 2 | The UNCT to enhance strategic focus and prioritization in the next CF.
3 | 3 and 8 | 3 | The UNCT to build from the good progress under HDP nexus approach | Accepted | The HDP nexus will remain as the core principle to inform a UNSDCF for Libya, building on the work coordinated by the Nexus Working Group since 2019 | 1 Building on the NWG's work, the UNCT to develop, implement, and monitor Collective Outcomes under the UNSDCF. | UNCT, NWG, RCO | Nov 2021 – May 2022
4 | 2, 4 and 12 | 4 | The UNCT to ensure next CF includes operational plans and planning tools to reflect Joint Programming | Accepted | In line with the UNDS reform requirements, the UNCT aims to develop Joint Work Plans and revamp the Results Groups to coordinate the UNCT's implementation of the UNSDCF for the period of 2023-2025. | PMT and its Results Groups to develop and implement the Joint Work Plans for the UNSDCF (2023-2025). The JWP should be regularly monitored by M&E Group and reported through the UNCT annual report. | UNCT, RCO | Jan 2023 -- Dec 2025 (TBC)
5 | 8 | 5 | The UNCT and implementing partners (where applicable) to ensure all interventions are grounded in strong needs assessments and thorough analysis of Libyan government buy-in. | Accepted | The CCA conducted in Sept-Nov 2021 was to assess the needs of the people in Libya across the H-D-P pillars, which should form a strong basis for the UNSDCF. During the UNSDCF process, regular government dialogues should be organized to ensure the government's buy-in. Based on annual CCA updates, the UNSDCF should be updated to correctly reflect the changing needs and contexts of Libya. | 1.Ensure that objectives within the new CF are informed by demands sensitized on the ground by the CCA 2. Efficiently engage donors and the international community on pursue of collective outcomes to ensure targeted and focused support. 3. Ensure efficient coordination with and engagement of the government at all levels starting from developing the CF to implementing it. | UNCT, RCO | Nov 2021 -- Dec 2025 (TBC).
6 | 6 | 6 | The UNCT to integrate periodic risk analysis, scenario definition and contingency planning exercises into programmes planning and implementation. | Partially accepted | While the UNCT and RCO in Libya have limited capacities in these areas, particularly due to extremely volatile context of Libya, but the UNCT and RCO should endeavor to integrate regular risk analysis as part of the annual CCA updates, which subsequently inform the UNCT's programming. | 1. 1. Regular update of a light risk analysis as part of the CCA 2. As relevant and capacity/situation allows, scenario planning and thorough risks analyses could be conducted. | UNCT, RCO | Nov 2021 -- Dec 2025 (TBC).
7 | 9,12,16,18 | 7 | The UN to increase capacity of the RCO to provide support, coordination, follow up, M&E and outreach to donors uniquely in areas of comparative advantages. | Partially accepted | The RCO has completed its recruitment of core staff in Sept 2021, which allows the coordination of the internal UNCT issues. However, as per the DCO-OECD mission findings (Oct 2021), the RCO would require additional capabilities to deliver additional functions such as the coordination of international community and liaison with the government as per their high expectations. | 1. Explore the possibility of recruiting additional capacity to support coordination with donors and international community, as well as the government of Libya. | RCO | Nov 2021 -- Dec 2025 (TBC).
8 | 4,12,13,16 | 8 | The Libyan government, UNCT and donors to set realistic aims and targets for coordination and what specific, coherent outcomes coordination is supposed to produce for Libyans, migrants, and refugees | Accepted | The implementation of the UNSF was challenged in many ways, ranging from its own limitations such as lack of human resources within the RCO for coordination and limited functioning of the UNCT coordination mechanisms to another layer of complexity that came from the government given divided institutions between the East and the West and the lack of a National Development Plan. While there are many external factors that are beyond the UN's control, through the new UNSDCF to be developed in consultation with the government and international community, the UNCT aims to be strategic in delivering its identified/agreed priorities to the people in need through well-coordination implementations (Results Group, JWP, etc.). | 1. RCO should continue to facilitate regular UNCT meetings, UNSMIL bi-weekly briefings, WGs meetings for improved information sharing and coordination within the UN system. 2. UNCT and RCO should continue to work on implementing the recommendations of the OECD-DCO mission, particularly on a coordination model within the international community and with the government. 3. UNCT and RCO to ensure engagement with government counterparts in the different stages of developing the UNSDCF. 4.Work on the communication and advocacy strategy of the UNSDCF | UNCT, PMT, UNCG, RCO | Jan 2022 -- Dec 2025 (TBC)
9 | 2 | 9 | The UNCT to work across regions and sectors in an agile mode, where sector/location-related teams both share information and coordinate interventions, and closely plan and implement integrated approaches | Accepted | The annual CCA updates should allow regular review of the UNSDCF's relevance in the fast-changing context of Libya. Once launched, the UNSDCF should institutionalize its Results Groups (sectors) as well as the Nexus Working Group (sector and location). In addition, if additional capacity can be recruited, RCO aims to deploy its staff to the Benghazi hub. | 1. UNCT and RCO should regularly update the CCA and make adjustments to the UNSDCF as needed. 2. UNCT and RCO should revamp the Results Group under the PMT and the Nexus Working Group informed by the outcome areas of the UNSDCF, including new Collective Outcomes. | UNCT, PMT, NWG RCO | Jan 2023 -- Dec 2025 (TBC)
10 | 11 | 10 | The UNCT to adopt a system building approach to support and build the capacities and practices around data collection and analysis for relevant authorities (a national statistical system including the Bureau of Statistics and other agencies). | Accepted | As identified in the CCA, the data ecosystem in Libya requires significant efforts across all areas. In other words, it would require longer-term approach in partnership with all international and national stakeholders. The UNCT, together with the EU and the WB, aims to support the government in data capacity through the Recovery and Peace-Building Assessment (RPBA) that was endorsed by the government in Sept 2021. The RPBA is planned to conclude with the launch of a national development plan in 2023. | 1. The UNSDCF should support national stakeholders, especially for the National Statistics System, with capacity building on good practices related to data collection, consolidation, and analysis, to the extent possible. 2. The UNCT in partnership with the EU and the World Bank focuses on building institutional capacity for data collection, consolidation, and analysis through the RPBA. | UNCT, RCO | Jan 2022 -- Dec 2025 (TBC)
11 | 9 and 18 | 11 | The RCO to consider whether more detail could be provided on results indicators and lessons learned in annual reporting, which may require more support from the UNCT’s M&E working group. | Accepted | Agreed with no further comments. | 1. PMT, M&E WG and the RCO should clearly elaborate the result framework of the UNSDCF to allow effective monitoring of the UNSDCF implementation. | PMT, M&E WG, RCO | Feb 2022 -- Dec 2025 (TBC)
12 | 10 and 16 | 12 | The UNCT to continue to champion right based approaches and gender equalities, however, UNSF for the next two years should consider including managed expectations about a generational perceptions and attitudes reform and ensure no harm when working on issues that have negative perceptions | Accepted | Recommendation 12 emphasized on UNCT to continue the good practices on championing right based approaches, gender equality and inclusion of youth. The UNCT aims to build on good practice, while carefully tailoring messages and designing programmes given the sensitivities of those normative areas in the Libyan context. | 1. UNCT and the Gender Working Group continue to promote policies and issues on gender with the national stakeholders. 2. On women equality and empowerment issues, ensure that designing programs is demand based, i.e., addresses priorities from Libyan women's perspective. 3. Ensure that Gender Equality and Women Empowerment, Rights-based approach, Leave No One Behind, are cross cutting themes in all outcomes to be achieved when developing the new CF | GWG, UNCT, RCO | Nov 2021 -- Dec 2025 (TBC).