## Sheet1
Cooperation Framework Cycle |  | 2023 |  |  |  | 2024 | [11 empty] | 2025
|  | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Roadmap | bar: 2023 9 to 2023 10
Capacity development of the UNCT | bar: 2023 9 to 2023 11
UNDAF Evaluation | bar: 2023 11 to 2024 7
Common Country Analysis | bar: 2024 4 to 2024 9
Strategic Prioritization | bar: 2024 9 to 2024 12
Results Framework | bar: 2024 12 to 2025 4
UNCT Configuration | bar: 2024 12 to 2025 4
CF Drafting and consultations | bar: 2024 12 to 2025 5
Multi-Year Funding Framework | bar: 2025 1 to 2025 5
CF signature | bar: 2025 6 to 2025 7
Governance Structure | bar: 2025 7 to 2025 12
Resource mobilization strategy | bar: 2025 9 to 2025 12
Joint Work plans | bar: 2025 9 to 2025 12
[31 empty] | Process/Roles | Milestone
[30 empty] | Roadmap | RCO develops a Roadmap. UNCT approves in October 2024. UNCT commits resources to follow the guidelines. After the roadmap is approved RC (in November-December) shares the roadmap and informs the government about preparations for the CF process, requesting support etc. | Roadmap completed.
[30 empty] | UNCT Capacity building | A session for the UNCT and/or focal points on UNSDCF organized by RCO
[30 empty] | UNDAF Evaluation | RCO develops TOR in October-November 2023. UNCT Approves (November UNCT). RCO recruits consultant (funding available in 2024 only). | Evaluation submitted before the UNCT starts discussion on Strategic Priorities.
[30 empty] | Common Country Analysis | RCO develops process descriptions, and necessary TORs. CCA process goes beyond update, envisages engagement of external experts, consultations with civil society etc. UNCT commits to provide inputs and contribute to CCA discussion and draft texts . Final editorial work done by RCO. UNCT approves the CCA. Two versions. | CCA submitted before the UNCT starts discussion on Strategic Priorities.
[30 empty] | Strategic Prioritization | RCO develops workshop agenda (UNCT retreat 3 days, preliminarily in September-October 2024). UNCT member attend and identify initial priorities. Key priorities are shared with the government - through NV, and a consultative meeting is organized.
[30 empty] | Results Framework | Once Strategic priorities are identified RCO triggers three parallel processes: Results Framework, UNCT Configuration, and CF drafting and consultations. RCO will convene a series of meetings on results framework to identify indicators and targets; UNCT configuration exercise and CF drafting. External expert might be recruited for editorial work by RCO. A series of the consultations will be organized: 1) Government, 2) Civil Society (possibly more than 1, youth groups and e.g. specific meeting or feedback from LNOB groups), 3) Business. To present greater detail. The text of the UNSDCF is shared officially with the Government in April-May 2024 for validation. | RF is ready
[30 empty] | UNCT Configuration |  | UNCT configuration confirmed
[30 empty] | CF Drafting and consultations |  | CF text is finalized; no less than 3 public consultations
[30 empty] | Multi-Year Funding Framework | Once key indicators, targets and outcomes are identified, the costing should RCO will convene UNCT members to draft the multi-year funding framework. To be finalized before the signing. | MYFF is in place.
[30 empty] | CF signature | Final UN Cooperation Framework signed by the Government and UNCT and officially launched. Signing event organized by the RCO.Signatures of all entities, incluidng non-resident Agencies are collected. | Signing event carried out
[30 empty] | Governance Structure | Establishment of the National-UN Joint Steering Committee. NV with the request is sent to the Prime Minister of Kazakhstan, and the JSC is established (need to look whether this is through a prikaz of the PM or FM).
[30 empty] | Resource mobilization strategy | Once CF in place, UNCT designs the Resource mobilization strategy. | RM Strategy is in place.
[30 empty] | Joint Work plans | Joint Work Plans are prepared by the UNCT, and introduced into UN INFO | UNINFO data