## Sheet1
Country Malawi; CF 2019 - 2023 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Evaluation of the 2019-2023 UN Sustainable Development Cooperation Framework / 2022 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation:PMT, OMT, SP groups, MEAL, GHRTWG, UNCGG groups, Youth Taskforce and Private Sector Taskforce • Frequency of monitoring and updating: Semi-Annual
Recommendation 1: Ensure that the next CF continues to align with national development planning framework and strategies and pay special attention to emerging complexity of emergencies such as climate change, environment, gender, youth, demographic dynamics and other needs to be assessed through consultations on on-going reviewed mechanisms and address new needs to address the complexity of emergencies.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Design the next Cooperation Framework (CF) that aligns with national, regional, and global frameworks and ensures that there is complementarity among the agency manadates | Q4 December | UNCT/Strategic priority groups | The new CF has ensured that the four mutually reinforcing strategic priority areas are well aligned with the SDGs, AU 2063 and MIP-1. Furthermore, a UNCT configuration was done to assess the capacities required to enhance coordination transparency and efficiency on how the UNCT plans to achieve the desired results through the new CF. | completed | December | 2023
1.2 | Conduct after-action reviews immediately after the response to improve future responses to emrgencies. | Q4 December | UNCT | An internal mid-point after-action review was undertaken and efforts are ongoing to reflect and implement the findings. A follow up action review led by government is expected in JUly 2023 | ongoing as expected | December | 2023
1.3 | Identify areas for strengthening the monitoring framework for SDGs within the CF, to effectively track progress and ensure accountability. | Q2 June | MEAL group | The UNCT has identified the area of stregthening data gaps on SDG monitoring as paramount. The MEAL will review the SDG indicator framework and identify the critical indicator with no data whose systems require development/ strengthening. Furthermore, the UNCT during its last retreat agreed to allocate a minimum of 1 percent of the donor proposals budgets towards activities on research, monitoring, evaluation, and knowledge management to ensure predictable funding | ongoing as expected | June | 2024
Recommendation 2: Continue to strengthen coherence between the next CF and other development frameworks; foster coherence between implementing partners and inter-sector linkages, which is critical to effective and efficient delivery of results. Continue collaboration between UN agencies and joint programmes in Thematic Working Groups with multiple national and international partners tend to provide opportunity for improved coherence and alignment to the development activities in the country
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Establish a coordination structure for the new CF involving co-chairs from government and the UN | Q4 December | RC and UNCT | During the month of October in 2022, both the United Nations and the Government came to an agreement to establish a CF Taskforce that would be jointly led by the Resident Coordinator (RC) and the Secretary to the President. Additionally, it was mutually decided that each of the strategic priority groups would be co-chaired by two UN entities and two government entities. | completed | December | 2022
2.2 | Review the terms of reference for all the coordination working groups and strategic priority groups, ensuring they are fit for purpose in relation to the new CF | Q4 December | SP groups and all coordination groups | Work is in progress | ongoing as expected | December | 2023
2.3 | Strengthen Linkages with between UN Pillars and Government Pillar and Enabler Groups - PMT to select designated members for each pillar and enabler group | Q4 December | UNCT and PMT | Work is in progress | ongoing as expected | December | 2023
2.4 | Enhance the engagement of Technical Working Groups in the planning, implementation, and reporting, ensuring that the forthcoming Joint programmes under the Malawi SDG Acceleration Fund and the Joint SDG Fund effectively tackle the identified SDG gaps | Q4 December | RCO, MEAL, GHRTWG, and UNCG groups | UNCT has agreed to strengthen involvement of MEAL in the design of Joint programmes to ensure stregthening the monitoring frameworks for SDGs. This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | Ongoing | 2023
Recommendation 3: Strengthen the Monitoring and Evaluation system including supporting the development of national data ecosystems ensuring that custodian UN agencies of SDG indicators support the government to build systems that generate data on the SDG indicators with gaps. Improve the use and updating of the UNINFO system for improved data archiving. Align indicators with the country’s SDG Framework.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Identify areas for strengthening the monitoring framework for SDGs within the CF, to effectively track progress and ensure accountability. | Q2 June | MEAL group | The UNCT has identified the area of stregthening data gaps on SDG monitoring as paramount. The MEAL will review the SDG indicator framework and identify the critical indicator with no data whose systems require development/ strengthening. Furthermore, the UNCT during its last retreat agreed to allocate a minimum of 1 percent of the donor proposals budgets towards activities on research, monitoring, evaluation, and knowledge management to ensure predictable funding | ongoing as expected | June | Annual
3.2 | Align the outcome and output indicators with the national, regional, and global frameworks | Q4 December | SP and MEAL groups | The CF result frameworks has ensured that the majority of outcome indicators are jointly selected with government from the SDG indicator framework. The output indicators will be selected from the UNSDG global output indicator framework | ongoing as expected | December | 2023
3.3 | Undertake periodic M&E joint visit to selected districts. | Q4 December | UNCT, PMT, MEAL, GHRTWG, and UNCG groups | The MEAL groups has planned a Joint M&E visit scheduled for early September 2023. This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
Recommendation 4: Explore opportunities for functional collaboration and coordination with development partners, donors and district levels of government to promote development at the district levels. Continue to lobby regional and HQ offices for resolution on the harmonization of financial and report writing templates.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | DCO has advanced on a phased approach to integrate UN INFO with the systems of other agencies. Therefore the later recommendation is not considered under this management response as work is still underway
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Promote coordination through existing coordination mechanisms such as the Pillar and Enabler Coordination Groups | Q4 December | PMT, GHRTWG | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
1.2 | Strengthen linkage between Ministry of Local Government, Development Actors (including UN) and local governments. | Q4 December | UNCT, PMT, SP groups and RCO | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
Recommendation 5: Develop alternative coherent funding strategy to jointly mobilize resources for the implementation of next Cooperation Framework, especially in the face of shrinking funding space. Complete the development of the Joint Resource Mobilisation Strategy under the coordination of the RCO and tracked by the Results Groups. Ensure that agency efforts are harmonized and not creating overlaps.
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Develop Resource mobilization and Partnerships Strategy for the new Cooperation Framework | Q4 December | UNCT, PMT, SP groups and RCO | Work is in progress to draft the ToRs for the consultant to develop the strategy. | ongoing as expected | December | 2023
1.2 | Design a new SDG Acceleration Fund for the new CF | Q4 December | UNCT, PMT, SP groups and RCO | The UNCT has agreed with the proposal to launch the process to hire a consultant to to support in designing a new SDG Acceleration Fund for the new CF | ongoing as expected | December | 2023
Recommendation 6: Cover the full spectrum of humanitarian-development-peace actions as offerings to support Malawi government to avoid inefficient parallel planning and implementation processes and tools. Lessons learned during the humanitarian emergencies should be adopted for any re-occurrence in the next CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Formulate a new CF that integrates and emphasizes on humanitarian-development-peace nexus | Q4 December | UNCT and SP groups | The UNCT held a retreat that reflected on the possible interventions to support government in having sustainable and durable solutions to emergencies through a humanitrian-development-peace nexus. The CF narrative document has made emphasis on the humanitarian-development-peace nexus to ensure stability, resilence, and inclusive development that leads to sustainable outcomes | completed | December | 2023
Recommendation 7: Strategize on and foster sustainability of interventions more clearly from the on-set. Use documented best practices to lay the foundation for sustainability.
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Strengthen the generation and compilation of impactful human-interest stories and home grown solutions | Q4 December | UNCG, SP groups, MEAL | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
1.2 | Undertake evaluations of Joint Programmes and utilize the findings to inform subsequent programmes | Q4 December | JPs, MEAL | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
1.3 | Design Joint Programs that promote the use government structures, fosters capacity building and systems stregthening | Q4 December | RCO, PMT, JPs, MEAL, UNCG | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
Recommendation 8: Promote a higher degree of awareness among UN staff members about the UN Reform and its implications for joint delivery that is the key elements of the reform, objectives, what it means for cooperation and joint implementation on the ground.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Raise awareness of the UN reforms and its progress thrugh the internal coordination meetings and townhalls | Q4 December | RCO | Planned | ongoing as expected | December | 2024
1.2
…
Recommendation 9: Result Groups and MEAG should play a greater role in joint planning to ensure that planning under the next CF is not seen as the sum of agency plans but as a process that consolidates and integrates the efforts of the UN agencies with clear-cut SMART indicators.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Build capacity of result group members in the use of UN INFO for planning, monitoring, and reporting | Q4 December | SP Groups/MEAG | The RCO has lined up a series of UNIINFO trainings for programme staff involved in planning, monitoring and reporting of the CF | Planned | December | 2023
1.2 | Promote the use of markers in planning, monitoring, and reporting | Q4 December | SP Groups/GHRTWG, MEAG | Planned. This is an ongoing initiative to take place throughout the programme cycle of the new CF | Planned | December | 2023
1.3 | Enhance the undertaking of quarterly meetings for the strategic priority groups | Q4 December | SP Groups | Planned. This is an ongoing initiative to take place throughout the programme cycle of the new CF | Planned | December | 2023
Recommendation 10: Complementarities should be strengthened to enable agencies to fully implement their mandates while working together. Facilitate a more harmonious alignment of UN planning processes with government planning approaches at the sectoral, national and district levels.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Rejected
If rejected or partially accepted, please provide an explanation: …… |  | Rejected as a standalone recommendation. This has been addressed as part of recommedation 1 and 2
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1
1.2
…
Recommendation 11: Establish a more systematic and integrated approach to youth programming to ensure youth participation and involvement in the programming process. Addressing challenges and issues related to demographic challenges including migrations. Develop joint youth-targeted programme considering the youth population is more than 50% of Malawi population without employment.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | While we acknoledge that the youths have not been fully engage, on the contrary we belive that issues of youths should be mainstreamed in each of the upcoming joint programmes. There is no need for a joint youth targeted programme
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Provide guidance to UNCT and PMT on a systematic and integrated approach to youth programming | Q4 December | Youth taskforce | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023
1.2 | Undertake a LNOB barrier anaysis to identify the structural and underlying causes | Q4 December | PMT, GHRTWG, MEAL, Youth taskforce, Private sector taskforce |  | ongoing as expected | December | 2024
…
Recommendation 12: Strengthen UNCT’s engagement with the government, civil society and private sector to ensure that resources of each group are deployed more effectively towards the solution of development priorities identified in the CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
|  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Undertake stakeholder consultations on the new CF with Regional Directors, donors, private Sector, CSOs, district councils | Q4 December | UNCT, PMT, SP groups, Private sector taskforce | The UNCT has consulted with regional directors and donors. Work is underway to engage district councils, CSOs, private sector in the design of the new CF. | ongoing as expected | December | 2023
Recommendation 13: Strengthen gender mainstreaming across CF outcomes; focus on integrating norms and standards in public policies, laws, strategies and development plans; mainstream gender equality and women empowerment in all activities and initiatives across all CF outcomes and outputs; follow gender transformative approach in all interventions; more effort should be deployed in strengthening the district level gender machinery to ensure local level mobilization to address negative gender social and cultural norms.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | NA
|  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Refine the GHRTWG Terms of reference in line with the new guidelines for GTGs | Q4 December | GHRTWG | Work is in progress | ongoing as expected | December | 2023
1.2 | Update the UNCT SWAP Gender scorecard and implement the agreed actions | Q4 December | UNCT, PMT, GHRTWG, OMT,MEAL | This is an ongoing initiative to take place annually in Q4 throughout the programme cycle of the new CF | ongoing as expected | December | 2023
1.3 | Develop and implement the annual GHRTWG work plan | Q4 December | GHRTWG | This is an ongoing initiative to take place throughout the programme cycle of the new CF | ongoing as expected | December | 2023

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030