### 2016-2022 TANZANIA UNITED NATIONS DEVELOPMENT ASSISTANCE PLAN

### FINAL EVALUATION REPORT

Submitted by

Dr. Annette Ittig

### December 2021

ACKNOWLEDGEMENTS

I am pleased to take this opportunity to express my appreciation to the many people who facilitated the research for this evaluation of the 2016-2022 Tanzania UNDAP II.  I am indebted to each of the Development Partners, UN staff and national and civil society stakeholders who took time to share information about their expectations of the 2016-2022 UNDAP II, their support towards its achievements, and their recommendations for the upcoming UNSDCF cycle.

Many thanks are also due to Mr. Alexander Meland for his proofreading of and comments on the final draft evaluation report.

Dr. Annette Ittig

Evaluator, 2016-2022 Tanzania UNDAP II

ACRONYMS

AMREF		African Medical and Research Foundation

CCA		Common Country Analysis

CEDAW		Convention on the Elimination of All forms of Discrimination against Women

CPD		Country Programme Document

CRC		Convention on the Rights of the Child

DaO		Delivering as One

DCO		Development Cooperation Office

DP		Development Partner

DRR		Disaster Risk Reduction

ECG		Emergency Coordination Group

EGE		Economic Growth and Employment

FAO		Food and Agriculture Organization

FDI		Foreign Direct Investment

FGD		Focus Group Discussion

GBS		General Budget Support

GCM		Gender Coordination Mechanism

GEWE		Gender Equality and Women Empowerment

GPEDC 		Global Partnership for Effective Development Cooperation

GTG		Gender Theme Group

GURT		Government of the United Republic of Tanzania

HDR		Human Development Report

HoA		Head of Agency

HRBA		Human Rights Based Approach

ILO		International Labour Organization

JP		Joint Programme

JSC		Joint Steering Committee

JWP		Joint Work Plan

KII		Key Informant Interview

KJP		Kigoma Joint Programme

LIC		Low Income Country

LMIC		Lower Middle-Income Country

M&E		Monitoring and Evaluation

MAPS		Mainstreaming, Acceleration and Policy Support

MIC		Middle Income Country

MoFP		Ministry of Finance and Planning

MoFA		Ministry of Foreign Affairs

MoHCDEC	Ministry of Health, Community Development, Gender, Elderly and Children

NACOPHA	National Council of People Living with HIV

NRA		Non-resident Agency

OG		Outcome Group

OHCHR		Office of the High Commissioner for Human Rights

OMT		Operations Management Team

PLWD		People Living with Disability

PMEG		Planning, Monitoring and Evaluation Group

PMT		Programme Management Team

PO-RALG	President’s Office – Regional Administration and Local Governments

PPP		Public-Private Partnership

PPTT		Programming Principles Task Team

RC		Resident Coordinator

RCO		Resident Coordinator Office

RGoZ		Revolutionary Government of Zanzibar

SAE		Small Area Estimation

SBS		Sector Budget Support

SDC		Swiss Agency for Development and Cooperation

SDG		Sustainable Development Goal

SERP		Socio-Economic Response Plan

SIDA		Swedish International Development Cooperation Agency

SSC		South-South Cooperation

SWAP		Sector Wide Approach

ToR		Terms of Reference

TRG		Thematic Results Group

UNAIDS	United Nations Programme on HIV/AIDS

UNCG		United Nations Communications Group

UNCMT		United Nations Country Management Team

UNCT		United Nations Country Team

UNDAC		United Nations Disaster Assessment and Coordination

UNDAP		United Nations Development Assistance Plan

UNDG		United Nations Development Group

UNDCO		United Nations Development Coordination Office

UNDP		United Nations Development Programme

UNEG		United Nations Evaluation Group

UNEP		United Nations Environment Programme

UNFPA		United Nations Population Fund

UNICEF		United Nations Children’s Fund

UNIDO		United Nations Industrial Development Organization

UNSDCF	United Nations Sustainable Development Cooperation Framework

UPR		Universal Periodic Review

VAWC		Violence Against Women and Children

WASH		Water, Sanitation and Hygiene

WFP		World Food Programme

WHO		World Health Organization

WPPL		Women’s Political Participation and Leadership

ZJP		Zanzibar Joint Programme

TABLE OF CONTENTS

Acknowledgements	2

Acronyms	3

Table of Contents 	5

Executive Summary	6

1. Introduction	13

1.1 The Tanzania Context and National Development Priorities	 13

1.2 The 2016-2022 Tanzania UNDAP II	 15

1.3 The 2016-2022 Tanzania UNDAP II Evaluation 	18

2. Major Findings of the Evaluation	 22

  - Relevance	 22

  - Coherence 	29

  - Effectiveness and Efficiency	 31

  - Sustainability	40

3.         Lessons Learned and Best Practices	40

4.         Conclusions	41

5.         Recommendations	43

Select Bibliography	 46

Annexes

- Terms of Reference	50

- Evaluation Schedule 	55

- Evaluation Respondents	59

- Evaluation Matrix	61

- Evaluator Profile 	65

Tables

- Alignment of UNDAP II Themes and Outcomes to the FYDP II and the Mkuza III	17

- Total UNDAP II Expenditure on GEWE for 2020-21 by Gender Marker	24

- Total UNDAP II Expenditure on GEWE for 2020-21 by Outcome and Gender Marker	25

- Total UNDAP II Expenditure on Human Rights for 2020-21 by Human Rights Marker	27

- Total UNDAP II Expenditure on Human Rights for 2020-21 by Outcome, Human Rights Marker…..28

- UNDAP II Results	31

EXECUTIVE SUMMARY

Summary Overview of the Tanzania Context and National Development Priorities.  As stated in its long-term development strategy, the Vision 2025, the Government of the United Republic of Tanzania (GURT) intends to graduate to a middle-income country (MIC), with high-quality livelihoods, peace, stability and unity, good governance, a well-educated population, and a competitive economy capable of sustainable, inclusive growth by that year.  Similar aspirations were expressed in the Zanzibar Vision 2020; and in its recently launched Vision 2050, the Revolutionary Government of Zanzibar (RGoZ) aims to achieve upper middle-income status by that year.

Tanzania is currently ranked as a low human development country, with a rating of 163 out of 189 countries in UNDP’s  2020 human development index.  Fiscally, however, Tanzania was reclassified from a low-income country to lower-middle-income country (LMIC) status in July 2020, after its gross national income (GNI) per capita increased to $1,080, exceeding the threshold for lower-middle income status.

.

Over the past twenty years, Tanzania has achieved significant development gains, fueled by growth in its extractives, agriculture and tourism industries.  These gains include, among others, a notable reduction in the poverty rate, an increase in primary school enrolment and a decrease in child mortality rates.  There has also been some progress towards achieving gender equality and women’s empowerment (GEWE).  However, these socio-economic advances have not been equitably distributed; and regional disparities and inequalities have persisted, particularly in the South, Central, Lake and Western Zones, as well as in Zanzibar.

The onset of the COVID-19 pandemic in Tanzania in March 2020 has exacerbated pre-existing socio-economic inequalities.   Although the country did not impose a full lockdown, its regional and global supply chains were severely disrupted; and that in turn has negatively impacted upon its economy.  The tourism, hospitality, transportation and storage industries, agriculture sector, wholesale and retail trade, finance and insurance, and social sectors have suffered particularly heavy losses; and the socio-economic consequences of the pandemic threaten the progress that the country has realized over the past two decades. In addition, it has also intensified the population’s many pre-existing vulnerabilities; including gender, geographical location, disability and migratory status, among others.

Finally, Tanzania’s achievement of LMIC status also has implications for the bilateral and multi-lateral assistance it still receives, as it is assumed that middle income countries are able to finance their own development priorities, or to share those costs with Development Partners (DPs); and since 2011, actual inflows to the country have decreased by 58.5 percent. There has also been a shift in Government interest to non-ODA sources of funding, including an increased focus on domestic resource mobilization. Indeed, with greater own-source resources available, Tanzania has begun to cost-share in some of the interventions conducted by external aid actors in the country.  The country has also deepened its South-South relationships, including through, among others, the Belt and Road Initiative.  Moreover, external borrowing, in the form of budget support, project support and non-concessional loans, is also expected to significantly increase over the next five years, in part in to fund the economic and industrial transformations envisaged in the its 2021/2022-2025/2026 Five Year Development Plan (FYDP III).

These changes in development financing models and partnerships also have implications for Tanzania’s customary donors and other aid actors.   Although it is not expected that traditional aid will be discontinued in the near future, given the country’s current challenges, other kinds of financing, including foreign direct investment (FDI), public-private partnerships (PPPs) and South-South Triangular Cooperation (SSTC), offer ways in which cooperation between Tanzania and its development partners can continue after MIC graduation. As these types of finance tend to be used for integrated, high-quality policy advice and capacity development, rather than for more traditional types of aid, such as direct support and service provision, aid actors may need to adjust their programming and partnership modalities to remain relevant and fit for purpose in Tanzania’s dynamic context.

The 2016-2022 UNDAP (UNDAP II).  The 2016-2022 United Nations Assistance Development Plan II, or UNDAP II, is the framework for the UN Development System’s (UNDS) work in Tanzania for that period. The UNDAP II presents four interrelated strategic thematic areas through which the UN system can respond most effectively to Tanzania’s development priorities: 1). inclusive growth; 2) healthy nation; 3) democratic governance, human rights and gender equality; and 4) resilience.  Under these four themes, there are twelve programmatic Outcome Areas; these twelve outcome areas include 39 outputs and 204 indicators. The initial budget estimate for the UNDAP II was $1.3 billion.

The 2016-2022 UNDAP II Evaluation.   The UNDAP II evaluation was commissioned by the UN Tanzania; the objective of this consultancy was to conduct the final evaluation of the 2016-2022 Tanzania UNDAP II, based on the detailed Terms of Reference (ToR) presented below in Annex 1. The evaluation considers the UNDAP II’s relevance, coherence, its achievements and progress against planned results, and its effectiveness as a coordination and partnership framework and as a platform for resource mobilization. The findings and recommendations from the evaluation are intended to inform elements of UN programming, coordination and financing in the forthcoming UNSDCF period (2022-2027). The primary audiences for whom the evaluation is intended are the UN and Government counterparts, as well as other Development Partners (DPs), including donors, the private sector, NGOs and civil society.  As the 2018-2020 UN Annual Report provides recent information on UNDAP II activities and outputs, and as the 2019 internal mid-term review (MTR) of the UNDAP II was extensive, this evaluation was intended to be a macro-level, summative assessment with a light programme review

Major findings of the evaluation include:

Finding 1 (Relevance):  Despite significant changes in the country context during the UNDAP II cycle,

the UNDAP II is broadly relevant to and supports the achievement of Tanzania’s national development priorities.

Finding 2: (Relevance) The cross-cutting principles of gender equality, human rights and LNOB are referenced and well-integrated across the UNDAP II outcome areas.   This reflects the numerous advocacy and programming activities through which the UN promotes GEWE, human rights and leaving no one behind (LNOB) in Tanzania.  However, despite its importance as a core UN programming principle and as a strategic intervention area in the FYDP III, environmental sustainability is far less visible in the UNDAP II than the other cross-cutting issues.

Finding 4 (Relevance):  There is good collaboration between UN agencies to advocate for key gender and human rights issues such as violence against women and children (VAWC), and as seen in the joint UNCT submission for the 2021 Universal Periodic Review (UPR) of Tanzania.

Finding 5 (Relevance):  The classification of UNDAP II interventions using gender and human rights markers may overstate the extent to which the UNCT promotes GEWE and the human rights-based approach (HRBA).  The markers do not, on their own, provide an effective means of assessing the quality of GEWE or human rights-related results; and there are other tools, such as gender audits and human rights impact assessments which should be used for those purposes.

Finding 7 (Coherence):  Internal coherence between UNCT members toward common objectives and Delivering as One (DaO) has been hindered by the design of the UNDAP II:  its twelve outcomes are more reflective of specific agencies’ priorities and projects than a DaO approach.  Nonetheless, there is good evidence of vertical coherence along sector lines in some of the UNDAP Outcome areas.  Horizontal coherence across outcomes is more visible in cross-cutting areas such as youth and gender.

Finding 8 (Coherence): With regard to external coherence at the strategic level, Government engagement in, commitment to and ownership of the UNDAP II processes has been limited:   from the launch of UNDAP II in 2016 until November 2020, no UN-Government Joint Steering Committee (JSC) meetings were held.

Finding 10 (Effectiveness):  The UN has well-leveraged its comparative advantages in technical and policy advice, advocacy and capacity building, to contribute to significant development gains in Tanzania in the areas of economic growth, governance, resilience-building and human development. However, many of these results are more visible at the agency level, rather than through the framework of the UNDAP II.

Finding 24 (Effectiveness - governance):  The UNDAP II management and coordination architecture is complex, with overlapping roles and functions, which reduces efficiencies and effectiveness.

Finding 25 (Effectiveness - financing): The UNDAP II budget was overly optimistic about the expected size and scope of the results that could be delivered with the available resources, resource mobilization opportunities and partners; and no joint partnership and resource mobilization strategy, which would have identified potential partners and means of engagement, was developed to support its implementation.

Finding 29 (Sustainability):  UNDAP results could be sustained and scaled up where they align with national and subnational partners’ priorities and policies, and where the counterpart organizations have the staff, institutional capacities and long term, sustained funding required to maintain them once UN support ends.  The fact that UN advocacy for human rights, gender equality and other issues has been institutionalized through the enactment of relevant national policies and legislation, for example, UN advocacy and support to the development of the NPA-VAWG, and the inclusion of CRC and CEDAW principles in the FYPD III, also suggests that UNDAP outcomes in those areas will be maintained. However, although some of the UNDAP II results have been institutionalized, their operationalization and the monitoring of their implementation will be key to ensuring their sustainability.

The conclusions of the evaluation include:

Conclusion 1 (Relevance): (Based on Findings 1, 2, 3, 4 and 5) The themes of the 2016-2022 UNDAP II are broadly relevant to the Tanzania context: the UNDAP outcomes were aligned with national development priorities identified during its formulation phase; and they also addressed several contextual development challenges identified in the 2015 Situational Analysis. Moreover, they also broadly aligned with the priorities presented in the subsequent medium-term development plan, the 2015-2021 Five Year Development Plan, primarily because major development challenges such as poverty and exclusion remained the same throughout this UNDAP cycle. The cross-cutting principles of LNOB, human rights and gender equality are visible in UNDAP II outcome statements, indicators and outputs.  However, the extent to which these principles have been mainstreamed into the UNDAP II, if they are measured through the marker system, is unclear; and marker ratings may also change as a result of programming adjustments. Moreover, the markers do not, on their own, provide an effective means of assessing the quality of GEWE and human rights results; and there are other means, such as gender audits and human rights impact assessments, through which those outcomes should be measured.

LNOB has become even more visible as a key theme through the UN’s COVID response, as the focus of one of the three pillars in the UN Tanzania SERP.  Whether LNOB should now be considered through its own theme group, or whether it should be combined with the Gender Coordination Mechanism (GCM), is currently under discussion.  The LNOB theme encompasses a wide range of groups that have intersecting vulnerabilities, not all of which are related to gender; and fully operationalizing LNOB at the country level will require data collection and disaggregation techniques and tools, such as small area estimation, which are usually associated with M&E functions.  Accordingly, there is a strong link between more fully operationalizing LNOB in the UNDAP/UNSDCF and the work of the PMEG.

Environmental sustainability, despite its importance as a core UN programming principle and as a strategic intervention area in the FYDP III, is far less visible in the UNDAP than the other cross-cutting issues; and there are no tags or markers for it in UN INFO or in any UNDAP II outcomes, beyond those in the Environment Outcome area.  Respondents noted that sustainability is a complex area which requires an understanding of critical development-environment linkages, such as those between sustainability and clean energy; or agricultural productivity and food security, or national security, to be able to develop and apply relevant markers for it.  As sustainability will continue to be a core UN programming principle, it must become more visible in the new UNSDCF cycle.  Beyond providing training to the OGs by a subject matter expert, environmental sustainability requires a high-level champion, analogous to those for gender who are now placed within RCOs, who can vigorously promote this theme.

Conclusion 4 (Efficiency - governance) (based on finding 24): The current UNDAP II management and coordination architecture is complex, with overlapping roles and functions, which reduces efficiencies and effectiveness; and a more streamlined system is needed.  As the Tanzania UNCT is now preparing for a new UNSDCF cycle, and as Tanzania’s fiscal status has recently changed, it is timely and appropriate to consider what skills the Country Office would need going forward, to successfully lead and implement the new CF, as well as to adjust its offer to a MIC context.  Following that exercise, it would be appropriate to consider how its governance structures might be adjusted to be more efficient, particularly if an increased focus on policy and “influencing”, rather than implementing, which is considered best practice for the UN in MICS, is envisaged.

There are numerous examples of how Country Offices of a comparable size and complexity have tried to rationalize their UNSDCF governance structures.  However, an assessment of each is beyond the scope of this evaluation.  Although the UNCT will undertake a configuration exercise following its UNSDCF formulation, that will focus on agencies’ technical capacities, rather than on management and leadership skills.  The independent capacity assessment commissioned by the Tanzania UNCMT at the start of its One Programme/DaO pilot in 2008 provides a precedent for this kind of capacity assessment exercise.

Conclusion 5 (Effectiveness-financing) (based on findings 25, 26, 27): The UNDAP’s effectiveness as a financing platform has been uneven. Significant amounts have been mobilized for large joint programme initiatives such as the  KigomaJP, as well as through agencies’ global programmes. However, it appears that nearly 40% of the UNDAP II remains unfunded, noting that the figures provided to the evaluation were inconsistent.  The 2021 Development Finance Assessment for Tanzania notes a variety of mechanisms through which the country’s SDGs might be funded; and some of these modalities, including social enterprise; blended finance and Islamic finance, could be appropriate for the UN to further explore, as would cost-sharing, through which some UN agencies already benefit. Moreover, financing through these modalities could also be used to leverage larger amounts from traditional donor sources.

Recommendations for the Tanzania UNCT to build on the results of the 2016-2022 UNDAP II during the remainder of the current cycle and beyond are presented below.

| Evaluation Criteria | Recommendation | Parties Responsible | Timeline |
| --- | --- | --- | --- |
| Relevance (Findings 1-5) | Cross-cutting issues-environmental sustainability: To increase its visibility in the new UNSDCF cycle, the UNCMT should consider placing a focal point for environment sustainability in the RCO, at least on a part-time basis. | RC, UNCMT, PMT, OGs | Before the end of the current UNDAP II cycle |
|  | Environmental sustainability: Training in this area for OGs should be re-initiated, to better guide the development and application of markers for this principle. | PMT, OGs | Before the first UNSDCF mid-year review |
|  | Gender and human rights marker system: Gender and human rights markers should be reviewed annually and updated where necessary, to ensure that they accurately present the level of focus of the UN’s activities in these areas, noting that the marker ratings cannot replace other analytical exercises, e.g. gender audits and human rights impact assessments. | PMT, OGs | Before end of the UNDAP II cycle |
|  | LNOB: it is recommended that the LNOB theme continue to be considered through the GCM, rather than add another theme group to the existing UNDAP architecture. | UNCMT, GCM, PMT | Ongoing |
|  | LNOB: Given the strong link between more fully operationalizing LNOB in the UNDAP/UNSDCF and the need for fine-grained data collection and disaggregation, it is recommended that LNOB be placed on the PMEG agenda as an area of focus, and that there be PMEG representation during the GCM/ LNOB discussions. | GCM, PMT, PMEG | Before end of the UNDAP II cycle |
| Efficiency and effectiveness (Findings 24,25, 26, 27) | Financing: The UNSDCF resource mobilization strategy should be developed in consultation with the Ministry of Finance, to ensure the harmonization of UN and GURT approaches to funders. | UNCMT, PMT, RC, RCO | Following the development of the UNSDCF funding framework |
|  | Financing: The UNCMT should pro-actively explore those innovative financing modalities referenced in the Tanzania 2021 DFA which are appropriate for UNDAP/UNSDCF interventions, and through which it could leverage larger donor funding, including green bonds and Islamic finance. The latter may be particularly appropriate to the Zanzibar context. | UNCMT, PMT, RC, RCO | During the first year of the UNSDCF cycle |
|  | Governance: the UNCMT should commission a functional review of the UNCT to determine the extent to which it is fit for purpose as it starts a new UNSDCF cycle, to further inform any adjustments to the current UNDAP/UNSDCF governance structure | UNCMT, external management consultancy firm | Before the end of the UNDAP II cycle |
|  | Governance: the UNDAP II management and coordination architecture should be reduced and simplified in the successor UNSDCF. Adjustments to the governance structure should be informed by the recommended functional review. | UNCT, external management consultancy firm | Before the end of the UNDAP II cycle |

INTRODUCTION

1.1	Summary Overview of the Tanzania Context and National Development Priorities.  As stated in its long-term development strategy, the Vision 2025, the Government of the United Republic of Tanzania (GURT) intends to graduate to a middle-income country (MIC), with high-quality livelihoods, peace, stability, and unity, good governance, a well-educated population, and a competitive economy capable of sustainable, inclusive growth by that year.  Similar aspirations were expressed in the Zanzibar Vision 2020 and, in its recently launched Vision 2050, the Revolutionary Government of Zanzibar (RGoZ) aims to achieve upper middle-income status by that year.

Tanzania is currently ranked as a low human development country, with a rating of 163 out of 189 countries in UNDP’s 2020 human development index.  Fiscally, however, Tanzania was reclassified from a low-income country to lower-middle-income country status in July 2020, after its gross national income (GNI) per capita increased to $1,080, exceeding the threshold for lower-middle income status.

Over the past twenty years, Tanzania has achieved significant development gains, fueled by growth in its extractives, agriculture and tourism industries.  These gains include a notable reduction in the poverty rate from 86 percent in 2000 to 26.4 percent on the mainland and to 25.7 percent in Zanzibar in 2018,and an increase in primary school enrolment from 68.8 percent in 2000 to   95.7 percent on the mainland and to 86.3 percent in Zanzibar in 2020. Moreover, between 1990-2009, child mortality rates dropped from 162 to 108, and infant mortality rates dropped from 99 to 68 per 1000 live births.   However, these socio-economic advances have not been equitably distributed; and regional disparities and inequalities have persisted, particularly in the South, Central, Lake and Western Zones, as well as in Zanzibar.

There has also been progress towards gender equality and women’s empowerment (GEWE).  The country is, for example, a signatory to various international obligations on women’s human rights, including the United Nation Convention on Elimination of All forms of Discrimination against Women (CEDAW), the Beijing Platform for Action, the Protocol to the African Commission on Human and People’s Rights on the Rights of Women in Africa (the Maputo Protocol), the Millennium Development Goals and the global Agenda 2030. Moreover, the Tanzania Development Vision 2025 aims to realize GEWE in all socio-economic and political relations by that year; and the goals of the Zanzibar Vision 2020 include ensuring women equal access to opportunities to improve their socio-economic status and engendering full participation in the development process.

However, despite these commitments, gender inequality remains pervasive in Tanzania; and women and girls are consistently behind their male counterparts in various key socio-economic indicators of well-being, including completion of secondary education, formal employment and financial inclusion, as well as land ownership. According to the 2020 Human Development Report, Tanzania had a Gender Inequality Index rating of 0.556, with a ranking of 140 out of the 187 countries.

The onset of the COVID-19 pandemic in Tanzania in March 2020 exacerbated pre-existing socio-economic inequalities.   Although the country did not impose a full lockdown, its regional and global supply chains were severely disrupted; and that in turn has negatively impacted upon its economy.  In particular, the tourism, hospitality, transportation and storage industries, the agricultural sector, wholesale and retail trade, finance and insurance, and social sectors have suffered heavy losses.  By mid-2020, it was estimated that some 40,000 formal jobs had been lost, and that the income of another 2.2 million non-farm informal workers had been reduced.  Moreover, it is estimated that only 16 percent of all businesses have sufficient reserves to survive 2021.  Furthermore, the crisis could push an additional 600,000 people below the national poverty line.

The socio-economic consequences of the pandemic thus threaten the progress that the country has realized over the past two decades, as well as the achievement of the 2030 Agenda pledge to leave no one behind (LNOB) to which the GURT has committed.  In addition, it has also intensified the population’s many pre-existing vulnerabilities, including those related to gender, geographical location, disability and migratory status, among others.

Finally, Tanzania’s achievement of LMIC status also has implications for the bilateral and multi-lateral assistance it still receives, as it is assumed that middle income countries are able to finance their own development priorities, or to share those costs with Development Partners (DPs). Although Tanzania has traditionally been one of the largest recipients of official development assistance (ODA) in Africa,  since 2011, actual inflows to the country have decreased by 58.5 percent.   Furthermore, the percentage of ODA grants relative to GDP (Gross Domestic Product) has declined from 4.7 percent in 2010 to 0.3 percent in 2018.,

With the country’s achievement of LMIC status, there has also been a shift in Government interest to non-ODA sources of funding, including an increased focus on domestic resource mobilization. Indeed, with greater own-source resources available, Tanzania has begun to cost-share in some of the interventions conducted by external aid actors in the country.  Tanzania has also deepened its South-South relationships, including through, among others, the Belt and Road Initiative.  Moreover, external borrowing, in the form of budget support, project support and non-concessional loans, is also expected to significantly increase over the next five years, in order to fund the economic and industrial transformations envisaged in the new FYDP III.

These changes in development financing models and partnerships also have implications for Tanzania’s customary donors and other aid actors.  Although it is not expected that traditional aid will be discontinued in the near future, given the country’s current challenges, other kinds of financing, including foreign direct investment (FDI), public-private partnerships (PPPs) and South-South Triangular Cooperation (SSTC), offer ways in which cooperation between Tanzania and its development partners can continue after MIC graduation. As these types of finance tend to be used for integrated, high-quality policy advice and capacity development rather than for the more traditional types of aid, such as direct support and service provision,  aid actors may need to adjust their programming and partnership modalities to remain relevant in the country’s dynamic context.

1.2. The 2016-2022 UNDAP (UNDAP II)

With the aim of supporting the achievement of the Government of Tanzania’s development priorities, including both the Tanzania Development Vision 2025 and the Zanzibar Vision 2020, the GURT and the United Nations Country Team Tanzania (UNCT) launched the 2016-2022 Tanzania United Nations Development Assistance Plan (UNDAP II) in 2016.  The Tanzania UNDAP II presents the United Nations Development System’s stated areas of collaboration with national, sub-national and local stakeholders for this period. It is the fourth generation of a common UN development assistance framework in Tanzania; and it is the second UNDAP to reference the Delivering as One (DaO) approach since Tanzania became a DaO pilot country in 2007.

The UNDAP II was designed to align both with the Government of Tanzania’s national development priorities and with the Sustainable Development Goals (SDGs), as well as with other key internationally agreed development goals and principles. UNDAP II was intended to provide a common operational framework for development activities, upon which UN organisations could formulate their programmes, either as individual agencies or jointly.

UNDAP II articulates four thematic areas through which the UN system can respond most effectively, based on its comparative advantages, to Tanzania’s development priorities:

- Inclusive Growth

- Healthy Nation

- Democratic Governance, Human Rights and Gender Equality

- Resilience

Under these four themes, there are twelve programmatic Outcome Areas, including: economic growth and employment; education; social protection; health; HIV/AIDS; nutrition; water, sanitation and hygiene; democratic governance, human rights and gender equality; women’s political participation and leadership; violence against women and children; environment and climate change; and refugees and migrants.  These twelve outcome areas include 39 outputs and 204 indicators.

The selection of UNDAP II thematic areas and outcomes was informed by the key contextual development challenges and root causes identified in the 2015 Situation Analysis (SitAn), as well as by the priorities presented in the then-draft FYDP II and MKUZA III.  To further ensure the alignment of UNDAP II results areas with national policies and programmes, the UN in Tanzania also consulted with donors, national partners and NGOs.

The UNDAP II thematic areas and outcomes and the national development priorities to which they align are presented in the table below:

Table 1

Alignment of UNDAP II Themes and Outcomes to the FYDP II and the Mkuza III

|  | FYDP II | Supportive UNDAP II Themes | Supportive UNDAP II Outcomes |
| --- | --- | --- | --- |
| 1 | Economic Growth | Inclusive Growth Resilience | Outcome 1, “Economic Growth and Employment Outcome 2, “Education” Outcome 11, “Environment” |
| 2 | Human Development | Healthy Nation Democratic Governance | Outcome 4, “Health” Outcome 5, “HIV/AIDS” Outcome 6, “Nutrition” Outcome 7, “WASH” Outcome 9, “WPPL” |
| 3 | Enabling Environment | Inclusive Growth | Outcome 1, “Economic Growth and Employment” |

|  | Mkuze III | Supportive UNDAP II Themes | Supportive UNDAP II Outcomes |
| --- | --- | --- | --- |
| 1 | Inclusive Growth | Inclusive Growth | Outcome 1, “Economic Growth and Employment” |
| 2 | Human Capital Development | Healthy Nation | Outcome 4, “Health” Outcome 2, “Education” Outcome 5, “HIV/AIDS” |
| 3 | Quality Service Provision | Healthy Nation | Outcome 7, “WASH” |
| 4 | Environmental sustainability | Resilience | Outcome 11, “Environment” |
| 5 | Good Governance | Democratic Governance | Outcome 9, “WPPL” Outcome 7, “Governance” |

The extent to which the UNDAP II is aligned with national development priorities, and to which it has proved flexible and responsive to contextual changes, is considered in 2.1, “Relevance.”

An Outcome Group (OG) was established for each of the twelve UNDAP II outcome areas. Each OG is chaired by the lead UN agency’s Head of Agency (HoA).  The OGs are responsible for the operationalization of the UNDAP. They report to the UNCMT, which has overall responsibility for the delivery of UNDAP II results, through their respective UN agency chairs. The implementation of the UNDAP II is guided by rolling joint work plans (JWPs), which outline the detailed activities, budgets and agencies responsible for implementation.  The UNDAP II management and coordination structures are considered further under “2.3.5, UNDAP II Management and Coordination”.

The resources required for UNDAP II were originally estimated at US $ 1.3 billion. .

1.3	The 2016-2022 UNDAP II Evaluation

1.3.1	Evaluation objectives and scope.  The UNDAP II evaluation was commissioned by the Tanzania UNCT. The UNRCO supported the evaluation at the technical level, including the provision of UNDAP-related documentation and the facilitation of meetings with key UN staff, Government of Tanzania counterparts, Development Partners and civil society stakeholders.  The detailed terms of reference (ToR) for the evaluation are presented in Annex 1.

The ToR anticipates that the evaluation findings and recommendations would inform elements of the design and governance structure of the forthcoming 2022-2027 Tanzania United Nations Sustainable Development Cooperation Framework (UNSDCF).  An internal midterm review of UNDAP II, which resulted in recommendations for outcome and output level revisions, was undertaken in 2019.  However, no external evaluation of the UNDAP II has yet been conducted.

As the 2018-2020 Annual Report provides recent information on UNDAP II activities and outputs, and as the 2019 internal MTR of the UNDAP II was extensive, this evaluation was meant to be a macro-level, summative assessment with a light programme review.  It was expected that the evaluation would draw upon agencies’ Country Programme (CP) evaluations, which were planned to have been completed before the start of the UNDAP II evaluation.  However, as only two CP evaluations had been finalized by the time the UNDAP II evaluation was completed, this was not possible.

The primary audiences for whom the UNDAP II evaluation is intended are the UN Country Team and Government of Tanzania counterparts, as well as Development Partners, civil society and private sector stakeholders.

1.3.2	Evaluability Assessment.  The evaluator conducted a rapid evaluability assessment during the inception stage, based upon an initial document review and interviews. The results of that assessment are presented in Annex 4, below.  Based on the evaluability assessment, the evaluator considered the UNDAP II to be conditionally evaluable, noting the limitations mentioned in Annex 4, as well as those referenced below.

1.3.3	Evaluation Approach.  Data gaps and challenges in scheduling interviews with GURT stakeholders and DPs, as well as the short timeframe for the UNDAP evaluation, limited the scope of study and depth of analysis. The timeframe, as well as other limitations referenced in the evaluability assessment, did not permit an in-depth analysis of all documentation for each outcome.  Consequently, the evaluation focused upon areas where the triangulation of key informant interviews and focus group discussions with primary documentation and UNINFO data was possible.  These areas included: the relevance and appropriateness of UNDAP II, including conformity with cross-cutting principles; the effectiveness of the UNDAP, with particular reference to the large joint programmes in Kigoma (KJP) and Zanzibar (ZJP) and to the UN’s COVID-19 response, as well as the UNDAP management structure (internal cohesion), financing and partnerships (external cohesion); and indications of sustainability.

The evaluation methodologies and matrix to support this prioritized approach are presented below and in Annex 4.

This approach was also discussed by the evaluator during her presentation to the UNCMT on 27th September.

1.3.4	Evaluation Methodologies. Document Reviews, Key Informant Interviews, Focus Group Discussions, Stakeholder Validation Session.  The evaluation employed an inclusive, participatory approach; and it followed the United Nations Development Group’s (UNDG) Guidelines for UNDAF Evaluations as well as the OECD/DAC evaluation criteria noted in the ToR. It also adhered to the United Nations Evaluation Group’s Ethical Guidelines for Evaluation principles.

The evaluation was informed by a literature review, key informant interviews (KIIs), and focus group discussions (FGDs). This mixed methodological approach allowed the triangulation of qualitative and quantitative data.  Moreover, the evaluation utilized a human rights-based approach through consultations with both duty bearers and rights holders. The list of UN, Government of Tanzania, donor and civil society stakeholders interviewed is presented below in Annex 3, “Respondents”. A select bibliography of sources utilized by the Evaluator is presented in the Select Bibliography, below.

Due to the limited evaluation timeframe, a systematic purposive sampling approach was employed for the selection of those interviewed.   The selection was based on the mapping of stakeholders undertaken at the start of the evaluation by the consultant.

1.3.5	Evaluation Matrix. The evaluation matrix, which is derived from the evaluation ToR and presented in Annex 4 below, summarizes the key evaluation areas, questions and criteria; and it also includes comments on data and respondent availability, as well as risks and mitigations and topics for prioritized analysis.

1.3.6	Evaluation Timeframe and Deliverables.  The evaluation schedule, including deliverables and respondents, is presented below in Annex 2, “Evaluation Schedule”.

1.3.7	Evaluation Limitations.  UNDAP II interventions are numerous and wide-ranging, and they are under implementation throughout Tanzania.  Although the UNDAP II evaluation was expected to adopt a light approach,  the scope of the evaluation described in the ToR was, nonetheless, highly ambitious for a thirty-day level of effort by a single evaluator.

Moreover, the turnover of staff in the RCO as well as in UN agencies and in DP and Government offices since the inception of UNDAP II hindered the collection of background information on its formulation and early implementation phase.  The timing of the inception phase of the evaluation has coincided with the refinement of outcome areas for forthcoming UNSDCF; and some key UN and Government staff were, therefore, not available during this period. This also delayed the scheduling of key KIIs and FGDs with the GURT counterparts and DPs whose engagement was key to the credibility of the evaluation.

Furthermore, the evaluation also coincided with the migration of the UNINFO system to another platform.  It was therefore inaccessible, and only data for the period 2020-2021 could be extracted from the backup files maintained by the RCO M&E.  Other gaps in programmatic, monitoring and outcome data also limited the ability of the evaluator to assess progress and performance.

The absence of baselines and other information for at least 24% of the UNDAP outcome and output indicators, and incomplete documentation from Outcome Groups and other stakeholders, also hindered the assessment of current progress against plan.  Moreover, the figures for UNDAP financing, which are available in UNINFO, do not differentiate funds that have been carried over from previous years from newly mobilized funds; and total UNDAP financing and financing gaps are therefore yet to be clarified.

In addition, the direct attribution of UNDAP interventions to development outcomes is problematic, as many other actors, beyond the UN, including multilateral donors and corporate philanthropies, also support and implement development activities in Tanzania. Moreover, the direct attribution of UNDAP II interventions to development outcomes is complicated by the fact that it captures only initiatives conducted by, or on behalf of, the UN; it excludes activities carried out by other development partners that may have also contributed to results.  In addition, there is a lack of counterfactual evidence that would indicate what development results might have been achieved in the absence of UNDAP II. The assessment of UNDAP II results is therefore based on contribution analysis.

Finally, due to COVID-19-related travel restrictions, the evaluation did not include field visits.  All primary data collection for the evaluation was therefore undertaken virtually, including focus group discussions and key informant interviews with UN staff, government officials, development partners and NGOs.

- MAJOR FINDINGS OF THE UNDAP II EVALUATION

2.1       Relevance

- Has the UN system supported achievement of national development goals and targets?

- Has the UN system remained responsive to emerging and unforeseen needs of the country and the people?

- To what extent have the cross-cutting principles of gender equality, human rights and environmental sustainability have been promoted and followed under UNDAP II?

- To what extent has UN system support prioritized and extended in such a way to leave no one behind (LNOB)?

2.1.1      UNDAP II alignment to national development goals and targets

Finding 1: Despite significant changes in the country context during the UNDAP II cycle, the UNDAP II is broadly relevant to and supports the achievement of Tanzania’s national development priorities.

The relevance of UNDAP II is related to its broad alignment to national development priorities at the time of its formulation in early 2015, as well as to those in the revised FYDP II which was issued after the October 2015 elections.  Its themes are most closely linked to the Human Development, Economic Growth and Good Governance pillars of the FYDP II and MKUZA III (see above, Table 1).   Moreover, the UNDAP thematic areas and outcomes also address several of the contextual development challenges and root causes identified in the 2015 SitAn.

Following its 2018 internal mid-year review (MYR), and in response to changes within the development context, as well as the availability of funds and the likelihood of full delivery of results, the UNCT initiated a reconfiguration of the UNDAP II results framework.  However, the MYR did not result in either the development of a (reconstructed) UNDAP Theory of Change, or in a closer alignment of the UNDAP II to the FYDP II or the Mkuza III (see also below, 2.3.7, “UNDAP II Design”).

    - UNDAP II responsiveness to emerging and unforeseen needs (see below, 2.3.3 “The UN’s COVID 19 responses”; also 2.3.7, “UNDAP II Design”, below)

    - Conformity with the crosscutting principles

Finding 2:  The cross-cutting principles of gender equality, human rights and LNOB are referenced and well-integrated across the UNDAP II outcome areas.   This is indicative of the numerous advocacy and programming activities through which the UN promotes GEWE, human rights and LNOB in Tanzania.  However, despite its importance as a core UN programming principle and as a strategic intervention area in the FYDP III, environmental sustainability is far less visible than the other cross-cutting issues.

Finding 3:  Government requests for the UN to support its obligations to report on international treaties and conventions, including CEDAW, the Universal Periodic Review (UPR) and the Convention on  the Rights of the Child (CRC), are indicative of its acknowledgement of the UN’s expertise and comparative advantage in the areas of GEWE and  human rights.

Finding 4:  There is good collaboration between UN agencies to advocate for key gender and human rights issues such as VAWC  (Violence against Women and Children), and as seen in the joint UNCT submission for the 2021 Tanzania Universal Periodic Review of Tanzania.

Finding 5:  The classification of UNDAP II interventions using gender and human rights markers  may overstate the extent to which the UNCT promotes GEWE and the HRBA.  The markers do not, on their own, provide an effective means of assessing the quality of  GEWE or human rights-related results; and there are other tools which should be used for those purposes.

      - Gender Equality.  As recommended in the evaluation of UNDAP I, the integration of gender in the results framework of UNDAP II has been made more visible than in its predecessor: GEWE cuts across all of the UNDAP II outcome areas, including as the focus of two UNDAP II outcomes, as well as in other indicators of mainstreaming.  GEWE is also more visible in the post-2019 JWPs and results framework, following the internal 2019 UNDAP MYR.  However, gender is still not fully disaggregated in the UNDAP II results framework, either in all of its indicators or in all of its results.

Moreover, GEWE as a programming principle and an area of UN comparative advantage is also now more visible within the UNCT and to external partners.  During the first years of the UNDAP II cycle, the mainstreaming of GEWE was delegated to a gender subgroup of the PPTT, which reported to the PMT. Following the 2018 UNCT SWAP Gender Equality Scorecard Assessment, and the launch of a pro-active RC-led GCM in January 2021, GEWE has become more noticeable as a cross-cutting issue, both within the UNCT and to  external partners, e.g. through the Development Partners Gender Group; and through the coordination between UN Women and the World Bank for the Tanzania country gender profile.

Furthermore, national and NGO respondents to the evaluation acknowledged the UN’s comparative advantage in GEWE (see below, 2.3.4, “COVID-19 response”); and Government requests for UN support to its international reporting obligations on gender equality, e.g. with submissions for the CEDAW MTR in 2018 and the Beijing Platform for Action 25+ in 2019, are indicative of its appreciation of the UN’s expertise in this area.  Beyond international reporting, the UN also supported gender mainstreaming in legislative work, with positive results achieved in the adoption of gender-responsive budget analyses for all parliamentary committees and the gender analysis of bills; and in Zanzibar, the UN has supported the engendering of the Planning Commission’s reporting system.

There is good collaboration between UN agencies to advocate for key gender issues such as VAWC, for example, between UN Women, UNFPA, IOM and UNICEF in Kigoma,.  There has also been a deliberate attempt to mainstream GEWE in both the ZJP and the KJP, including the building of national and local capacities to plan, budget for, and implement gender-responsive investments (see below, 2.3.2, “The Kigoma Joint Programme”, and 2.3.3, “The Zanzibar Joint Programme”.  It is as well evident in agencies’ COVID-related interventions, including an awareness of the disproportionate effects of the pandemic on women as caregivers and as workers in the informal economy (see below, 2.3.4, “The UN’s COVID-19 Response”).

From the evaluation’s review of gender markers  in UNINFO for 2020-2021, GEWE-related programming totals $119,800,545, or approximately 12% of the total UNDAP II budget (see Tables 2 and 3 below).  While this is indicative of the importance now given to the integration of GEWE in UN Tanzania programming, it must be noted that the weight of the gender marker – GEN0, GEN1, GEN2 or GEN3 – is determined by the inputting agency; and gender markers/ratings are input in post-facto reporting, rather than during planning.

Moreover, expenditures by gender marker, whether measured by marker weight or by outcome, do not necessarily indicate how widely GEWE was mainstreamed by the UNCT through its members, since a high/low expenditure associated with a particular marker might be the result of one or a few agencies reporting high/low expenditure.  For example, according to the gender markers, the total GEWE-related expenditures for VAWC and Womens Political Participation and Leadership (WPPL), both of which are gender-focused outcome areas concerned primarily with capacity development and social norm change, are far lower than for the Refugees Outcome.  However, the Refugees Outcome has higher programme-related expenditures, such as for the purchase and distribution of food and other commodities; and those higher expenditures may be reflected in higher gender markers/ratings.

Finally, the markers do not, on their own, provide an effective means of assessing the type or quality of the GEWE results; and there are other tools, such as gender audits, or the use of the UNCT Gender Scorecard, which should be utilized for that purpose.

Table 2

TOTAL UNDAP II Expenditure on GEWE for 2020-2021

By Gender Markers Per Outcome Group

|  | Expenditure 2020/2021 (USD) |  |  |  | Total Expenditure (USD) |
| --- | --- | --- | --- | --- | --- |
| Outcome Group | Gender Marker0 | Gender Marker1 | Gender Marker2 | Gender Marker3 | GEN1, GEN2, GEN3 |
| Education | 91,483 | 570,225 |  | 89,872 | 660,098 |
| EGE | 6,881,826 | 2,164,199 | 9,692,802 | 4,620,502 | 16,477,503 |
| Environment | 20,000 | 137,100 | 2,011,357 | 1,985,902 | 4,134,359 |
| Governance |  | - | 13,964,563 | 878,840 | 14,843,404 |
| Health | 22,000 | 616,962 | 12,898,869 | 285,000 | 13,800,831 |
| HIV | - | 2,255,151 | 1,632,975 | 160,252 | 4,048,378 |
| Nutrition |  | 5,639,045 | 3,074,473 | - | 8,713,518 |
| Refugees |  |  | 21,929,060 | 17,132,256 | 39,061,316 |
| Social Protection |  |  | 447,000 | 302,536 | 749,536 |
| VAWC |  | 135,000 | 2,748,727 | 4,444,495 | 7,328,222 |
| WASH |  | 2,947,152 | 4,446,018 | - | 7,393,170 |
| WPPL |  |  | 25,000 | 2,565,211 | 2,590,211 |
| TOTAL (USD) | 7,015,309 | 14,464,835 | 72,870,844 | 32,464,867 | 119,800,545 |

Table 3

Total UNDAP II Expenditure on GEWE for 2020-2021 by Gender Marker

(USD)

|  | Planned | Available | Expenditure | Total Expenditure GEN1, GEN2, GEN3 |
| --- | --- | --- | --- | --- |
| Gender Marker 3 | 130,710,950 | 40,437,247 | 32,464,867 | 32,464,867 |
| Gender Marker 2 | 145,299,499 | 109,999,022 | 72,870,844 | 72,870,844 |
| Gender Marker 1 | 19,396,221 | 13,786,723 | 14,464,835 | 14,464,835 |
| Gender Marker 0 | 9,013,368 | 8,290,896 | 7,015,309 |  |
| Not Tagged | 16,891,551 | 16,474,301 | 10,630,784 |  |
| Total UNDAP Budget 2020/2021 | 321,311,588 | 188,988,189 | 137,446,639 | 119,800,546 |

Finding 6:  Many of the GEWE-related interventions in UNDAP II focus upon mainstreaming, that is, primarily upon engagement and participation or are gender-responsive, focusing upon the equitable distribution of benefits, resources, status and rights.  However, they do not necessarily address the root causes of gender inequality such as social norms.   Nonetheless, there are UNDAP II initiatives which are, or have the potential to be, gender transformative, by contributing to changes in norms, cultural values and power structures, and by addressing root causes of gender inequality and discrimination.  For example, although the budgets for the WPLL and VAWC outcomes are modest, there are initiatives under those areas that have had positive impact on the gender machineries in the country, such as support towards the reform of legislation discriminating against girls’ and young women’s access to education.  In addition, UN support to the development and rollout of the NPA VAWC may also prove to be gender-transformative, although it is still premature to assess its impact.

2.1.3.2 	Human Rights

Human rights language, including references to rights holders and duty bearers, is visible across the UNDAP II outcome areas.  This is indicative of the numerous advocacy and programming activities through which the UN promotes human rights in Tanzania.  For example, the UN has supported the formulation and rollout of several rights-focused policies, including the NHRAP and the NPA-VAWC, among others, although the extent to which they will be fully implemented is not yet known.

There has been good collaboration between UN agencies in the area of human rights, including in reporting, e.g. the UNCT’s joint submission for the 2021 Tanzania Universal Periodic Review of Tanzania.  Furthermore, there is a deliberate effort to measure the extent of these activities through UN INFO (see below, Table 4, UNDAP II Expenditure on Human Rights for 2020-2021).

Finding:  Government requests for the UN to support its obligations to report on international treaties and conventions, including the Universal Periodic Review (UPR) and the Convention on the Rights of the Child (CRC), are indicative of its acknowledgement of the UN’s expertise and comparative advantage in the area of human rights.

However, despite efforts by the UN and other human rights advocates, democratic and civic space in Tanzania has diminished during the UNDAP II cycle.  For example, there have been several legislative changes that have adversely impacted upon civil and political rights, particularly the freedoms of assembly, association and expression.  The scope for the UN to pursue improvements in human rights protections in Tanzania has, therefore, become more limited.  Beyond mainstreaming HRBA, strong advocacy will be required to reverse this trend and to increase national efforts to address human rights commitments.

Human Rights Markers. From the evaluator’s review of human rights markers in UNINFO for 2020-2021, human rights-related programming totals $121,053,557, or approximately 12% of the UNDAP budget (see Tables 5 and 6 below).  While this is indicative of the importance given to the integration of human rights and the HRBA in UN Tanzania programming, it must be noted that, as in the findings for GEWE, above, the weight of the human rights marker – 0, 1, 2 or 3– is determined by the inputting agency; and that human rights markers/ratings are also input in (post-facto) reporting, rather than during planning.

Table 4

UNDAP II Expenditure on Human Rights for 2020-2021

By Human Rights Markers Per Outcome Group

|  | Expenditure 2020-2021 (USD) |  |  |  | Total Expenditure (USD) |
| --- | --- | --- | --- | --- | --- |
| Outcome Group | Human Rights Marker0 | Human Rights Marker1 | Human Rights Marker2 | Human Rights Marker3 | Human Rights Markers 1, 2, 3 |
| Education |  |  | 661,709 | 89,872 | 751,581 |
| EGE |  | 7,913,790 | 12,907,845 | 1,492,352 | 22,313,987 |
| Environment | 268,919 | 137,100 | 3,548,340 | 200,000 | 3,885,440 |
| Governance |  |  | 11,698,430 | 3,144,973 | 14,843,404 |
| Health | 40,000 | 905,099 | 10,754,511 | 457,189 | 12,116,799 |
| HIV |  | 332,349 | 1,071,024 | 38,000 | 1,441,373 |
| Nutrition |  | 3,247,915 | 5,316,960 | 148,643 | 8,713,518 |
| Refugees |  |  | 21,762,060 | 17,299,256 | 39,061,316 |
| Social Protection |  |  | 519,536 | 230,000 | 749,536 |
| VAWC |  |  | 3,266,155 | 3,927,067 | 7,193,222 |
| WASH |  | 6,139,803 | 1,253,367 |  | 7,393,170 |
| WPPL |  |  | 25,000 | 2,565,211 | 2,590,211 |
| TOTAL | 308,919 | 18,676,056 | 72,784,937 | 29,592,564 | 121,053,557 |

Table 5

UNDAP II Expenditure on Human Rights for 2020-2021

By Human Rights Markers (USD)

|  | Planned | Available | Expenditure | Total Expenditure HR Markers 1,2,3 |
| --- | --- | --- | --- | --- |
| Human Right Marker 3 | 130,589,589 | 44,404,521 | 29,592,564 | 29,592,564 |
| Human Right Marker 2 | 141,443,532 | 102,599,805 | 72,784,937 | 72,784,937 |
| Human Right Marker 1 | 26,337,375 | 20,192,970 | 18,676,056 | 18,676,056 |
| Human Right Marker 0 | 1,203,900 | 1,023,900 | 308,919 |  |
| Not Tagged | 21,737,192 | 20,766,993 | 16,084,163 |  |
| Total UNDAP Budget 2020/2021 (USD) | 321,311,588 | 188,988,189 | 137,446,639 | 121,053,557 |

Moreover, as also noted with gender markers, expenditures by human rights marker do not necessarily indicate how widely human rights were mainstreamed by the UNCT through its members, since a high/low expenditure associated with a particular marker might be the result of one or a few agencies reporting high/low expenditure.  For example, according to the markers, the greatest expenditure for human rights was under the Refugees Outcome, but this may be due to comparatively higher programme-related expenditures, such as for the purchase and distribution of food and other commodities; and those higher expenditures may be reflected in higher human rights markers/ratings.

Finally, the markers do not, on their own, provide an effective means of assessing the quality of the human rights results; and there are other means, such as human rights impact assessments, through which those outcomes can be measured.

2.1.3.3	Environmental Sustainability

Environmental sustainability has been a core UN programming principle throughout the UNDAP II period, and it will continue to be so in the upcoming UNSDCF cycle.  Moreover, environment, natural resource management and the blue economy feature as strategic intervention areas in Tanzania’s 2021/2022-2025/2026 FYDP III. However, despite its importance, environmental sustainability has been less well-integrated than other crosscutting issues in UNDAP II, even after the 2019 MYR reconfiguration.  For example, there are no tags or markers for environmental sustainability in UN INFO for any UNDAP II outcomes, beyond those in the Environment Outcome area

Respondents noted that environmental sustainability is a complex topic which requires some understanding of critical development-environment linkages, such as its links to clean energy; or to agricultural productivity and food security, or to national security, in order to be able to develop and apply relevant markers.  Indeed, training in this area had been provided to OGs by the PPTT in the early UNDAP II phase, but it was not repeated.  As sustainability will continue to be a core UN programming principle, it must become more visible in the new UNSDCF cycle.

2.1.3.4: Leaving No One Behind (LNOB)

As the central, transformative promise of the 2030 Agenda, LNOB represents the unequivocal commitment of all UN Member States to eradicate poverty in all its forms, end discrimination and exclusion, and reduce the inequalities and vulnerabilities that leave people behind and undermine the potential of individuals and of humanity as a whole.

As a key cross-cutting issue, LNOB is referenced in each UNDAP II outcome statement, particularly through the terms “poor” and “vulnerable”, although disaggregation could be stronger.  It is also the primary stated objective of many of the UN’s interventions, for example, for refugees, among others.   Moreover, although LNOB has been a foundational principle in the UNDAP throughout this cycle, it has become even more visible as a key theme in the UN’s COVID response, as the focus of one of the three pillars in the UN Tanzania SERP.  There has been some debate within the UNCT as to whether LNOB should now be considered through its own theme group, or whether it should be combined with the GCM, given that many of the same people would be involved in both themes.  Currently, LNOB as a specific theme is considered in GCM meetings; and some respondents have questioned whether a more formal LNOB structure would be necessary to strengthen accountability.

However, it must also be noted that the LNOB theme encompasses a wide range of groups that have intersecting vulnerabilities, not all of which are related to gender.  Fully operationalizing LNOB at the country level will require extensive data collection and disaggregation, which includes all grounds of discrimination prohibited under international law, to better identify the lagging segments of the population and to ensure progress for all population groups at a disaggregated level.

  - Coherence of the UN system support

- Has UNDAP II strengthened the coherence of support by UNCT members towards common objectives and to deliver quality, integrated, SDG-focused policy support?

- Has UNDAP II strengthened the position, credibility and reliability of the UN system as a partner for the government and other actors?

Finding 7:  Internal coherence between UNCT members toward common objectives and DaO has been hindered by the design of the UNDAP II:  its twelve outcomes are more reflective of specific agencies’ priorities and projects rather than a DaO approach.  Nonetheless, there is good evidence of vertical coherence along sector lines in some of the UNDAP Outcome areas.  Horizontal coherence across outcomes is more visible in cross-cutting areas such as youth and gender.

Finding 8:  In regard to external coherence, Government engagement in, commitment to, and ownership of the UNDAP II processes has been limited:   from the launch of UNDAP II in 2016 until November 2020, no UN-Government JSC meetings were held.

Finding 9:  External coherence at the implementation level is mixed.  Interaction between the OGs and national counterparts was reduced after OG membership was limited to UN staff.  More recently, the OGs have been requested to again institutionalize meetings with Government.

2.2.1	Internal coherence between UNCT members toward common objectives and DaO has been hindered by the design of the UNDAP II: its twelve outcomes are more reflective of specific agencies’ priorities and projects rather than a DaO approach; and there is no overarching UNDAP II theory of change or vision statement which would better link these outcomes (see also 2.3.7, “UNDAP Design”).  Nonetheless, there is good evidence of vertical coherence along sector lines in some of the UNDAP Outcome areas, particularly in the Health Thematic Results Area and including the health pillars in the KJP and ZJP (see below, 2.3.2. “KJP”; 2.3.3 “ZJP”; 2.3.4, “UN COVID 19 Response”).  Horizontal coherence across outcomes is more visible in cross-cutting areas such as youth and gender, for example, in the support to the development of the NPA VWAC and its regional rollout in Kigoma; and in the VAWC pillar of the ZJP.

The most visible evidence of the UNDAP II as a platform for DaO has been the UN COVID 19 response (see below, 2.3.4).

2.2.2 External coherence at the strategic level:  The UN-GURT partnership envisaged in the UNDAP II document has been strained throughout the current UNDAP cycle.  However, some consultations with GURT counterparts continued at the Thematic Results Group and the Outcome Group levels; and JSC GURT members also provided endorsements for annual One UN Fund allocations, as well as for the extension of UNDAP II to 2022.  The erosion of trust and confidence between the GURT and its development partners can be linked to various events, including the TANESCO corruption scandal and donor withdrawal of general budget support in 2015; a shift in Government interest from ODA to non-ODA sources of funding; and development partners’ criticism of the 2015 election results.

There has recently been some re-engagement with the UN by Government, and two high-level meetings have been convened since November 2020 to date, in conjunction with the development of the forthcoming UNSDCF.

  - Effectiveness and Efficiency

2.3.1	Overall UNDAP II Results

Finding  10:  The UN has well-leveraged its comparative advantages in technical and policy advice, advocacy and capacity building, to contribute to significant development gains in Tanzania in the areas of economic growth, governance, resilience-building and human development. However, many of these results are more visible at the agency level, rather than through the framework of the UNDAP II.

Finding 11:  In the final year of the UNDAP II, progress towards planned results is mixed: 39% of the targets for 2018-2020 have been fully achieved, and 55% have been partially achieved. According to the 2018-2020 results report, some 2% of the targets have not been achieved or are unmeasurable, due in part to indicators that were either not well-defined or which lacked baselines, and which therefore cannot be measured.

UNDAP II progress is summarized in Table 6, below:

TABLE 6

UNDAP II Results Achieved for 2018-2020

(at 31 December 2020)

| Thematic Area | # Indicator Targets | # Targets/No Data | # Targets Low and Partial Achievement | # Targets High Achievement | # Targets Fully Achieved | % Targets Fully Achieved |
| --- | --- | --- | --- | --- | --- | --- |
| Inclusive Growth | 63 | 1 | 16 | 22 | 25 | 39% |
| Health | 95 | 0 | 17 | 36 | 42 | 38% |
| Governance | 68 | 1 | 28 | 19 | 20 | 29% |
| Resilience | 60 | 5 | 14 | 8 | 31 | 50% |
| TOTAL | 286 | 7 | 75 | 85 | 118 |  |
| Average rate of Achievement |  |  |  |  | 29.5 | 39% |

The constraint to achievement that was most frequently cited by UN respondents was inadequate financing.  Funding shortfalls are considered further below, in “Financing”.

2.3.2 	UNDAP Results – the Kigoma Joint Programme (KJP)

The KJP is an area-based UN joint activity that supports refugee-hosting communities in Kigoma, a regional high-risk area in western Tanzania.  It builds upon and expands previous UN interventions in Kigoma, including a 2005-2008 UN joint programme on human security and the 2008-2011 Joint Programme on the Transition from Humanitarian Assistance to Sustainable Development.  It involves 16 UN agencies and includes six components: Sustainable Energy and Environment (SEE), Youth and women’s economic empowerment; VAWC; education with a focus on girls and adolescent girls; WASH; and agriculture with a focus on developing local markets.  The KJP is coordinated by a field-based Area Coordinator under the RCO.

Finding 12:  Building on previous UN JPs in Kigoma, there is a close collaboration between the KJP and the Local Government Authority (LGA)from the top down to the extension workers, and this indicates the relevance of the programme to other government policies and plans.  Moreover, the LGA has contributed to the KJP through inputs of cash, or cost sharing, as well as in kind, e.g., labour; and this collaboration is a positive sustainability indicator.

Finding 13:  The support of donors for joint funding from the inception of the KJP has been key to its achievements.  Moreover, there has been good cohesion among the KJP agencies around support for funding.  However, donor contributions to the ONE FUND have fallen off (see below, “Financing”), and other means of financing the KJP will need to be identified.

Finding 14:  Changes in government policies have affected the KJP’s planned intervention; and although this was noted as a possible risk in the project document, proposed mitigation measures have not been sufficient.  Although originally planned to support the Kigoma host community, with some activities also benefitting refugees encamped in the region, the introduction of a strict encampment policy by the Government in early 2019 has prevented the KJP from undertaking any of its activities directly focused on refugees.  While various UN agencies do provide emergency assistance to the camp refugees, these activities are implemented outside of the KJP.

The risk matrix in the KJP project document notes changes in the political landscape as a risk, and it suggests high level dialogue with Government as a risk mitigation measure.  However, although the KJP liaises and has good relationships with local and regional government, it is the MoFA and MoHA and other national level actors who determine refugee policies.

Finding 15:  While there is strong evidence for gender mainstreaming in the KJP, the supposition that its VAWC component contributes to transformational change is less well documented. The National Plan of Action – Violence Against Women and Children (NPA-VAWC) is a costed programme intended for national implementation and national scale. It is supported collaboratively by UNFPA, UN Women, UNICEF and IOM, and it has been rolled out in Kigoma through the KJP.  According to the 2019 NORAD review of the KJP, “... anecdotal evidence suggests that the KJP’s VAWC theme contributes to changes at the outcome level,” and it recommended that the KJP “…move on from tracking and reporting on raised awareness to (reporting on) changed practices.” Evidence that the VAWC activities under the KJP may contribute to transformational change has yet to be further documented.

Finding 16: At least some of the KJP activities appear scalable, although their scalability would be strengthened by the inclusion of exit strategies.  Although not all of the KJP activities appear scalable, there are some practices and results from its VAWC pillar that could be scaled up to other regions and districts, e.g. the LGA VAC coordination of a case management referral system, the use of volunteers/fit families and the ToT manual adopted by the government.  However, at this stage of implementation, no exit strategies have yet been clearly articulated, including how the ongoing costs for these activities would be met after JP funding ceases.

Finding 17:  The aid landscape in Kigoma is crowded, and some respondents suggested that the region is over-serviced by aid actors:  There are more than 30 partners who coordinate and respond to the refugee emergency in Kigoma.  Moreover, some 170 are reported to be active in the region with other interventions; and it is unclear the extent to which all of their activities have been mapped. Some respondents suggested that the Kigoma region is over-serviced by the UN and other development actors; and they recommended that the UN widen its scope of activities to other, less-serviced regions.  Given the large number of aid actors in Kigoma, it is not surprising that there is some overlapping of activities, for example, between the KJP agricultural component and the AGRA and SAKIRP projects.

2.3.3.	The Zanzibar Joint Programme

The Zanzibar Joint Programme (ZJP) is a UN joint activity which was launched in 2018 and which is supported by nine agencies. The ZJP aims to address gender inequalities through four inter-related thematic areas: improved access to maternal and newborn health services; livelihoods, particularly with regard to the seaweed value chain; protection (VAWC); and the effective tracking of results, including capacity building for SDG coordination and reporting, particularly for SDG 5.  The original budget estimate for the ZJP was US $33.8 mln.  The ZJP is coordinated by a field-based Area Coordinator under the RCO.

Finding 18:  The offer of the ZJP as an integrated package of services has been partially achieved:

The ZJP agencies are also involved in several other programmes in Zanzibar, and there are good synergies between some of the ZJP pillars and those interventions, for example, between the ZJP health component and the Afya Bora ya Mama na Mtoto project, which was designed to address maternal and child mortality.

Other ZJP achievements to date include health systems strengthening with a focus on management of Mnazi Mmoja and Chake-Chake hospital. In the VAWC pillar, UN influence contributed to the declaration of a Fatwa by the Mufti’s Office of Zanzibar on eliminating child marriage. In addition, coordination mechanisms to support the elimination of violence against women and children were established at the community level in all 386 Shehias, and at the national level; technical support and cooperation with the Inter-Ministerial Coordination Committees made this operational. In the SDG coordination, monitoring and reporting thematic area, progress was made in strengthening institutional capacities for coordination and reporting, as well as improving national statistical frameworks and systems, particularly for gender monitoring and reporting.

Finding 19:  Unlike the KJP, which began with approximately 25% of its total budget in hand, the ZJP has had limited funding, and this has curtailed some of the programme’s original objectives, particularly its livelihood component.  Due to funding shortfalls, the four pillars of the ZJP could not progress simultaneously.  In response to these challenges, the programme was reconfigured in 2020.  With the onset of the pandemic in March 2020, the ZJP also adapted its programming  to the response lead by WHO.  Programme adaption included, among others, activities to increase public awareness of COVID-19 through radio programming; and faith leaders were supported to establish and adopt COVID-19 safety guidelines and protocols in places of worship.

2.3.4	The UN’s Response to COVID 19

As noted above, the first cases of COVID-19 in Tanzania were recorded in mid-March 2020.  In response, the Government closed schools, restricted public gatherings and stopped commercial air travel. However, in June, the President declared that there was no COVID in the country, and schools and the airports were re-opened.

Despite these constraints, the UN responded to COVID-19 in Tanzania through a range of mechanisms, including both within the UN (UNCMT, the PMT, the OGs, the OMT, UNCG, and the ERG) and with external partners, including the Development Partners Group; NGOs and the GURT (through the pillar-structure of the national response plan and with the multi-sectoral committee under the Ministry of Finance).  Initially, the UN developed a Joint UN Response Framework around three pillars, including an LNOB pillar to ensure that the needs and rights of vulnerable groups and left behind populations would be addressed.  The Socio-Economic Response Framework (SERF) was linked to the four UNDAP II Thematic Areas, with the intention that any UN COVID-responsive interventions would thereby also contribute to the achievement of UNDAP results.  Subsequently, a socio-economic response plan (SERP) was prepared, and an appeal was launched through OCHA.

With partners, the UN also supported the Government to develop and implement the initial National COVID-19 Response Plan, which transitioned into the National Infection Prevention and Control (IPC) Plan.  The UN agencies worked through the WHO’s eight outbreak response plan pillars,; and in Zanzibar and Kigoma, the UN’s response was as well coordinated through WHO, also using the outbreak response pillars.

Finding:  As a country team, UN Tanzania was not successful in mobilizing funds for the COVID specific plans it developed.  For most agencies, no additional funding was leveraged either through the Emergency Appeal or the SERP. Agencies therefore did not continue to operate under the three pillars that had been established for the UN Coordination and Response Framework or the five pillars of the SERP.  Instead, individual agencies re-purposed existing funds and incorporated COVID-19-related interventions into their existing programming under the UNDAP II.  Some agencies were also able to raise significant amounts for COVID-19 response activities through their own channels.

Finding – LNOB: Although LNOB has been a foundational principle in the UNDAP throughout this cycle, it has become even more visible as a key theme in the UN’s COVID response, as the focus of one of the three pillars in the UN Tanzania SERP (see above, 2.1.3.4, Cross-cutting Issues – LNOB).

Finding: Business continuity and adaptive programming:  COVID-19-related restrictions on movement and access have had a significant impact on the Tanzania CO’s programming, including an increase in operational costs both for agencies and for their implementing partners.  Moreover, many activities and work streams had to be redesigned for virtual platforms, including the introduction of remote monitoring and data collection through mobile phones, and a work from home modality.  Agencies also repurposed programming from developmental to humanitarian where necessary, and with donors’ consent, with the caveat that the former would be resumed as soon as circumstances permit.

Finding:  The COVID-19 pandemic has exacerbated pre-existing gender inequalities in Tanzania; and women, who already earn on average less than men, and who also constitute the majority of workers in the sectors most negatively affected, have been proportionally more impacted than men by these shocks. Furthermore, women’s work as traditional caregivers has also increased as a result of the pandemic; and women who participate in the workforce bear a double burden of paid and unpaid work.   The UN has made a multi-sectoral response to this challenge, for example, by working with cooperating partners to increase awareness among men and women on issues of gender-based violence and information on reporting channels; through public awareness and communications campaigns to challenge discrimination and stigma; and by working through the KJP VAWC intervention to support Government to develop a TOR for Social Welfare Officers which was disseminated to those working in the Kigoma camps and host communities, among others.  A national respondent to the evaluation noted that gender inequities in the health sector had been aggravated by the pandemic, and suggested that there should be greater UN participation in the Health SWAP to inform solutions to this challenge.

Finding:  As no single response pillar can act independently of the others when responding to an emergency of the scale of the COVID-19 pandemic, the UNCT’s response to this emergency has required collaborative approaches and considerable coordination to deliver results, including within the UN and with Government and other partners.  As a result of these efforts, the UN has been able to achieve significant synergies and inter-agency coordination in its response to the COVID-19 emergency.  Beyond the sector-based programme management structure of the UNDAP OGs, synergies and coordination in the UN’s COVID response have been both vertical, particularly in the health sector, as well as horizontal, across outcomes, particularly in cross-cutting areas like gender.

2.3.5	UNDAP II Management and Coordination

- How effectively has the UNDAF been managed?

Finding:  The UNDAP II management and coordination architecture is complex, with overlapping roles and functions, which reduces efficiencies and effectiveness.  It comprises:

- A Joint Steering Committee (JSC), which is co-chaired by the Permanent Secretary, Ministry of Finance and Planning, together with the UN Resident Coordinator (UN RC).  The JSC is intended to provide overall, macro-level coordination between the UN system and the GURT for the realization of the UNDAP II.  An Inter-Ministerial Technical Committee (IMTC), which is co-chaired by Zanzibar’s Chief Principal Secretary and the UN RC, is intended to meet one week prior to the JSC to discuss issues of specific concern to Zanzibar.  These matters are to be subsequently tabled for consideration by the JSC.

- The UN Country Management Team (UNCMT), which includes the UN Resident Coordinator and the Heads, Representatives or Country Directors of UN Funds, Programmes and Agencies operational in Tanzania, including Non-Resident Agencies (NRAs). The UNCMT directs UNDAP II planning, implementation and reporting processes; and it is responsible for progress on DaO reform.

- The UNDAP II governance structure also includes four Thematic Results Groups, who report to the UNCMT and who are tasked to coordinate, monitor and report on UNDAP implementation by thematic area, according to the Outcome Groups under their responsibility;

- The Programme Management Team (PMT), chaired by a HoA, or equivalent, and whose membership is comprised of Deputy Heads of Agencies (HoAs) or Heads of Programmes.  The PMT is intended to ensure that UN agencies’ work plans align to UNDAP outcomes, and to coordinate reviews, joint site visits and other data collection and analysis tasks.  It is thus intended to act as the “think tank” for the UNDAP.

- At the implementation level, an Outcome Group (OG) was established for each of the twelve UNDAP II results areas. During the UNDAP II cycle, membership in the OGs has been limited to UN agencies; and each OG is chaired by the lead UN agency’s Head of Agency (HoA). The OGs are intended to ensure a coordinated approach with national mechanisms and partners for UNDAP results; and they are responsible for the operationalization of UNDAP II.

- The Operations Management Team (OMT) and the UN Communications Group (UNCG) are also intended to support UNDAP II coordination and cohesion. Rather than the usual standalone BOS, the UNCT decided to integrate it as a result area within the UNDAP II. The Resident Coordinator’s Office (RCO) is intended to further support UNDAP II coordination, as well as monitoring and evaluation, knowledge management and resource mobilization.

- Additional support to UNDAP II implementation and reporting is provided by the Gender Coordination Mechanism and the Programme Monitoring and Evaluation Group.

The utility of the TRG function has been questioned; and there are overlaps between its intended functions and those of the PMT.  The role of the TRGs in supporting communication between OGs, and from management to OGs, has been less than anticipated.  For example, communications from management about One Fund allocations, UNCMT decisions on UNDAP matters and other areas, do not always reach Outcome Groups, making it sometimes difficult to plan.  Moreover, information on OG activities is not always shared between OGs or with the PMT.

.

Finding: Commitment and participation in the TRG, PMT and OGs is mixed; and only the OG ToR stipulates that both OG lead and members’ responsibilities are to be included and reviewed in their performance appraisals.    Furthermore, although the ToRs for each group note the job levels required of members, there is less mention of the management and leadership skills and competencies required of their chairs and co-chairs.

As the Tanzania UNCT is now preparing for a new UNSDCF cycle, and as the country context has significantly changed since the formulation of the UNDAP II in 2015, it is timely and appropriate to consider what skills the Country Office would need going forward to successfully lead and implement the CF and, following that exercise, to consider how its governance structures might be adjusted, particularly if an increased focus on policy and “influencing”, rather than implementing, is envisaged.

2.3.6	Financing

Although not explicitly mentioned as an area of focus in the evaluation ToR, funding, or the lack of it, was the challenge most frequently cited by UN respondents to the achievement of UNDAP II results.  A consideration of UNDAP II financing is therefore included in the evaluation report.

Finding: The UNDAP II budget was overly optimistic about the expected size and scope of the results that could be delivered with the available resources, resource mobilization opportunities and partners, and no joint partnership and resource mobilization strategy, which would have identified potential partners and means of engagement, was developed to support its implementation.  The funding required for UNDAP II was originally estimated at $1.3 bln; the funding currently mobilized is approximately $998 mln.  This leaves a 42% funding gap in the final six months of the UNDAP II cycle.  The largest funding gaps are seen in the VAWC and WLPP Outcome areas.

Finding: As noted above, as a country team, UN Tanzania has not been successful in raising funds for any of the COVID response and recovery plans that it developed; although some individual agencies have mobilized significant sums to support their COVID-related interventions.  (see above, section 2.3.4, “UN COVID-19 Response”)

Finding:  GURT cost-sharing also accounts for a significant percentage of funding for some agencies.

Finding:  The UNDAP has been an effective platform for the mobilization of funds for some joint initiatives through, for example, the ONE FUND, the Global Fund and the CERF.  Although it accounts for only approximately 5% of the total UNDAP budget, and approximately 6% of the total resources mobilized, the ONE FUND has provided a critical source of funding for the ZJP, KJP and some other under-resourced interventions.

However, the amount of support for the ONE FUND has decreased considerably since 2019; and only two of the 11 donors who supported it in 2016 are still contributors.  The reasons cited for this by DP respondents to this evaluation include, among others, that pooled funds provide less visibility and accountability.  This should be seen as part of a global trend whereby donor interest in joint funding mechanisms has waned, and which is considered in detail elsewhere .   Nonetheless, all those interviewed affirmed their support for a One UN and for DaO.

2.3.7  UNDAP II Design

Finding:  As noted above (2.2, “Coherence”), the design of the UNDAP II has hindered  internal coherence between UNCT members toward common objectives and delivering as one; and its twelve outcomes are more reflective of specific agencies’ priorities and projects rather than a DaO approach.  Reflecting the UNDAP’s siloed structure, it has no overarching theory of change or vision statement which would have more clearly linked its twelve outcomes.

An extended internal MYR of UNDAP II in 2019 resulted in some adjustments to the UNDAP II outcome statements and indicators, including greater attention to sex-disaggregated and gender-sensitive data, a reduction in the number of indicators, and a recalibration of funding requirements. However, despite recommendations from the PMT/donor peer review committee that the number of UNDAP outcomes be reduced from twelve to eight, based on their disappointing performance, coherence and funding, all twelve were retained.  Furthermore, the MTR did not result in either the development of a (reconstructed) UNDAP Theory of Change, or in a closer alignment of the UNDAP II to the FYDP II or the Mkuza III.

Finding:  The utility of the UNDAP II as a strategic planning document is further hindered by the absence of a Risk/Risk Mitigation Strategy, as well as the lack of a resource mobilization strategy (this is considered in greater detail under 2.3.6, “Financing”).

  - Sustainability

Finding 29:  UNDAP results could be sustained and scaled up where they align with national and subnational partners’ priorities and policies, and where the counterpart organizations have the staff, institutional capacities and long term, sustained funding required to maintain them once UN support ends.  The fact that UN advocacy for human rights, gender equality and other issues has been institutionalized through the enactment of relevant national policies and legislation, for example, UN advocacy and support to the development of the NPA-VAWG, and the inclusion of CRC and CEDAW principles in the FYPD III, also suggests that UNDAP outcomes in those areas will be maintained. However, although some of the UNDAP II results have been institutionalized, their operationalization and the monitoring of their implementation will be key to ensuring their sustainability.

Finding  30:  There are indicators for the sustainability of some of the interventions in both the KJP and ZJP; for the KJP, these include government payment of social workers salaries and cash contributions to its infrastructure projects; the LGA VAC coordination of a case management referral system, the use of volunteers/fit families and the ToT manual. In Zanzibar, these include the Planning Commission’s incorporation of gender indicators into its M&E system for GRB and other planning uses.

Finding 31: To strengthen the sustainability of their results, technical advice and capacity building feature in most of these JPs’ interventions, although it is not clear the extent to which lasting capacities have been built within the institutions with which they work, as no assessment of capacity building results has yet been undertaken by either JP.

Finding 32:  Sustainability risks for both JPs include the absence of clear exit or handover strategies, and the fact that national funding for social development initiatives is uncertain at present.

- Lessons Learned and Best Practices

Coordination.  Effective programme coordination requires commitments of both time and funding.  As both the KJP and ZJP have demonstrated, joint programme preparation and inception periods can be lengthy.  Moreover, the initial investments of staff time as well as the funding required to establish joint administration and financing mechanisms carry high transaction costs.  With regard to coordination at the Outcome level, only one of the 12 OGs has a dedicated, paid, full-time coordinator; and this has proved to be valuable investment in terms of knowledge management, coordination and communication.

Furthermore, In Tanzania’s complex aid environment, where large numbers of aid actors may be present within a particular region such as Kigoma, the mapping of interventions is key to reducing the duplication and overlapping of projects.  The mapping tool of UN agencies’ work on VAWC, which shows who is working with different Government partners at the national level and what their geographical coverage is at the sub-national level, is a best practice towards coordination.

Finally, coordination and collaboration among UN agencies is more easily facilitated when it is structured around a specific joint programme like the KJP or a joint response like the COVID 19 response.

Joint Programming and DaO.  Although joint programmes indicate an intention to deliver as one, they do not necessarily result in DaO; and other enabling factors must be in place.  For example, as the ZJP demonstrates, if JP funding is not in place for all its pillars at the programme’s inception, implementation cannot proceed in a coherent manner.

4	Conclusions

Conclusion 1 (Relevance): (Based on Findings 1, 2, 3, 4 and 5) The themes of the 2016-2022 UNDAP II are broadly relevant to the Tanzania context: the UNDAP outcomes were aligned with national development priorities identified during its formulation phase; and they also addressed several contextual development challenges identified in the 2015 Situational Analysis. Moreover, they also broadly aligned with the priorities presented in the subsequent medium-term development plan, the 2015-2021 Five Year Development Plan, primarily because major development challenges such as poverty and exclusion remained the same throughout this UNDAP cycle.

The cross-cutting principles of LNOB, human rights and gender equality are visible in UNDAP II outcome statements, indicators and outputs.  However, the extent to which these principles have been mainstreamed into the UNDAP II, if they are measured through the marker system, is unclear; and marker ratings may also change as a result of programming adjustments. Moreover, the markers do not, on their own, provide an effective means of assessing the quality of GEWE and human rights results; and there are other means, such as gender audits and human rights impact assessments, through which those outcomes should be measured.

LNOB has become even more visible as a key theme through the UN’s COVID response, as the focus of one of the three pillars in the UN Tanzania SERP.  Whether LNOB should now be considered through its own theme group, or whether it should be combined with the Gender Coordination Mechanism (GCM), is currently under discussion.  The LNOB theme encompasses a wide range of groups that have intersecting vulnerabilities, not all of which are related to gender; and fully operationalizing LNOB at the country level will require data collection and disaggregation techniques and tools, such as small area estimation, which are usually associated with M&E functions.  Accordingly, there is a strong link between more fully operationalizing LNOB in the UNDAP/UNSDCF and the work of the PMEG.

Environmental sustainability, despite its importance as a core UN programming principle and as a strategic intervention area in the FYDP III, is far less visible in the UNDAP than the other cross-cutting issues; and there are no tags or markers for it in UN INFO or in any UNDAP II outcomes, beyond those in the Environment Outcome area.  Respondents noted that sustainability is a complex area which requires an understanding of critical development-environment linkages, such as those between sustainability and clean energy; or agricultural productivity and food security, or national security, to be able to develop and apply relevant markers for it.  As sustainability will continue to be a core UN programming principle, it must become more visible in the new UNSDCF cycle.  Beyond providing training to the OGs by a subject matter expert, environmental sustainability requires a high-level champion, analogous to those for gender who are now placed within RCOs, who can vigorously promote this theme.

Conclusion 2 (Efficiency - governance) (based on finding 24): The current UNDAP II management and coordination architecture is complex, with overlapping roles and functions, which reduces efficiencies and effectiveness; and a more streamlined system is needed.  As the Tanzania UNCT is now preparing for a new UNSDCF cycle, and as the country context has changed significantly from the time of the UNDAP II formulation in 2015, it is timely and appropriate to consider what skills the Country Office would need going forward, to successfully lead and implement the new CF, and to make such adjustments as needed to its offer to the GURT.  Following that exercise, it would be appropriate to consider how its governance structures might be adjusted to be more efficient, particularly if an increased focus on policy and “influencing”, rather than implementing, which is considered best practice for the UN in MICS, is envisaged.

There are numerous examples of how Country Offices of a comparable size and complexity have tried to rationalize their UNSDCF governance structures.  However, an assessment of each is beyond the scope of this evaluation.  Although the UNCT will undertake a configuration exercise following its UNSDCF formulation, that will focus on agencies’ technical capacities, rather than on management and leadership skills.  The independent capacity assessment commissioned by the Tanzania UNCMT at the start of its One Programme/DaO pilot in 2008 provides a precedent for this kind of capacity assessment exercise.

Conclusion 3 (Effectiveness-financing) (based on findings 25, 26, 27): The UNDAP’s effectiveness as a financing platform has been uneven, although significant amounts have been mobilized through, for example, the CERF, the Global Fund and the ONE FUND.  Despite these successes, as a country team, the UN Tanzania was unsuccessful in raising funds for any of the COVID-19 response and recovery plans it developed. Moreover,  it appears that nearly 40% of the UNDAP II remains unfunded, noting that the figures provided to the evaluation were inconsistent.   Moreover, since 2019, the amount of support available through the ONE FUND has decreased considerably, as donors seek greater visibility and accountability for their contributions than is offered through pooled funding; and this is indicative of the global trend whereby donor interest in joint funding mechanisms has waned.

The 2021 Development Finance Assessment for Tanzania references a variety of mechanisms through which the country’s SDGs might be funded; and some of these modalities, including social enterprise; blended finance and Islamic finance, could be appropriate for the UN to further explore, as would   cost-sharing, through which some UN agencies already benefit.  Moreover, financing through these modalities could also be used to leverage larger amounts from traditional donor sources.

Conclusion 4 (Sustainability-findings 30, 31)  There are positive indicators for the sustainability of the UN’s interventions, including institutionalization and cost-sharing.  Moreover, in each of its Outcome areas, the  UN has undertaken significant capacity development of its national and local partners to strengthen the sustainability of UNDAP II results.   However, it is not clear the extent to which lasting capacities have been built within the institutions with which the UN works, as the UNCT has not yet taken any structured  assessment of progress of these activities towards national ownership, either within or across outcomes.

5	Recommendations

Recommendations for the Tanzania UNCT to build on the results of the 2016-2022 UNDAP II during the remainder of the current cycle and beyond are presented below.

| Evaluation Criteria | Recommendation | Parties Responsible | Timeline |
| --- | --- | --- | --- |
| Relevance (Findings 1-5) | Cross-cutting issues-environmental sustainability: To increase its visibility in the new UNSDCF cycle, the UNCMT should consider placing a focal point for environmental sustainability in the RCO, at least on a part-time basis. | RC, UNCMT, PMT, OGs | Before the end of the current UNDAP II cycle |
|  | Environmental sustainability: Training in this area for OGs should be re-initiated, to better guide the development and application of markers for this principle. | PMT, OGs | Before the first UNSDCF mid-year review |
|  | Gender and human rights marker system: Gender and human rights markers should be reviewed annually and updated where necessary, to ensure that they accurately present the level of focus of the UN’s activities, noting that the marker ratings cannot replace other analytical exercises, e.g. gender audits, human rights impact assessments. | PMT, OGs | Before end of UNDAP II cycle |
|  | LNOB: it is recommended that the LNOB theme continue to be considered through the GCM, rather than add another theme group to the existing UNDAP architecture. | UNCMT, GCM, PMT | Ongoing |
|  | LNOB: Given the strong link between more fully operationalizing LNOB in the UNDAP/UNSDCF and the need for fine-grained data collection and disaggregation, it is recommended that LNOB be placed on the PMEG agenda as an area of focus, and that there be PMEG representation during the GCM/ LNOB discussions. | GCM, PMT, PMEG | Before end of UNDAP II cycle |
| Efficiency and effectiveness (Findings 24,25, 26, 27) | Financing-The UNSDCF resource mobilization strategy should be developed in consultation with the Ministry of Finance, to ensure the harmonization of UN and GURT approaches to funders. | UNCMT, PMT, RC, RCO | Following the development of the UNSDCF funding framework |
|  | Financing: The UNCMT should pro-actively explore those innovative financing modalities referenced in the Tanzania 2021 DFA which are appropriate for UNDAP/UNSDCF interventions, and through which it could leverage larger donor funding, including green bonds and Islamic finance. The latter may be particularly appropriate to the Zanzibar context. | UNCMT, PMT, RC, RCO | During the first year of the UNSDCF cycle |
|  | Governance: the UNCMT should commission a functional review of the UNCT to determine the extent to which it is fit for purpose as it starts a new UNSDCF cycle, to further inform any adjustments to the current UNDAP/UNSDCF governance structure | UNCMT, external management consultancy firm | Before the end of the UNDAP II cycle |
|  | Governance: the UNDAP II management and coordination architecture should be reduced and simplified in the successor UNSDCF. Adjustments to the governance structure should be informed by the recommended functional review. | UNCT, external management consultancy firm | Before the end of the UNDAP II cycle |
| Sustainability (findings 30, 31) | To better ascertain the extent to which lasting capacities have been built within the institutions with which the UN works, and therefore sustainability, it is recommended that the UNCT undertake a survey to follow up on its trainings and knowledge transfer initiatives with selected key ministries and local partners. | UNCMT, PMT, OGs | By the end of the first year of the new UNSDCF cycle |

Select Bibliography

Unpublished Sources

UNINFO, UNDAP II Indicator Report, 24 February 2021

United Nations Tanzania, Common Country Analysis, 6 August 2021 (Draft)

United Nations Tanzania, United Nations Country Management Team Meeting Minutes 2019

United Nations Tanzania, Outcome Groups’ Minutes of Meetings, 2017 – 2021 (various)

United Nations Tanzania, Programme Management Team Meetings, 2020 – 2021 (various)

United Nations Tanzania, Programme Management Team Peer Review 2019

United Nations Tanzania, Reconfiguration Validation Report, October 2019

United Nations Tanzania, Self-Evaluation of Socio-Economic Response Plans (SERPs) March 2021

United Nations Tanzania, Terms of Reference – UNCT Gender Coordination Mechanism for Gender Equality, December 2019 (draft)

United Nations Tanzania, Terms of Reference – Joint Government of Tanzania and UN Steering Committee, April 2016 (final draft)

United Nations Tanzania, Terms of Reference – Operations Management Team (n.d.)

United Nations Tanzania, Terms of Reference – Inter-Agency RBM Technical Group (n.d.)

United Nations Tanzania, Terms of Reference – Programme Management Team, February 2016

United Nations Tanzania, Terms of Reference – Outcome Groups (updated 30 October)

United Nations Tanzania, Terms of Reference – Thematic Results Groups (n.d.)

United Nations Tanzania, Terms of Reference – Programming Principles Task Team (n.d. 2017?)

United Nations Tanzania, Terms of Reference – United Nations Communications Group, August 2016

United Nations Tanzania, Terms of Reference – Emergency Coordination Group (n.d.)

United Nations Tanzania, Terms of Reference – One Fund for the United Republic of Tanzania, April 2016

Published Sources

Arnesen, Odd Erik Arnesen et al., Review of the Joint Programme for the Kigoma Region. Requested by Royal Norwegian Embassy, Dar es Salaam, May 2019.

Asian Development Bank Statistics and Data Innovation Unit, Economic Research and Regional Cooperation Department, Asian Development Bank International Workshop on SDG Data Disaggregation 28-30 January 2019: https://unstats.un.org/sdgs/files/meetings/sdg-inter-workshop-jan-2019/Session%207.a_ADB_Small%20Area%20Estimation%20-%20jan29.pdf

Cooksey, Brian, “IPTL, Richmond and “Escrow”: The price of private power procurement in Tanzania”, Understanding Africa Today, Africa Research Institute Briefing Note 1702:  November 2017:  https://www.africaresearchinstitute.org/newsite/wp-content/uploads/2017/11/ARI_IPTL_BN_November2017-1.pdf

Davids, Christopher and Emmanuel Maliti, Tanzania Situation Analysis: In support of UNDAP II, April 2015:  https://erc.undp.org/evaluation/documents/download/9341

Government of the United Republic of Tanzania, Tanzania Development Vision 2025:  https://mof.go.tz/mofdocs/overarch/vision2025.htm#:~:text=The%20Tanzania%20development%20Vision%202025%20seeks%20to%20realize%20patriotism%2C%20nationalism,political%20and%20other%20relevant%20factors.

Government of the United Republic of Tanzania and United Nations Tanzania, Joint Damage Tanzania Situation Analysis: In support of UNDAP II and Needs Assessment Report on Earthquake, Kagera Region, 26 September 2016:  https://reliefweb.int/report/united-republic-tanzania/joint-damage-and-needs-assessment-report-earthquake-kagera-region

McKee, C., Blampied, C., Mitchell, I., and Rogerson, A., (2020), ‘Revisiting Aid Effectiveness: A New Framework and Set of Measures for Assessing Aid “Quality,”’ Centre for Global Development: https://www.cgdev.org/sites/default/files/WP524-McKee-Mitchell-Aid-Effectiveness.pdf

Ministry of Finance and Planning and United Nations Development Programme Tanzania, Tanzania: Development Finance Assessment Report 2021, May, 2021.

## Mirondo, Rosemary, “First Islamic bond in Tanzania is oversubscribed”, The Citizen, 20 August 2021:   https://www.thecitizen.co.tz/tanzania/news/business/first-islamic-bond-in-tanzania-is-oversubscribed-3516148

## Okonji, Grace Achieng and Kokuteta Baregu Mutembei, Thematic evaluation of UNDP’s contribution to Gender Equality and Women’s Empowerment at mid-term stage of implementation of the Country Programme Document 2016 – 2021, UNDP Tanzania, 2018:  C:/Users/user/Downloads/Final%20Gender%20Thematic%20Evaluation%20 Report%2020181214%20nr%20(1).pdf

Organization for Economic Co-operation and Development – Development Assistance Committee, Criteria for Evaluating Development Assistance:  https://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

Tripp, Aili Mari, Donor Assistance and Political Reform in Tanzania,  UNU Wider World Institute for Development Economics Research, Working Paper No. 2021/37:   https://www.wider.unu.edu/sites/default/files/wp2012-037.pdf

UNICEF Tanzania, Country Office Annual Report 2020:  https://www.unicef.org/reports/country-regional-divisional-annual-reports-2020/United-Republic-of-Tanzania

UNICEF Tanzania, Country Programme Evaluation, 2021.

United Nations Development Programme, Tanzania Development Finance Assessment Report, 2021.

United Nations Development Programme, Human Development Report 2020:  The Next Frontier – Human Development and the Anthropocene, New York, 2020: http://hdr.undp.org/en/2020-report

UNDP, “Briefing Note:  Tanzania”, Human Development Indices and Indicators: 2018 Statistical Update

United Nations Development Programme Independent Evaluation Office, Independent Country Programme Review:  Tanzania, 2021: http://web.undp.org/evaluation/evaluations/adr/tanzania.shtml

United Nations Development Programme, Socio-economic Impact Assessment of COVID-19 in Tanzania, April 2020:  https://www.greengrowthknowledge.org/research/socio-economic-impact-assessment-t anzania

United Nations Sustainable Development Group, Leaving No One Behind:  A UNSDG Operational Guide for UN Country Teams (Interim Draft), March 2019:  https://unsdg.un.org/sites/default/files/Interim-Draft-Operational-Guide-on-LNOB-for-UNCTs.pdf

United Nations Sustainable Development Group, Cooperation Framework Consolidated Annexes, July 2020.

United Nations Tanzania, 2016-2021 Tanzania United Nations Development Assistance Plan II:  https://tanzania.un.org/sites/default/files/2019-12/UN%20Development%20Assistance%20Plan%20%28UNDAP%20II%29_2016-2021.pdf

United Nations Tanzania, 2016-2021 Tanzania United Nations Development Assistance Plan II Results Report 1 July 2018- 30 June 2020, Dar es Salam, 2020.

United Nations Tanzania, Mainstreaming, Acceleration and Policy Support (MAPS) Mission Report, 2018.

United Nations Tanzania, One Programme Annual Report. Delivering as One Pilot Programme in Tanzania, 2008.

United Nations Tanzania, 2008 Stocktaking Report and Annual One Programme Report:  https://mptf.undp.org/document/download/6327

United Nations Development Group, United Nations Development Assistance Guidance, New York, May 2017:  https://undg.org/wp-content/uploads/2017/05/2017-UNDAP_Guidance_01-May-2017.pdf

United Nations Evaluation Group, Guidance Note on the Application of Programming Principles to the UNDAF, 2010.

World Bank, Tanzania Overview, March 2021:  https://www.worldbank.org/en/country/tanzania/overview#1

World Food Programme Tanzania, Annual Country Report 2020, February 2021:  https://docs.wfp.org/api/documents/WFP-0000125457/download/

ANNEX 1

# TERMS OF REFERENCE

# Evaluation of the United Nations Development Assistance Plan 2016-2022 (UNDAP II) Tanzania

## BACKGROUND AND CONTEXT

### UNDAP II Thematic Results Groups and Outcomes

The United Nations Development Assistance Plan 2016-2022 (UNDAP Il) defines the collective vision and response of the UN Country Team (UNCT) in Tanzania to the 2030 Agenda for Sustainable Development and Tanzania’s national development priorities (as defined in the Five-Year Development Plan 2016/17-2020/21, FYDP II and the Zanzibar Strategy for Growth and Reduction of Poverty 2016-20/MKUZA III). UNDAP ll results are grouped under four inter-related, mutually dependent themes, which acknowledge that Inclusive Growth requires a Healthy Nation, as well as Resilient to shocks (both natural and man-made) within the context of transparent and accountable Governance serving citizens’ needs. These four thematic areas are further divided into 12 Outcomes and 39 Outputs, with indicators measuring delivery on an end-of-term and annual basis, respectively.

The Plan runs from 1 July 2016 to 30 June 2022, in alignment with the Government of the United Republic of Tanzania’s (GURT) planning and budgetary cycle. It is nationally executed and managed by the Joint Government and UN Steering Committee (JSC), which is co-chaired by the Permanent Secretary of the Ministry of Finance and Planning (MoFP) and the UN Resident Coordinator. Members from central and line ministries (including Zanzibar) sit on the JSC, with rotating representation by UN Heads of Agencies.

UNDAP II is implemented through a set of Joint Work Plans (JWP) for each of the 12 Outcomes, coordinated through 12 technical level results groups with members drawn from 23 UN (resident and non-resident) Agencies, Funds and Programmes. Each JWP is reviewed and updated on a bi-annual basis in consultation with government, development and civil society partners, for final approval by the JSC.

As UNDAP II nears completion, the UNCT and national partners have agreed to undertake an evaluation. This will build upon the findings of the UNDAP II Mid-Term Review 2019 and agency-specific country evaluations to further promote accountability for results. Moreover, this will contribute to developing knowledge for the design of the Plan’s successor: the UN Sustainable Development Cooperation Framework (UNSDCF) 2022-2027.

The primary users of the UNDAP II evaluation at the country level will be the UNCT (resident and non-resident, management and technical level staff), the Government and Non-State Actors (including civil society and private sector), alongside Development Partners. On the global stage, the evaluation should contribute to knowledge regarding good practice; other UN country offices, UNDCO-regional and UNDCO HQ will therefore also form an important audience.

## PURPOSE, OBJECTIVES AND SCOPE

The purpose of the evaluation is twofold:

- to support learning for improved results at the country level, specifically informing programme systems and processes including UN coordination for the forthcoming UNSDCF.

- to promote accountability for the achievement of agreed results as defined in UNDAP II, in support of national development priorities within the context of the 2030 Agenda.

The evaluation has five key objectives:

- to assess the relevance, appropriateness and effectiveness of UN System support under UNDAP II

- to determine the coherence of UN system support under UNDAP II

- to measure the extent to which UN system support has supported transformational changes

- to evaluate the extent to which the cross-cutting principles of gender equality, human rights and environmental sustainability have been promoted and followed under UNDAP II

- to provide actionable recommendations for improving the UNCT's contribution across all of the aforementioned elements (i-iv) in the new UNSDCF. These should focus upon:

- successful interventions which have the potential for scale-up/replication

- key constraints/challenges for mitigation in the next cycle (including internal reasons for sub-optimal delivery)

- options for improvements in UNCT governance/coordination mechanisms

UNDAP II encompasses both development and humanitarian assistance, with a focus on building the capacity of the GURT to realise its responsibilities as the primary duty bearer across a range of sectors, and support to empower rights-holders to claim their rights across those same programme areas. The majority of initiatives are national in coverage and upstream; notwithstanding there are a significant number of components that operate at the sub-national level. There are also two area based Joint Programmes in Zanzibar and Kigoma, which contribute to four+ UNDAP II Outcomes.

The evaluation should cover all activities implemented during the UNDAP II cycle until the start of the evaluation. However, it is not intended as a full evaluation of individual programmes, project or activities of UNCT members, but rather, builds on the programme and project evaluations conducted by each agency. Where a paucity of data necessitates a quick assessment of a contribution, this should be carried out using appropriate evaluation methodologies that identify contributions at the outcome level and ascertain the plausibility of causal relationships between activities and outcomes.

Going forward, a complementary UNDAP II results report, featuring stories of transformation from the field, will be produced by the UNCT. Selection will be informed by those ‘successes’ highlighted in the UNDAP II evaluation. The purpose is to further strengthen accountability, whilst showcasing the UN’s contribution to the lives of Tanzanians covering the lifetime of UNDAP II (2016-2022).

## EVALUATION QUESTIONS AND METHODOLOGY

The evaluation should respond to the following questions:

Relevance, appropriateness and effectiveness of the UN system support

- Has the UN system supported achievement of national development goals and targets?

- Has the UN system prioritized and extended in such a way to leave no one behind?

- Has the UN system remained responsive to emerging and unforeseen needs of the country and the people?

Coherence of the UN system support

- Has the UN system collectively prioritized activities based on needs (demand side) rather than on availability of resources (supply side), and reallocated resources according to collective priorities if necessary?

- Has UNDAP II strengthened the coherence of support by UNCT members towards common objectives and to deliver quality, integrated, SDG-focused policy support?

- Has UNDAP II strengthened the position, credibility and reliability of the UN system as a partner for the government and other actors?

Supporting transformational changes

- Has UN system support extended in such a way to build national and local capacities and ensure long-term gains?

- Has the UN system promoted and supported inclusive and sustainable economic growth that leaves no one behind and strengthens ecological foundations of the economy and the society?

- Has the UN system promoted or supported policies that are consistent among each other and across sectors, given the multi-sectoral nature of social and economic development?

- Has the UN system supported the country and the people in strengthening economic and individual resilience and contributed to reducing vulnerability against shocks and crises?

Conformity with the crosscutting principles

- Has the UN system support extended in such a way to promote gender equality?

- Has the UN system support followed Human Rights principles?

- Has the UN system support been designed and delivered in due consideration to environmental implications?

The Evaluation methodology should consist primarily of a desk review of the evaluations, reviews and assessments related to UNDAP II that have already been undertaken or are currently underway. These are:

- Agency-specific evaluations

- Kigoma Joint Programme Evaluation

- UNDAP II Mid-Term Review 2019

- UNDAP II JWP Biannual Reviews (2017-2021)

- Annual Gender Scorecard Assessments (2018-2020)

- Disability Scorecard Assessment (2020)

- FYDP II and MKUZA III Reviews (2020-21)

Findings should be complemented by interviews and/or focus groups encompassing the fullest possible range of stakeholders. These should be identified based upon availability, logistical constraints, ethical considerations, as well as current UN and Government COVID-19 provisions. The extent to which many potential respondents may have already been called upon to participate in the agency specific evaluations must also be taken into account.

In acknowledgement of the 2030 Agenda’s transformative promise to leave no-one behind, all efforts should be made to draw upon and generate both data and analysis, which supports understanding of the dimensions of inequity relevant to the country. This should include but not be limited to sex, age, geographical location, disability and migratory status.

It is anticipated that the inception report will include an evaluation matrix linking the data collection methods to the evaluation criteria and questions. Analysis should combine qualitative and quantitative tools, triangulating information sources and findings where possible for validation purposes.

## MANAGEMENT OF THE EVALUATION

The UN Country Management Team will serve as the Evaluation Steering Committee. These will be assisted by a Consultative Group comprised of key stakeholders, including technical representatives from the UN Country Team, government, development partners and civil society. An Evaluation Manager from within the UN Resident Coordinator’s Office will be appointed to serve as the day-to-day interlocutor with the Evaluation Consultant.

The Evaluation Consultant will conduct the evaluation process in a timely manner, communicate with the Evaluation Manager on a regular basis, and highlight progress made and challenges encountered.

S/he must possess the following:

- A Master’s Degree in International Development, Public Administration, Evaluation or Related Field

- A minimum of 10 years’ experience of conducting Complex Evaluations, preferably at least one UNDAF/UNSDCF Evaluation

- Demonstrable experience of conducting Gender Equality and Human Rights responsive evaluations

- Familiarity with the UN system in development cooperation

- A good understanding of the SDGs and their implications for development cooperation

- A strong record of assessing management structures, in terms of cohesiveness, responsiveness and procedural approach

- Experience of qualitative and quantitative data collection and analysis methods including interview techniques and facilitation skills

- Proficiency in English (spoken and written, with capacity to write inception, draft and final evaluation reports)

Sound knowledge of the country context is also desirable.

## EVALUATION PROCESS

The evaluation consultant must prepare an inception report that operationalizes the design elements of the Terms of Reference. The report should include a description of evaluation methodology/methodological approach, data collection plan, data collection tools and analysis methods, key informants, evaluation questions, performance criteria, issues to be studied and timeline. The report should also include a brief evaluability assessment including foreseen limitations and risks, plus list resource requirements and logistic support needed. To facilitate the development of the inception report the key documents listed above will be provided to the evaluator at the beginning of the consultancy. The Evaluation Manager and Consultative Group will review and provide substantive comments to the inception report, before final approval can be awarded by the Steering Committee.

The evaluation consultant must then proceed with data collection and analysis. This process should be planned in close consultation with the Evaluation Manager to ensure the necessary logistical support can be provided. Preliminary findings and a clear set of recommendations should be presented to the Consultative Group, plus other invited stakeholders. These should take the form of a PowerPoint Presentation with accompanying notes packaged in a concise report. Based on their feedback, a draft and then final report should be produced, in accordance with UNEG Norms and Standards.

Once the evaluation report has been validated by the Steering Committee, it will be made publicly available through posting on the UNDG and UNCT websites. The UNCT in collaboration with the Consultative Group, will develop a management response to the evaluation recommendations, including a timeframe and responsibilities for follow up. The key findings from the evaluation and summarized points from the management response will be shared through a stakeholder workshop, to contribute to decision-making at all levels, including for the formulation of the UNSDCF 2022-2027.

Annex 2

Evaluation Schedule and Deliverables

| Date | Time | Name/Group/Institution | Location/ Platform | Persons Met |
| --- | --- | --- | --- | --- |
| Monday, 13 September | 10.30 – 11.30 | Induction zoom call with RCO M&E | By Zoom | Helga, Annette |
|  |  | Initial document review |  | Annette |
| Tuesday, 14 September |  | Document review | Home-based | Annette |
| Wednesday, 15 September | 2.30 – 3.00 | Internal documentation: UNINFO, annual reports, | By Zoom | Josephine, Annette |
|  | 4.00 – 5.30 | Narrative reports, budget, UNINFO – call (2) | By Zoom | Josephine, Annette |
|  |  | Document review |  | Annette |
| Thursday, 16 September | 10.30 – 11.00 | Documentation | By Zoom | Helga, Annette |
| Friday, 17 September | 9.00 – 10.00 | Documentation | By Zoom | Helga, Annette |
|  |  | Inception report preparation | Home-based | Annette |
| Monday, 20 September |  | Document review; meetings with RCO re outcome areas; ToC; RF; KM; other annexes | Home-based | Annette |
| Tuesday, 21 September |  | Document review; documentation requests (Jenni/Freya for Gender; Helga; others) | Home-based | Annette |
|  | 4.15 – 4.45 | Meeting by Teams with RCO members of PME re additional internal documentation (rescheduled) | Home-based | Helga, Susan, Josephine, Irene, Annette |
| Wednesday, 22 September | 1.30 – 2.30 | Background materials for which RCO was secretariat; data extraction from backup files for UNINFO | By Teams | RCO members of PMEG: Helga, Susan, Josephine, Irene; Annette |
| Friday, 24 September | 1.00 – 2.00 | GCM, LNOB | By Teams | Jenni, Annette |
|  |  | Preparation of inception presentation | Home-based | Annette |
| Monday, 27 September | 2.00 – 3.00 | Presentation of inception report | By Teams | UNCMT; RCO; Annette |
| Tuesday, 28 September |  | Document review; internal UN meetings | Home-based | Annette |
| Wednesday, 29 September | 9.00 – 9.30 | UNDAP Design | By Teams | Helga, Annette |
|  | 10.00 – 11.00 | Meeting with TRG leads and alternates | By Teams | Ms. Christine Musisi, RR, UNDP; Ms. Jacqueline Mahon, UNFPA; Ms. Julia Broussard, UN Women; Mr. Stephen Kargbo, UNIDO; Helga (as event organizer); Annette |
|  |  | Meeting with Outcome Group Leads | By Teams | See OG Respondents List |
| Thursday, 30 September | 10.00 – 11.00 | UNDAP II – meeting with Resident Coordinator | By Teams | Mr. Zlatan Milisic, UNRC Tanzania; Helga, Annette |
|  | 11.00 – 12.00 | UNDAP II partnerships | By Teams | Ms. Zhanara Bakaouva, RCO, Annette |
|  | 2.00 – 3.00 | UNDAP background | By Zoom | Ms. Aine Mushi, UNCDF; Annette |
|  | 10.00 – 11.15 | PMT focus group discussion | By Teams | See Respondents – PMT |
|  | 10.00 – 10.30 | DP interviews; additional documentation | By Teams | Annette, Susan |
| Tuesday, 5 October | 10.00 – 11.00 | PME meeting | By Teams | PME Group (see participant list); Annette |
|  | 11.30 – 12.00 | UNDAP evaluation inception report feedback | By Teams | Ms. Shabnam Mallick, Head of RCO: Annette |
| Wednesday, 6 October | 8.45 – 9.30 | UNDAP governance: PMT | By Teams | Ms. Shalini Bahuguna, UNICEF; Annette |
|  | 2.00 – 3.00 | UNDAP – GEWE | By Zoom | Ms. Freya Larsen, UN Women; Annette |
|  | 3.00 – 4.00 | Gender Coordination Mechanism FGD | By Zoom | GCM Group (see participant list); Annette |
| Thursday, 7 October | 10.00 – 10.30 | UNDAP partnerships: Switzerland | By Zoom | Mr. Leo Nascher, SDC, Annette |
| Friday, 8 October | 8.00 – 8.30 | UNDAP partnerships: Sweden | By Zoom | Ms. Lina Palmer, SIDA; Annette |
|  | 12.00 – 12.30 | UNDAP partnerships: DPG | By Zoom | Mr. Ambrose Mugisha; UNDP - DPG secretariat |
|  | 2.00 – 2.15 | Evaluation update | By Zoom | Shabnam, Annette |
|  |  | Revision of inception report |  |  |
| Monday, 11 October | 11.00 – 11.30 | UNDAP partnerships: Sweden | By Zoom | Ms. Jenny Akerback, SIDA; Annette |
|  | 2.15 – 3.00 | UNDAP partnerships: World Bank | By Teams | Ms. Preeti Arora, World Bank |
| Wednesday, 13 October | 8.00 – 8.30 | PMT | By Zoom | Mr. Rene von Drogen, UNICEF & -PMT; Annette |
|  | 2.00 – 2.30 | UNDAP documentation; interviews | By Zoom and Teams | Susan, Annette; Helga |
| Thursday, 14 October | 8.30 – 9.30 | KJP | By Zoom | Evance, RCO Kigoma; Annette |
| Friday, 15 October | 10.00 – 10.30 | ZJP | By Zoom | Dorothy; Annette |
|  | 11.00 – 11.30 | Environment Outcome | By Zoom | Ms. Clara Makenya, UNEP; Annette |
|  | 12.30 – 1.00 | ZJP | By Zoom | Dorothy Temu-Usiri, RCO Zanzibar; Annette |
|  | 5.00 – 5.30 | UN INFO; UNSDCF coordination; partnerships | By Zoom | Mr. Kwasi Amankwaah, DCO; Annette |
| Tuesday, 19 October | 8.30 – 9.30 | COVID response; gender | By Zoom | Mr. Inaam Haq, World Bank; Annette |
|  | 1.30 – 2.00 | UNDAP II formulation; implementation | By Zoom | Mr. Alvaro Rodrigues, former RC, Tanzania; Annette |
| Wednesday, 20 October | 10.15-11.30 | UNDAP Partnerships-MoF | By Phone | Ms. Sauda Msemo, Commissioner, External Partnerships, Annette |
|  | 12.00-12.30 | UNDAP Partnership, NORAD | By Zoom | Ms. Vivian Ospvik, NORAD; Mr. Edmund Einer Walton, Embassy of Norway; Annette |
|  | 3.30-4.30 | ZJP partners | By Zoom |  |
|  | 4.30-5.00 | ZJP additional partners | By Zoom | Dorothy Temu Usiri, RCO; Annette |
| Thursday, 21 October | 9.00 – 9.30 | UNDAP II Partnerships | By Zoom; WhatsApp | Mr. Dastan Kweke, Irish Aid; Annette |
|  | 11.30 – 12.00 | UNDAP II evaluation update | By Zoom | Zlatan; Annette |
|  | 2.00-3.00 | Zanzibar liaison officers | By Zoom | Dorothy; UN Tanzania liaison officers, Annette |
|  | 4.45-5.00 | NGO links | By Teams | Helga, Annette |
| Monday, 25 October | 5.00 – 5.30 | LNOB; DPG Gender | By Google Meet | Ms. Maya Hansen, UNFPA; Annette |
| Tuesday, 26 October | 11.30 – 12.30 | Preliminary Findings PPT Presentation | By Teams | UNCMT; PMT; RCO; Annette |
| Wednesday, 27 October | 10.00-11.00 | MoH | By phone | Ms. Subsiya; Annette |
| Thursday, 28 October | 10.00-11.00 | GURT COVID Response | By Signal | Mr. Charles Msangi, OPM DRR; Annette |
| Friday, 29 October | 9.30 – 10.30 | CSO FGD | By Zoom | Seraphina, Amos, James: AMREF; Annette Benedicto, TAYO |
| Saturday, 30 October | 9.00 – 10.00 | CSO KII | By Zoom | Mathew, NACOPHA; Annette |
| Friday, 5 November | 5.00 – 5.30 | COVID Response | By Zoom | Dr. Annemarie Terveen, RCO; Annette |
| Saturday, 6 November | 1.00 – 1.45 | UNDAP Partnerships - Government | By Zoom | Dr. Catherine Joachim, MoH; Annette |
| Friday, 12 November |  | Zero draft submitted |  |  |
| Wednesday, 17 November |  | Feedback on zero draft received |  |  |
| Monday, 22 November |  | Draft 1 submitted |  |  |
| Monday, 6 December |  | Final feedback on draft received |  |  |
| Wednesday, 15 December |  | Final draft submitted |  |  |

ANNEX 3

Respondents - Key Informant Interviews and Focus Group Discussions

| Institution | Name | Title |
| --- | --- | --- |
| Government |  |  |
| Ministry of Finance and Planning | Ms. Sauda Msemo | Commissioner, External Finance |
| OPM-Disaster Management Dept. | Mr. Charles Msangi | UN Focal Point, Emergencies |
| Ministry of Health, Social Welfare, Gender, Elderly and Children | Dr. Catherine Joachim | Health Systems Specialist |
| PO-RALG, Social Protection | Ms. Subisya Kabuje | Assistant Director, Health, Nutrition and Social Welfare |
| Zanzibar Planning Commission | Ms. Mashavu Omar | Commissioner |
| Zanzibar Planning Commission | Ms. Salama Makame | Commissioner |
| Zanzibar Ministry of Finance | Dr. Afua Mohammed | Commissioner |
| UN Respondents |  |  |
| RCO | Mr. Zlatan Milisic | Resident Coordinator |
| RCO | Ms. Shabnam Mallick | Head of RCO |
| RCO | Ms. Josephine Laswai | Data Management & Results Reporting |
| RCO | Ms. Irene Mwogsa | Data Management & Results Reporting |
| RCO | Ms. Susan Kiragu Nottingham | RBM Specialist |
| RCO | Ms. Jenni Ratilainen | LNOB Agenda, Gender |
| RCO | Ms. Zhanara Bakauova | Partnership and Development Finance |
| RCO | Dr. Annemarie Terveen | Consultant, COVID focal point |
| RCO | Mr. Evance Siangicha | Head of Kigoma JP |
| RCO | Ms. Dorothy Temu-Usiri | Head of RCO, Zanzibar |
| RCO | Mr. Alvaro Rodriguez | Former Resident Coordinator Tanzania |
| RCO | Ms. Helga Gibbons | Former M&E Consultant |
| RCO Rwanda | Ms. Josephine | Head of UN Rwanda RCO |
| UNDCO | Mr. Kwasi Amankwaah | Regional Programme Advisor |
| UN Women | Ms. Hodan Addou | Country Representative, OG Lead WPPL |
| UN Women | Ms. Julia Broussard | Deputy Country Representative (TRG, PMT) |
| UNIC | Ms. Stella Vuzo |  |
| UNICEF | Ms. Shalini Bahuguna | Country Representative; Chair, PMT |
| UNICEF | Mr. Rene Van Dongen | Deputy Country Representative |
| UNIDO | Mr. Stephen Kargbo | TRG Co-Lead |
| WFP | Mr. Juvenal Kisanga | ERC secretariat |
| WFP | Mr. Sawiche Wamunza |  |
| WFP | Mr. Brian Bogart | Deputy Country Director |
| WFP | Ms. Tiziana Zoccheddu |  |
| ILO | Mr. Jealous Chirove | OG Lead, EGE |
| UNEP | Ms. Clara Makenya | Evaluation Focal Point |
| UNDP | Ms. Christine Musisi | Resident Representative (TRG Co-Lead) |
| UNDP | Mr. Ambrose Mugaisha | OG Lead, Environment & DRR; Head of DPG Secretariat |
| UNDP | Mr. Sergio Valdini | Deputy Resident Representative |
| UNDP | Mr. Amon Manyama |  |
| UNCDF | Ms. Anie Mushi |  |
| UNCDF | Ms. Rashida Sharif | GMC |
| UNCDF | Ms. Ivana Damjanov |  |
| UNCDF | Mr. Abraham Byamungu | Evaluation Focal Point |
| UN Women | Ms. Freya Larsen | OG Lead Support, WPPL |
| UNFPA | Ms. Jacqueline Mahon | Country Representative |
| UNFPA | Ms. Maya Hansen | Technical Advisor Gender Equality |
| UNAIDS | Dr. Otilia Scutelniciuc | OG Lead Support, HIV/AIDS |
| FAO | Mr. Charles Tulahi |  |
| ITC | Mr. Sébastien Turrel | Evaluation Focal Point |
| ITC | Ms. Lida Azatyan |  |
| UNHCR | Ms. Julia Seevinck | OG Lead Support, Refugees |
| UNOPS | Mr. John Fofanu | Evaluation Focal Point |
| WHO | Mr. Maximillian Kassian K. Mapunda |  |
| WHO | Dr. Andemichael |  |
| UNDP | Ms. Rukiya Wadoud |  |
| NGOs |  |  |
| Amref | Amos |  |
| Amref | James |  |
| Amref | Serafina |  |
| NACOPHA | Mathew Kawogo | Private Sector and Community Engagement Manager |
| Tanzania Youth Alliance | Benedicto Luvanda |  |
| Development Partners |  |  |
| SIDA | Ms. Lina Palmer | First Embassy Secretary, Development Analyst |
| SIDA | Ms. Jenny Akerback | Former Development Analyst, Tanzania |
| Embassy of Switzerland/SDC | Mr. Leo Nascher | Deputy Head of Mission, Head of Cooperation |
| Embassy of Ireland/Irish Aid | Mr. Dastan Kweke | Political Analyst |
| Embassy of Norway | Ms. Vivian Hilde Opsvik | Development Counsellor |
| Embassy of Norway | Mr. Edmund Einar Walton | Embassy Secretary |
| World Bank | Mr. Inaam Ul Haq | Programme Lead, Health Sector Team |
| World Bank | Ms. Preeti Arora | Operations Manager |

Annex 4

Evaluation Matrix

| Criteria | Key Questions | Means of Verification | Comments/Constraints |
| --- | --- | --- | --- |
| Relevance, appropriateness, effectiveness of UN system support | Has the UN system supported achievement of national development goals and targets? | Document review, including Government of Tanzania Vision 2025; other GURT, policies and plans; 2016-2022 UNDAP; UNDAP annual reviews; UNCT Annual Reports; PMT, Outcome Groups’ minutes of meetings; JSC minutes of meetings; donor country strategies and evaluations; GURT SWAP documents ONE FUND reports; PMT, Outcome Groups’ meeting minutes; donor reports; JP reports, evaluations; AFPs’ Country programme/portfolio evaluations Rapid Socio-economic Impact Assessment – COVID (2020) KIIs, FGDs with TRG and Outcome Leads; LNOB focal point; GCM lead; PM&E Group; JSC; Development Partners | Constraints: The turnover of UN and DP staff has hindered information about the formulation and early implementation of UNDAP II, including the availability of key documentation such as the comparative advantage exercise; also, availability of national and local respondents is not confirmed, as of day 20 of the evaluation; These interviews have not yet been scheduled, and they are critical to the credibility of the evaluation; JSC meeting minutes-only one meeting has been convened since 2016 Mitigation: Interviews with former UN and DP staff, if possible, noting that this will involve additional time Mitigation: review evaluation timeframe |
|  | Has the UN system support prioritized and extended in such a way to leave no one behind? | JP Kigoma, JP Zanzibar, COVID 19 response KIIs and documentation, including evaluation; any recent CP/country portfolio evaluations; UNINFO selected markers and tags; GURT, DP, CSO/NGO KIIs, FGDs | Constraint: Only one of the AFPs’ CP evaluations, which were to be a basis for this evaluation, has been completed Mitigation: review timeframe for completion of AFPs’ evaluations; review timeframe for UNDAP evaluation Constraint: no FGDs with GURT or rights holders have been arranged, both of which are critical to the credibility of the evaluation Mitigation: review evaluation timeframe |
|  | Has the UN system remained responsive to emerging and unforeseen needs of the country and the people? | COVID -19 Response; SERF; UN Cooperation Strategy-COVID -19 Response Explanatory Note; Minutes of TRG, PMT; UNCMT meetings; FGDs with PMT, OGs, DPs, national partners | Constraint: Only 1 of the AFPs’ CP evaluations, which were to be a basis for this evaluation, has been completed Mitigation: review timeframe for completion of AFPs’ evaluations; focus on one whole of UN response, e.g. COVID response; review timeframe for UNDAP evaluation Constraint: no FGDs with GURT or rights holders have been arranged Mitigation: arrange key GURT interviews week 5 of evaluation (Office of President; Mofaz; Mop; Mohr & Gender Dept.); review evaluation timeframe |
| Coherence of UN system support | Have the UN system collectively prioritized activities based on needs (demand side) rather than on availability of resources (supply side), and reallocated resources according to collective priorities if necessary? | Document review, including 2016--2020 UNDAP; annual reviews of UNDAP; AFPs’ CPs and evaluations; OG meeting minutes; JP documents; Rapid Socio-economic Impact Assessment – COVID (2020); CP evaluations; World Bank, other IFI country strategies Interviews with TRGs, Outcome Leads; Development Partners; Government of Tanzania stakeholders; UNCG; OMT; donors, including IFIs UNINFO reports on indicators, markers, tags | Constraint: only 5 of 12 OG minutes of meetings files received Constraint: only 1 of AFP CP evaluations finalized Constraint: as of day 20 of evaluation, no KIIs or FGDs with national or local partners arranged; these are critical for evaluation credibility Mitigation: review evaluation timeframe Constraint: UNINFO currently unavailable, as system is migrating to a new platform Mitigation: use RCO back up files for documentation of 2020-1 only |
|  | Has UNDAP II strengthened the coherence of support by UNCT members towards common objectives and to deliver quality, integrated, SDG-focused policy support? | Internal coherence: OG, PMT, TRG, UNCMT meeting minutes and ToRs | Constraint: not all documentation may be readily available, e.g. Comparative Advantage exercise from UNDAP II formulation; e.g. minutes for only 5 of the 12 OG have been received |
|  | Has UNDAP II strengthened the position, credibility and reliability of the UN system as a partner for the government and other actors? | External Coherence: SWAPs; donor evaluations; stakeholder consultations, perception survey from UNDAP II formulation phase; GURT and DP KIIs | Constraint: not all documentation may be readily available, e.g. Comparative Advantage exercise from UNDAP II formulation Mitigation: triangulate through FGDs, KIIs Constraint: Many of the DPs have recently changed, so institutional memory on UNDAP II, interactions with and between UN could be limited Mitigation: interview former embassy aid officials, if available and amenable, noting that this will involve additional time Constraint: Interviews with DPs were not arranged until day 19 of the evaluation; as of day 20 of the evaluation, no interviews with national stakeholders had been arranged; the latter are essential for the credibility of the evaluation Constraint: only 1 of AFP CP evaluations finalized Mitigation: review evaluation timeframe for feasibility |
| Supporting transformational changes | Has UN system support extended in such a way to build national and local capacities and ensure long-term gains? | Interviews with UNCMT; OGs; OMT; Development Partners; GURT stakeholders; annual reviews; Review of AFPs’ recent CP evaluations | Constraint: only 1 of AFP CP evaluations finalized Mitigation: review timeframe for completion of AFP CP evaluations, as well as UNDAP evaluation timeframe for feasibility Mitigation: focus on one key whole of UN intervention, e.g. COVID 19 response; reference JPK and Zanzibar for DaO based on evaluations; KIIs |
|  | Has the UN system promoted and supported inclusive and sustainable economic growth that leaves no one behind and strengthens ecological foundations of the economy and the society? | Review of AFPs’ recent CP evaluations; Interviews with UNCT; RGs; OMT; Development Partners; Government of Tanzania stakeholders; annual reviews |  |
|  | Has the UN system promoted or supported policies that are consistent among each other and across sectors, given the multi-sectoral nature of social and economic development? | Review of AFPs’ recent CP evaluations; Interviews with UNCMT; OGs; OMT; Development Partners; GURT stakeholders; annual reviews |  |
|  | Has the UN system supported the country and the people in strengthening economic and individual resilience and contributed to reducing vulnerability against shocks and crises? | Review of AFPs’ recent CP evaluations; Interviews with UNCMT; OGs; OMT; Development Partners; GURT stakeholders; annual reviews |  |
| Conformity with crosscutting principles | Has the UN system support extended in such a way to promote gender equality? | KIIs, FGDs with TRG leads, PMT; Outcome leads; RCO; GURT partners; Development Partners; Tanzania VNR; GCM FGD Minutes of PPTT, PMT, Outcome Groups’ meetings; UNDAP reports; JP documents; GCM Group minutes; donor reports Gender, HR, environment markers in UNINFO; UNCT SWAP Gender Scorecard reports | Constraint: UNINFO currently being migrated to another system; it is therefore not currently possible to search it for gender, HR and other crosscutting tags and markers Mitigation: data for the current year can be extracted from RCO back up files Only 5 of 12 Outcome Group meeting minutes have been shared |
|  | Has the UN system support followed Human Rights principles? |  | UNINFO currently being migrated to another system; it is therefore not currently possible to search it for gender, HR and other crosscutting tags and markers; although data for the current year can be extracted from RCO back up files Only 5 of 12 Outcome Groups have shared selected meeting minutes with the evaluator |
|  | Has the UN system support been designed and delivered in due consideration to environmental implications? |  | Constraint: UNINFO currently being migrated to another platform; it is therefore not currently possible to search it for gender, HR and other crosscutting tags and markers Mitigation: data for the current year can be extracted from RCO back up files Constraint: Only 5 of 12 Outcome Group selected meeting minutes have been shared with the evaluator |

ANNEX 5

UNDAP II Evaluator Bio

Dr. Annette Ittig, the UNDAP II evaluator, is an evaluation and partnership expert with extensive experience in both staff and contractor roles in donor, UN agency and private sector assignments, including with the World Bank, UNDP, UNICEF, ILO, WFP, DPKO, UN-Habitat and the MasterCard Foundation, in Tanzania, Kenya, Ghana, Zimbabwe, the Gambia, South Sudan, Somalia, Iraq, Afghanistan, the UAE and elsewhere.  Her strategic framework experience includes the evaluations of the 2014-2018 Kenya UNDAF, the 2016-2021 Uzbekistan UNDAF, the 2014 evaluation of the 2012-2015 Zimbabwe ZUNDA and the final evaluation of the 2012-2016 Gambia UNDAF, as well as the narratives for the 2018-2022 Nepal UNDAF, the 2021-2025 Eswatini UNSDCF and the 2022-2023 UN Women Myanmar Interim Strategic Note documents.  Dr. Ittig received her doctorate from the University of Oxford.

For example, GURT cost-sharing accounts for USD $42.4 mln of UNDP Tanzania’s funding from 2016-2019: UNDP Tanzania:  Independent Evaluation Office, United Nations Development Programme, Independent Country Programme Review:  Tanzania, New York, March, 2021, pp. 72: http://web.undp.org/evaluation/evaluations/adr/tanzania.shtml.   Among other examples, WFP received “…locally generated funds, mainly the value-added tax reimbursement of USD 2.5 million… from the Government, of which USD 1.5 million was instrumental in maintaining a minimum ration for the refugee operation”. WFP Annual Country Report 2020 p, 11; the Kigoma Joint Programme has also received cash from the Government for some of its interventions

UNDP, Tanzania Development Finance Assessment 2021, p. 42

The numbers of the findings and conclusions in this Executive Summary are those that are given in the evaluation text.

:https://unstats.un.org/sdgs/files/meetings/sdg-inter-workshop-jan-2019/Session%207.a_ADB_Small%20Area%20Estimation%20-%20jan29.pdf

United Nations General Assembly, Development cooperation with middle-income countries:  Report of the Secretary General, A/72/269, 5 August 2019, p. 13

For example, the Uzbekistan CO has eliminated the PMT stratum; the Rwanda CO, which was also a DaO pilot country, presents a more streamlined model, with only four Results Groups, in addition to ad hoc issue-specific task teams.  Although not originally included, a PMT was subsequently added to the Rwanda UNDAP architecture.  As another example, the Ethiopia CF management includes issue groups, which work across sectors, rather than Results Groups.

It would be appropriate for DCO or the UNCMT to consider this.

In 2008s, the UNCMT commissioned an independent capacity assessment of the UNCT to determine if its skills base was fit for purpose.  The assessment, which was part of review of UN capacities in each of the DaO pilot countries, was undertaken by Dalberg Global Development Advisors in coordination with the UN Global Change Management Task Force.  According to the UN Tanzania 2008 Stocktaking Report and Annual Programme Report, pp. 25-27:

“The capacity assessment exercise proved to be one of the most useful change management processes so far, providing the UNCT in Tanzania with aggregate data to take decisions that will shape the way the UN works in the future. The results of the capacity assessment indicated that there needs to be a substantial shift of human resources from traditional project management functions to policy advice and technical assistance.... The main shift however is expected to come from comprehensive training to ensure that staff acquire the necessary skills to cover modified job descriptions or posts with new functions. The UNCT also set clear quantifiable targets to guide the implementation of a shift in human resource capacity over the next four years".

“This decision is in line with the recommendations from the High-Level Panel on System-wide Coherence, and will lead to different skills mix in the future. The expected result is a UN that uses its comparative advantage to function, a UN that sets normative standards, and a UN that delivers the highest quality technical assistance.”

UNDP Tanzania, Tanzania Development Finance Assessment Report 2021

Islamic financing may be appropriate for some types of UN interventions in mainland Tanzania, where a sukuk, or Islamic bond, was recently launched and over-subscribed; as well as in Zanzibar, where there is already a general understanding of this type of funding.  The ZJP, which already has an established programming structure and relationships with government and local stakeholders, may be an appropriate vehicle through which to explore this option; and the potential role of Zanzibar as an incubator for innovation, piloting and modelling has already been noted.

Following their respective independence in 1961 and 1964, and the ratification of Articles of Union between Tanganyika and Zanzibar in 1964, the two entities merged as the United Republic of Tanzania.

Both strategies are operationalized through five-year development plans, the Tanzania Five Year Development Plans (FYDP) and the Zanzibar Strategies for Growth and Reduction of Poverty (ZSGRP), or MKUZA, according to its Kiswahili acronym.  To date, Tanzania has launched three FYDPs (2011/12-2015/16, 2016/17-2020/21, and 2021/22-2025/26), as has Zanzibar (2006/7-2010/11, 2011/12-2015/16, and 2016/17-2020/21).

UNDP, “Briefing Note:  Tanzania”, Human Development Indices and Indicators: 2018 Statistical Update

UNDP, Human Development Report 2020 (HDR) New York, 2020, p. 372

World Bank Tanzania Overview March 2021:  https://www.worldbank.org/en/country/tanzania/overview#1

United Nations Tanzania, Common Country Analysis, (CCA) 6 August 2021 (Draft), p. 6

CCA, p. 15:  on the mainland, the rates for females and males were 96.7 percent and 94.8 percent, respectively; and in Zanzibar, 86.3 percent for females and 86.3 percent for males.

Ibid.

See, for example, CCA, pp. 7-12.

Zanzibar Vision 2020, Section 5.

CCA, p. 80

HDR 2020, p.363; see also UN Tanzania, Common Country Analysis August 2021 (draft), p. 54; “Tanzania falls short of the 50/50 representation required by African Union and SADC Commitments to which it is a signatory and, at the current rate, Tanzania will not realize the goal of 50 percent of elected female members of parliament until the year 2069.”:  CCA, p. 80

The first case of COVID-19 in Tanzania was registered on 16 March 2020.

World Bank, Tanzania Overview 2021:  https://www.worldbank.org/en/country/tanzania/overview

CCA, p. 44

World Bank, Tanzania Overview 2021:  https://www.worldbank.org/en/country/tanzania/overview

The 2030 Agenda, including the 17 SDGs, was officially agreed upon and adapted by all of the 193 Member States of the United Nations, including Tanzania, at the Sustainable Development Summit held 25-27 September 2015 at UN Headquarters in New York:  http://www.un.org.cn/info/6/620.html

See, for example, for gender:  https://media.africaportal.org/documents/Impact-of-Covid-19-PB.pdf; for People Living With Disabilities (PLWD), see UN Tanzania, “Situational Analysis on Persons with Disabilities in the United Republic of Tanzania”, November 2021; and for migratory status, OCHA, Flash Appeal for COVID-19 Tanzania, July - December 2020:  https://reliefweb.int/report/united-republic-tanzania/flash-appeal-covid-19-tanzania-july-december-2020, which references the vulnerabilities of refugees.

United Nations Development Programme, Tanzania Development Finance Assessment Report 2021:  https://inff.org/assets/resource/tanzania-development-finance-assessment-(1).pdf.  Also,

From TZS 1,7 trillion in 2010/2011 to TZS 1.0 trillion in 2019/2020:  Development Finance Assessment Report 2021 (DFA), p. 31

Ibid. The cessation of general budget support by international donors in 2014 will account for at least some of this reduction.  Also, In 2014, international donors withheld budget support worth over US$500m, following an alleged corruption case in which officials were accused of transferring $124 million from the central bank to a private energy company: https://www.africaresearchinstitute.org/newsite/wp-content/uploads/2017/11/ARI_IPTL_BN_November2017-1.pdf

For example, GURT cost-sharing accounts for 42.4 percent of UNDP Tanzania’s UNDP Tanzania:  Independent Evaluation Office, United Nations Development Programme, Independent Country Programme Review:  Tanzania, New York, March, 2021, pp. 72, 75: http://web.undp.org/evaluation/evaluations/adr/tanzania.shtml.   Also, among other examples, WFP received “…locally generated funds, mainly the value-added tax reimbursement of USD 2.5 million… from the Government, of which USD 1.5 million was instrumental in maintaining a minimum ration for the refugee operation”. WFP Annual Country Report 2020 p, 11; the KJP has also received cash from the Government for some of its interventions

DFA, p. 42

Ibid p. 20

Twenty-three Agencies, Funds and Programmes (AFPs) are represented in the Tanzania United Nations Country Team: IAEA, IFAD, ITC, FAO, ILO, IOM, OHCHR, UN-HABITAT, UNCDF, UNCTAD, UNDP, UNEP, UNICEF, UNFPA, UN Women, UNESCO, UNHCR, UNIDO, UNODC, UNAIDS, UNV, WFP and WHO

The original end date for UNDAP II was 2021, but this was extended by one year to allow planning for the 2023-2027 UNSDCF to be informed by the 2021/2022 – 2025/2026 FYDP III and the MKUZA IV

In 2006, the UN General Assembly (UNGA) adapted the Delivering as One (DaO) approach, which aims for a more effective, efficient, coherent, coordinated and better performing United Nations country presence with a strengthened role of the senior resident official and a common management, programming and monitoring framework. Tanzania was one of eight countries selected to pilot this initiative:  https://www.un.org/en/ga/deliveringasone/.  The governments of Albania, Cape Verde, Mozambique, Pakistan, Rwanda, Uruguay and Vietnam also volunteered to pilot the Delivering as One approach.  In the initial DaO phase in Tanzania, from January 2007-2010, seven Joint Programmes (JPs) were developed under the framework of the One Programme: 2008 Stocktaking Report, p 24.  These included the precursors to the Zanzibar Joint Programme (ZJP) and the Kigoma Joint Programme (KJP), namely, JP 5, “Capacity building support to Zanzibar”, and JP 6.1, “Transition in Northwestern Tanzania”.  Three more JPs were added to the One Programme in 2009-2010.

The UNDAP II also includes two additional Outcomes focused upon 1) Business Harmonization and 2) Communications, Outreach, Advocacy and Partnerships.

For example, limited progress towards gender equality in education; limited economic empowerment of women; limited progress towards gender equality; inadequate civil registration and vital statistics:

Davids, Christopher and Emmanuel Maliti, Tanzania Situation Analysis: In support of UNDAP II (SitAn 2015), April 2015:  https://erc.undp.org/evaluation/documents/download/9341

The UNDAP was signed in July 2015, three months before the national elections.  Subsequent to its win in October 2015, the new government modified the draft FYDP II for a greater focus on industrialization and economic transformation.

UNDAP II, p. 48

The evaluation Terms of Reference (ToR) also anticipated that a multi-stakeholder Consultative Group would as well support this exercise:   See below, Annex 1, “Terms of Reference”, section IV, Management of The Evaluation: “The UN Country Management Team will serve as the Evaluation Steering Committee. These will be assisted by a Consultative Group comprised of key stakeholders, including technical representatives from the UN Country Team, government, development partners and civil society”.   Unfortunately, this Consultative Group was not established.

UN Tanzania, Reconfiguration Validation Report, October 2019

UNDP and UNICEF.

Purposeful sampling is a sampling technique used by qualitative researchers to recruit participants who can provide in-depth and detailed information about the phenomenon under investigation. As such, it is one of the most time-effective sampling methodologies.

The rationale for a light approach includes the lengthy 2019  MTR; the commitment to not have an evaluation in the UNDAP II signed by GURT; the experience of UNDAP I evaluation when Government partners complained of the administrative burden of participating in a number of simultaneous evaluations, for example, those for the various CPDs in addition to the UNDAP evaluation; the challenges of timing – the strategic prioritization and the formulation of the results framework would be completed by the time of the Evaluation.  It was also expected that the evaluation would “… consist primarily of a desk review of the evaluations, reviews and assessments related to UNDAP II that have already been undertaken or are currently underway”: evaluation ToR, Section III, Evaluation Methodology.

UNDAP indicator report, 24 February 2021

Only five of the twelve OGs have shared selected minutes of meetings with the evaluator:  EGE; VAWG; Nutrition; Governance; HIV/AIDS

“Contribution Analysis …offers an approach designed to reduce uncertainty about the contribution (an) intervention is making to the observed results through an increased understanding of why the observed results have occurred (or not!) and the roles played by the intervention and other internal and external factors…Contribution analysis ….helps to confirm or revise a theory of change…(and to provide) evidence (for) a plausible conclusion that, within some level of confidence, (a) program has made an important contribution to the documented results.”  https://www.betterevaluation.org/en/plan/approach/contribution_analysis

Relevance refers to “the extent to which the aid activity is suited to the priorities and policies of the target group, recipient and donor”: Organization for Economic Co-operation and Development - Development Assistance Committee, Criteria for Evaluating Development Assistance

See above, footnote 42, 2015 SitAn.

UN Tanzania, Evaluation of Tanzania UNDAP 2011-2016, 2015, p.85

VAWC and WPPL

For example, “No. of grade one children learning through innovative technology in UN-‐supported regions

Baseline:  500 (400 Mainland; 100 Zanzibar) “

UNDAP II Programming Principles Task Team. Terms of Reference (n.d.)

The UNCMT agreed to the establishment of the GCM in August 2020, and regular GCM meetings were launched in January 2021.

DP KII

National Partner KII; NGO KII

See, for example, OGVAWC minutes of 16 July 2018 meeting; see also, for example, the coordination between UNFPA, UN Women and UNICEF in response to a request from the police for VAWC-related support:  OGVAWC minutes of 13 August 2020 meeting.

A GEN1 marker indicates that the Key Activity contributes to GEWE in a limited way; GEN2 indicates that GEWE is a significant objective of the Key Activity’s overall intent; GEN3 indicates that GEWE is the main objective of the Key Activity:  UNSDG, UNCT Gender Equality Marker Guidance Note, pp. 12-14

Unfortunately, the UN INFO system was being transferred to another platform during the evaluation period; and it was not possible to extract data from it or, therefore, to capture trends in budget allocations to GEWE over the UNDAP II cycle. It was only possible to extract data for the past year from backup files maintained by RCO.

The current NPA VAWC was rolled out in 2017/2018.

E.g., the Cybercrimes Act 2015, the Statistics Act 2015 and the 2018 Non-Governmental Organizations (Financial Transparency and Accountability) Regulation G.N 609:  CCA, p. 123. In late 2019, Tanzania also withdrew from the Article 34(6) of the Protocol to the African Charter on Human and Peoples’ Rights, which allows individuals and NGOs to directly access the Court. CCA p 78. However, “…early signals from the new President suggest there is an appetite for reversing this trend and opening up the civic and democratic space in-country”:  CCA, p. 123

The Human Rights Marker reflects the extent to which a development project contributes towards the realization of human rights in its planning and implementation. The Human Rights Marker uses a scale of zero to three (0-3):  A Human Rights 1 marker indicates that a project has made a limited contribution to human rights; Human Rights 2 indicates that human rights has been integrated in a project in a significant and consistent way; Human Rights 3 indicates that human rights is the main objective of the project.

Ministry of Finance and Planning, “5.3 Interventions for Deepening Industrialization and service provision”, United Republic of Tanzania National Five-Year Development Plan, June 2021.

See also UNDAP II Programming Principles Task Team Terms of Reference, n.d., which references training on environmental sustainability.

Co-chair of LNOB Pillar UNFPA and UNWOMEN proposed that we make the LNOB pillar a more permanent mechanism that goes beyond the COVID-19 response and this group will cover LNOB issues including disability inclusion and youth. UNFPA and UNWOMEN volunteer to co-chair and they are preparing the TOR, which will soon be shared: PMT minutes of 17 March 2021 meeting.

UNSDG, Leaving No One Behind:  A UNSDG Operational Guide for UN Country Teams:  https://sdgintegration.undp.org/leaving-no-one-behind-unsdg-operational-guide-un-country-teams?utm_source=EN&utm_medium=GSR&utm_content=US_UNDP_PaidSearch_Brand_English&utm_campaign=CENTRAL&c_src=CENTRAL&c_src2=GSR&gclid=EAIaIQobChMI_uXCio6k9AIVjJBoCR3McwwmEAAYASAAEgIk3_D_BwE

The compatibility of the intervention with other interventions in a country, sector or institution: The extent to which other interventions (particularly policies) support or undermine the intervention, and vice versa. Includes internal coherence and external coherence: Internal coherence addresses the synergies and interlinkages between the intervention and other interventions carried out by the same institution/government, as well as the consistency of the intervention with the relevant international norms and standards to which that institution/government adheres. External coherence considers the consistency of the intervention with other actors’ interventions in the same context. This includes complementarity, harmonization and co-ordination with others, and the extent to which the intervention is adding value while avoiding duplication of effort. https://www.oecd.org/dac/evaluation/daccriteriaforevaluatingdevelopmentassistance.htm

Under UNDAP I, these groups included Government membership. However, as noted in the Governance Outcome Group minutes of 21 April 2020, “(the) OG (was) to institutionalize meetings with Government, correct what was not done in the past and make government part and parcel of all UNDAP process”

Similar findings are presented in the UNICEF CPE 202l, e.g.  “…many question UNDAP II performance and relate this to the different approach to project development, consisting mainly of combining existing agency projects. xiii and xiv;  “The UNDAP II is not considered to be strategic and focused, but rather a compilation of 20 different agency programmes”, p. 59; see also UNDP Independent Evaluation Office, Independent Country Programme Review:  Tanzania, 2021, p. 22:   file:///C:/Users/user/Downloads/Report_ICPR%20Tanzania%20(1).pdf

Respondents also noted good coherence and division of labour between agencies in the SWAPs, particularly in the health SWAP.

Relations were also strained by the expulsion of the former Country Director of UNDP from Tanzania in 2017 by the Government “…citing concerns about poor performance and strained relations with her staff, according to various news sources. Other reports stated that the Country Director had been critical of Zanzibar’s 2015 election and the controversial re-run in 2016, and opposition party members attributed her expulsion to this.”:  IOE UNDP Tanzania 2020, footnote 14.

However, the indicator report for February 2021 indicates that 45 out of 204 indicators, or some 22%, are unmeasurable:  see above, footnote 41

Compiled from UNDAP II Report 2018-2020

Number of indicators x 2 (years)

These are identically marked in the report

As noted above and in the evaluation inception report, at the evaluation has prioritized key areas that could be effectively analyzed within the thirty-day work period.  was also proposed that analysis of transformative changes focus upon the UN-wide COVID-19 response, with reference also to the large Joint Programmes in Kigoma and Zanzibar in which most of the UN Tanzania AFPs participate.  This approach was agreed with RCO

UNHCR, WHO, UNICEF, WFP, UN-Women, IOM, UNIDO, UNESCO, UNDP, FAO, UNCDF, UNEP, ILO, ITC, UNFPA, and UN-Habitat.

However, as SEE has not been funded, some of the agencies participating in this theme have not implemented any physical activity.

NORAD Review, 2019, p. 12

MPTF– One FUND reports

The KJP’s planned support to refugees was intended to complement pre-existing humanitarian programmes for them:  “A holistic durable approach is applied in this programme to include both refugees and migrants in the region as well as the surrounding host communities. The humanitarian-development nexus is supported by linking together our existing response to refugees and migrants with an expanded development support to the host communities….

The support to the host communities also links up to and provide services and benefits to the refugee community in several of the outputs.” UN Tanzania, UN Joint Programme for the region of Kigoma 2017-2021 (project document), 2016, p. 4

# Review Of the Joint Programme for The Kigoma Region (JPK) (Hereafter NORAD Review 2019), p. 24

KJP Prodoc, p. 97

NORAD Review 2019

KII

Norad review, 2019

FAO, UNFPA, UNDP, ILO, IOM, UNIDO, UN Women, UNICEF, WHO

This project, which was led by UNICEF, was completed in October 2019.

The controversy surrounding the conduct of the 2015 election in Zanzibar, and the March 2016 re-run, resulted in the withdrawal of donor funding from Zanzibar.

See above, “Introduction”, footnote 17.

SERF; principles and strategies aiming to ensure the rights and needs of vulnerable groups and left behind populations are addressed throughout the plan. It is essential for the implementation, monitoring and evaluation of the SERP to be guided by these principles, including through detailed tagging and inclusion of sex, age and disability-disaggregated data in the reporting process”.

“The Socio-Economic Recovery Framework (SERF) is anchored in the United Nations Development Assistance Plan 2016-2022 (UNDAP II). It is directly linked to the outcomes under the four results groups, namely Inclusive Growth; Healthy Nation; Democratic Governance, Human Rights and Gender Equality; and Resilience. Planned interventions will contribute to the achievement of these agreed UNDAP II results…”: UN Tanzania, Self-Evaluation of Socio-Economic Response Plans (SERPs) March 2021, p. 1 (unpublished)

Surveillance and contact tracing, testing, case management, infection prevention and control, epidemiological and outbreak analytics, logistics and risk communication and community engagement.

See for example, OG VAWC 2020-2021 MYR ppt, slide 8; OG EGE 2020-2021 MYR ppt, slide x

See, for example, the 2020-2021 MYR OG presentations

E.g. UNICEF raised $20 mln.

For example, UNICEF has estimated that some 27 percent of the TCO’s planned results for 2020 were constrained: UNICEF Country Office Annual Report. 2020, p 2;

E.g., WFP, Annual Country Report 2020, p. 8; FGD and KII with NGO partners

WFP ACR 2020 p 25

KII

UN Tanzania, Terms of Reference – Joint Steering Committee

UNDAP II Thematic Results Group Terms of Reference, n.d.

Under UNDAP I, these groups included Government membership. However, see Governance Outcome Group minutes of 21 April 2020, in which “OG to institutionalize meetings with Government, correct what was not done in the past and make government part and parcel of all UNDAP process”.

UN Tanzania, Terms of Reference:  Operational Management Team; Terms of Reference:  United Nations Communications Group (internal documents)

RCO TOR, if available;

Prior to the 2019 UNDAP MTR, the mainstreaming of GEWE and other programming principles was the responsibility of the PPTT, who reported to the PMT.  In August 2020, the CMT agreed to establish the GCM, which focuses upon the implementation of the Gender Scorecard, including ensuring the integration of GEWE into UNDAP programming, among others.

UNCMT meeting minutes 2019: “On UNDAP II Management structure, there was a question of the need of TRGs, it was suggested to remove the TRG layer and have fewer Outcomes, with empowered Outcome group leads (i.e. Having Heads of Agencies as the Outcome Group Leads)”.

“Instead, focus of the (MT) review is a) identifying and documenting any major changes and bottlenecks and the related adjustments needed in the JWP and b) internal reflection on functions of the UNDAP II management structures.” OGVAWG, 7 Dec 2017

See, e.g., OGVAWG minutes 7 Dec, 2017, “5. AOB. Lack of participation and response of the outcome group members were discussed and it was agreed on contacting head of programmes to ensure participation from all agencies in the following meetings and responsiveness on requests for inputs”, e.g. only one TRG provided inputs into the 2019 MTR:  UNCMT meeting minutes; UN KII

UNDAP II Outcome Groups Terms of Reference, n.d., “6.3. Head of Agencies must ensure that the Outcome Group members’ responsibilities and key deliverables are included in their respective agency performance appraisal and, where possible, performance is reviewed by outcome group lead and/or other group members”.

A similar emphasis on policy and influencing is seen in the 2021 UNICEF Tanzania Country Programme Evaluation

E.g. WFP Tanzanian Annual Country Report 2020, February 2021: In 2020, funding constraints remained one of the major risks for WFP, p.8:   https://docs.wfp.org/api/documents/WFP-0000125457/download/

According to the available UNINFO figures

For example, UNICEF has mobilized more than US $20 mln

For example, UNDP received $42.4 mil from GURT as cost sharing: IEO UNDP 2021.  Also, WFP received “…locally generated funds, mainly the value-added tax reimbursement of USD 2.5 million… from the Government, of which USD 1.5 million was instrumental in maintaining a minimum ration for the refugee operation”. WFP Annual Country Report 2020 p, 11; the KJP has also received cash from the Government for some of its interventions

ONE FUND Annual Progress and Financial Reports for 2017, 2018, 2019 and 2020 are available at https://mptf.undp.org/factsheet/fund/TZ100

DP KIIs

Although a detailed discussion of this topic is beyond the scope of this evaluation, it has been discussed in depth elsewhere: see, for example, McKee, C., Blampied, C., Mitchell, I., and Rogerson, A., (2020), ‘Revisiting Aid Effectiveness: A New Framework and Set of Measures for Assessing Aid “Quality,”’ Centre for Global Development. https://www.cgdev.org/sites/default/files/WP524-McKee-Mitchell-Aid-Effectiveness.pdf

Similar findings are presented in the UNICEF CPE 202l, e.g.  “…many question UNDAP II performance and relate this to the different approach to project development, consisting mainly of combining existing agency projects. xiii and xiv; “The UNDAP II is not considered to be strategic and focused, but rather a compilation of 20 different agency programmes”, p. 59; see also UNDP Independent Evaluation Office, Independent Country Programme Review:  Tanzania, 2021, p. 22:   file:///C:/Users/user/Downloads/Report_ICPR%20Tanzania%20(1).pdf.  Nonetheless, the twelve outcomes in UNDAP II represent a significant reduction from the 58 outcomes featured in UNDAP I.

Based on their poor performance, it was recommended that the Education, Social Protection, WASH and DRR/Environment Outcomes be rolled into other Outcomes:  PMT Peer Review 2019

Under UNDAP II’s EGE Outcome, Assumptions:  Change in Government leadership following 2015 Elections does not result in postponement or change in policy direction.  When this happened, there was no mitigation in place

The extent to which the benefits of a programme are likely to continue after funding has ceased.

:https://unstats.un.org/sdgs/files/meetings/sdg-inter-workshop-jan-2019/Session%207.a_ADB_Small%20Area%20Estimation%20-%20jan29.pdf

United Nations General Assembly, Development cooperation with middle-income countries:  Report of the Secretary General, A/72/269, 5 August 2019, p. 13

For example, the Uzbekistan CO has eliminated the PMT stratum; the Rwanda CO, which was also a DaO pilot country, presents a more streamlined model, with only four Results Groups, in addition to ad hoc issue-specific task teams.  Although not originally included, a PMT was subsequently added to the Rwanda UNDAP architecture.  As another example, the Ethiopia CF management includes issue groups, which work across sectors, rather than Results Groups.

It would be appropriate for DCO or the UNCMT to consider this.

In 2008s, the UNCMT commissioned an independent capacity assessment of the UNCT to determine if its skills base was fit for purpose.  The assessment, which was part of review of UN capacities in each of the DaO pilot countries, was undertaken by Dalberg Global Development Advisors in coordination with the UN Global Change Management Task Force.  According to the UN Tanzania 2008 Stocktaking Report and Annual Programme Report, pp. 25-27:

“The capacity assessment exercise proved to be one of the most useful change management processes so far, providing the UNCT in Tanzania with aggregate data to take decisions that will shape the way the UN works in the future. The results of the capacity assessment indicated that there needs to be a substantial shift of human resources from traditional project management functions to policy advice and technical assistance.... The main shift however is expected to come from comprehensive training to ensure that staff acquire the necessary skills to cover modified job descriptions or posts with new functions. The UNCT also set clear quantifiable targets to guide the implementation of a shift in human resource capacity over the next four years".

This decision is in line with the recommendations from the High-Level Panel on System-wide Coherence, and will lead to different skills mix in the future. The expected result is a UN that uses its comparative advantage to function, a UN that sets normative standards, and a UN that delivers the highest quality technical assistance. ”

The original budget for UNDAP II was $1.3 billion; the total anticipated budget referenced in the December 2020 outcome budgets is $1.2 billion; a third figure of $1.7 billion is noted on the UN Tanzania webpage.

UNDP Tanzania, Tanzania Development Finance Assessment Report 2021

Islamic financing may be appropriate for some types of UN interventions in mainland Tanzania, where a sukuk, or Islamic bond, was recently launched and over-subscribed; as well as in Zanzibar, where there is already a general understanding of this type of funding.  The ZJP, which already has an established programming structure and relationships with government and local stakeholders, may be an appropriate vehicle through which to explore this option; and the potential role of Zanzibar as an incubator for innovation, piloting and modelling has already been noted.

Original term 2016-2021; extended by one year to align with Government planning processes.

All times are EAT

All locations are home-based

For example, background materials on UNDAP II design, including the analysis of development challenges and root causes undertaken during its formulation, were provided to the consultant on 29 September, that is, day 13 of the evaluation: