## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sheet1
| Table 1 | Sheet1
Sheet2
| Table 1 | Sheet2

## Sheet1
Country: South Africa: Cooperation Framework 2020-2025 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Evaluation of the Cooperation Framework for South Africa (2020-2025) - 2024 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: Evaluation Managers with support from the Data Management Officer (RCO) and M&E Group • Frequency of monitoring and updating: Annual
RECOMMENDATIONS TO IMPROVE THE RELEVANCE AND ADAPTABILITY OF THE COOPERATION FRAMEWORK **
Recommendation 1: 1. Enhance the localisation of UNSDCF objectives by deepening engagement with provincial and municipal governments to align more closely with sub-national plans.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UN already has deep engagements with the provincial and municipal levels, having signed numerous MOUs and supported the development of sub-national plans. The UN has also implemented several programmes at the sub-national level, together with government and other partners.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Expand engagement with subnational governments through existing coordination platforms or through engagement with departments specialised in providing capacity to local government - example SALGA | 2025-12-01 | RCO and the UNCT | An MOU was established with SALGA, the UN also signed a DOI with the Eastern Cape Province | completed | December | 2025
1.2 | Enhance partnerships with civil society, community-based organizations, and traditional/local leadership structures to ensure inclusion and ownership. | 2025-12-31 | UNCT (RGs) | Targeted consultations were conducted with subnational stakeholders (government, civil society, CBOs), strengthening collaboration, enhancing local ownership, and ensuring their priorities were meaningfully integrated into the Cooperation Framework. | completed | December | 2025
Recommendation 2: Improve adaptability by incorporating real-time monitoring mechanisms to adjust interventions based on changing socio-economic conditions.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted, as the UN has already been incorporating real-time monitoring mechanisms to inform adaptive management of interventions in response to changing socio-economic conditions; however, efforts will continue to further systematise and strengthen these processes where feasible.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1. | Adopt a risk-informed development approach across all Outcome Groups, ensuring risk analysis is integrated into Theory of Change and results frameworks.. | 2025-11-01 | Inter-agency Task Team | a risk analysis was included in the development of the new Cooperation Framework inlcuding in the Theory of Change | completed | June | 2025
2.2 | Align adaptive processes with the UN INFO and Joint Work Plans systems to ensure real-time tracking and transparent reporting of adjustment | 2025-12-01 | M&E Theme Group | This will be concluded in 2026 | delayed | December | 2025
Recommendation 3: continue refining cross-sector integration, particularly in addressing intersecting challenges of poverty, violence, and health disparities.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted, as the United Nations Country Team in South Africa has a strong record of cross-sectoral collaboration reflected in its annual results reports, working across agencies and with Government, civil society, and development partners to address interconnected challenges such as poverty, inequality, health disparities, and violence through integrated programmes and joint planning under the Sustainable Development Cooperation Framework; continued refinement of these integrated approaches will be pursued to enhance collective impact.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Enhance collaboration between thematic Results Groups, particularly those focusing on governance, health, education, and social inclusion, to co-design integrated interventions targeting multiple deprivations. | 2025-12-31 | Result Group Chairs (as well as focal points) | Several actions have been taken by different result and working groups to ensure that there is ongoing cross-sector integration in the areas pertaining to the various challenges that the country experiences. Examples include The Education Working Group strengthened cross-sector integration through collaborative engagement with UNESCO (as co-chair) and other partners, including the joint confirmation and finalisation of a shared work plan in February 2025 and a mid-year review meeting in May 2025 to assess implementation progress. In addition, cross-sector participation is expected to expand in 2025, supported by additional UNAIDS funding for the highly integrated Education Plus Initiative. In the updating of JWPs the RGs also looked at different areas of cross-sector collaborations including on violence (notable GBV), poverty, unemployment, health etc. | completed | December | 2025
3.2 | Use existing coordination mechanisms (e.g., Gender Theme Group, Youth Theme Group, and Social Protection Working Group) to address the intersections between poverty, gender-based violence (GBV), and public health outcomes. | 2025-12-31 | YTG, GTG and Social protection Chairs | During the development of the new CF and through the country analysis the various ytheme groups i.e. Gender Theme Group, Youth Theme Group, and Social Protection Working Group were leveraged to jointly address the intersections between poverty, gender-based violence, and public health outcomes through coordinated planning, information sharing, and aligned programming. | completed | December | 2025
RECOMMENDATIONS TO IMPROVE COHERENCE OF THE NEW COOPERATION FRAMEWORK
Recommendation 4: The joint delivery mechanisms of UN agencies must be strengthened through integrated programming and shared performance indicators.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted, as joint delivery mechanisms among UN agencies are already strengthened through integrated programming and shared performance indicators embedded within the current Cooperation Framework and its monitoring arrangements. At the same time, the UNCT acknowledges the need for further enhancement of these mechanisms and will build on existing practices to strengthen integration and performance measurement in the development of the new Cooperation Framework.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1. | Finalise a unified results framework in UN INFO that reflects collective outcomes and shared indicators across agencies. | 2025-12-31 | M&E Theme Group and Inter_agency group | M&E Theme Group has reviewed and finalised a unified results framework, which informs the UNINFO | completed | December | 2025
4.2. | Conduct joint monitoring and evaluation exercises, including mid-year and annual reviews, to assess integrated delivery and performance. | 2026-03-31 | M&E theme group, result groups |  | delayed | December | 2025
Recommendation 5: The UN must also develop a multi-stakeholder coordination platform that includes local NGOs, grassroots organisations, and the private sector to foster greater co-ownership. Furthermore, the UN must promote policy coherence by aligning UN efforts with South Africa’s multi-sectoral working groups and SDG coordination platforms.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted, as the UN in South Africa already engages a wide range of stakeholders, including local NGOs, grassroots organisations, and private sector actors, through existing multi-stakeholder and government-led coordination mechanisms aligned with national multi-sectoral working groups and SDG coordination platforms. Rather than establishing parallel structures, the UN will continue to tap into and strengthen these existing coordination mechanisms to enhance co-ownership and policy coherence, while exploring opportunities for further improvement where gaps are identified.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1. | Map and Leverage Existing Multi-Stakeholder Platforms Rather than establishing a new platform, the UNCT will identify and strengthen existing national coordination mechanisms that already convene government, civil society, private sector, and development partners | 2025-12-01 | RCO and Technical Steering Committee | The team has identified the IMC- SDGs, SADC-RISDP and Agenda 2063 has a multi-stakeholder platform to engage stakeholders on the Cooperation Framework- 2026-2030 | completed | June | 2025
5.2. | Promote Policy Coherence and Alignment Align UNCT results groups with South Africa’s multi-sectoral working groups (e.g., DPME’s sector clusters on social, economic, and governance priorities). | 2025-12-31 | RCO and RG Chairs | Discussions with government have commenced on aligning RGs to the Clusters | ongoing as expected | December | 2025
5.3. | Use existing sub-national coordination mechanisms, such as Premier’s Offices and Provincial Planning Commissions, to engage NGOs, community structures, and local private sector actors. | 2025-12-31 | RC, UNCT | The UNCT has started with the Eastern Cape Premiers Office by signing a Declaration of Intent and signed an MOU with SALGA | ongoing as expected | December | 2025
RECOMMENDATIONS TO IMPROVE THE EFFECTIVENESS OF THE NEW COOPERATION FRAMEWORK
Recommendation 6: The Government, UN agencies and development partners must invest in data systems and disaggregated reporting, particularly for tracking impacts on marginalized groups and identifying equity gaps. In this regard, it is crucial to prioritise capacity building for national and local institutions to sustain and scale impact beyond the program cycle.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted, as the UN in South Africa, in collaboration with Government and development partners, already supports strengthened data systems and disaggregated reporting to track impacts on marginalized groups and identify equity gaps, with agencies such as UNECA and UNFPA actively supporting these efforts in country. These initiatives include capacity-building for national and local institutions and are embedded within existing programmes and monitoring frameworks; however, the UNCT recognises the need to further enhance and scale these investments to ensure sustainability and impact beyond the current programme cycle.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1. | Build on existing national data platforms such as Statistics South Africa (Stats SA), the Department of Planning, Monitoring and Evaluation (DPME), and the SDG Data Portal to strengthen integrated data collection and reporting aligned with CF indicators | ongoing | UNECA, UNFPA, M&E Theme Group | UNECA and UNFPA are supporting efforts in improving the data systems within Stats SA | ongoing as expected | December | 2025
6.2. | Support capacity development for Stats SA and sector departments to improve administrative data quality, use of geospatial data, and real-time monitoring tools. | ongoing | UNECA, UNFPA regional | UNECA has been providing on-going support to StatSA. UNICEF continues to provide technical support to the Department of Basic Education (DBE) to strengthen its Education Management and Information Systems (EMIS), including data collection, analysis, and quality improvement in partnership with Statistics South Africa under the SASQAF framework. This support is complemented by ongoing stakeholder engagement and advocacy with Stats SA, DBE, and the Department of Planning, Monitoring, and Evaluation. Key 2025 outputs include the publication of finalized 2019–2020 Education Statistics and the 2024–2025 School Realitiesreport, learner ID verification with the Department of Home Affairs, provisional analysis of 2025 key indicators, and the finalization of the DBE Data Management Policy through inclusive consultations. These activities reflect UNICEF’s sustained commitment to strengthening national education data systems to support evidence-based planning and policy. | ongoing as expected | December | 2025
6.3 | Continue strengthening partnerships with academia and think tanks (e.g., HSRC, UNU-WIDER, universities) for research and evaluation to strengthen evidence-based policymaking and equity-focused reporting. | ongoing | UNCT (All agencies) and M&E Theme Group | The UN agencies have been working with academic institutions, the UNCT plans to solidify our work collectively. The UNCT has also included UNU-Wider in the configuration to further cement this activity | ongoing as expected | December | 2025
Recommendation 7: It is also necessary to continue promoting inclusive programming, especially around gender equality, climate resilience, and youth participation to address glaring gaps in these areas
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Inclusive programming on gender equality, climate resilience, and youth participation is core business for the UN in South Africa and has been fully institutionalized through the current Cooperation Framework cycle. These approaches are reinforced by the country analysis and embedded priorities in the Cooperation Framework, ensuring that interventions consistently address gaps in these areas. Across programmes, agencies continue to integrate gender and youth considerations, promote climate-resilient solutions, and engage marginalized groups, reflecting sustained commitment rather than new initiatives.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Leverage established UN coordination structures particularly the Gender and Youth Theme Groups, the Disability inclusion task team, OHCHR to mainstream inclusion and strengthen joint programming across all CF outcomes. | 2025-12-31 | UNWomen, UNFPA, OHCHR leads (UNCT and RCO) | The coordination mechanism mainstreamed all LNOB groups in the development of the Cooperation Framework. | ongoing as expected | December | 2025
1.2 | Work through national and regional platforms already promoting inclusive and sustainable development, including but not limited to : Ministry of Women, Youth and Persons with Disabilities’ National Gender Machinery; Presidential Climate Commission (PCC); National Youth Development Agency (NYDA); and South African National Climate Change Adaptation Strategy mechanisms. | 2025-12-31 | RC, UNCT and RCO | During the development of the Cooperation Framework, consulted the national stakeholders involved in promoting inclusive development. The UN has also been working with these stakeholders in the implementation of programmes | ongoing as expected | December | 2025
Recommendation 8: Furthermore, addressing bottlenecks in delivery by improving resource mobilisation, expanding donor partnerships, and streamlining administrative processes will improve the effectiveness of the next CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | While the recommendation is acknowledged in principle, its full implementation is constrained by the current financing landscape. In the country context, official development assistance (ODA) remains limited and highly competitive, reflecting broader structural funding constraints. Although partnerships and relationship-building are essential and will continue to be pursued, they do not automatically translate into additional or predictable financial resources. As such, progress will depend not only on strengthened engagement with partners but also on the actual availability of funding, which remains outside the direct control of the programme.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1. | Utilise the UNCT’s Operations Management Team (OMT) and Business Operations Strategy (BOS) as platforms for joint operational efficiency reforms, including procurement, HR, ICT, and common services. | 2025-12-31 | UNFPA (as the chair of OMT) | Develop TORs for the OMT Working Groups to sustain the efficiency. | ongoing as expected | December | 2025
8.2. | Strengthen the UNCT Resource Mobilization and Partnerships Group to develop a Joint Financing and Partnership Strategy, focusing on pooled and blended financing mechanisms. | 2025-12-31 | UNODC and OHCHR (Chairs of the Partnership Group) | A draft resource mobilisation strategy has been developed and the discussed with the National Treasury is ongoing UN RM&P group is also engaging the National Treasury & SARS seeking authorisation for UN agencies to issue 18A tax deduction certificates to donors. | ongoing as expected | December | 2025
8.3 | Leverage UN Common Premises initiatives (One UN House) to reduce administrative overheads and enhance joint delivery capacity. | 2025-12-31 | RCO | This is ongoing and the South African government has committed to providing one UN house in 2026 | ongoing as expected | December | 2025
RECOMMENDATIONS TO IMPROVE EFFICIENCY IN THE NEW COOPERATION FRAMEWORK
Recommendation 9: The United Nations in South Africa must finalize and operationalize an Integrated Financing Framework (INFF) that maps domestic, international, public, and private funding sources aligned with SDG outcomes.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Significant elements of the INFF process have already been initiated, including analytical work, stakeholder engagement, and alignment with existing national planning and financing instruments. As such, the recommendation has been partially accepted to allow for refinement that more accurately reflects ongoing efforts, clarifies institutional roles, and recognizes that further operationalization will be contingent on collective system-wide coordination and available capacities.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1. | Undertake a comprehensive financing landscape analysis (covering public budgets, ODA, blended finance, and private investment) to identify entry points for leveraging domestic and international resources for SDG-aligned programmes. | 2025-12-31 | Partnership and resource mobilisation group - UNODC and OHCHR as chairs | A draft RM Strategy has been undertaken and an initial financial landscape analysis has been undertaken | ongoing as expected | December | 2025
| To support the operationalisation of the INFF, the UN will convene a joint UN–Government financing coordination process to finalise the INFF roadmap and translate it into action. This will include consolidating existing analytical work, validating the mapping of domestic, international, public, and private financing sources against national SDG priorities, and identifying a prioritized set of catalytic financing actions | 2026-12-01 | Led by RC and UNDP (support from the UNCT) |  | ongoing as expected | December | 2025
Recommendation 10: The UN must also improve financial planning and forecasting to ensure timely and efficient resource flow to high-impact areas.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UN partially agrees with the recommendation of improving financial planning and forecasting to support timely and efficient allocation of resources to high-impact areas. However, the recommendation is partially accepted as it does not fully reflect measures already in place. The UN has been strengthening financial planning and forecasting through existing system-wide mechanisms, including the OMT, which undertakes coordinated financial forecasting, cash-flow planning, and resource monitoring across agencies.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Strengthen financial forecasting capacity within the RCO and UNCT OMT to consolidate agency-level projections and monitor multi-year funding pipelines. | 2026-12-01 | RCO, UNFPA (as chair of OMT), UNCT |  | ongoing as expected | December | 2025
10.2 | Institutionalise semi-annual resource reviews within the UNCT to identify funding shortfalls and enable early reallocation to underfunded or high-impact areas. | 2026-12-01 | UNFPA (as the chair of OMT), RC, UNCT |  | ongoing as expected | December | 2025
10.3 | Encourage joint programme planning, joint research, shared TORs, integrated training/workshops to reduce duplication and lower transaction costs | 2026-12-01 | RCO and RG chairs |  | ongoing as expected | December | 2025
Recommendation 11: It is also imperative that the organisation expands the use of joint resource mobilization and pooled funding mechanisms to reduce fragmentation and improve cost-efficiency.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UN agrees with the intent of expanding joint resource mobilisation and pooled funding mechanisms to reduce fragmentation and improve cost-efficiency. However, the recommendation is partially accepted as it does not fully reflect ongoing practice under the current Cooperation Framework cycle. The UN has been actively utilising joint funding instruments throughout the CF cycle, including the SDG Fund and the Multi-Partner Trust Fund (MPTF), to support integrated programming, promote coherence across agencies, and channel resources to shared priorities.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
11.1 | Use existing pooled mechanisms such as the UN Multi-Partner Trust Fund (MPTF) platform and Joint SDG Fund to manage collective financing and reporting transparently. | 2026-12-01 | RCO, Partnerships and resource mobilisation , economist |  | ongoing as expected | December | 2025
11.2 | Encourage joint proposal development for multi-agency programmes to attract larger and more strategic funding opportunities from bilateral donors and international financial institutions. | 2026-03-01 | RCO, Partnerships and resource mobilisation and Result Groups | During the development of the JWPs, the RGs have been encouraged to identify flagship programmes and to resource mobilise around these | ongoing as expected | December | 2025
11.3 | Document and share lessons from joint resource mobilisation efforts (e.g., UN-EU partnerships, SDG Fund projects) to inform continuous improvement and replication. | 2026-12-01 | Partnership and resource mobilisation group - UNODC and OHCHR as chairs and UNCG |  | delayed | December | 2025
RECOMMENDATIONS TO IMPROVE COORDINATION OF THE COOPERATION FRAMEWORK
Recommendation 12: UN agencies must ensure that agency work plans are systematically aligned to the CF results matrix, with joint indicators and outcomes across thematic areas and 2. It is also necessary to institutionalize joint work planning and annual reviews to maintain alignment and adaptive management
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The recommendation is partially accepted as it does not fully reflect current practices already in place. Under the existing CF cycle, UN agencies align their work plans to CF outcomes through the several mechanisms which include directly deriving agency specific plans from the CF, via the UNCT coordination mechanisms, joint results groups, and annual CF reviews, which support coherence, collective accountability, and adaptive management. Joint indicators and cross-thematic outcomes have already been incorporated where feasible, taking into account agency mandates and comparative advantages. Further institutionalization of joint planning and review processes will therefore build on these established mechanisms, rather than introducing new parallel requirements, and will remain subject to agency-specific planning cycles and corporate requirements.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
12.1 | Require co-signature of joint outputs and outcomes in the CF Results Framework, ensuring shared accountability across agencies contributing to the same results. | 2025-12-01 | Result group Chairs (support from M&E Theme Group) | The UNCT signed off the outcome level indicators | ongoing as expected | December | 2025
12.2 | Institutionalise performance reporting through UN INFO, linking data directly to Cooperation Framework indicators. | 2026-03-01 | Result and M&E group focal points | Training are being planned for all RGs once the JWPs have been developed | ongoing as expected | December | 2025
12.3 | Convene an annual UNCT Results Forum, chaired by the Resident Coordinator, to review progress across pillars, address delivery bottlenecks, and document joint lessons learned. | 2025-12-01 | RCO (Result and ME Group) | This will be done annually and has been done for 2025 | ongoing as expected | December | 2025
Recommendation 13: The RCO must be further capacitated to function as a coordination hub, including resourcing for M&E, partnerships, and knowledge sharing
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The recommendation is partially accepted as it should not be interpreted solely as a call for additional staffing. RCO coordination effectiveness depends as much on active participation and collaboration from UN agencies through timely data provision, reporting, UN INFO updates, and engagement in joint planning as it does on RCO resources. In addition, the political and institutional context requires careful balance, as agencies may be cautious about any perception that the RCO is “becoming an agency” itself. Future efforts to strengthen the RCO will therefore focus on enhancing coordination mechanisms, knowledge management, and system-wide participation, alongside targeted capacity support, rather than relying solely on increases in staff or resources.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
13.1 | Enhance technical capacity within the RCO by providing capacity building for M&E, partnerships, and knowledge management | 2027-12-01 | RC and UNCT | This is an ongoing activity, with support from DCO, the staff continues to participate in capacity building courses and trainings | ongoing as expected | December | 2025
13.2 | Leverage the existing groups such as the M&E Group and the Partnerships & Resource Mobilization Group to ensure systematic coordination across agencies on evidence generation and joint advocacy. | 2027-12-01 | Partnerships and M&E Chairs and RCO | This is an ongoing activity | ongoing as expected | December | 2025
Recommendation 14: Coordination gaps must be addressed through standardized templates and timelines for UNCT members’ program planning and reporting.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The recommendation is partially accepted, as it does not fully reflect current practices under the CF cycle. The UNCT already uses standardised templates and agreed-upon reporting schedules, along with joint work planning exercises and mechanisms for aligning agency plans and submissions. While these tools provide a strong foundation for coordination, their effectiveness depends on active engagement from all UNCT members, timely data provision, and adherence to shared processes. Future efforts will focus on further optimising and reinforcing these existing templates and processes to improve consistency, clarity, and alignment, rather than introducing entirely new systems, while remaining sensitive to agency-specific planning requirements and capacities.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
14.1 | Continue the roll out standardised joint planning and reporting templates for Results Groups, Outcome Teams, and Thematic Working Groups, ensuring consistency in inputs, indicators, and timelines. | 2025-12-01 | RCO (M&E Group) | standardised joint planning and reporting templates for Results Groups are implemented | ongoing as expected | December | 2025
14.2 | Synchronize agency-level planning cycles with the CF annual review and reporting calendar, using a UNCT coordination timeline endorsed by all Heads of Agencies. | 2026-12-01 | Result and M&E group focal points |  | ongoing as expected | December | 2025
14.3 | Institutionalise accountability for coordination compliance by including planning and reporting deliverables in Results Group co-chairs’ TORs and UNCT performance compacts. | 2026-12-01 | RCO and RG Chairs |  | ongoing as expected | December | 2025
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE (ORIENTATION TO IMPACT)
Recommendation 15: The CF must strengthen the impact measurement framework, including outcome-level indicators and disaggregated data collection for marginalized populations.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UNCT has integrated outcome-level indicators into the CF results matrix and is systematically collecting disaggregated data where feasible to inform monitoring, reporting, and adaptive management. While further enhancements are possible, the effectiveness of the impact measurement framework depends on timely and accurate data submission from all UN agencies, as well as alignment with national statistical systems and capacities. Future efforts will therefore focus on refining existing indicators, strengthening disaggregated data collection, and enhancing reporting mechanisms to improve evidence-based decision-making, rather than creating an entirely new framework
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
15.1 | Build partner capacity (especially subnational institutions) in results-based management (RBM) and data use for evidence-informed decision-making. | 2026-12-01 | M&E Ttheme group and result groups |  | ongoing as expected | December | 2025
15.2 | Promote joint evaluations and impact assessments with government and academic partners to ensure credibility and sustainability of measurement systems. | 2026-12-01 | M&E Ttheme group and result groups |  | ongoing as expected | December | 2025
Recommendation 16: It must expand support to climate-smart interventions and integrate environmental sustainability into all programme areas.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | Integration of climate-smart approaches and environmental sustainability is already underway for example, through the Joint Energy Transition framing and will continue to be prioritized in the new CF cycle. While policy alignment has been achieved, the main gap lies in joint implementation across agencies rather than in strategy alone. Cross-cutting areas, such as digitisation, have also been identified as requiring coordinated thematic discussion and a plan that moves beyond information-sharing toward joint programming. Future efforts will therefore focus on building system-wide approaches, strengthening joint implementation, and embedding climate-smart and sustainability considerations into programmatic and operational planning across all CF outcomes.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
16.1 | Continue mainstreaming climate and environmental considerations into all programme design templates and Joint Work Plans, using Result Group 3: Environmental Resilience to provide technical oversight | 2026-12-01 | Chairs of Strategic Pillar 3: Outcome 5 |  | ongoing as expected | December | 2025
Recommendation 17: Also important is the promotion of transformative approaches that shift systems (e.g., health, education, economic inclusion) rather than isolated service delivery
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The recommendation is partially accepted, as it does not fully reflect current efforts under the Cooperation Framework cycle. System-level approaches have already been integrated into the CF through initiatives that emphasize policy coherence, capacity strengthening, and cross-sectoral collaboration. While progress has been made in shifting towards systems-level impact, the remaining challenge lies in ensuring consistent joint implementation across agencies, rather than in strategy or policy alignment alone. Future efforts will therefore focus on reinforcing joint programming, scaling system-wide interventions, and embedding transformative approaches across thematic areas to ensure sustainable, long-term impact beyond individual projects.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
17.1 | Adopt a systems-thinking lens in Cooperation Framework design, identifying interdependencies between governance, social protection, health, education, and economic inclusion. | 2025-06-01 | RCO, UNCT | The Country Analysis which used the systems-thinking lens was used in the design of the new Cooperation Framework. This was in an attempt to ensure that the interdependencies are identified. This is also clearly articulated in the ToC | completed | December | 2025
17.2 | Support sector reforms and institutional strengthening rather than short-term service delivery e.g., improving regulatory frameworks, financing mechanisms, and accountability systems. | 2026-12-01 | PMT, RGs, RCO (HOO, Economist and Partnerships) |  | delayed | December | 2025
17.3 | Encourage multi-sectoral programmes that integrate innovation, digital transformation, and inclusive growth (e.g., green jobs, digital skills, and equitable education access). | 2026-12-01 | ITU, UNDO, UNEP, ILO, UNICEF, UNESCO | There are some initiative with government which are currently jointly implemented which adopt transformative, systems-oriented approaches. An example is the through the AI-based measurement tool for the General Education Certificate. The tool assesses a broad range of competencies, including transferable skills, life skills, and soft skills, enabling a more holistic evaluation of learners’ capabilities beyond academic performance at Grade 9. This initiative directly supports the Government’s Three-Stream Model i.e. Academic, Vocational, and Occupational by strengthening system-level assessment and expanding future pathways for learners, rather than focusing on isolated service delivery. This ultimately aims to improve educational outcomes in the country. In 2025, UNICEF continued to support two online education platforms, Junior Tukkies and Siyavula, which are owned by the Department of Basic Education. As a result, they reached a total of 3,502,049 learners. | ongoing as expected | December | 2025
Recommendation 18: The CF must establish stronger feedback loops from beneficiaries and local actors to inform adaptive strategies and real-time improvements.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | This recommendation is partially accepted as it does not fully reflect existing approaches through which feedback is already being integrated, particularly within an increasingly upstream, advisory model of engagement. While much of the UN’s support focuses on upstream policy and systems strengthening, these efforts are informed by lived realities and community knowledge through ongoing consultations, stakeholder engagement, and partnerships with civil society and local actors. The key gap is therefore not the absence of feedback mechanisms, but the need to further strengthen, systematize, and harmonize their use across thematic areas. Future efforts will focus on consolidating existing feedback channels, improving their consistency and use in decision-making, and ensuring that insights from communities and local stakeholders more systematically inform adaptive management and programme adjustments.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
18.1 | Institutionalize participatory monitoring mechanisms, allowing communities and local partners to provide regular input on programme effectiveness. | 2026-12-01 | M&E Group and Result and Theme Groups |  | delayed | December | 2025
18.2 | Collaborate with civil society and local authorities to co-facilitate inclusive review sessions and “learning dialogues.” | 2026-12-01 | UNCG, M&E Group and Result Groups |  | delayed | December | 2025
RECOMMENDATIONS TO IMPROVE SUPPORT FOR THE SUSTAINABILITY OF COOPERATION FRAMEWORK INTERVENTIONS
Recommendation 19: Going forward, there should be greater investment in capacity building of local institutions, including data systems, to maintain momentum post-2025.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
19.1 | Support sector departments and municipalities through targeted technical assistance, focusing on data management, monitoring, and evaluation aligned with SDG targets. | 2025-12-01 | UNDP and UNODC as Chairs of the Building a capable state supported by M&E Group |  | ongoing as expected | December | 2025
19.2 | Collaborate with Stats SA and DPME to institutionalize local data collection systems and evidence-based planning processes. | 2025-12-01 | M&E Group and the Economist Group |  | ongoing as expected | December | 2025
19.3 | Utilise UN Volunteers (UNV) and South–South Cooperation mechanisms to transfer skills, promote peer learning, and sustain institutional memory. | 2025-12-01 | UNV and UNCT (all agencies) |  | ongoing as expected | December | 2025
Recommendation 20: Strengthening national ownership by embedding UNSDCF strategies into sector-specific government plans and budgets is necessary to ensure continuity.
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: …… |  | Under the current Cooperation Framework , UN support is already closely aligned with national development priorities, with CF outcomes integrated into sectoral strategies, policy frameworks, and planning processes through sustained engagement with line ministries and central government institutions. While opportunities remain to deepen this alignment, particularly in budgetary integration, the primary challenge lies not in strategic alignment but in the pace and scope of sector-specific planning and budget cycles, which are led by government processes. Future efforts will therefore focus on reinforcing existing embedding practices, strengthening policy–budget linkages where feasible, and supporting government-led planning and financing processes to further enhance national ownership and continuity.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
20.1 | Align new CF outcomes and outputs with national and sectoral plans, including the MTDP and departmental implementation strategies. | 2026-12-01 | Inter-Agency team (RC and UNCT) | During the development of the new Cooperation Framework, the Inter-agency team used the CA, outcomes and outputs of the MTDP and other instruments to ensure alignment to the country's priorities | ongoing as expected | December | 2025
20.2 | Promote policy dialogues and capacity exchanges to institutionalise UN-supported models within government delivery systems. | 2025-12-01 | RC and UNCT (also through RGs) | During the consultations with government, this was highlighted and will continue to be a key outcome during the implementation of the new CF | ongoing as expected | December | 2025
Recommendation 21: For progress towards the SDGs to be maintained, there should be a continuous facilitation of multi-stakeholder platforms for continuous dialogue, accountability, and knowledge transfer between the UN, Government of South Africa, civil society, and the private sector.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UN is already supporting and participating in a range of multi-stakeholder platforms and dialogue processes that facilitate collaboration, policy engagement, and knowledge transfer across sectors. These platforms are embedded within existing national coordination structures and thematic forums and are aligned with Cooperation Framework priorities. While there is scope to strengthen coherence, follow-up, and accountability across these platforms, the gap lies not in their existence but in ensuring their sustained use, effective linkage to decision-making processes, and integration across thematic areas. Future efforts will therefore focus on reinforcing and better connecting existing platforms, rather than establishing parallel structures, while remaining responsive to stakeholder capacities and resource
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
21.1 | Encourage peer learning and knowledge exchange, documenting best practices and lessons for dissemination across sectors. | 2026-12-01 | UNCG, M&E Group and Result Groups |  | ongoing as expected | December | 2025
22.2 | Institutionalize accountability mechanisms by producing annual joint progress reports co-signed by the UN and Government through existing platforms such as the IMC for SDGs, SADC and Agenda 2063 | 2026-12-01 | RC and UNCT |  | ongoing as expected | December | 2025
Recommendation 22: The next CF should also more emphatically promote climate resilience and environmental stewardship as integral to sustainable development by embedding green transition strategies across sectors.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Climate resilience and environmental sustainability are already embedded across multiple CF outcomes through cross-sectoral approaches, including support for just and green transition initiatives, climate-informed planning, and resilience-building interventions. While there is strong policy alignment, the key opportunity moving forward lies in further strengthening joint implementation and ensuring coherence across sectors, rather than introducing entirely new strategic directions. The next CF will therefore build on existing foundations by reinforcing green transition strategies across sectors, deepening systems-level approaches, and enhancing coordinated delivery in line with national priorities and capacities.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
23.1 | Ensure that the Cooperation Framework for the next cycle (2026-2030) promotes climate resilience and environmental stewardship as a key accelerator of the SDGs | 2025-12-01 | UNEP, UNDP, UNIDO, FAO,UNWOMEN, RCO | The new CF incorporates this and also has a strategic pillar dedicated to climate resilience and environmental stewardship | completed | December | 2025
23.2 | Promote green skills development, sustainable finance, and circular economy initiatives to drive a just and inclusive green transition. | 2026-12-01 | Strategic Pillar 1 and 3 Result Groups (Chairs) |  | ongoing as expected | December | 2025
23.3 | Encourage cross-sectoral collaboration between agencies (UNDP, UNEP, UNIDO, FAO) to implement integrated climate-smart interventions at scale. | 2026-12-01 | RCO |  | ongoing as expected | December | 2025
Recommendation 23: Furthermore, the next CF should have comprehensively developed Sustainability and Exit Strategy that outlines the transition of key programs to national leadership, which includes financing plans, and promotes long-term impact ownership by national stakeholders.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Sustainability, national ownership, and transition planning are already integrated across CF outcomes through capacity development, policy alignment, and government-led implementation approaches. While these elements may not be consolidated into a single, standalone exit strategy, they are reflected within sectoral strategies, programme design, and engagement with national counterparts. The key opportunity moving forward is therefore to better articulate and systematise these existing sustainability and transition measures rather than introduce an entirely new framework taking into account sector-specific contexts, varying capacities, and the realities of financing predictability. The next CF will build on these foundations to further strengthen national leadership and long-term impact ownership.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
24.1 | Integrate a dedicated Sustainability and Exit Strategy into the new CF, outlining transition plans, resource sustainability, and institutional handover mechanisms. | 2025-12-01 | PMT | Issues of how sustainability will be maintained are mainstreamed into the new CF | completed | December | 2025
24.2 | Develop joint transition roadmaps in collaboration with DPME and sector ministries to ensure smooth handover of successful interventions. | 2026-12-01 | RC and UNCT |  | ongoing as expected | December | 2025
**In total, 28 recommendations were identified; however, many were repeated across multiple evaluation criteria, particularly those related to coordination, and to avoid duplication and ensure clarity, overlapping recommendations were consolidated and not restated.

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030