## Sheet1
UNDAF Evaluation Management Response Action Plan |  |  |  | COMPLETION STATUS
[6 empty] | Plan Duration |  |  |  | Actual Start |  |  |  | % Complete |  |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
AREAS | RECOMMENDED ACTIVITIES FOR THE UNCT | COMMENTS (BASED ON THE UNSDCF DRAFT) | RESPONSIBLE | PERCENT COMPLETE | 2021 | [10 empty] | 2022
[5 empty] | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | OCT | NOV | DEC
Relevance | 1. Review government reassessed priorities through consultation of ongoing review mechanisms and address new needs, namely to allow flexibility in contexts of emergencies. | The CF formulation process was conducted in consultation with the Government and CSOs and aligned to the governments annual plans (PQG 2020-2024), policies and strategies (ENDE 2015-2035). | UNCT/PMT | bar: 2021 JUL to 2021 NOV
| 2. Build from programmes with good results and where the UN brings added-value. | The UNCT configuration process took into consideration the UN added-value and how non resident agencies (ITC, UNCTAD, UNEP, UNECA) can also contribute to the CF. | UNCT | bar: 2021 AUG to 2021 DEC
|  | Two new agencies became part of the Mozambican UNCT: UNOPS and UNECA. | UNCT | bar: 2021 AUG to 2021 DEC
| 3. The UNSDCF needs to make the SDGs more evident and at the same time concentrate the Outcomes in fewer areas. | Only 1 outcome was identified for each of the 4 SP areas. The outcomes were specifically designed to be cross-sectoral to create synergies between the SDGs targets. | SP Leads/RCO | bar: 2021 DEC to 2022 DEC
Effectiveness | 4. Until the end of the current UNDAF, the UNCT will have to monitor and closely follow-up the results still to be achieved. |  | UNCT/RCO
| 5. To allow increased and improved flexibility, the UNSDCF will have to anticipate the main risks and trends at the economic and political levels. | The UNSDCF design brings programmatic flexibility to respond to risks and crisis and the RC in coordination with the UNCT conduct programme criticality assessments (PCA). The last PCA was conducted in June 2021. | RCO | bar: 2021 AUG to 2021 DEC
Efficiency | 6. Here too, the next UNSDCF will have to be more flexible to absorb (foreseen) new changes in the context of Mozambique. | The 4 pillars identified are very aligned with the forseaable environmental, socio-economic and political changes and challenges in the Mozambican context namely, human development, economic diversification, climate resilience and sustainable use of natural resources, and peacebuilding and human rights. | SP Leads/RCO | bar: 2021 JUL to 2021 NOV
| 7. The joint work of the UNCT requires improvements in systems and procedures, as well as in terms of the human resources available. | On an annual or bi-annual basis, all agencies involved in each of the SP areas are to prepare joint workplans in coordination with partners and in consideration with the CF outcomes, outputs, targets and indicators. | SP Leads | bar: 2022 NOV to 2022 DEC
Impact | 8. The combination of emergency work with a continued focus on UN’s strategic areas is desired and should be pursued. |  | UNCT | bar: 2021 DEC to 2022 DEC
Sustainability | 9. The UN needs to strategize sustainability more clearly in the next UNSDCF. | The CF 2022-2026 includes sustainability in its Strategic Priority 3: "Climate resilience and sustainable use of natural resources" | UNCT | bar: 2021 JUN to 2021 OCT
Coordination | 10. The preparation of the new UNSDCF should take momentum from the good practices developed for emergency work. |  | UNCT/RCO | bar: 2021 JUN to 2021 DEC
Coherence | 11. Agency and joint participation in multi-stakeholders thematic and task groups should continue, as well as more collaboration with government. | The Indicators were chosen taking into consideration the National indicators (Including the countries SDG Indicator Framework) and available data. | SP Leads | bar: 2021 JUL to 2021 DEC
|  | Each SP was co-chaired by the UN and Government Counterparts. | SP Leads | bar: 2021 DEC