## Sheet1
China; CF 2021 - 2025 EVALUATION MANAGEMENT RESPONSE | [7 empty] | Comments
Evaluation Title/Year: China Sustainable Development Cooperation Framework 2021-2025, External Evaluation Report/ April 2025 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RCO and Programme, Monitoring and Evaluation Group • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: The UNCT needs to clearly identify a purpose for the CF over and above providing directional alignment for UN programmes. The CF should articulate a clear vision for the UN system in China over the next five years structured around 2-3 key messages and building on core UN principles such as Leave No One Behind
Management response - Accepted/Partially Accepted/rejected: Accepted. The CF is a strategic document that provides high level structure for UN Programming. It is designed to incentivize and promote inter-agency collaboration and is now more streamlined in nature with 3 strategic priorities and 4 outcomes statements that articule a vision for the UN in China over the next five years.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Develop a strategic CF that is more streamlined in nature that promotes increased opportunities for inter-agency collaboration | 31/5/2025 | RCO | CF finalized and signed by GOC and UNCT | completed | June | 2025
Recommendation 2: For the CF to be the embodiment of the value-added of the UN system in China, there must be a stronger focus on common results where the UN comes together around a clearly defined theory of change using a variety of joint programming modalities (alongside the bilateral work of agencies).
Management response - Accepted/Partially Accepted/rejected: Accepted. gestions for Management Response: Accepted. The UNCT agrees that the Cooperation Framework must serve as the primary vehicle for demonstrating the value-add of the UN system in China, particularly by articulating common results under a shared theory of change. The UNCT is committed to strengthening the use of coordination bodies (e.g., Results Groups and Thematic Working Groups) to jointly identify priorities, design interventions, and track collective progress. While joint programming is constrained by limited availability of pooled or joint funding, the UNCT will continue to seek opportunities for joint resource mobilization, co-financing arrangements, and innovative partnerships that can support joint initiatives.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Interagency coordination mechanisms will be established in line with new guidelines from Sistem Wide Evaluation that focus on joint work and where agencies can come together, and this will also be reflected in new joint work lans that focus on inter-agency work, collaboration and joint initiatives. | 31/12/2025 | RCO/RG Co-Chairs |  | ongoing as expected
2.2 | Draft a guidance note for the inter-agency group outlining the different ways in which agencies can come together: joint initaitives, joint advocacy, joint research, light programming or parallel programming, etc. to expand opportunities beyond only the pooled funding mechanism. | 31/12/2025 | RCO/RG Co-Chairs |  | ongoing as expected
2.3 | Develop a partnership/resource mobilization strategy for the new CF that can support these joint initiatives by proposing a structured manner to engage with donors, private sector, foundations and other partners. | 31/12/2025 | RCO/RG Co-Chairs |  | ongoing as expected
Recommendation 3: Consideration should be given to explicitly adopting the "For China", "With China" and "From China" taxonomy as the key organizing principle for the CF to better capture the evolving relationship between the UN system and China. • At a minimum, the new CF should devote a section to discussing the different modalities being used by the UN in China and the gradual shift in focus that this represents
Management response - Accepted/Partially Accepted/rejected: Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Review this new taxonomy to explore its possible incorporation into CF. | 31/5/2025 | RCO | Taxonomy is implicitly incorporated into finalized CF, although the percise language proposed by the evaluator is not referenced in the CF. | completed | June | 2025
3.2 | Given China's move towards High Income Status and the impact this will have on the type of physical presence some agencies may shift towards, the impact of this shift will be explored and a UN in China strategy will be developed to focus on upstream and partnership work in the context of agencies' particular business models. | 31/12/2025 | RCO and RG and TG Co-Chairs |  | ongoing as expected
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: The UN Communications Group should be tasked with developing a clear forward looking strategy to raise awareness about the CF and its key priorities. • It is critical to ensure that there is a Chinese translation of the CF to facilitate increased advocacy around the CF. • HOAs should commit to highlighting the CF priorities and core messages in all communications with external partners.
Management response - Accepted/Partially Accepted/rejected: Accepted. The UNCG will develop a strategy document and a Translation of the CF will be prepared.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCG Co-Chairs
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Finalize Chinese Translation of CF | 31/12/2025 | RCO |  | ongoing as expected
4.2 | Development of a strategic communications strategy to raise awareness of the new CF and its priorities. | 31/12/2025 | UNCG co-chairs |  | ongoing as expected
4.2 | Develop standardized TPs of CF priorities and core messages to support common messaging among UNCT members | 31/12/2025 | RCO and UNCG co-chairs |  | ongoing as expected
Recommendation 5: The UN in China should develop clear and transparent standards and criteria for SSTC engagement in the new CF that would provide structure against which to measure progress.
Management response - Accepted/Partially Accepted/rejected: Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | It is difficult to develop measurable criteria against which to measure the SSTC engagement given that this work is mainly upstream policy work and does not have an easy way to quantify progress. That being said, it is acknowledged that it is important to harmonize the SSTC engagement and the new CF includes one outcome indicator against which to measure progress and output indicators will be developed by the Results Groups during the second half of 2025.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO and Partnership RG Co-Chairs
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Organize a discussion with Chinese counterparts to continue work of identfying additional metrics against which to measure progress. | 31/12/2025 | Partnership RG Co-Chairs |  | ongoing as expected
5.2 | Ouput indicators developed/identified to measure UNCT work on SSTC engagement | 31/12/2025 | Partnership RG Co-Chairs |  | ongoing as expected
Recommendation 6: Consideration should be given to structuring each pillar around service lines - policy support, capacity development and advocacy and social mobilization - and thereby embed HRBA principles into the CF and better demonstrate the collective value-added of the UN system. • The UN should highlight the impact of UN interventions on men and women and on particular vulnerable groups through dedicated CF outputs (alongside the use of sex disaggregated data). • The UN should split the Prosperity and People Priority Area into stand-alone pillars. This will allow the agencies to better explore the synergies between Outcome 1 and Outcome 3 especially in relation to rural revitalization and agricultural transformation.
Management response - Accepted/Partially Accepted/rejected: Partially accepted. The UNCT gave due consideration to structuring each Strategic Priority Area/Outcome around service lines as suggested by the evaluation. However, gived the results-based management approach of the CF, it was not possible to develop outputs that followed this taxonomy. Nevertheless, the CF includes a chapeau highlighting the emphasis on the principle of leaving no one behind, focusing on vulnerable groups such as persons with disabilities, older persons, children, etc. along with one dedicated output focused on gender (output 1.5) and 2 outcomes that include explicit reference to gender in the outcome statements. There are two distinct Outcome Areas: one focused on social development and another on economic development (people and prosperity), as recommended, although these fall under 1 strategic priority of "People and Prosperity" based on government feedback. Reporting on the CF, via the Annual Report, will explore using this taxonomy to present the work of the UN in China.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | New CF to include focus on gender via at least one dedicated output. | 31/5/2025 | RCO |  | completed | June | 2025
6.2 | CF to split People and Prosperity into two outcome areas; will retaining an overarching pillar that includes both outcome areas. | 31/5/2025 | RCO |  | completed | June | 2025
6.3 | The Annual Results Report will focus on demonstrating the collective value-added of the UN System in China by exploring different structures to accomplish this objective. | 31/12/2025 | RCO/M&E Group |  | ongoing as expected
Recommendation 7: The UN should actively explore holding joint planning meetings with key window ministries and departments such as NHC, MEE and MARA who all currently work (bilaterally) with multiple UN agencies and work towards the development of joint work plans and reporting structures. • The UN should include process indicators in the Annual Report to better capture the extent to which the UN has been able to work more cohesively over the life of the new CF.
Management response - Accepted/Partially Accepted/rejected: Accepted. As deemed appropriate by the respective UN entities, the UN in China will explore holding joint planning meetings with key window ministries in areas in which multiple agencies are working on similar areas.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by M&E Group Co-Chairs
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | RGs will contact relevant Government Ministries to explore the idea of holding joint meetings to discuss programme planning and implementation. | 31/12/2025 | RG Co-Chairs |  | ongoing as expected
7.2 | Results groups will explore and seek to identify process (output) indicators that can assess the extent to which enhanced coordination and inter-agency implementation is taking place, including by reviewing the list of UNSDG Indicators to see which could be applied to monitor progress on the new CF. | 31/12/2025 | RG Co-Chairs and M&E Group Co-Chairs |  | ongoing as expected
Recommendation 8: The UN should consider identifying one of the 11 GOC designated SDG zones where UN agencies would commit to working more colalboratively (potentially around issue of LNOB).
Management response - Accepted/Partially Accepted/rejected: Accepted. The UN in China was invited by the Ministry of Foreign Affairs to visit Pengshui County, Chongqing, a former poverty-stricken county, and has organized scoping missions and plans to pursue an area-based programme in the County. While Pengshui is not one of the 11 GOC designated SDG zones, this collaboration can serve as a pilot to promote the UN in China delivering as one over the course of the new CF.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s)
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Development of a programme strategy for the UN's activities in Pengshui County | 30/4/2025 | RCO |  | completed | June | 2025
8.2 | Implementation of activities as part of the joint programme in Pengshui county commences and updates to programme and review of progress take place | 31/12/2025 | RCO | Monitoring done at end of each calendar year. | ongoing as expected
8.3 | UNCT Members will actively explore opportunities to come together by using the 11 GOC designated SDG zones as a catalyst to develop joint activities, initiatives and interventions, using the recently developed joint UNDP, UNFPA, UNICEF programme for Gonghe County in Qinghai (one of the 11 GOC SDG Zones), as a pilot for future implementation in other areas. | 31/12/2025 | RG Co-Chairs, UNCT, RCO | Monitoring done on biannual basis | ongoing as expected
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 9: The RCO should take the lead of developing knowledge products on positioning the UN in China in the post 2030 era. This could include the financial implications of China graduating to High Income status and collective resource mobilization strategies and programmatic modalities.
Management response - Accepted/Partially Accepted/rejected: Accepted, an UN in China Analytical Group will be created, chaired by the RCO Economist, to prepare inter-agency knowledge and analytical products on key issues for the final 5 years of SDG implementation (aligning with the new CF cycle), with a look towards to post-2030 era as well.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | TORs and membership of a UN in China Analytical Group are developed and approved by UNCT | 30/9/2025 | RCO |  | ongoing as expected
9.2 | Knowledge products on key UN and SDG topics are regularly prepared and disseminated, both in the UNCT and through regional and global networks, including the preparation of the impact of China's graduation to HIC status and how the UN can be fit for purpose in the post-2030 area. | 31/12/2025 | RCO |  | ongoing as expected
Recommendation 10: The RCO and RGs must improve the use of UNINFO as a means of strengthening coordination, increasing transparency and robuse results oriented reporting. • The RGs (agencies) must provide current and accurate programme data and work with the RCO to streamline reporting including harmonisation of timelines and templates to minimize the reporting burden on agencies (potentially through the use of AI). • The RCO and RGs need to able to produce much more detailed who, where and what infographics about the UN’s work in China. • Pilot projects need to be linked more directly to policy impact and scaling up and should be tracked as part of the CF indicator framework. • UNCT Reports should be cumulative to better capture progress over time rather than the annual reporting that only presents a partial picture of UN achievements.
Management response - Accepted/Partially Accepted/rejected: Accepted. RCO will work with M&E Group and UN agencies to expand the use of UNINFO with more and better data included in UNINFO.
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO and M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Taking into account the recommendations of the System Wide Evaluation and the Management Response, a strategy document will be developed to improve the comprehensiveness of programme data reported into the system. | 31/12/2025 | RCO, M&E Group | Pilot with UNDP ongoing | ongoing as expected
10.2 | RCO will work with RGs and M&E Group to identify innovative ways to creatively and clearly present the work and accomplishments of the UN in China and its accomplishments that would be reflected in the annual results report. | 31/12/2025 | RCO, M&E Group |  | ongoing as expected
10.3 | RCO and M&E Group will develop a strategy to incorporate multiyear accomplishments into annual results report so that each report in the CF cycle builds on the previous one to the extent possible. | 31/12/2025 | RCO, M&E Group | First reporting in 2026 than annually update | ongoing as expected

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030