Roadmap

Common Country Analysis 2025

Yemen

| Time/Stage | Milestone | Objectives/Outputs/Actions | Responsible Agency | Progress | Notes |
| --- | --- | --- | --- | --- | --- |
| April – May 15 CCA Preparatory Stage | CCA Group and Roadmap | Establish a dedicated CCA Task Team. Approve the CCA Roadmap. Collect a repository of reports and documentation from agencies for the desk review. Decision on dates for the focus and reference groups & decision on leading agencies Output: CCA Group Output: CCA Roadmap developed | PMT and RCO | The CCA structure and approach options have been approved by UNCT. PMT/UNCT to nominate their focal points for the CCA Task Team. CCA Task Team to gather a repository of all analytical documents, reports, data and relevant information which will be used for the desk review. |  |
| June – July Focus & Reference groups | Organization of focus and reference groups Desk review and outline of the CCA completed | RCO to provide terms of reference for the focus and reference groups including guiding questions. Inputs to the CCA stemming from the focus and reference groups discussions Output: Advanced outline of the CCA document | CCA Task Team / RCO |  |  |
| August Data collection | Foresight analysis | One day workshop on foresight analysis for the CCA Task Team Completion of the foresight analysis based on the agreed methodology | CCA Task Team / RCO / DCO HQ / PSG |  |  |
| August 20 – September 30 First draft of the CCA | CCA first draft | First draft of the CCA completed and circulated to the PMT for inputs (timeframe 2 working weeks). | CCA Task Team / PMT / RCO (penholder) |  |  |
| October 1 Review of the CCA first draft | CCA Advanced draft presented and circulated to the UNCT | Completion of inputs from the PMT and last round of comments from the UNCT | CCA Task Team / PMT / UNCT |  |  |
| 30 October Final CCA document | CCA document finalised and sent for review to Peers Support Group | RC and UNCT decision on the publication and presentation of the CCA | CCA Task Team / RCO / DCO RO |  |  |

To note:

- Because of the unique operating context of Yemen, DCO Headquarters (Programme and Policy Branch i.e. Helene Fraiser and Jorg Schiemel) need to be involved at all times to provide correct language in line with the HQ guidance.

- OSESGY/UNMHA to be involved in contributing to the conflict analysis and the foresight element.