## Sheet1
THAILAND; CF 2022 - 2026 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Mid-Term Evaluation of the United Nations Sustainable Development Cooperation Framework (UNSDCF) Thailand 2022–2026 / 2026 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: RCO • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
1. Next CF should strengthen UN strategic positioning and relevance in Thailand: 1.1 Consider aligning more clearly the next CF results not only to the NESDP but also to other relevant plans (including the NSPP). 1.2 Prioritize strategic issues like ageing, AI, and OECD accession-related reforms, as well as support towards the fulfilment of international commitments. 1.3 Link UN support to Thailand’s regional leadership and global commitments (e.g., ASEAN, UN Human Rights Council, etc.). 1.4 Include in the CF adequate analysis of cross-border challenges and how the UN can contribute (leveraging also UN regional or multi-country offices based in Thailand).
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted | 1.1 Partially Accepted 1.2 Accepted 1.3 Accepted 1.4 Accepted
If rejected or partially accepted, please provide an explanation: …… |  | 1.1 The UNCT partially accepts this recommendation. The CF is aligned with the 14th NESDP, which serves as the overarching national sustainable development framework. Oversight is ensured through the TSC, co-chaired by MFA and NESDC, reflecting the agreed government structure with NESDC as steward of the NESDP and thereby ensuring alignment with national priorities. Reference can be made to other, aligned strategies and policies, including those under the umbrella of the NESDP, in the Outcome Groups’ work. However, maintaining the current governance arrangements is essential, as they reflect government-endorsed structures. Introducing additional alignment at the governance level would fall outside the scope of the process agreed with government, require new negotiations for limited added value, and risk disrupting the clarity of oversight and accountability.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Consider aligning more clearly the next CF results not only to the NESDP but also to other relevant plans (including the NSPP). | Short | UNCT / TSC | The CF is aligned with the 14th NESDP, which serves as the overarching national sustainable development framework. Oversight is ensured through the TSC, co-chaired by MFA and NESDC, reflecting the agreed government structure with NESDC as steward of the NESDP and thereby ensuring alignment with national priorities. Reference can be made to other, aligned strategies and policies, including those under the umbrella of the NESDP, in the Outcome Groups’ work. However, maintaining the current governance arrangements is essential, as they reflect government-endorsed structures. Introducing additional alignment at the governance level would fall outside the scope of the process agreed with government, require new negotiations for limited added value, and risk disrupting the clarity of oversight and accountability.
1.2 | Prioritize strategic issues like ageing, AI, and OECD accession-related reforms, as well as support towards the fulfilment of international commitments. | Short | UNCT / TSC | The three Outcomes of the new CF explicitly prioritize these areas: ageing is reflected under Outcome 1 through demographic resilience and the care economy; digital transformation and innovation, including AI, are embedded across outcomes; and support to international commitments and OECD-related reforms is reflected under Outcomes 2 and 3, including policy alignment, governance, and global engagement.
1.3 | Link UN support to Thailand’s regional leadership and global commitments (e.g., ASEAN, UN Human Rights Council, etc.). | Short | UNCT / TSC | The new CF explicitly links UN support to Thailand’s regional and global role, including through Outcome 3, which strengthens institutions to advance regional and international cooperation, and Outcome 2, which supports implementation of global commitments. The CF also builds on Thailand’s engagement with ASEAN, the UN Human Rights Council, and other multilateral platforms.
1.4 | Include in the CF adequate analysis of cross-border challenges and how the UN can contribute (leveraging also UN regional or multi-country offices based in Thailand). | Short | UNCT / TSC | Cross-border challenges are addressed across outcomes, including on people on the move, refugees, trafficking, pollution, and environmental risks, such as Mekong River contamination, and cybersecurity. Notably, the UN has already supported responses to emerging transnational risks, including cyber-fraud and trafficking for forced criminality. Given Thailand’s role as a UN regional hub and the presence of multiple regional and multi-country offices, the new CF aims to leverage the UN’s regional footprint, where 16 of 21 UNCT members are regional or multi-country offices, enabling a strengthened and coordinated response to transboundary issues and promotion of joint programming approaches where relevant.
Recommendation 2: Improve shared understanding of the role of CF and internal ownership, including by enhancing the use of UN Info: 2.1 Include in the CF well-defined outputs and accompany the results framework with a clear ToC (developed in consultation with relevant counterparts). 2.2 Ensure that, as part of the JWP design and agencies’ specific country programmes, the contribution of SOs is clearly linked to a specific CF output. Use the “narrative” part of UN Info to include this information. 2.3 Organise “CF townhall meetings” or interactive workshops where all UN staff operating in Thailand has an opportunity to engage in discussions around CF results and see where the projects, they implement fit in the bigger picture. 2.4 Use the information collected via UN Info to produce the ARR (both narrative on agencies’ SOs and monitoring indicators’ data). 2.5 Ensure that all UN activities are captured in UN Info, even if part of a regional programme – RCO to design clear guidelines for regional offices on how to determine country-level contribution.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Include in the CF well-defined outputs and accompany the results framework with a clear ToC (developed in consultation with relevant counterparts). | Short | UNCT / RCO | A TOC has been developed for the new CF through extensive consultations within the UNCT and with the tripartite Steering Committee. This process culminated in a multi-stakeholder validation exercise involving over 200 participants from line ministries, civil society, the private sector, and academia, ensuring that outputs and pathways to results are clearly defined and nationally grounded.
2.2 | Ensure that, as part of the JWP design and agencies’ specific country programmes, the contribution of SOs is clearly linked to a specific CF output. Use the “narrative” part of UN Info to include this information. | Short | UNCT / RCO | The UNCT will strengthen more consistent and complete reporting in UN Info going forward, supported by technical training to ensure a common standard across entities. The focus will be on improving the quality, completeness, and usability of information to better reflect actual implementation and support coordination. These efforts will be reinforced through the governance arrangements of the new CF to ensure clearer accountability for reporting and alignment, with the aim of improving coherence, reducing duplication, and enhancing the strategic use of UN Info.
2.3 | Organise “CF townhall meetings” or interactive workshops where all UN staff operating in Thailand has an opportunity to engage in discussions around CF results and see where the projects, they implement fit in the bigger picture. | Short | UNCT / RCO | A plan will be developed to engage UN personnel operating in Thailand to implement the CF. The aim will be to strengthen understanding of CF results and support staff in linking their programmes and projects to the broader strategic framework.
2.4 | Use the information collected via UN Info to produce the ARR (both narrative on agencies’ SOs and monitoring indicators’ data). | Short | UNCT / RCO | The UNCT utilizes UN Info data alongside complementary sources to develop the ARR. Starting in 2025, the UNCT is strengthening the evidence base and improving the integration of UN Info data into the ARR.
2.5 | Ensure that all UN activities are captured in UN Info, even if part of a regional programme – RCO to design clear guidelines for regional offices on how to determine country-level contribution. | Short | UNCT / RCO | Considerable progress has been made by the UNCT to strengthen the entry and use of UN Info data in support of common, transparent UN reporting, recognizing that UN Info serves as an additional reporting mechanism alongside agency systems. Reporting guidelines are shared with all agencies at the start of the annual reporting cycle. Starting in 2026, these will include streamlined protocols on how to capture regional commitments. These resources are further supported by technical training and targeted capacity-building to promote consistency, completeness, and a common standard across entities.
Recommendation 3: Use UN Info as a platform to showcase UN achievements in Thailand and progress towards results: 3.1 Outcome groups should “own” UN Info data and use it as reference for coordination and communication purposes. 3.2 RCO to provide clear guidelines on how to report in UN Info, providing a clear definition of SOs, trainings on how to define the level of gender and human rights markers, and assignment of QCPR functions. 3.3 Monitoring data should be annually revised and output targets changed if proven unrealistic.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Outcome groups should “own” UN Info data and use it as reference for coordination and communication purposes. | Short | RCO / Outcome Groups | Since 2025, considerable efforts have been made to strengthen agency capacity to enter and use UN Info data, including through targeted capacity-building. UN Info data is a standing agenda item for all Outcome Group meetings to drive evidence-based decision making and is regularly validated with agencies, including informing the RC’s high-level engagements with partners such as the Partners Briefing. In 2026, UN Info data is also planned to be further visualized to enhance accessibility and support more effective analysis and communication.
3.2 | RCO to provide clear guidelines on how to report in UN Info, providing a clear definition of SOs, trainings on how to define the level of gender and human rights markers, and assignment of QCPR functions. | Short | RCO | The RCO will continue to strengthen and clarify guidance on UN Info reporting. This builds on existing efforts, including guidance notes and training delivered to agencies. Dedicated training on the Human Rights Marker and Gender Equality Marker was delivered in March 2026 with support from the Issue Based Coalition on Human Rights, GEWE and Disability Inclusion.
3.3 | Monitoring data should be annually revised and output targets changed if proven unrealistic. | Short | RCO / UN Data Group | Indicator results from 2022 are being validated and adjusted by the UN Data Group. Moving forward, the new CF cycle will incorporate annual data reviews to facilitate target recalibration, in line with donor commitments and entity requirements, ensuring our outputs stay responsive to changing programmatic environments.
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: Improve coordination and efficiency of UN operations in Thailand: 4.1 Explore the opportunity to include ESCAP in the UNCT through an appointed coordination programme officer (as is the case in other UNCTs with respective regional commissions). 4.2 Consider having one HoA chairing the outcome groups, who could take full ownership for the UN delivery under that outcome. Their authority should be recognized by the other HoAs. The chair should be empowered to accompany the RC in talks to government counterparts on behalf of the group. 4.3 The RCO should provide secretariat support to the outcome groups and maintain up to date and well-organized files on the group’s work. 4.4 Engage counterparts and stakeholders, as relevant, in the work of the outcome groups (see recommendation 6.2) and use such forum to develop and rediscuss the ToC for UN contributions. 4.5 Establish clear ToRs for the Outcome groups and have them regularly report to the UNCT. The ToRs should include the commitment of agencies to use this forum for sharing emerging opportunities, including for resource mobilization. 4.6 Develop a joint resource mobilization strategy for the CF, led by the RCO, engaging with the private sector, government, funds, and international development partners. 4.7 Carefully time and plan CPDs’ design and evaluation not to overlap with the CF related processes to avoid high transaction costs for counterparts. The CPD consultations and design should build on (and if needed follow) those carried out for the development of the CF. Vice versa, if a full-fledged CPDs evaluation needs to be carried out, this should be planned in order to feed into the CF evaluation.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted | 4.1 Accepted 4.2 Partially Accepted 4.3 Accepted 4.4 Accepted 4.5 Accepted 4.6 Accepted 4.7 Partially Accepted
If rejected or partially accepted, please provide an explanation: …… |  | 4.2 The UNCT partially accepts this recommendation. Within each outcome, programmatic, operational, and financial accountability and delivery rest with respective UN entities. However, the designation of a Head of Agency as chair of each Outcome Group will be further strengthened to ensure clear leadership for each outcome, as set out in an Outcome Chair Terms of Reference to be signed off by the UNCT. The UNCT will also reinforce recognition of this role across agencies and support chairs. Outcome Chairs will play an important role in facilitating coordinated planning and engagement on cross-cutting issues across agencies, while respecting entity-specific accountabilities. The Outcome Group chairs, for example, may accompany the RC in their meetings on the Cooperation Framework with government, representing the Outcome groups, as appropriate, in lieu of the entire UNCT. 4.7 The UNCT partially accepts this recommendation. The RC and Heads of Agencies with CPDs will continue to seek opportunities to appropriately sequence CPD and CF design and evaluations to minimize duplication, while maintaining required timelines and ownership of Government’s consultations by respective agencies, in line with expectations for Executive Board’s submission of CPDs. For the new cycle, and at the Government’s request, the CF Results Framework was presented alongside the CPDs of UNDP, UNFPA and UNICEF to the SDG Working Group. This approach reflects strong Government ownership and a deliberate effort to streamline engagement, avoiding parallel consultations while clearly demonstrating interlinkages and ensuring a coherent approach with national counterparts.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Explore the opportunity to include ESCAP in the UNCT through an appointed coordination programme officer (as is the case in other UNCTs with respective regional commissions). | Short | UNCT / regional UN entities | ESCAP is already represented in the UNCT through the Head of its Subregional Office for South-East Asia. Building on this, the UNCT will explore options to further strengthen ESCAP’s engagement to more consistent collaboration aligned with CF priorities and in line with the outcomes of UN80 initiative and the UNCT reconfiguration.
4.2 | Consider having one HoA chairing the outcome groups, who could take full ownership for the UN delivery under that outcome. Their authority should be recognized by the other HoAs. The chair should be empowered to accompany the RC in talks to government counterparts on behalf of the group. | Short | UNCT | Within each outcome, programmatic, operational, and financial accountability and delivery rest with respective UN entities. However, the designation of a Head of Agency as chair of each Outcome Group will be further strengthened to ensure clear leadership for each outcome, as set out in an Outcome Chair Terms of Reference to be signed off by the UNCT. The UNCT will also reinforce recognition of this role across agencies and support chairs. Outcome Chairs will play an important role in facilitating coordinated planning and engagement on cross-cutting issues across agencies, while respecting entity-specific accountabilities. The Outcome Group chairs, for example, may accompany the RC in their meetings on the Cooperation Framework with government, representing the Outcome groups, as appropriate, in lieu of the entire UNCT.
4.3 | The RCO should provide secretariat support to the outcome groups and maintain up to date and well-organized files on the group’s work. | Short | UNCT / regional UN entities / CPD agencies | The RCO will continue to strengthen its secretariat support to Outcome Groups, including through the development of a centralized SharePoint platform to support coordination and knowledge management.
4.4 | Engage counterparts and stakeholders, as relevant, in the work of the outcome groups (see recommendation 6.2) and use such forum to develop and rediscuss the ToC for UN contributions. | Short | UNCT / regional UN entities / CPD agencies | Outcome Groups will further strengthen engagement with relevant counterparts and stakeholders, as appropriate, by including external participants in meetings and deep dives.
4.5 | Establish clear ToRs for the Outcome groups and have them regularly report to the UNCT. The ToRs should include the commitment of agencies to use this forum for sharing emerging opportunities, including for resource mobilization. | Short | UNCT / regional UN entities / CPD agencies | Outcome Group TORs will be further strengthened, including provisions on coordination, information sharing, and resource mobilization. Since 2024, the Outcome Group updates are a standing UNCT meeting agenda item and groups are requested to share minutes in advance with the UNCT.
4.6 | Develop a joint resource mobilization strategy for the CF, led by the RCO, engaging with the private sector, government, funds, and international development partners. | Short | UNCT / regional UN entities / CPD agencies | The RCO will lead the development of a joint CF resource mobilization strategy, as part of the Multi Year Funding Framework. This will capture opportunities with government, private sector partners, pooled funds, and international development partners to support coordinated and strategic financing of CF priorities.
4.7 | Carefully time and plan CPDs’ design and evaluation not to overlap with the CF related processes to avoid high transaction costs for counterparts. The CPD consultations and design should build on (and if needed follow) those carried out for the development of the CF. Vice versa, if a full-fledged CPDs evaluation needs to be carried out, this should be planned in order to feed into the CF evaluation. | Short | UNCT / regional UN entities / CPD agencies | The RC and Heads of Agencies with CPDs will continue to seek opportunities to appropriately sequence CPD and CF design and evaluations to minimize duplication, while maintaining required timelines and ownership of Government’s consultations by respective agencies, in line with expectations for Executive Board’s submission of CPDs. For the new cycle, and at the Government’s request, the CF Results Framework was presented alongside the CPDs of UNDP, UNFPA and UNICEF to the SDG Working Group. This approach reflects strong Government ownership and a deliberate effort to streamline engagement, avoiding parallel consultations while clearly demonstrating interlinkages and ensuring a coherent approach with national counterparts.
Recommendation 5: Leverage UN comparative advantages in Thailand and address limitations: 5.1 Use the UN’s global and regional networks and impartiality to support Thailand in navigating geopolitical shifts. 5.2 Establish an UN-parliament platform for engagement, coordinated by the RC to ensure policy support is provided in a timely and collective manner as relevant. 5.3 Ensure UN entities’ joint engagement with counterparts, leveraging each other’s political capital and promoting internal RTG’s coordination. 5.4 Explore UN-wide solutions through the BOS to improve retainment of professional staff ensuring continuity.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted | 5.1 Accepted 5.2 Partially Accepted 5.3 Partially Accepted 5.4 Accepted
If rejected or partially accepted, please provide an explanation: …… |  | 5.2 The UNCT partially accepts this recommendation. Building on existing engagement with parliamentary sub-committees, the UNCT will explore options to further systematize engagement with Parliament. This will support timely, coherent UN policy engagement on priority issues, in line with national processes and needs. 5.3 The UNCT partially accepts this recommendation. Joint UN engagement with counterparts will continue to be strengthened on key strategic priority issues, leveraging the RCs convening role to bring together UN entities and Government on joint issues. However, UN entities must remain at the forefront of their programmatic engagement. This approach supports more coherent UN engagement, maximizes collective expertise and political capital, and promotes coordination across the Royal Thai Government.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Use the UN’s global and regional networks and impartiality to support Thailand in navigating geopolitical shifts. | Medium | UNCT | The CF builds on the UN’s comparative advantage in leveraging global and regional networks and its impartiality to support Thailand in navigating complex and evolving dynamics. To strengthen this further, the UNCT will prioritize the use of in-house expertise, including from Thailand-based regional offices, in line with UN80 and related reform efforts, before resorting to external consultancies, ensuring the UN’s own value-add remains central to the partnership.
5.2 | Establish an UN-parliament platform for engagement, coordinated by the RC to ensure policy support is provided in a timely and collective manner as relevant. | Medium | UNCT | Building on existing engagement with parliamentary sub-committees, the UNCT will explore options to further systematize engagement with Parliament. This will support timely, coherent UN policy engagement on priority issues, in line with national processes and needs.
5.3 | Ensure UN entities’ joint engagement with counterparts, leveraging each other’s political capital and promoting internal RTG’s coordination. | Medium | UNCT | Joint UN engagement with counterparts will continue to be strengthened on key strategic priority issues, leveraging the RCs convening role to bring together UN entities and Government on joint issues. However, UN entities must remain at the forefront of their programmatic engagement. This approach supports more coherent UN engagement, maximizes collective expertise and political capital, and promotes coordination across the Royal Thai Government.
5.4 | Explore UN-wide solutions through the BOS to improve retainment of professional staff ensuring continuity. | Medium | UNCT | Efforts will be made to explore UN-wide approaches to improve staff retention and ensure continuity. At the same time, this remains challenging in the context of ongoing UN80 reforms and broader budget constraints across the UN system. Within these parameters, the UNCT will identify practical, context-appropriate measures to support workforce stability where feasible.
Recommendation 6: Expand ownership of the CF among government counterparts: 6.1 Consider expanding the Tripartite Steering Committee composition to include all relevant line ministries (LMs) and national institutions. 6.2 Include relevant counterparts in the “deep dive” discussions at thematic level. 6.3 Leverage the “Governors’ Forum” to introduce the CF and discuss how this can be translated at the sub-national level.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted | 6.1 Accepted 6.2 Accepted 6.3 Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Consider expanding the Tripartite Steering Committee composition to include all relevant line ministries (LMs) and national institutions. | Short | UNCT / TSC | The new CF is addressing this through its governance structure, with the Steering Group (MFA, NESDC, and the RC) complemented by broader engagement of the UNCT and through the government’s SDG Working Group, which brings together relevant line ministries at both technical and senior levels. This approach has been applied during the multi-stakeholder validation of the new CF outcomes and continues including through consultations on the new CF results framework.
6.2 | Include relevant counterparts in the “deep dive” discussions at thematic level. | Short / Medium | UNCT / Outcome Groups | Outcome Groups will further strengthen engagement with relevant counterparts and stakeholders, including by involving external participants in thematic discussions and deep dives. This will help ensure continued relevance, national ownership, and alignment with evolving priorities, in line with the approach outlined under Recommendation 4.4.
6.3 | Leverage the “Governors’ Forum” to introduce the CF and discuss how this can be translated at the sub-national level. | Medium | UNCT / TSC | The Governors’ Forum will be leveraged as a platform to introduce the CF and discuss its translation at the sub-national level, supporting alignment with local priorities and implementation.

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030