## Sheet1
LAO PDR 2022-2026 COOPERATION FRAMEWORK EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Evaluation of UN-Lao PDR 2022-2026 UN Sustainable Development Cooperation Framework • Preparation of the management response: UNCT, led by UN RCO • Approval of the management response: UNCT and JSC • Follow-up monitoring and updating of the management response’s implementation: UNCT, CF working groups, RCO • Frequency of monitoring and updating: Semi-Annual
RELEVANCE AND ADAPTIBILITY
Recommendation 1: Balance service delivery with systemic and sustainable change
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: …… |  | Partially Accepted: Under 1.3, UNCT will prioritize national data systems strengthening first over subnational as there are many gaps.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Identify 3–4 flagship initiatives for the next CF with explicit pilot-to-scale and government budget absorption pathways | 2026-2028 | UNCT | - In 2025, UNCT initiated coming together on several new joint initiatives, like Digital Transformation, Social Protection, Youth and Jobs - In 2026, UNCT will work towards developing them into flagship initiatives and include pilot to scale, capacity building and handover roadmap in the design
1.2 | Design with scale from the start: Require every major intervention or joint programme to include a handover and financing roadmap agreed with national counterparts (skills transfer, systems strengthening, financing and handover timelines) | 2026-2028 | UNCT | - UNCT will identify existing major interventions/ JPs where a handover and finnacing roadmap can be applied - UNCT will co-design with donors new interventions/ JPs to include a handover and financing roadmap
1.3 | Prioritise subnational delivery capacity as a core sustainability lever (e.g. decentralised data systems, providing training and coaching for local service providers, piloting budget allocation mechanisms that link national priorities with local implementation capacity) | 2027-2031 | UNCT | - UNCT and LEAD identified that while some coaching/ training of local service providers can be provided, stregthening of data systems will need to be done first at the national level, especially administrative and register-based systems including CRVS
Recommendation 2: Institutionalise LNOB, human rights, and gender equality across planning, delivery, and monitoring
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Mandate LNOB/HR/GEWE dimensions and minimum disaggregation standards across all outcomes and outputs | 2026-2027 | UNCT | - In 2025, LNOB, HR and GEWE dimensions were explicitly addressed in the Country Analysis, Theory of Change and Strategic Prioritization exercises in formulating the new CF - In 2026, UNCT will request support from Regional IBC on LNOB/HRBA/GEWE to share a mainstreaming checklist and conduct a training for all RGs at the beginning of the new CF cycle to embed LNOB/HR/GEWE into the CF narrative, results framework, outcomes and outputs in the most optimal way - LEAD will draft D18LNOB/HR/GEWE measurable indicators and disaggregated data where available
2.2 | Establish a system wide quality assurance function (Gender/HR Thematic Group) with a formal role in Results Group planning and LEAD-led monitoring. | 2026-12-31 | UNCT | - In 2025, the RC established an interim GTG, under RG 3 and co-chaired by UNDP and UNFPA for review in 2026 - Based on this recommendation, RC will strongly advocate with UNCT for a GTG under the 2027-2031 CF
2.3 | Continue work with the Ministry of Finance and Planning to embed gender, disability, and youth indicators into national planning, monitoring, and budgeting frameworks, and strengthen treaty reporting mechanisms, parliamentary oversight, and other national institutions to make LNOB gains resilient over time. | 2026-2031 | UNCT & LEAD | - In 2025, LEAD provided support to include relevant data and indicators on LNOB, HR and GEWE in the 10th NSEDP M&E Framework, LEAD will continue to support monitoring - UNCT will continue to strengthen treaty reporting mechanisms, engage with parliamentarians and other national insitutions focusing on LNOB
COHERENCE and COORDINATION
Recommendation 3: Streamline the CF coordination architecture to reduce transaction costs and enhance functionality
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Review and simplify coordination structures, clarifying mandates (Results Groups for technical coordination and implementation; POG for upstream strategic guidance and coherence; LEAD group for evidence generation, and foresight) and ensuring clear chairing/accountability and light secretariat support where needed. | 2026-12-31 | UNCT & RCO | - The 2027-2031 CF will have more streamlined coordination architecture with reduced startegic priorities and better alignment with working groups - ToRs for all working groups will be updated and annexed under the 2027-2031 CF
3.2 | Strengthen vertical decision making, including a formal feedback loop between Results Groups and the POG to allow delivery-level insights to inform upstream planning, while aligning strategic priorities with real-time implementation realities. | 2026-12-31 | UNCT & RCO | - Co-chairing of RGs and POG will be clarified with clear roles and accountabilities for Heads of Agencies/ Deputies
3.3 | Reduce transaction drivers by streamlining the CF results structure with fewer, clearer outcomes/outputs and lighter, decision-relevant reporting through JWPs, aligned with NSEDP priorities and SDG transition pathways. | 2027-2031 | UNCT & RCO | - The 2027-2031 CF will have fewer priorities/ outcomes (from 4 to 3) and outputs (from 21 to 10) aligned with the 10th NSEDP and SDG transitions - JWPs will be revitalized as the main coordinating, reporting and resource mobilisation tool
Recommendation 4: Use joint programmes selectively as vehicles for transformation and financing
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Apply clear criteria for joint programmes, prioritising initiatives that enable scale, pooled or catalytic financing, and complementary mandates, and limiting participation to a maximum of 3-4 agencies with comparative advantage | 2026-2031 | UNCT, POG, LEAD | UNCT will develop criteria for JPs under the new Partnerships Strategy
4.2 | Position joint programmes as transformative, bundled interventions aligned with the SDG transitions and national priorities. Mainstream climate resilience, youth, and digital transformation as flagship thematic pillars within the next UNSDCF, integrated into both programming and financing strategies | 2026-2031 | UNCT | UNCT agrees
4.3 | Strengthen discipline and accountability by clarifying lead agency roles and RC oversight in joint programmes, including streamlined governance arrangements to contain transaction costs | 2026-2031 | UNCT | Will be included under the new Partnerships Strategy
Recommendation 5: Strengthen collaboration within the UNCT under the RC’s leadership role in line with the MAF framework
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Operationalise the RC’s MAF role by explicitly mandating the RC to broker collective priorities, mediate inter-agency competition, and arbitrate overlaps based on comparative advantage | 2026-12-31 | RC & UNCT | UNCT will commit to a Code of Conduct to agree on a set of principles aimed at strengthening collaboration, information-sharing, transparency, coherence and accountability and avoiding duplication
5.2 | Institutionalise collaborative practices by linking UNCT retreats, foresight exercises, and planning cycles to joint priority-setting and collective resource mobilisation, making collaboration the default rather than ad hoc. | 2026-2031 | RC & UNCT | - Annual UNCT retreats will include foresight - JWPs will be platforms for joint resource mobilisation - UNCT Code of Conduct and new Partnerships Strategy developed
5.3 | Strengthen the RCO’s enabling capacity by ensuring dedicated technical support for foresight, MEL, and coordination functions that underpin collective accountability | 2026-2031 | RCO | -RCO annual budget will include foresight training - UN 2.0 trainings and tools will be accessible to RCO team as well as LEAD and POG
Recommendation 6: Strengthen collective resource mobilisation and financing coherence
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Implement a UNCT-owned annual resource mobilisation plan aligned with CF priorities | 2026-2027 | RCO | RCO & Partnerships Officers will deveop annual joint resource mobilisation and engagement plans under the new Partnerships Strategy
6.2 | Improve financial transparency and data quality in corporate and country-level funding and reporting systems, including systematic and timely reporting of expenditures and allocations | 2026-2031 | UNCT & RCO | - UNCT will work with national counterparts to strengthen the aid effectiveness dashboard - RCO and M&E focal points will regularly ensure that UNINFO is completed, updated and accurate - RCO will develop a UNINFO dashbaord for UNCT use of UN data
6.3 | Pilot focused pooled or thematic funding windows where they demonstrably reduce duplication and support scale | 2026-2031 | UNCT & RCO | - The Green and Climate Finance project is being piloted as a prototype for a country level pooled fund - With recent ODA cuts, UNCT will commit to undertake a feasibility assessment to establish a country level pooled fund, with RCO support in bringing lessons from other countries
EFFECTIVENESS
Recommendation 7: Clarify the UN’s comparative advantage and strengthen strategic partnerships
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Agree internally, based on LEAD analysis of overlaps, synergies and risks, on 3–4 priority of comparative advantage and a clear division of labour | 2026-2027 | RCO | Clear ToRs for all working groups under the new CF will be developed
7.2 | Develop a single UN value proposition narrative for engagement with government, donors, IFIs and the private sector, aligned with national priorities and SDG transitions | 2026-2027 | UNCT | UNCT will task the UNCG and Partnerships focal points to develop a UNCT-wide ‘UN in Lao PDR Value Proposition’ to articulate the UN’s comparative advantages, strategic ambition, and joint value offer vis-à-vis other development partners. The Value Proposition will serve as a core reference for resource mobilization and partnership outreach, and be updated periodically to remain current with evolving national priorities.
7.3 | Engage CSOs, INGOs, and rights holders as co-creators, not subcontractors in programme design and policy dialogue | 2026-2031 | UNCT | The new Partnerships Strategy will include a 5-year work plan of progressive engagement with key stakeholders including iNGOs, CSOs, academia and private sector moving beyond annual/ bi-annual information-sharing meetings to co-designing, inclusive consultations and scaling up successful pilots particularly on strategic and overarching issues like support to 10th plan, JPs etc.
EFFICIENCY
Recommendation 8: Strengthen the National Aid and Donor Coordination Architecture
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | Partially accepted: The Round Table Process and SWGs involve several stakeholders and while the UN can influence and support some actions, the Government needs to take them on board as these are Government mechanisms.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Recalibrate the Round Table Process to focus on fewer, thematic policy dialogues linked to NSEDP and SDG transitions | 2026-2031 | RC & UNCT | Ongoing discussions led by the RC with UNDP's technical support, ultimate decision is by the RTP Secretariat (Ministry of Finance)
8.2 | Strengthen the Sector Working Groups as joint planning and follow-up mechanisms, with greater participation from CSOs, INGOs, and subnational actors and ensure coherence with UN Result Groups and Joint Workplans | 2026-2031 | RC & UNCT | UN agencies co-chair some SWGs and particpate in others and where possible will enusre alignment of UN RGs, JWPs and SWGs
8.3 | Establish a joint aid effectiveness dashboard with government and partners to track alignment of financing with national priorities and SDGs | 2026-2031 | UNCT | An aid effectivess dashboard exists, the focus will be on strengthening it but not developing a new one
Recommendation 9: Strengthen the results and data ecosystem for evidence based decision making
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Streamline the indicator framework to a focused, attributable results framework aligned with systemic change | 2026-08-30 | LEAD | LEAD will conduct an SDG indicator stocktake by Q2 2026, assessing the availability, quality, and frequency of country-level data to track Lao PDR’s progress under both the SDG Global Indicator Framework and the M&E framework of the 10th NSEDP and 5th Population Census . This stocktake ensures SMART indicators (specific, measurable, achievable, relevant, and time-bound) are ready for adoption as outcome and output indicators in the UNSDCF Results Framework.
9.2 | Strengthen baselines, targets, and LNOB disaggregation through partnership with the LSB and line ministries, including improved use of administrative data systems
9.3 | Institutionalise mid-cycle evidence-based reviews, requiring Result Groups to use performance data to inform course correction and policy dialogue | 2029-12-31 | UNCT | MTR of the 2027-2031 CF will be undertaken
SUSTAINABILITY
Recommendation 10: Reduce transaction costs and unlock operational efficiency
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Co-Evaluation Managers
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Expand shared services solutions through the OMT and embed BOS gains into CF planning | 2026-2031 | OMT | BOS will remain as a standing agenda item at OMT meetings to continue monitoring and ensuring high cost savings
10.2 | Align operations and programmes to directly support CF priority areas | 2026-2031 | RCO | Annual joint retreats will be organised for the POG/ RGs, OMT and UNCG to strengthen alignment between operational needs and programmes/joint advocacy and strengthen cost efficiencies through LTAs under the BOS
10.3 | Track and communicate efficiency gains (e.g. staff time freed, cost savings) to demonstrate value and build donor confidence | 2026-2031 | OMT | OMT will introduce indicators and track efficiency gains

## Sheet2
LAO PDR 2022-2026 COOPERATION FRAMEWORK EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Evaluation of UN-Lao PDR 2022-2026 UN Sustainable Development Cooperation Framework • Preparation of the management response: UNCT, led by UN RCO • Approval of the management response: UNCT and JSC • Follow-up monitoring and updating of the management response’s implementation: UNCT, CF working groups, RCO • Frequency of monitoring and updating: Semi-Annual
RELEVANCE AND ADAPTIBILITY
Recommendation | Sub-recommendation | Comments | Key actions | Time frame/deadline | Responsible Agencies | Implementation monitoring
[6 empty] | Time of monitoring | Progress update | Comments
Recommendation 1: Balance service delivery with systemic capacity development and policy influence | 1.1. Identify 3–4 flagship social sector initiatives and develop transition pathways beyond 2026, with milestones for government budget absorption and ownership. For each area, develop a transition pathway that spells out how service delivery pilots will shift toward government ownership, with budget absorption milestones beyond 2026.
1.2. Require every major intervention or joint programme to include a capacity development roadmap (skills transfer, systems strengthening, handover timelines).
1.3. Use Joint Workplans to identify pairing of service delivery with policy, financing, or governance reforms
1.4. Reinforce internal coherence by ensuring advocacy on governance, rights, and green transition is pursued collectively, not in silos. This would entail joint advocacy positions through joint UNCT policy briefs; conceptual design of bundled programming under JWPs, cross-RG collaboration sponsoring cross-cutting issues on key prioirty areas such as youth employment or green economy; as well as continued joint messaging and campaigns.
Recommendation 2: Systematically integrate LNOB, human rights, and gender equality into outcomes, outputs, and monitoring
COHERENCE ANF COORDINATION
Recommendation 3: Streamline CF coordination architecture
Recommendation 4: Reposition JWPs and JPs as bundled, transformative tools
Recommendation 5: Strengthen collaboration under RC’s leadership
Recommendation 6: Clarify UN’s comparative advantage and strengthen partnerships
EFFECTIVENESS
Recommendation 7: Rationalize the indicator framework
EFFICIENCY
Recommendation 8: Reinforce and diversify resource mobilisation
Recommendation 9: Reduce transaction costs and unlock efficiency
SUSTAINABILITY
Recommendation 10: Move from pilots to nationally owned platforms
Recommednation 11: Position climate resilience and green growth as central pillars