## Sheet1
Country Timor-Leste; CF 2021-2025 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: UNSDCF 2021-2025 Evaluation / 2024 • Preparation of the management response: UN Programme Management Team • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: UN Programme Management Team • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Invest in third party-facilitated Strategic Planning Session with the participation of RC, Head of RCO, and all Heads of Agencies of the UNCT members to meet outside the UN campus and preferably outside Dili. The purpose is two fold: (i) to strategize around better results framework, key priority areas for the next planning cycle, to agree on the comparative advantages of each UN Agency, to shape the composition of the desired UNCT in Timor-Leste for the next round of the CF implementation, and agree on ‘rules’ of internal coordination; and (ii) to reconcile operational discrepancies among UN Agencies in Timor-Leste and consolidate around the RC and regain strength as One UN. This could be organized after the CCA but before the CF planning. | [5 empty] | Responsible Head of RCO | Short-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | UNCT to organize discussion on the CF Results Framework in January 2025 | 2025-01-01 | RCO | 4 workshops were held on the results framework. One in each quarter. | completed | December | 2025
1.2 | UNCT retreat in early March 2025 to discuss UNCT composition, internal coordination and operational discrepancies | 2025-03-01 | RCO | 2 UNCT retreats were held. | completed | December | 2025
1.3 | UNCT participation in the SDG Leadership Lab facilitated by Presencing Institute on food systems will showcase how UNCT can coordinate around specific outcome areas of the CF. | Quarter 1 and 2 | RCO and SDG lab | Not held due to financial cuts on the SDG Lab | cancelled | June | 2025
Recommendation 2: Critically revise current results framework with the focus on realistic sub-outcomes for the remaining period and indicators to capture UN performance fully in line with the corporate reporting system of UN Agencies to avoid double reporting. | [5 empty] | Responsible Head of RCO | Short-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Rejected
If rejected or partially accepted, please provide an explanation: …… |  | A new CF (2026 - 2030) is currently under development to be finalized by December 2025 including developing a new Results Framework which will build on evaluation findings and recommendations.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1
2.2
…
Recommendation 3: Restart strategic partnership with the Government of Timor-Leste through a series of measures: o Organize UN Conference in Dili with high-level, preferably Under Secretary General (USG), representation to proudly present the scope of the work done collectively by all UN Agencies under each of the six outcome areas and refresh strategic partnership with the Government of Timor-Leste. This could be combined with the launch of the new CF in Timor-Leste. Ensure the CF is available in Portuguese and widely disseminated among government representatives. o Reactivate the Joint Steering Committee between the Government of Timor-Leste and UN. | [5 empty] | Responsible UN RC | Short-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1. | Quarterly meetings already initiatied with Prime Minister and President with RC and UNCT to discuss UN initiatives in the ocuntry, including presenting 'top ticket items' will be continued. | Quarterly | RCO
3.2. | Launch event of the new UN CF (the attendance of USG will depend on availability) | Quarter 4 of 2025 | RCO | This is schedule for 10th December. | ongoing as expected | June | 2025
3.3. | UN Steering Committee has been reactivated with a meeting in December 2024 and further meetings will happen in 2025 (every 6 months as per ToR). | June and December 2025 | RCO | The second meeting will be held in Dec 2025 | ongoing as expected | June | 2025
3.4. | New UN CF to be translated into Tetum and a summary provided in Portuguese | Quarter 4 of 2025 | RCO | The CF is available in Portuguese, Tetum and English | completed | June | 2025
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: Improve the governance mechanism around the CF through several measures: o Simplify and strategically position thematic groups within UNCT ensuring there are (i) LNOB group including all cross-cutting issues; (ii) Communication group; (iii) OMT; (iv) Security Management Team (SMT); and (v) Policy group (to coordinate and harmonize UN’s efforts across normative work). Ensure rotational on semi-annual basis Chair and Co-Chair roles among the Agencies involved in each thematic group except SMT. o Strengthen the function of the M&E group and ensure there are quarterly monitoring updates (qualitative and quantitative) of the progress on the revised sub-outcome indicators provided to the PMT to inform strategic discussion at the UNCT and Agency levels. o Improve the performance of the Results Group by ensuring there are quarterly joint work programmes. Ensure semi-annual rotation of the Chair and Co-Chair of the RGs. o Strengthen accountability towards the CF through ensuring that RC contributes to the performance review of each Head of Agency, while each Head of Agency contributes to the RC’s performance review. Establish mechanism in collaboration with the DCO HQ and pilot in 2024. o Adopt nexus narrative as a guiding principle for the UN programming in Timor-Leste to ensure maximum impact of the programming. | [5 empty] | Responsible UN RC | Short-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Don't agree with quaterly work plans of RGs and don't agree with semi-annual Chairs
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Create an LNOB group to address inequities and needs of vulnerable groups (LGTBQI+, women, children, youth, PWDs) | Quarter 4 of 2025 | UNCT | The group has been created | completed | December | 2025
4.2 | M&E group to meet quarterly and provide feedback on progress to PMT. M&E group will also cover data systems and therefore would need to review the ToR | Every quarter | M&E Group | The revised TOR been sent to PMT for further clearaance | completed | December | 2025
4.3 | UN Agencies and RC to agree on key UN coordination indicators according to MAF to improve performance management and accountability | For performance management of 2024 | UNCT | This will be discussed in 2026 | delayed |  | 2025
4.5 | RGs ToRs will be reviewed to ensure better performance and accountability | Quarter 2 of 2025 | UNCT | UNCT decided there will be no RGs and PMT will be responsible for the JWPs. | completed | December | 2025
Recommendation 5: Establish ‘analytical’ function of the RCO by taking several steps: o creating a repository of key documents, o producing Monthly Analytical Bulletins to inform the UNCT meetings on (a) the most important political, socio-economic, development, etc. changes in the country and in the region; key progress made by UNCT in the last reporting period (with the support of the M&E group); and (c) ensuring there is follow up on the decisions taken at the UNCT; | [5 empty] | Responsible Head of RCO | Medium-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We don't agree with including monthly progress made by UNCT in the bulletin. Follow-up of decisions by UNCT will be done at UNCT meetings not as part of the bulletin.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | To develop the monthly bulletin with important updates on the context | Every month | RCO | The RC shares the updates of the context with DCO | completed | June | 2025
5.2 | To create the repository of documents and share with all agencies | mid 2025 | RCO | This will be done in 2026 | delayed | December | 2025
…
Recommendation 6: Develop UN investment strategies in the key sectors under the relevant RG (e.g. health, education, agriculture, economic diversification and decent work, food security, and disaster risk reduction). Ensure there is senior international economic advisor to RC (could be cost-shared from a UN Agency or provided as in-kind contribution to RCO) at least for one year to develop investment plans for each priority area with all Agencies. | [5 empty] | Senior Economist | Medium-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Cost-sharing for an economist is not possible due to funding capabilities of the agencies. A national economist position already exist at the RCO as well as an economist group that meets regularly.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Revisit the functions of Results Groups to include the possibility of developing joint UN investment Cases on pertinent issues based on joint analysis with government and development partners. | 4th Quarter | UNCT | The functions have been revised. PMT will hold the functions of the RGs and the case for joint analysis will start being implemented in 2026. | completed | December | 2025
6.2 | UNCT to discuss on possibility of joint funding specific RCO functions based on DCO standards. | During UNCT retreat | UNCT | This discussion was not held and is delayed for the UNCT retreat 2026. Changes in the context of UN 2.0, UN80 and the UNCT configuration may impact in the implementation of this task | delayed | December | 2025
…
Recommendation 7: Raise the human resource management issue to the attention of the DCO and all regional HR offices and initiate assessment of the human resource among UN Agencies, identify and address capability gaps. | [5 empty] | Responsible UN RC | Medium-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Rejected
If rejected or partially accepted, please provide an explanation: …… |  | Issues with RCO HR capacity have been raised and improved by now. Agencies HR is is the prerogative of each agency and is depending on project funding. However the UNCT will discuss the UNCT configuration as part of the UN CF preparation.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1
1.2
…
Recommendation 8: Request stronger support and guidance from the DCO in designing and implementing the CF. A coaching scheme could be established to guide UN Agencies in Timor-Leste through 2025 towards the new CF. | [5 empty] | Responsible Head of RCO | Medium-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | DCO is supporting through training and will continue support in 2025 | Key moments of support to be defined | DCO/RCO | DCO has also provided adhoc training and capacity based on requests of the country office. This is on top of the trainings provided throughout the year. | completed | December | 2025
…
Recommendation 9: Explore mechanism of country level pooled fund to ensure implementation of joint programmes under the new cycle of the CF’s implementation. | [5 empty] | Responsible UN RC | Medium-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Assess the feasiblity of a pooled fund | Quarter 4 of 2025 | RCO and agencies | This has been done. Three meetings have been held on this. The environment at the duty station is not conducive to pooled funds at the moment. The RCO will approach it differently next year with an advocacy and engagement campaign first. | ongoing as expected | December | 2025
…
Recommendation 10: Radically revise approach to capacity development – move away from ‘one-few day training’ and engage with long-term (weeks – months) training combining in-class and on-job training. Should be coupled with strong incentive schemes to allow absence from the job, ensure diversity of participants, access to merit-based promotion, and suchlike. A guidance note should be produced on how to approach CD and how to shape incentive schemes within UN initiatives. | [5 empty] | Responsible Heads of Agencies | Short-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | Some of the issues mentioned are not the mandate of the UNCT but are part of public function policies
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Develop generic guidance note on CD for the next CF - in particular around payments for CD events. OMT to develop guidance on payments for CD: payment of DSA, transport, payment of facilitators in a harmonized way for the whole UNCT | Quarter 2 of 2025 | OMT | This has been done. A letter of Harmonized rates for all UN agencies has been shared with Government | completed | December | 2025
…
Recommendation 11: Invest in addressing data gap in Timor-Leste by organizing assessments (including but not limited to child labour, skilled personnel attended birth, etc.). Create a list of priority assessments to be conducted by UN Agencies in 2025 and during the next CF cycle. | [5 empty] | Responsible Heads of Agencies | Long-term
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
11.1 | M&E Group to map out all asessments, surveys, studies, research to be conducted by the agencies in 2025 to assess any gaps engaging also INE and planning and asess the possiblity of undertaking these assessments or engage other development partners. Establish a system to analyze the data, provide summary information and share the documents and reports | 2025-02-01 | M&E Group | This will be continued with the new CF. | completed | December | 2025
11.2 | RCO continues working on data with UNFPA and World Bank in support to INETL | whole of 2025 | RCO | This was continuously done throughout 2025. There is a good partnership. | ongoing as expected | December | 2025
11.3 | Mapping M & E Group capacities and idenfification of capacity gaps. Regional DCO or UN agencies to provide training responding to identified gaps. | Mapping quarter 1 2025 | M&E Group |  | completed | December | 2025

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030