## Sheet1
Country Kenya; UNDAF / CF YYY1 - YYYY2 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Final Evaluation of the UNDAF 2018 June -2022 June/ 2021 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: Resident Coordinators Office and Programme management team • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: “Expand the scope of the Common Country Assessment to include comprehensive identification of socio-economic development issues by county. CCA to inform the development of UNSCDF 2022-2026 to include a comprehensive analysis disaggregation of data by county as appropriate in all sectors covered in the assessment and provide a clear baseline for SDG indicators for all counties utilizing national and county M&E systems that were improved under the UNDAF. This analysis will enable UNSCDF to craft better guidance on how the UN will work at the county level in the next UNSCDF cycle.” Priority: High Target level: UN RCO Based on conclusion 1
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The UNCT prepared a new CCA in 2021, based on the country development context and needs. It, in turn, was based on a detailed Leave No One Behind Report anchored in deep data and launched by HE President Kenyatta. The new CCA takes a more holistic multi-dimensional approach across the country development trajectory. The CCA highlights poverty, inequality especially in ASAL counties and minimal representation of women and youth in governance structures as key development challenges. The CCA has been validated with the Government and key stakeholders and has been instrumental in informing the theory of change and results framework of the next UNSCDF 2022-2026.CCA Update is a live process, with emphasis on availing disaggregated data especially at county level. The CCA will further continue to inform programming and data analysis throughout the UNSCDF implementation process, and also design and monitoring of joint programme. The joint program on data will be instrumental in strengthening capacities for availing data as required to update the CCA. | CCA done in 2021 as part of the UNSDCF design process. The CCA will be updated annually. A light review of the CCA will be done in 2023, and in consequent years of the UNSCDF | RCO will coordinate all UN entities will participate in data collection /validation analysis and compilation. UNCT and PMT will be involved in the final validation and approval under the leadership of the RC | Concept note and workplan developed | ongoing as expected | June | 2023
1.2
…
Recommendation 2: “Develop a UN-wide framework to guide alignment of UN individual agencies programming with County Integrated Development Programmes (CIDPs) to improve harmonization of UN work at county level. Since the establishment of county governments in 2013, the UN has increased its presence in counties supporting county government across all sectors covered by UNDAF outcomes. Individual agencies select priority counties using clear criteria applicable to their programmes. However, UNDAF has not evolved a framework that could guide the UN on harmonizing and maximizing its resources at the county level. Coordination of UN work at the county level has been a week, as demonstrated by the UN programming in Turkana, where One UN office was established to improve coordination, although this initiative was affected by lack of funding. Therefore, an UN-wide framework for harmonization of UN work at the county level will come at the opportune time when the UN is looking to deepen the LNOB principle and further increase its support to prioritized counties. This framework will also enhance the UN application of its comparative advantages.” Priority: High Target level: UN RCO Based on conclusion 1 and 2
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | UN Kenya is intent on deepening the LNOB principle at county level and further increasing its support to prioritized counties especially those identified by the UN LNOB analysis. With the new UNSDCF priorities and the strong LNOB lens the UNCT will develop a model “UN at devolved level” to strengthen joint UN action on county level and ensure a coordinated UN at devolved level with a particular focus on ASALs where the needs are the greatest. The UN to support and engage in the county level CIDP processes as well as in the MTPIV process. Alignment of the CIDPs to the CF is very strong across the agencies ,in addition a framework for strengthening UN systemwide coordination and implementation at the devolved level will be developed to strengthen UN agencies synergies and avoid duplication- for effective and efficient realization of results. | 2023 December | RCO will coordinate all UN entities will participate in the CIDP and MTP V process | Kenya Medium Term Plan IV under the Kenya Vision 2030 process ongoing first half of 2022, UN Kenya to engage and RCO to facilitate coordinated UN input. CIPDs to be developed end 2022 and RCO to facilitate UN Kenya engagement. Model for strengthened UN joint action under the UNSDCF at devolved level (including the linkages with the CIPDs) to be finalized fall 2022. | ongoing as expected | December | 2023
2.2
…
Recommendation 3:“UN should use the next UN Sustainable Development Cooperation Framework to re-engineer its positioning in Kenya to priorities issues, geographical and populations targeting and use of strategies that match its capacity and comparative advantages in order to maximize its value addition. UN's next SDCF cannot be business as usual. UN should develop an SCF that matches its capacity and comparative advantages to increase its relevance and maximize its value addition. Therefore, the SCF should be prioritized, based on evidence, the geographical and target population and ensure the scope of the Cooperation Framework is delivered given the UN capacity and resources. In addition, the Cooperation framework should provide clear prioritization of UN work at national and county levels.” Priority: High Target level: UN RCO Based on conclusion 1 and 3
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | The new UNSDCF has a sharper focus than the UNDAF and includes only a few but strategic priorities. Based directly on the evidence coming from our new CCA, the geographical and population targeting is also tighter, ensuring the scope of the Cooperation Framework is delivered given the UN capacity and resources. The UN will focus its work on those furthest left behind and apply a strong leave no one behind lens. In addition, the Cooperation framework will provide clear prioritization of UN work at national and county levels. The UNCT will undertake a configuration exercise for the next UNSDCF in line with the new priorities in the UNSDCF including a discussion on UN at devolved and national levels. | The UNSDCF was launched in June 202 | RCO coordinated the process of developing the new UNSDCF under the leadership of the RC an the UNCT. | UNSDCF launched | completed | June | 2022
3.2
…
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: “Develop a UNSDCF that is integrated across sectors to improve programme cohesion, maximize synergies and promote Delivering as One The UN should consider developing the next UNSDCF that allows integration across sectors such as health, WASH or Governance and devolution, among others, to improve programming cohesion and promote delivering as one. The consequence of an integrated design of UNSDCF is a reduction of outcomes. However, this should not be just a reduction of the number of outcomes but, more importantly, deepening integrated programming across sectors that address common or interrelated issues and make and scaled up real impact.” Priority: High Target level: UN RCO Based on conclusion: 4
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The new UNSCDF has adopted a more integrated approach with few and more interrelated outcomes based on the 5Ps of Agenda 2030. The new UNSDCF has 5 interrelated outcomes and each outcome in turn has two outputs and each output has four sub-outputs. This format has allowed the UN agencies to craft the outputs and sub-outputs together so that they encompass joint cross cutting priorities. On the basis of this structure a manageable set of major joint programmes to implement the UNSDCF will be developed to ensure more impact. | April 2022- June 2023 Development of joint programmes and finalization of UNSDCF. Joint programmes to be developed at the onset of the UNSDCF period. | UNRCO to coordinate the process of developing joint programmes under the leadership of the RC and UNCT . PMT to provide technical support to the UN agencies and lead agencies during development of the joint programs working with key implementing partners and Government |  | ongoing as expected | June | 2023
1.2
…
Recommendation 5: “Develop a results framework and improve UNINFO to capture and disaggregate data by counties and ensure indicators selected have clear data sources that can provide data within the UNSDCF period The UN should develop a results framework that allows disaggregation of data by county to enable the UN to assess its contribution to the outcomes in the prioritized counties while focusing on the national picture. Secondly, select indicators with data sources that will generate data within the UNSDCF period. Under the current UNDAF, a considerable number of indicators lacked data partly due to data sources that rely on surveys that are not carried out within the period of the UNDAF.” Priority: High Target level: UN RCO Based on conclusion: 5
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | UNINFO structure to be set up well at the onset of the UNSDCF. Workshops and trainings etc. to be held with all agencies (both management and technical level) to jointly co-create and determine how UNINFO will be the tool that all agencies will use for reporting of resources and activities. UNINFO to encompass all UN development activities and their funding in Kenya. All output indicators in the UNSDCF will be disaggregated further by the four LNOB groups including sex and geographical location (national, county, ASAL, urban) as far as possible. And this disaggregation will also continuously be highlighted in the narrative of each annual report. Furthermore, disaggregation by the four LNOB groups including sex and geographical location will be included as far as possible in the design and implementation of the joint programmes and also in the structure for the UNSDCF in UNINFO. Undertake an evaluability assessment of the UNSDCF results framework during the first year of implementation to ensure that the UNSDCF results framework indicators are measurable, and that data is available. This assessment may also require a revision of the UNSDCF results framework indicators at outcome and output level. | 2022 June – February 2023 | Monitoring and Evaluation technical working group |  | Ongoing as expected | June | 2023
1.2
…
Recommendation 6: Develop a monitoring framework for the UN principles of integrated programming to allow for monitoring and availability of data to assess effective application of these principles In the next UNSDCF, the UN should effectively operationalize the principles of integrated programming by strengthening the monitoring and availability of data to inform a regular review of how the principles are applied. Therefore, a monitoring framework for these principles, detailing the indicators, data sources who will be reporting, and when necessary. Priority: High Target level: UN RCO Based on conclusion: 6
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | As noted above, undertake an evaluability assessment of the UNSDCF Results framework during first year of implementation to ensure that the UNSDCF results framework indicators are measurable, and that data is available. The UNCT to develop a set of flagship joint programmes under each outcome to ensure scaled up impact with joint monitoring under the UNSDCF. Also, the design of the implementation structure of the UNSDCF is intended to both enable and request stronger collaboration through joint programmes and by linking outcomes together under each strategic priority. The UNCT will also develop a joint programme on data and a UN Kenya data strategy to systematically address the data gaps/ and enhance knowledge management. | June 2022- December 2023 | UNCT/ M&E technical working group + Data strategy group |  | ongoing as expected | June | 2023
1.2
…
Recommendation 7: “Take deliberate steps to integrate development-humanitarian-peace triple nexus in the next UNSDCF The UN should deliberately ensure the next UNSDCF integrates the development-humanitarian-peace triple nexus to improve its resilience to shocks as it emerges from the COVID-19 pandemic. This will also maximize UN resources and expertise. It is also in line with the UN comparative advantage.” Priority: High Target level: UN RCO Based on conclusion: 7
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | The focus on ASALs as one of the LNOB groups in the new UNSDCF will be an important platform to address the triple nexus, including the transformation of the refugee camps to settlements. Also, the UNSDCF will include focus on multidimensional resilience (and not only focus on natural disasters). This broader resilience agenda includes economic resilience for example and this broader scope for resilience will in turn be a preventive effort towards addressing the triple nexus. This focus on resilience in all its aspects will also maximize UN resources and expertise and is an area where UN has comparative advantage. During the review of the CCA, adopt a multi-dimensional resilience approach | June 2022 February 2023 | UNCT and respective UN agencies, PMT to provide technical support, RCO to coordinate the process |  | ongoing as expected | June | 2023
1.2
…
Recommendation 8: “Revisit and establish fit for purpose UNSDCF coordination structures that promote synergies and effectively utilize expertise within the UN As part of the repositioning of the next UNSDCF, the UN should revisit the configuration of the coordination structure to ensure these structures promote synergies and utilize members' expertise in programming. This could include reducing the number of meetings and outcome groups considering a merger of SRA and Outcome groups, among other configurations. “ Priority: Medium Target level: UN RCO Based on conclusion: 8
Management response - Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | In comparison with the UNDAF, the new UNSDCF has five outcomes. The UNSDCF implementation structure will also aim at maximizing impact as well as reducing processes and transaction costs by crafting a number of scaled up joint programmes. Outcome groups are planned to be brought together under the Strategic Priorities to ensure synergies and avoid duplication. Undertake UNCT governance/implementation and configuration exercise in line with the new UNSDCF and review current UNDAF governance and implementation structures to align to the new UNSDCF. | June 2022 When the new UNSDCF is finalized and launched | UNCT /RCO coordinated process under the leadership of the RC |  | completed | June | 2022
1.2
…
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 9: “Strengthen resilience of systems and capacities of national and county governments across all outcomes/sectors to improve sustainability of gains made. UN should prioritize strengthening the resilience of systems and communities at all levels and sectors and involve civil society and the private sector as a sustainability strategy. Communities and the private sector have a role in planning in resilience that is key for sustaining gains made across all outcomes of UNDAF, and the focus should not be only on the government systems.” Priority: Medium Target level: UN RCO Based on conclusion: 9
Management response
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by Monitored by RCO and the programme management team
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Improve alignment of UNSDCF implementation structures and coordination mechanism to GOK structures including the sector working groups. The UNSDCF has multi-dimensional resilience as one of its “SDG accelerators” and it also has a dedicated output on the same. The enabler on partnerships will further reinforce engagement with the civil society organizations. | 2023 June | UNCT /RCO coordinated process under the leadership of the RC | Alignment will focus on the new government priorities and Medium Term plan 4 | ongoing as expected | June | 2023
1.2
…
Recommendation 10:
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1
1.2
…
Recommendation 11:
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1
1.2
…

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030