United Nations Development Assistance Framework for the State of Palestine 2014-2017

Evaluation Report

February 2018

Table of Contents

Acknowledgements	i

Acronyms and Abbreviations	ii

Executive Summary	iii

1	Background	1

1.1	The UN in the State of Palestine	1

2	Objectives and Deliverables	5

2.1	Scope of the Evaluation	6

2.2	Methodology and Approach	7

2.2.1	Desk Review	7

2.2.2	Key Informant Interviews (KII)	7

2.2.3	Limitations	8

MAIN FINDINGS	9

3	Relevance	9

3.1	Design and Focus	9

3.2	International Commitments, Norms and Standards	11

3.3	Flexibility	13

3.4	Conclusion	14

4	Efficiency	16

4.1	UNDAF / UN Coordination Structures	17

4.2	Reducing Transaction Costs for Government	19

4.3	Conclusion	21

5	Effectiveness	22

5.1	Joint Resource Mobilization	22

5.2	A More Cohesive UN	23

5.3	Strategic Partnerships	24

5.4	Project Level Collaboration	25

5.5	Promotion of Human Rights and Gender Equality	26

5.6	Working with Civil Society	27

5.7	Conclusion	27

6	Sustainability	28

6.1	Contribution to National Development	28

6.2	Lessons Learned	29

6.2.1	Leadership, UNCT Engagement and RCO support	29

6.2.2	Fragmentation	30

6.2.3	Lack of Prior UNDAF Experience	30

6.2.4	National Ownership	30

6.2.5	Communication and Advocacy	31

6.3	Conclusion	31

7	Recommendations	32

Ownership	32

Monitoring the UNDAF	32

Strengthening the One UN	33

Annexes	34

Bibliography	39

List of Table and Figures

Figure 1: UNDAF Management Arrangements	4

Table 1: UNDAF Estimated Budget	4

Table 2: Breakdown of Interview Participants	8

Table 3: UNDAF Resource Mobilization 2014-2016	23

### Acknowledgements

This Evaluation could not have been completed without the assistance of a large number of people associated with the United Nations system in the State of Palestine. The evaluator would like to thank Mr. Robert Piper, the UN Resident Coordinator for sharing his insights and taking time out of his schedule to review initial drafts of the report. The UNCT in the State of Palestine commissioned this evaluation and provided invaluable support in sharing their insights and experiences, providing material for desk review and facilitating access to national partners. Special thanks go to the Resident Coordinator’s Office and Subhra Bhattacharjee for her invaluable support arranging meetings, securing documentation and logistical support without which this evaluation would not have been possible.

The evaluator would like to acknowledge the generosity of colleagues from the UN and the Palestinian Authority for taking time out of their busy schedules to discuss the UNDAF.

The evaluation was commissioned by the United Nations in the State of Palestine. However, the sole responsibility for the content of the report and opinions therein lie with the author and does not represent the views of the UN system.

Babar Sobhan

### Acronyms and Abbreviations

AIDA 	Association of International Development Agencies

AWP	Annual Work Plan

BOS	Business Operation Strategy

CAT	Convention Against Torture

CBF	Common Budgetary Framework

CAP	Consolidated Appeals Process

CCA	Common Country Assessment

CCC	Commission for Climate Change

CEDAW 	The Convention on the Elimination of All Forms of Discrimination against Women

CERD	The International Convention on the Elimination of All Forms of Racial Discrimination

CSO	Civil Society Organisation

COAR	Country Office Annual Report (UNICEF)

CPD	Country Program Document

CRC	The Convention on the Rights of the Child

CRDP	Community Resilience and Development Programme (UNDP)

CRPD	The Convention on the Rights of Persons with Disabilities

DEEP	Deprived Families Economic Empowerment Programme (UNDP)

DOCO	Development Operations Coordination Office

EA	Executing Agency

EC	European Commission

ECCD	Early Childhood Care and Development

EU	European Union

FAO	Food and Agriculture Organisation

GDP	Gross Domestic Product

PA	Government of Palestine

HCT	Humanitarian Country Team

HDI	Human Development Index

HRBA	Human Rights-Based Approach

HRP	Humanitarian Response Plan

ICPD	International Conference on Population and Development

ICCPR	International Covenant on Civil and Political Rights

ICESCR 	International Covenant on Economic, Social and Cultural Rights

ILO	International Labour Organisation

IOM	International Office of Migration

JICA	Japan International Cooperation Agency

KII	Key Informant Interview

MDG(s)	Millennium Development Goal(s)

MIC	Middle Income Country

M&E	Monitoring and Evaluation

MTR	Mid Term Review

NGO	Non-Government Organisation

OECD	Organisation of Economic Cooperation and Development

OHCHR	Office of the High Commission on Human Rights

PA	Palestinian Authority

PAPP	Programme for the Assistance of the Palestinian People (UNDP)

PNGO	Palestinian Non-Governmental Organizations Network

QCPR	Quadrennial Comprehensive Policy Review

RBM	Results-Based Management

ROAR	Results Orientated Annual Reporting

SDG	Sustainable Development Goal

TWG	Technical Working Group

TF	Task Force

UN	United Nations

UNCT	United Nations Country Team

UNDAF	United Nations Development Assistance Framework

UNDG	United Nations Development Group

UNDP	United Nations Development Programme

UNDS	United Nations Development System

UNEG	United Nations Evaluation Group

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNFPA	United Nations Population Fund

UN-Habitat	United Nations Human Settlements Programme

UNIDO	United Nations Industrial Development Organization

UNICEF 	United Nation Children Fund

UNMAS	United Nations Mine Action Service

UNMEG	United Nations Monitoring and Evaluation Group

UNPG	United Nations Programme Group

UNOCHA	United Nations Office for Coordination of Humanitarian Affairs

UNODC	United Nations Office on Drugs and Crime

UNRWA	United Nations Relief and Works Agency for Palestine Refugees in the Near East

UN Women	United Nations Entity for Gender Equality and the Empowerment of Women

UNSC	United Nations Special Coordinator

UNSCO	United Nation Special Coordinator’s Office

WB	World Bank

WFP	World Food Programme

WHO	World Health Organisation

### Executive Summary

The United Nations Development Assistance Framework (UNDAF) 2014-2017 was developed through an inclusive and participatory process under the leadership of the Palestinian Authority (PA) in close consultation with civil society and development partners. It was the first attempt at developing a common UN framework in a situation of a protracted crisis and with the final status of the occupied Palestinian territory (oPt) unresolved. Its priorities were aligned with that of the National Development Plan 2014-2016. The UNDAF was anchored in core normative principles of human rights, gender equality, environmental sustainability, and culture and development. This was translated into six main priority areas for the UNDAF

- Economic Empowerment, Livelihoods, Food Security and Decent Work

- Governance, Rule of Law, Justice and Human Rights

- Education

- Health

- Social Protection

- Urban Development, Natural Resource Management and Infrastructure

The primary focus of this evaluation is to assess how [well] the UNDAF has brought the UN system together in support of national priorities in the oPt. Thus, particular emphasis was given to examples of joint programming, operational efficiencies and other instances where the UN—defined as two or more agencies—has come together to achieve joint results.

The operational context in the oPt is defined by the Israeli occupation, which restricts the lives and agency of Palestinian people, the policy space of the Government and the ability of the international community to provide development assistance. The first UNDAF was developed and implemented in a highly uncertain and fragile environment. The first year of implementation saw a devastating escalation of hostilities in Gaza. In the aftermath of the hostilities, the UN system in the State of Palestine as well as other development partners and donors had to redirect substantial portions of their planned development resources to humanitarian aid and reconstruction of Gaza.

Key Findings

Relevance

The specific interventions being supported by the UN in the oPt remained relevant and generally contributed to the achievement of national priorities. However, it is less clear that the UNDAF itself remained a relevant document as the primary framework for the partnership between the UN and the PA. It was superseded by events and the creation of interim coordination frameworks and tools tied more directly to the on-going humanitarian work being carried out in conjunction with national partners. More regular annual reviews with national counterparts alongside a more dedicated commitment to using the UNDAF as an advocacy tool will increase its overall long-term relevance.

Efficiency

Overall, the evaluation found that the there is significant scope to build on the learning that has emerged from the implementation of the first UNDAF in the oPt. There is unexplored opportunity to achieve reductions in transaction costs both internally and externally. The differences in operational space and environment in different parts of the occupied Palestinian territory preclude reaping economies of scale and scope. But reductions in transaction costs can still be achieved within specific areas. The Area-based Strategies for Hebron and East Jerusalem that were developed to coordinate implementation on the ground can serve as prototypes. Moving forward, it is important that the UN build on the lessons of the last three years and look to further realise the efficiency gains from the UNDAF process especially given the amount of time that continues to be invested in the planning and drafting process. It is critical the UN minimize the number of internal coordination structures

Effectiveness

The UNDAF has had some notable successes in promoting a more cohesive and effective UN in the State of Palestine. The UN system has been able to leverage its comparative advantage grounded in neutrality and impartiality to help to provide critical development interventions in communities and geographic localities that are beyond the reach of the PA. The UN continues to play an important role within the overall aid coordination architecture and has increasingly engaged with common partners as one UN spanning both humanitarian and development activities (albeit not always anchored in the UNDAF itself).

The UNDAF has been particularly effective as a vehicle for the UN to fulfill its normative mandates tied to the key human and cultural rights conventions that the State of Palestine signed and ratified since 2014. The engagement with the international human rights mechanisms has been one of the most notable achievements during the current cycle and has helped to lay the foundation for the new UNDAF. At the project level, the UN has been able to develop a number of highly effective joint programmes and joint-programming modalities including the development of area based strategies that are likely to enhance UN cohesion.

Sustainability

Numerous restrictions—on movement, on access to large areas of the West Bank and the entirety of Gaza, and on the ability of Palestinians to build and develop in Area C and East Jerusalem—threaten both short and long-term prospects for human development. The capacities of the PA to act remains constrained due to limited fiscal and operational space and this makes assessing the long-term sustainability of UN programmes extremely challenging. Nonetheless, the UN remains committed to ensuring the long-term sustainability of its support even under conditions of occupation and the focus on long-term development and building resilience are critical to the success of the UNDAF. Within that context, certain programmes—e.g. the investments in state-building including training of civil servants, modernizing the legal framework, building institutions and infrastructure—are likely to be more sustainable than service provision and livelihoods interventions anchored in projects

Overall, the view was that UN agencies continue to be a valued partner to the PA. The UNCT can point to significant progress towards developing a more cohesive One UN approach to the development agenda in the oPt through the UNDAF process despite some early setbacks. The UN has found a variety of ways of coming together in support of common goals using a wide variety of joint programming approaches. This has allowed the UN to flexibly respond to opportunities to work more closely together and made the, One UN experience in the oPt more demand-driven rather than mandated. The UN has been most effective when it has leveraged its comparative advantage and convening power to focus on important gaps in the national development process—most notably around areas of policy coherence and strengthening implementation capacities at the local level—which continues to be a major challenge in the oPt.

Recommendations

The primary aim of the recommendations is to provide the UN Country Team and its national partners, in particular the PA, a set of actionable and time-bound proposals that would help to build on the considerable achievements of the 2014-2017 UNDAF process. The recommendations are broadly clustered using the evaluation criteria and were discussed and refined during a consultation between the UN and national counterparts held in January 2018. It is also acknowledged that the UNCT and partners will need to prioritize action based on time and resources but nonetheless, the recommendations have been crafted to make them achievable within the lifetime of the new UNDAF and should act as important benchmarks for measuring UN cohesion.

Ownership

- There is a crucial need to convene the UNDAF National Steering Committee on a regular basis with senior representation from the Government to provide oversight and guidance over the UNDAF process from design through implementation and evaluation.

- Given the critical importance of a strong civil society in the oPt and the vital role they will continue to play as a partner to the UN system, it is strongly suggested that the UN establish a CSO Advisory Committee to the UNDAF process. This would build on precedents in other countries and would also very much be in line with the new emphasis on partnerships as a central pillar to the achievement of Agenda 2030.

- Donors in the oPt need to support the One UN concept financially and become more open to the idea of using funding mechanisms such as the UNDAF Fund as a more effective means of channeling resources. The continued reliance on project funding modalities along with other limits on the fungibility of resources reinforce traditional ways of working and thinking and act as a limitation on the flexibility of the UN to work more effectively as One UN with national partners

Monitoring the UNDAF

- It is critical that the UNCT and PA actively monitor progress against UNDAF results in a fashion that builds on agency level reviews while at the same time informing the monitoring of progress against the National Policy Agenda.

- Furthermore, the monitoring of UNDAF results needs to be better integrated into the overall monitoring of sector results.

- UNDAF results must be anchored by a clear set of intermediate indicators that better capture the contribution of the UN to the achievement of natural priorities and are tracked properly through the life of the next UNDAF.

Strengthening the One UN

- The next UNDAF should highlight those areas where the UN will work together under each pillar using a variety of joint programme modalities. These should serve as the “flagship” intervention(s) of the UN under the UNDAF and usefully build on the identification of 20 key vulnerable groups under taken in the Common Country Assessment (CCA).

- The UN should significantly streamline its coordination architecture to minimize the number of working groups and to avoid unnecessary duplication. It is proposed that the UN engage a management consultant to review the existing coordination architecture including those for humanitarian emergencies during the rollout of the UNDAF to come up with lightest possible structure with clear term of references and accountability.

- The UNDAF Results groups should also be encouraged to set concrete and measureable targets to capture increased levels of “joint-ness” including number of joint work plans, joint meetings and so forth with common partners.

- It is critical for the UN and in particular UNCT members to raise awareness about and advocate for the UNDAF. The CCA, with its focus on the 2O most vulnerable groups, can and should be a central part of this message alongside the normative mandate and focus on human rights in the oPt.

Main Report

# Background

- The occupied Palestinian territories (oPt) is made up of the West Bank (5,655 km2 including East Jerusalem) and the Gaza Strip (365 km2, including a 40 km coastline). The total population is estimated at around 4.8 million, of which 2.9 million live in the West Bank, concentrated in urban areas and 1.9 million live in Gaza. The GDP per capita stands at US$ 1,745.9 [2015] at 2004 prices. The State of Palestine has a Human Development Index (HDI) value of 0.684 (2015)—which is the equivalent of medium human development—and ranks 114 out of 188 countries and territories. This represents an increase of 4.4 percent since 2005. Between 1990 and 2015, life expectancy at birth increased by 5.0 years, mean years of schooling increased by 1.3 years and expected years of schooling increased by 3.0 years. Lastly, GNI per capita increased by about 81.7 percent between 1990 and 2015.

- In 1967 Israel took control of the West Bank and the Gaza Strip, which have been under Jordanian and Egyptian control, respectively since 1949. The Oslo Accords are bilateral agreements signed between the Palestine Liberation Organization (PLO) and Israel from 1993 until 1999 aimed at reaching a comprehensive peace agreement. The agreements established the PA, transferred most of the Gaza Strip under its control, and divided the West Bank into three administrative divisions—Areas A, B and C. Under the Oslo framework, the PA has full civil and security control of Area A, where the majority of the West Bank’s Palestinian population lives, and civil control of Area B where the PA is also responsible for public order. Area C, in which the majority of the Israeli settlements are located, is under administrative and military control of Israel, though the PA can provide certain basic services such as health and education to Palestinians living there. This arrangement was meant to last for five years pending negotiations on a final status agreement. However, several rounds of final status negotiations held by the parties between 2000 and 2014 failed to produce such an agreement. In 2005 Israel withdrew its military and settlements from the Gaza Strip, and signed the Agreement on Movement and Access with the PA concerning the movement of people and goods to and from the Strip. In 2006 Hamas won the Palestinian legislative elections and in 2007 took control of Gaza from the PA by force. This led to a decade long political division between Gaza and the West Bank and to a further tightening of Israel’s closure policy on Gaza, as well as of movement restrictions imposed by Egypt in Rafah Crossing.

## The UN in the State of Palestine

- The UN Country Team (UNCT) in the State of Palestine is currently composed of 24 agencies, funds and programmes—FAO, ILO, OCHA, OHCHR, UNDP, UNESCO, UNFPA, UN-Habitat, UNICEF, UNMAS, UNODC, UNOPS, UNRWA, UNRoD, UNSCO, UN Volunteers, UN Women, WFP and WHO. UNIDO, UNEP, UNCTAD and ITC are considered Non-Resident Agencies (NRAs). However, only the following agencies are signatories to the 2014-2016 UNDAF: FAO, ILO, OHCHR, UN Habitat, UN Women, UNDP/PAPP, UNESCO, UNFPA, UNICEF, UNIDO UNMAS, UNODC, UNOPS, UNRWA, UNV, WFP, WHO as well as UNCTAD, UNEP, UNIDO among the NRAs.

- The Resident / Humanitarian Coordinator serves as the Deputy Special Coordinator for the Middle East Peace Process. Under the leadership of the Resident Coordinator (RC) the UNCT ensures inter-agency coordination and decision making at the country-level on issues ranging from development assistance and humanitarian operations to common/ shared facilities and services. The UNCT works closely with the Government of Palestine and other development partners to ensure that its work is aligned with the National Policy Agenda (NPA).

- The United Nations Development Assistance Framework (UNDAF) 2014-2017 was developed through an inclusive and participatory process under the leadership of the PA in close consultation with civil society and other development partners. It was the first attempt at developing a common UN framework in a situation of a protracted protection crisis and with the final status of Palestine unresolved. The UNDAF priorities were broadly aligned with the National Development Plan 2014-2016 but it is notable that the narrative and results framework did not contain explicit links to the NDP results.

- The UNDAF embodies the support to be provided by the UN agencies to the PA both collectively and individually. It provides a common framework for the UN system and its partners, and increases the focus on development results. It uses a Results Based Management (RBM) approach, in line with ongoing UN Reform efforts as well as the Paris Declaration on Aid Effectiveness (2005), Accra Agenda for Action (2008), and the follow-up agreements of the High Level Forum on Aid Effectiveness in Busan (2011). The UNDAF was anchored in the core normative principles of human rights, gender equality, environmental sustainability, and culture and development. The six main priority areas for the UNDAF were:

- Economic Empowerment, Livelihoods, Food Security and Decent Work

- Governance, Rule of Law, Justice and Human Rights

- Education

- Health

- Social Protection

- Urban Development, Natural Resource Management and Infrastructure

These six priority areas were translated into 6 UNDAF Outcomes:

- By 2016, Palestinians in the oPt benefit from greater economic empowerment, improved livelihoods, access to decent work and food security

- By 2016, Palestinians in the oPt have improved access to more efficient, accountable and participatory governance, enhanced justice and security, and greater protection of human rights

- By 2016, Palestinian children and youth in the oPt have more equitable access to and completion of quality education in an inclusive child-friendly learning environment

- By 2016, Palestinians in the oPt have improved equitable access to quality health services provided by the national health system

- By 2016, more Palestinians in oPt, especially vulnerable and marginalised groups, benefit from an integrated, multi-sectoral social protection system that promotes economic security, protection from abuse and violence, gender equality, social justice and equity for all

- By 2016, Palestinian institutions more effectively manage and regulate urban development and natural resources to ensure the equitable provision of sustainable infrastructure and to safeguard cultural heritage

- A further 28 [joint] outputs were developed to capture how UN agencies intended to contribute towards each of these outcomes. In addition to joint planning, the UNDAF formulation process resulted in the identification of a number of potential areas for joint programming to further increase coherence and effectiveness among UN agencies and participating national partners.

- The estimated financial resources required for the assistance provided through the UNDAF amounted to US$1.2 billion for the period 2014-2017. This estimate reflected the UN’s continued commitment to Palestinian development and the state-building agenda following the November 2012 General Assembly vote according Palestine non-member observer state status, as well as the UN’s efforts to transition, when possible, from humanitarian assistance (previously in the Consolidated Appeals Process or CAP) to sustainable human development. This figure was subsequently revised upwards to US$2.1bn to take into account part of the cost of the Gaza reconstruction. However, in a situation of overall declining aid flows, the balance between resources that were mobilized for mostly humanitarian work including reconstruction out-paced the funds that were available for longer-term development activities.

Table 1: UNDAF Estimated Budget

|  | Total | Core | Non-Core |
| --- | --- | --- | --- |
| Economic Empowerment, Livelihoods, Food Security and Decent Work | US$154.770 | US$65.170 | US$89.600 |
| Governance, Rule of Law, Justice and Human Rights | US$143.632 | US$41.556 | US$102.076 |
| Education | US$162.123 | US$71.206 | US$90.917 |
| Health | US$84.383 | US$16.052 | US$68.331 |
| Social Protection | US$302.122 | US$16.537 | US$285.585 |
| Urban Development, Natural Resource Management and Infrastructure | US$390.558 | US$152.515 | US$238.043 |
| Total | US$1.237.588 | US$363.036 | US$874.552 |

Figure 1: UNDAF Management Arrangements

- The operational context in the oPt is defined by the Israeli occupation, which restricts the lives and agency of Palestinian people, the policy space of the Government and the ability of the international community to provide development assistance. The policy space of the PA, and the operational space of the UN and the international community is differentiated across oPt, especially when it comes to service provision and development interventions. The nature of engagement with Israel also differs widely across Areas A, B, and C of the West Bank, East Jerusalem, and Gaza, as do the development challenges in each area. The restrictions on movement have over time ruptured Palestinian social fabric and identity. To counter this and in recognition of the integrity of the State of Palestine, the UNDAF adopted a one-Palestine approach in the planning phase.

- The first year of implementation saw the most devastating round of hostilities in Gaza since 1967. Over 2,200 people (including 1,462 civilians) were killed, over 11,200 were injured, and half a million were displaced. After the hostilities subsided, over 18,000 families (some 100,000 people) were unable to return because their homes had been destroyed or heavily damaged. Gaza's social infrastructure was heavily damaged. In the aftermath of the hostilities, the UN system in the State of Palestine as well as other development partners and donors had to redirect substantial portions of their planned development resources to humanitarian aid and reconstruction of Gaza.

# Objectives and Deliverables

- The evaluation was asked to look at the following areas in line with the UN Evaluation Group UNDAF Evaluation Guidelines:

- Assess the relevance of the UNDAF outcomes, the effectiveness and efficiency by which UNDAF outcomes and Country Programme outcomes are being achieved, their sustainability and contribution to national priorities and goals.

- Determine how the UNDAF helped UN agencies to contribute more effectively and efficiently to national development efforts and capacity building

- Draw lessons learned from experiences of the current programming cycle, and identify issues and opportunities emerging from the implementation of the current UN DAF.

Based on these considerations, the general objectives of the UNDAF Evaluation are indicated below.

- Assess the role and relevance of the UNDAF (i) in relation to the oPt’s development challenges identified by the CCA undertaken in 2013 and the Palestinian National Development Plan 2014-2016; (ii) in supporting the achievement of the Millennium Development Goals; and (iii) in supporting compliance with international treaties that the State of Palestine acceded to, and international norms and standards guiding the work of agencies of the UN system and adopted by UN member states. Key questions to address:

- Do the UNDAF outcomes address key issues, their underlying causes, and challenges identified by the CCA? Were new issues and their causes as well as challenges that arose during the UNDAF cycle adequately addressed?

- Has the UNDAF results matrix been sufficiently flexible to adjust to evolving situation on the ground during the current programme cycle?

- Have the UNDAF outcomes been relevant in terms of internationally agreed goals and commitments, norms and standards guiding the work of agencies of the UN system (including the Millennium Declaration MDGs, UN human rights treaties)?

- Assess design and focus of the UNDAF, i.e. the quality of the formulation of results at different levels, i.e. the results chain. Key questions to address:

- To what extent is the current UNDAF designed as a results-oriented, coherent and focused framework?

- Are expected outcomes realistic given the UNDAF timeframe, resources and political situation?

- To what extent and in what ways have risks and assumptions been addressed in UNDAF design?

- Assess the validity of the stated collective comparative advantage of the UN System. Key questions to address:

- To what extent and in what ways have the comparative advantages of the UN organizations been utilized in the national context (including universality, neutrality, voluntary and grant-nature of contributions, multilateralism, and the special mandates of UN agencies)?

- Assess the effectiveness of the UNDAF as a coordination and partnership framework. Key questions to address:

- To what extent and in what ways has UNDAF contributed to achieving better synergies among the programmes of UN agencies?

- Have agency-supported programmes been mutually reinforcing in helping to achieve UNDAF outcomes? Has the effectiveness or programme support by individual agencies been enhanced as a result of joint programming?

- Did UNDAF promote effective partnerships and strategic alliances around the main UNDAF outcome areas (e.g. national partners, International Financial Institutions and other external support agencies)?

- Analyse to what extent results achieved and strategies used by the supported Country Programmes and projects are sustainable (i) as a contribution to national development; and (ii) in terms of the added value of UNDAF for cooperation among individual UN agencies.

## Scope of the Evaluation

- The evaluation was structured around the four main OCED evaluation criteria—Relevance, Efficiency, Effectiveness and Sustainability—using the following standard definitions:

Relevance: The extent to which the objectives of the UNDAF are consistent with country needs, national priorities and the country's international and regional commitments, including on human rights. This potentially encompasses both the design of the UNDAF and its ability to accommodate new and emerging challenges over its lifetime.

Efficiency: The extent to which the UNDAF has promoted greater synergies, reduced duplication between UN agencies and reduced transaction costs for the Government. This would aim to provide a measure of how economically resources / inputs—funds, expertise, time, and so forth—are converted to results.

Effectiveness: The extent to which the UNDAF's objectives have been achieved, compared to the overall purpose. In evaluating effectiveness, it is useful to consider: 1) if the planning activities were coherent with the overall objectives and purpose; 2) the analysis of principal factors influencing the achievement or non-achievement of the objectives.

Sustainability: Sustainability is defined as the extent to which the benefits from a development intervention have continued or are likely to continue, after it has been completed.

- The primary focus of the evaluation is on how [well] the UNDAF has brought the UN system together in support of national priorities. It is taken as a given that the work of individual agencies respond to specific national or sector needs in the oPt and that for the large part, this support continues to be valuable, relevant and contribute (broadly) to the achievement of UNDAF outcomes. Thus, particular emphasis was given to examples of joint programming, operational efficiencies and other instances where the UN—defined as two or more agencies—have worked collaboratively.

## Methodology and Approach

- The Evaluation was conducted in compliance with United Nations Quadrennial Comprehensive Policy Review (QCPR) and UNDAF guidelines including the Standard Operating Procedures (SOPs) for “Delivering as One” countries. The Terms of Reference (TOR) for the Evaluation specifies a period of 25 days for data collection, report writing and presentation of feedback to national stakeholders. In conducting the Evaluation, the following principles were followed:

- Impartiality: The same questions have been asked to all stakeholders.

- Independence: The evaluator has never worked in the oPt.

- Confidentiality: All information was collected with the understanding of complete confidentiality.

- Inclusivity: Given the scope of the evaluation, it was not possible to reach out to direct beneficiaries of UN programmes in the oPt.

- The critical inputs to the Evaluation included a desk review of key reports, evaluations, studies and other programme monitoring information from UNCT members, interviews with key UN and national stakeholders. The preliminary findings were shared in draft form prior to the finalization of the report. The following section will briefly expand on each of the three approaches.

### Desk Review

- The evaluation drew upon existing documentation and reports to build the evidence base for the review. This included reports such as the RC Report(s) that are submitted to DOCO on an annual basis along side the relevant agency level reports. This included meeting minutes from key UNDAF oversight (UNCT) and operational (outcome groups) bodies as well as inter-agency bodies such as the M&E Group and Gender Thematic Working Group. The evaluation also drew upon the findings of agency programme and project evaluations that were conducted during the life of the UNDAF.

### Key Informant Interviews (KII)

- Semi-structured interviews were conducted with senior national counterparts who could speak knowledgably about the UNDAF and the work of the UN in the oPt. Priority was given to line ministries that work directly with one or more UN agencies at an operational level. An interview was also conducted with the Head of the Policy Reform Unit of the Prime Minister’s Office to speak to the "strategic" positioning of the UN in Palestine and in particular the degree to which the UNDAF (and supporting programmes) was aligned and supportive of national priorities.

- Ultimately, approximately 102 interviews were conducted with the Resident Coordinator, UN Heads of Agencies, UN Technical Staff and a select number of PA officials, and with national and international NGOs including via skype and group format. The following semi-structured questions were used to guide the KIIs.

- How has the UNDAF helped to provide strategic focus to the work of the UN system in support of national priorities?

- Do you feel that the UN is now working more effectively with Government and in coordination with other donors in the country?

- Do you think that the UN system has aligned itself well against national priorities and can you point to examples of greater cooperation / partnership within the UN in support of these priorities?

- To what extent has the UN system demonstrated a willingness to use national systems—including aid coordination mechanisms and national statistical systems—in their work?

Table 2: Breakdown of Interview Participants

|  | KIIs |
| --- | --- |
| UN | 37 (16) |
| PA | 17 (6) |
| National NGOs | 33 |
| International NGOs | 15 (5) |
| TOTAL | 102 |

### Limitations

- The consultant was only able to spend 10 working days in the oPT for data collection and was therefore not able to meet with a full range of partners in the oPt.

- There has been significant turnover both within the UN and in Government since the UNDAF was signed and many of those interviewed have had only limited engagement with UNDAF processes or lacked the historical perspective to comment in depth.

- The evaluation was limited to one round of interview with key informants so the opinions noted in the report should not be over generalized.

- It was not possible to customize and administer an online survey that would have provided another data point for the evaluation.

# MAIN FINDINGS

- This section of the report is structured around the four main areas of assessment—Relevance, Efficiency, Effectiveness and Sustainability—and is broken down into sub-questions that were part of the TOR.

# Relevance

The extent to which the objectives of the UNDAF are consistent with country needs, national priorities and the country's international and regional commitments, including on human rights.

- This section will assess the overall relevance of the UNDAF in two distinct time frames—the design phase and the implementation phase. The section also tries to assess the degree to which the UNDAF engendered a more strategic UN response to national development challenges and has helped to highlight the normative principles and commitments to Human Rights and Gender Equality that are at the heart of the UNDAF process. It is important to note that relevance is not a static concept especially in the context of national planning and by extension, the UNDAF. This is particularly true considering that a protracted crisis has characterized the development landscape in the oPt since the launch of the UNDAF in 2014.

## Design and Focus

Do the UNDAF outcomes address key issues, their underlying causes, and challenges identified by the CCA?

- The original decision to develop an UNDAF was in part a reflection of the aspirations of the Palestinian people and the optimism of the donor community following the recognition of Palestine as a non-member state of the United Nations, and the expectation that this would lay the ground for a more long-term development strategy. However, achievements in state-building have not led to increased autonomy of the Palestinian state and earlier gains appear to be eroding. This in turn has undermined many of the original aspirations of the UNDAF. The escalation of hostilities in Gaza in 2014 further weakened the UNDAF by shifting attention and resources away from development to humanitarian support.

- The design of the 2014-2017 UNDAF was in line with the 2010 UNDAF Guidelines. The UN conducted a CCA in 2013 and explicitly aligned the UNDAF to the national planning cycle and sector plans. The six UNDAF outcomes (and to a lesser extent the supporting outputs) can be linked to critical components of the last national development plan. The UNDAF priority areas also accommodated the different mandates (and priorities) of the individual agencies but did not necessarily articulate the comparative advantage of the UN system as a whole in the oPt.

- The outcomes, though time-bound to the four years of the UNDAF cycle, were framed to capture general progress across a range of different sectors and were broad enough to accommodate a wide variety of projects and programmes. The accompanying narrative drew from the relevant analysis in the CCA to build the case for how the UNDAF programmes would address important bottlenecks to help achieve national priorities, albeit in quite general terms.

- The UNDAF results themselves were pitched too broadly—i.e. essentially restatements of national-level goals—and therefore, did not capture the specific contribution(s) of the UN to the achievement of national goals and priorities. Furthermore, while baselines were developed for all six outcomes, they lacked targets against which to measure progress. At the output level, there is a clearer articulation of the type of interventions being proposed by the different agencies. These included a broad mix of policy support, capacity development / technical assistance and community engagement through local NGOs (with the exception of UNRWA which provides a range of direct services to refugees in the West Bank and Gaza). This would be typical for the UN in a middle-income country, though given the unique circumstances in the oPt perhaps with a greater emphasis on direct implementation than would be the norm. Output level targets mostly capture process indicators and do not always measure improvements in capacities—i.e. the result of a particular UN intervention.

- Annex C of the UNDAF attempted to capture the specific contributions of each agency per outcome but the level of detail was insufficient to provide a real sense of how these would collectively lead to the achievement of outcomes [as opposed to being an agglomeration of related interventions]. Overall it appears that the UNDAF was used as a collaborative planning tool across all of oPt and the area-based strategies developed later became the main instrument for harmonizing approaches and interventions of agencies in specific areas given the significant differences in operating space and rules of engagement in different areas of the country.

- In the case of Health and Education and to a lesser extent, Social Protection, there is a greater degree of coherence within the priority area with a clear focus on strengthening the overall policy framework while also developing the capacities of service providers such as teachers and healthcare workers with a particular focus on marginalized and vulnerable communities. Attempts have also been to disaggregate data to capture the differences between the West Bank and Gaza though not always by sex. However, it is important to note that this cohesion builds on a very clearly articulated and understood global division of labour between WHO, UNICEF and UNFPA in the health sector and between UNICEF, UNESCO and to a lesser extent, ILO in the education sector.

- It is also worth noting that while most of the individual interventions broadly “fit” together vertically under each priority area, the horizontal integration across UNDAF—i.e. how the six priority areas mutually reinforce one another—does not come across very strongly. This potentially supports the notion of a UN that still operates in discrete silos. However, one could argue that the horizontal integration is perhaps better captured in the area strategies that were subsequently developed within the broader framework of the UNDAF.

- Overall, the consensus among national partners was that the projects and programmes being supported by the UN were well aligned with national plans and strategies. There was a general agreement that the UN has played an important role in helping to connect the State of Palestine to international best practices and learning, and the UN continued to be valued and close partner. There continues to be strong appreciation for the normative role played by UN agencies especially in relation to engagement with the international human rights system. However, the fact that UN agencies do not provide direct budget support to line ministries (unlike many other bilateral and multilateral donors) was noted as a constraint given the difficulties the PA faces meeting day to day operational expenses. This has led some ministries to take on board intervention from donors (including the UN) not directly linked to their own priorities mostly to be able to secure resources and thus lacking the full commitment when it came to actual implementation.

- Ultimately, UNDAF was viewed by PA line ministries as a UN plan / requirement rather than a shared commitment with the Government of Palestine on how the UN will support national development priorities. The evaluation found limited evidence to suggest strong national ownership in the UNDAF including difficulties convening a National Steering Committee with high level PA engagement to provide strategic oversight and guidance. A number of respondents [including senior PA officials] further observed that the UNDAF was still not being used as means of monitoring the UN’s performance, which reduced its overall utility. The failure to hold regular annual UNDAF review meetings with external partners in particular was seen as one of the weakness of the UNDAF exercise. As noted previously, one of the major gaps in the UNDAF was the weak links to NDP results. Part of this can be attributed to gaps in the national planning and monitoring frameworks that made it difficult to meaningfully align the achievement of UNDAF results with national monitoring processes.

## International Commitments, Norms and Standards

Have the UNDAF outcomes been relevant in terms of internationally agreed goals and commitments, norms and standards guiding the work of agencies of the UN system (including the Millennium Declaration (MDGs), and UN human rights treaties).

- At the time of the development of the UNDAF in 2012, the State of Palestine was not a party to any of the major Human Rights conventions that would normally provide important entry points for the UN (in particular, those agencies with specific mandate tied to conventions such as the CRC and CEDAW). However, by virtue of its history and engagement with the international system, there is a high degree of human rights literacy in the oPt. This is captured by both the CCA and the UNDAF, which both attempt to frame the analysis in terms of the rights and obligations of duty bearers and rights holders. Again, the context of the occupation cannot be overlooked especially in its impact on the ability of the PA to meet many of the most basic obligations to its citizens. More important (and this is addressed later in the report), the State of Palestine subsequently signed seven major Human Rights conventions on April 2, 2014 and one of the optional protocols relating to children in armed conflict.

- Following its recognition by UNESCO as full-fledged State Member in 2011 and 2012 the State of Palestine also ratified a number of conventions related to cultural integrity. The access to and ratification of these conventions by Palestine framed the architecture of UNESCO’s support under the UNDAF under priority areas related to Governance, Rule of Law, Justice and Human Rights and Urban Development, Natural Resource Management and Infrastructure.

- The narrative makes it clear that the human rights based approach is one of the core normative principles that guided the design of the UNDAF. The CCA and UNDAF both highlight the issue of vulnerability and the violations of a range of human rights linked to the occupation. However, the focus on marginalized groups does not carry through that strongly into the results matrix even at the output level. Most of the results are framed in more general terms and reference the “Palestinian people” as opposed to a particular vulnerable groups (though in the case of the social development priority areas of health, education and social protection, there was an attempt to focus one of the outputs on vulnerable groups (broadly defined or to be defined later). This, however, can at least partially be attributed to the unique situation of oPt where the ability of the PA and its partners to meet their obligations to citizens remain severely constrained by the occupation and where the UN is also invested in helping the PA to put in place the basic structures of self-government and public administration.

- However, the human rights focus became clearer during actual implementation with the majority of projects under the economic development pillar—Deprived Families Economic Empowerment Porgramme (DEEP) and Community Resilience and Disaster Programme (CRDP) as well as the smaller projects focused on enabling disabled youth to access job markets—targeting marginalized communities. Similarly, under the governance pillar, the activities around gender based violence and legal aid clinics were all focused on highly vulnerable groups. The HRBA was mainstreamed as part of the ‘One UN’ Approach to Spatial Planning in “Area C” of the occupied West Bank adopted by the UNCT in 2015 to ensure ‘do no harm’ principles.  However, the UNCT has yet to take the next step of developing a formal joint programme in Area C focusing on a cross-sectoral approach to development.

- The UNDAF is explicit in its decision to mainstream gender throughout all the results areas having initially discussed the option of a stand-alone gender outcome to reflect the disproportionate burdens borne by women in the oPtin a range of areas. The CCA and UNDAF narrative both highlight women as a specific vulnerable group to be targeted in all the priority areas. However, the UNDAF is less successful when it comes to translating this commitment into concrete and measureable results. Only one out of the five outcome statements makes a reference to women and only 3 out of 28 outputs reference women or gender equality and even then only in the broadest terms. There is some attempt to highlight the importance of sex-disaggregated data in the monitoring framework but this is uneven.

- The UNCT conducted a gender scorecard exercise in December 2014 that made the following observations “The results reveal that the UNCT State of Palestine approaches or meets the minimum standards for gender mainstreaming processes in the areas of planning, programming and quality control and accountability. The team scored below the minimum standards, but on par with global results in partnerships and monitoring and evaluation. The weakest three areas scored low against the minimum standards as well as the global averages: UNCT capacities, budgeting, and decision-making. “ While the Gender Scorecard exercise was subsequently shared with the UNCT, it did not result in adjustments to the current UNDAF. However, it should be noted, however, that this experience informed the design and roll out of the new UNDAF 2018-22 which was based on a country analysis with an explicit focus on vulnerability.

## Flexibility

Has the UNDAF results matrix been sufficiently flexible to adjust to evolving situation on the ground during the current programme cycle? Were new issues and their causes as well as challenges adequately addressed?

- The UNDAF is considered a living document able to adjust to changing circumstances and information. However, global experience suggests that UNCTs often struggle to live up to this expectation and UNDAFs are rarely adjusted mid-cycle. In light of this experience and the specific circumstances in the oPt, it is perhaps not surprising that the UNDAF has not undergone a significant adjustment during its lifetime

- The UNDAF became less important in Gaza once the focus shifted to the Humanitarian Response Plan and to the reconstruction efforts that also, inter alia, required the creation of a separate set of coordination arrangement around the recovery and reconstruction efforts. This included working within the limitations imposed on the importation of dual-use goods for the rebuilding efforts. Again, given the broad framing of the UNDAF results and the early realisation that interventions under the same programme often had very different implementing approaches [and challenges], aspects of the Gaza reconstruction work were real time adjustments to the UNDAF. Efforts were made to capture the impact of the Gaza reconstruction during the first annual review but the specific details only became available once the needs assessment took place.

- The UN conducted an internal Annual Review in 2015 that included a dissemination workshop with external partners. However, it is not clear that the review resulted in significant revisions to the UNDAF, either in terms of its overall thrust or even at the level of outputs and activities. In the case of the latter, these adjustments were [likely] made and reflected in the annual work plans between agencies and line ministry partners, ensuring that the UN and its work continues to be relevant to the development needs of the oPtT.

- However, while the UNDAF itself did not undergo a formal revision over the course of the cycle, UNCT deserves recognition for how much joint work was achieved under very difficult circumstances. The first example of a need-based adjustment was the decision by the UNCT to develop a joint UN strategy for Hebron following consultations with the Governor of Hebron and other national counterparts, including civil society. The strategy includes a programmatic framework and approximately 40% of the projects were joint UN initiatives with two or more agencies coming together. The majority of interventions focused on the economic and basic social service needs of the residents of Hebron and approximately 30% of the projects were specifically tailored to focus on children, youth and women. Subsequently, the UNCT has developed fourteen comprehensive project proposals, out of which nine were joint concept notes.

- Separately, the UNCT developed an engagement strategy to deal with the deteriorating situation in East Jerusalem through the DPA-Chaired Inter-Agency Task Force for the oPt, as part of the UN’s efforts to ensure greater coherence between the political, human rights, humanitarian and developmental work of the UN in East Jerusalem. The strategy lays out the 10 key challenges facing Palestinian residents in Jerusalem, and the operating principles and approach for UN programming in East Jerusalem. Coordination with UN and non-UN actors is also articulated as well as the UN’s comparative advantage in operating in East Jerusalem. An interagency Task Force was set up to work on the operationalization of the strategy, including conducting a mapping exercise of all recent and ongoing UN programmes in East Jerusalem, as well as development of a policy paper on UN engagement with Israeli authorities.

## Conclusion

- Overall, the evaluation found that the UN system in the State of Palestine continues to be a trusted and valued partner and specific interventions being supported by the UN remain relevant and appreciated. However, the extent to which the UNDAF itself continues to the primary framework for the partnership between the UN and the PA is less clear. It has been largely superseded by events and the creation of interim coordination frameworks and tools tied to the on-going work being carried out in conjunction with national partners. Furthermore, funds nominally earmarked for development purposes were diverted to the emergency at a time when other regional conflicts and natural disasters were competing for an already shrinking pot of donor resources in the oPt.

- A robust annual review is critical if the UNDAF is to remain an active and relevant document both internally and externally. More important, the UNCT should aim to link the monitoring of agency programmes with the UNDAF monitoring cycle rather than seeing these as discrete / different exercises. Concerns about double reporting are best addressed during the first year of the UNDAF under the auspices of the M&E Group. The individual results groups should conduct a mapping exercise that links the agency-level indicator frameworks (and systems) to the UNDAF results matrix and corresponding indicators. This would help to build the case for how individual programme results contribute to overall UN results rather than approaching the UNDAF review as a year on year exercise requiring [effectively] stand-alone data collection.

# Efficiency

- Within the context of an evaluation that is trying to assess the degree of UN cohesion, the main guiding question was the extent to which the UNDAF has promoted greater synergies, reduced duplication between UN agencies and reduced transaction costs for national counterparts. With that in mind this section will attempt to assess the extent to which UNDAF processes specifically and the UN system more generally has achieved this goal.

- Even though the State of Palestine is not considered a DaO country, in deciding to develop the first UNDAF, the UNCT made a commitment to working together more cohesively on the development agenda (albeit under a unique set of constraints). The UNDG does not yet require UN agencies to set specific metrics for measuring cohesion and UNCTs have been given considerable latitude to define the appropriate level of “joint-ness” and what would be considered optimal in one context may well be unfeasible in another.

- The common consensus within the UN was that the process for developing the UNDAF was extremely time-consuming and at times, a difficult exercise given the very particular circumstances in the oPt. However, the consultation processes and the overall facilitation role played by the RCO to bring the UNCT together around the development agenda was seen as valuable and served to bring more cohesion to the UN’s work.

- Compared to many other countries, the UN in State of Palestine can point to an impressive number of examples of joint work. Part of this can be attributed to the very specific circumstances in the oPt including the different operating environments and development challenges and the need to develop a variety of strategies tied to the different degrees of access and permissions granted to the UN and the PA. The other major contributory factor was the strong leadership provided by the Resident Coordinator’s) and UNCT and the critical support of the RCO team and its willingness to fill gaps in order to move the UNDAF forward.

## UNDAF / UN Coordination Structures

Is the current approach to UNDAF management and implementation leading to operational synergies and optimization of resources?

- The UNDAF 2014-2017 envisaged a relatively light coordination structure with three thematic groups and six results groups chaired by a convening agency acting as the main forum for coordination at the outcome level. The Groups were composed of senior programme staff from participating UN agencies and were responsible for identifying joint programming opportunities, monitoring and engagement with non-UN actors, including representatives of line ministries, civil society and the donor community in their discussions and activities. Theme Groups operated under the guidance of the UN Deputies Group supported by UNSCO/RC Office and with a direct reporting line to the UNCT. It should be noted that this coordination architecture stands alongside a similar set of arrangements on the humanitarian side and the local aid coordination structure.

- The results groups served as a forum for information sharing and coordination though participation rates were generally uneven. This latter point can be traced in part to the fact that many agencies, in particular specialized and technical agencies, lack the personnel to fully participate in the range of UNDAF coordination structures alongside their regular responsibilities.

- In the first year of the UNDAF, the groups took the lead on developing a large number of joint funding proposals to help meet the very ambitious resource mobilization targets set for the UNDAF. The proposals specifically targeted donors from the Gulf region. It also aimed to raise awareness about the UNDAF Fund as the main vehicle for funding interventions under UNDAF and to highlight the UN’s commitment to joint work. Unfortunately, very few of the projects developed in 2014 were able secure sufficient funding to begin operations. However, it was generally noted that the exercise of thinking about working collectively (if not the actual number of proposals developed) helped to bring out a stronger understanding of where there were further opportunities for collaboration. The exercise also helped to lessen the perception of a UN that is in competition with itself. In a scenario where the funds available for development work in the oPt continue to shrink, UN agencies will need to develop a much more coordinated approach to resource mobilization.

- Despite this there were other examples of the UN coming together to work more collaboratively during implementation. As noted earlier, both the Hebron and East Jerusalem area strategies were notable attempts for the UN to develop a more cohesive approach to implementation. The strategies have not yet evolved into full fledged joint work plans [as is the expectation under an UNDAF] but the UN has been able to adopt a harmonized approach to working with local government counterparts. Similarly, the UNCT has also developed a coordination structure to oversee the Gaza reconstruction which is another example of good UN collaboration. The evaluation also found numerous cases of two or more UN agencies working together very effectively in response to emerging opportunities.

- Of the three thematic groups developed to support the UNDAF, the M&E Group co-chaired by the RCO and the Youth Theme Group have proven to be more effective vehicles for UN coordination. In the case of the former, the group has tried to develop a more systematic approach to tracking progress against the UNDAF indicators and overseeing the annual reporting process and has taken the lead in overseeing the evaluation. As noted previously, there is a disconnect between the monitoring processes of the individual agencies and the UNDAF processes and the M&E group is well placed to develop a common approach to tracking progress more systematically over the life of the new UNDAF.

- The Youth Theme Group coordinated inter-agency activities and programming for youth and was cited as a good example of UN cohesion around a common theme. The cohesion was driven in part by the strong leadership provided by UNFPA but also by the decision to focus on developing a UN Youth Strategy and the joint UNFPA-UNICEF collaboration on a detailed study on the status of “Youth in Palestine 2017”. In contrast, the Gender Theme Group had more difficulties in its efforts to work with agencies on gender mainstreaming and has found it difficult to quantify progress. However, the experience has helped to inform the design of the new UNDAF where the UN has agreed to include a dedicated outcome (2.4) that looks specifically at the issue of gender equality along with a renewed efforts to mainstream gender fully in the new CCA and UNDAF.

- This experience would suggest that there is scope for the UN to rethink its approach to coordination and the UNDAF process that better reflects the multiple demands being made on the limited time and resources of the UN in State of Palestine. In particular, the UN needs to be able to respond flexibly to emerging opportunities and challenges that will often not lend themselves to a highly structured set of tools. The UN groups functioned best when they were assigned a specific [time-bound] task—e.g. the development of the new CCA—or when asked to think about spatial convergence that came about from the conditions on the ground. This would call for a coordination structure that can better capture the multitude of ad hoc arrangements that characterize UN coordination in State of Palestine. Some of this would merit further codification along the lines of the area-based planning exercises. But other forms of cooperation will likely emerge more organically and the UNDAF processes need to do a better job of capturing this cooperation within its monitoring framework and with partners.

## Reducing Transaction Costs for Government

To what extent and in what way has the UNDAF contributed to a reduction of transaction costs for the government and for each of the UN agencies? In what ways could transaction costs be further reduced?

- The other main aim of UN reform is to reduce the overall transaction costs of doing business with the UN for national counterparts that may often be ill-equipped to deal with the demands of 20+ UN agencies. The UNDAF is supposed to provide conceptual focus to the work of the UN under a select number of strategic areas [priorities] while also realizing operational efficiencies for national partners. It presumes a situation where common country programming tools gradually replace the individual programme documents and work plans of individual agencies. It also presumes a situation where the work of national governments are similarly moving away from a sector-based approach towards a more integrated approach to national development planning [including, the presumption of full national control of all aspects of economic and national policies].

- Globally, the UN system remains far away from the original ambitions of the UN Reform process when it was launched in the late 1990s and the recent report from the UN SG once again underlined the difficulties of achieving genuine harmonization when each agency remains ultimately beholden to its executive boards and corporate strategic plans (the SDG agenda not withstanding). More important, in the specific context of the oPt, the UN is attempting to work with national counterparts and a national administrative system that faces severe financial and capacity constraints in trying to fully meet its responsibilities and obligations to its citizens.

- It may well be premature to expect that this first attempt at UN cohesion will have realized significant efficiency gains especially given the relatively short time span (four years) of the current UNDAF and the highly challenging external environment. However, the evaluation found that there was room for improvement that would build on the current experiences with joint work under the UNDAF at both the project level and with common partners.

- There is scope for the UN agencies to further explore the possibility of developing joint work plans and reports when working with the same line ministry [outside the specific joint programmes]. The need to provide multiple reports to donors was also cited by local NGOs as a major concern and is an area where the UN could take a more proactive role in advocating for the use of common / standard reports tied to capacity support to strengthen the overall quality of reporting. For the moment, there appears to be only limited awareness within government that the different strategic priority areas (and sub-groups) in the UNDAF represent an articulation of a common UN approach to a key national development challenge. The overall perception [among those interviewed] continues to be of an UN system that prefers to work bilaterally rather than as one UN.

- However, it was also noted that many of the line ministries also share responsibility for the continued silo approach, and anecdotal evidence suggests that communication even among departments within the same ministry is often a problem. Absent a strong demand for a more UN coherent approach on the part of counterparts, it is less surprising that agencies have continued to work through the traditional tools and partnerships that have served them so well to date.

Implementation of HACT

Participating UN agencies have taken important steps towards the introduction of the Harmonized Approach to Cash Transfers (HACT) which is a UN system wide goal aimed at certifying the financial systems of different Implementing Partners (IPs) [though a series of micro-assessments] which then allows UN agencies to channel funding directly via a standardized Funding and Authorization and Certificate of Expenditure (FACE) form. The UN in the State of Palestine has established an HACT working group in 2014 and has been meeting regularly to review progress. A consultant was hired to oversee the implementation of HACT and both UNICEF and UNDP have conducted a large number of assessments of local IPs.

UNFPA has been able to channel funds to the Ministry of Health in Ramallah and have recruited a coordinator assigned to work on Gaza related financial matters. and oversee the implementation activities. A consolidated FACE form for Gaza is processed through Ramallah. Both UNICEF and UNDP are now exploring using a similar approach with government counterparts.

As part of the on-going public administration reform process, a number of ministries have put in place policy and development cooperation units to track progress against sector plans and to better coordinate partners. Further efforts should be made to use these bodies as a means of engagement around the shared UNDAF vision with less emphasis on individual agency mandates and priorities.

- The utility of the UNDAF as a coordinating framework was further hampered by effective lack of an institutional home within the government due to an internal reorganisation within the PA. In the run up to the development of the UNDAF, this nodal function was carried out by the Ministry of Planning and Development that was subsequently folded into the Ministry of Finance which became the Ministry of Finance and Planning (MOFP). Unfortunately, the MoFP has been less engaged in development coordination including the UNDAF. Subsequently the Policy Reform Unit in the PMO took the lead in development coordination with donors and the formulation of the NPA 2017-2022.

- The lack of an overall nodal ministry for national planning process and the fact the PA does not yet have a monitoring and evaluation framework for its own national development plans (though four ministries are attempting to do so under the new NPA) resulted in no one  actively monitoring progress against the UNDAF itself. For the most part, monitoring takes place against the respective agency work plans in conjunction with sectoral reviews. The lack of a strong national planning and monitoring framework against which the UNDAF can be aligned and evaluated further limited its overall usefulness.

## Conclusion

- Overall, the evaluation found that the there is significant scope to build on the learning that has emerged from the implementation of the first UNDAF in the State of Palestine. There is unexplored opportunity to achieve reductions in transaction costs both internally and externally. Part of this can be simply attributed to an overall lack of familiarity with UNDAF processes and the longer-term developmental timelines on the part of both the PA and UN.

- The different operating environments in Area C, East Jerusalem and Gaza preclude reaping some of the economies of scale and scope that are available in traditional development contexts, however, within each area, the UN system can reduce transactions costs both internally and externally. The internal structures of the PA do not always lend themselves to realizing operational efficiencies, but there is recognition on all sides that this will continue to be an integral part of the on-going public administration reform process. The PMO has taken significant steps to enhance within-PA coordination in recent years. An ongoing reform of the local aid coordination structure may also create new opportunities for better coordination that the UN system will do well to leverage, especially by working with non-state actors, who are not part of the consultations and policy-making processes of the local aid coordination structures in the oPt.

- Moving forward, it is important that the UN build on the lessons of the last four years and look to further realise the efficiency gains from the UNDAF process especially given the amount of time that continues to be invested in the planning and drafting process. As noted previously, it is critical the UN minimize the number of internal coordination structures including potentially moving to online meetings rather than face to face discussions that can prove difficult to coordinate given the disparate locations of UN offices. On the monitoring front, further thought needs to be given on how to track the UNDAF that would reduce the overall number of indicators and link these more systematically to agencies results. This would include continuing to track disaggregated indicators for the West Bank and Gaza and would allow for a clearer link between humanitarian and development interventions.

- However, it is perhaps more important that the UN start following through on some of the initial steps towards reducing the transaction costs of doing business with the UN. This should include further roll out of the HACT and in particular its expansion to line ministries. As noted previously, the UNCT should aim to start consolidating its work with common partners through the gradual adoption of joint work plans and with development partners through a more integrated approach to engagement with the LACS sector (and thematic) working groups. There is also scope for the UN system collectively to review its engagement with local NGOs, many of whom noted that the reporting and audit requirements for working as a sub-contractor to the UN were particularly onerous and often took time away from direct implementation.

# Effectiveness

- The evaluation was asked to assess the extent to which the UNDAF's objectives have been achieved, compared to the overall purpose. In evaluating effectiveness, it is useful to consider: 1) if the planning activities were coherent with the overall objectives and purpose; 2) the analysis of principal factors influencing the achievement or non-achievement of the objectives.

- The Evaluation was provided with a large number of agency evaluation documents which indicate that most of the projects being supported by the UN would be considered effective in that they were seen to respond to a specific need usually in a timely fashion. The UN can point to notable successes providing a range of different services to communities in the West Bank and Gaza. The CRDP programme is recognized as having placed Area C and East Jerusalem on the political and development map, and raised awareness regarding the urgency of addressing the development issues both with the PA and the international donor community.

## Joint Resource Mobilization

- It is fair to say that one of the biggest limitations on the full achievement of the UNDAF was its lack of success as a resource mobilization vehicle. Perhaps buoyed by the optimism that led to the decision to develop an UNDAF in the first place, the original financial envelope for the UNDAF was projected at around US$1.2 billion over three years of which just under 30% would come from core resources. Priority areas 1,3 and 6 had secured approximately 40% resources at the time of signing but the main outlier was the social protection priority area which was only 5% funded but had the second largest budget after priority area 6 that covered urban development and infrastructure among others. However, by end-2016, the total resources mobilized (core and non-core) came to approximately US$512m, which represented an overall shortfall of around 59%. Of more concern, however, was that the UN was only able to mobilize around US$150m over the course of the UNDAF which was well short of the approximately US$800m that was supposed to be mobilized over the cycle. The performance varied depending on the priority area with health and education being the most successful and social protection being the area where there was the least success. This was coupled with reluctance among donors to utilize the Palestinian UNDAF Fund as a means of providing un-earmarked funds to the UN in support of UNDAF priorities and a continued use of project funding modalities had a significant negative impact on the overall effectiveness of the UNDAF.

Table 3: UNDAF Resource Mobilization 2014-2016

|  | Budget | Actual | % | Non-core |
| --- | --- | --- | --- | --- |
| Priority Area 1 | $154,770,000 | $68,883,956 | 45% | $3,713,956 |
| Priority Area 2 | $143,632,000 | $68,059,158 | 47% | $26,503,158 |
| Priority Area 3 | $162,123,000 | $93,415,305 | 58% | $22,209,305 |
| Priority Area 4 | $84,383,000 | $58,744,481 | 70% | $42,692,481 |
| Priority Area 5 | $302,122,000 | $31,233,868 | 10% | $14,696,868 |
| Priority Area 6 | $390,558,000 | $192,498,199 | 49% | $39,983,199 |
| Total | $1,237,588,000 | $512,834,967 | 41% | $149,798,967 |

- One of the major challenges that the UNDAF faced has been the continued reliance on project-based resource mobilization. Most UN agencies have very limited core resources available for programming purposes in Palestine . This has resulted in a very fragmented approach to resource mobilization that has seen the focus on mobilizing resources for individual projects almost on a case-by-case basis. Even in the instances where the UN adopted a multi-year programming framework, it was rare for funding to be secured for the full three years. This challenge is exacerbated by the fact that the primary donors to the UN in Palestine either have restrictions on the use / fungibility of resources or to the preference for project-based funding rather than from a tradition of investing in long-term development. This need to respect the inherent “indivisibility” of development programmes and to fund the UN (as opposed to individual agencies) accordingly remains one of the biggest obstacles to the achievement of the UNDAF.

## A More Cohesive UN

To what extent and in what ways has UNDAF contributed to achieving better synergies among the programmes of UN agencies? Have agency-supported programmes been mutually reinforcing in helping to achieve UNDAF outcomes?

- The evaluation found a growing number of examples where the UN has begun to work together more effectively over the course of the UNDAF cycle. Some of these interventions can be said to have grown out of the UNDAF itself including a number of specific joint programmes, but many have happened more organically based on opportunities that emerged based on happenstance rather than design. Some examples, such as the UNICEF-WFP partnership around the e-voucher scheme grew out of the humanitarian response but has gradually begun to evolve to have a more long-term developmental focus as part of an emerging nexus between humanitarian and development activities in the oPt. Other forms of cooperation can be linked to working with common partners—e.g. in health and education—where the needs and complexity of responsibilities (including the need to coordinate with both parts of UNRWA) has led to a more integrated UN response.

- The partnership between WFP and UNICEF was also an example of collaboration based on working with the same population. Vulnerable families were provided with electronic vouchers that could be redeemed for a pre-approved list of food, water/sanitation and education items at local shops. This allowed 27,565 school children to purchase school uniforms, shoes and winter clothing, and 17,146 households could purchase WASH items in Gaza through this joint UNICEF-WFP e-vouchers program, benefitting around 205,752 people. UNICEF and WFP also supported the Ministry of Social Development to identify families to be prioritized for assistance by establishing eligibility criteria based on vulnerability assessments and field visits.

- The UN has also been effective in working together to support the PA’s ability to meet its obligations to International Human Rights mechanisms and the SDG agenda. In the case of the former, the UNCT has come together to support the Convention on the Rights of the Child (CRC) and Convention on the Rights of the Persons with Disability (CRPD) reporting process. Likewise, the UN has come together to help support the roll out of the SDG Agenda in the State of Palestine.

- In the health sector, a number of working partnerships emerged over the course of the UNDAF cycle. UNICEF and UNRWA partnered together to set up Early Childhood Development (ECD) and Early Childhood Intervention (ECI) services with focus on early detection of children with developmental delays and disabilities and provision of early intervention. Furthermore, UNICEF has supported UNRWA in Gaza to maintain and ensure the safe and effective immunization programme through procurement of solar refrigerators for UNRWA health clinics. In addition, UNICEF continues working with the WHO on immunization and infant feeding programmes. UNICEF jointly with WHO and UNFPA supported improvement of the neonatal health care in Gaza and West Bank. This interagency contribution to the improvement of the neonatal health care was articulated in the National Early Newborn Action Plan (2017-2021). Lastly, WHO, ILO, UNDP, UNESCO and UNICEF have formed a partnership working on the rights of people with disabilities. Likewise, in the education sector UNRWA and UNESCO contributed to the Out-of-School Children Initiative (OOSCI) study in partnership with UNICEF.

## Strategic Partnerships

Did the UNDAF promote effective partnerships and strategic alliances around the main National Development Goals and UNDAF outcomes areas (e.g. within Government, with national partners, IFIs and other external support agencies)?

- The evaluation found some evidence to suggest that the UNDAF had resulted in a more effective strategic partnership around national goals. The two proposed metrics for measuring this were: the number of external working groups [chaired or co-chaired] by the UN and the number of specific multi-partner campaigns and programmes launched during the life of the UNDAF.

- UNSCO is a co-chair of the Local Aid Coordination Secretariat and individual agencies work closely with and through the different sector working groups that have become the primary mechanism for coordinating work in support of line ministry priorities. It has been acknowledged that until recently, there was only limited UN coordination within the LACS working groups. Steps have been taken to develop a single UN voice / position at the meetings while recognizing the relative areas of technical expertise of the different UN agencies that are part of the working groups but there continues to be scope for improvement.

- Most (UN) respondents were of the view that the sector working groups were not a good forum to discuss the UNDAF since it also involved other stakeholders. However, it was noted that UN agencies had begun to engage within these broader coordination mechanisms using a One UN approach but that this had not yet extended to engagement around the UNDAF. This would suggest that the UN could do more to advance the perception of the UNDAF as a vehicle for a UN that is committed to working together more cohesively.

- The UNCT also established a Government-UN SDG Task Force under the leadership of UNDP to coordinate the mainstreaming of the SDGs into UN and Government development programming. The group has worked closely with the Prime Minister’s Office in coordinating UN support to the Government on implementing SDGs often working with multiple ministries on specific SDGs. Additionally, UN agencies have been assisting line ministries to mainstream the SDGs into the drafting of the NPA at all levels, from the overall national priorities, to the specific indicators that will be used to measure progress. UN Agencies also point to work with the Palestinian Central Bureau of Statistics (PCBS) on the mapping of data availability for SDG indicators as another example where the UN has effectively come together around national priorities.

## Project Level Collaboration

Has the effectiveness or programme support by individual agencies been enhanced as a result of joint programming?

- A notable success at the project level has been the SAWASYA Rule of Law programme that brings together UN Women and UNDP (and in the latest phase, UNICEF) and was able to mobilize approximately US$21m from the MDG Trust Fund. The programme has provided over 53,000 people (50% of whom were women) with legal representation and counselling in the West Bank (including East Jerusalem) and Gaza Strip. At the policy level, the project has supported the integration of justice and security priorities in the National Policy Agenda (2017-2022), and finalisation of justice and security sector strategies and finalization and implementation of the Juvenile Protection Law. The project has also seen the development of the first Police Gender Strategy in the Arab region, which was a major achievement in terms of gender mainstreaming. The project has also helped to establish a Specialised Prosecution Unit with 19 public prosecutors specialised in handling Violence Against Women (VAW) cases. A pro bono legal aid scheme by the Palestinian Bar Association, with a focus on vulnerable groups including indigent clients, women and children has been developed and the National Legal Aid Committee launched in 2017.

- The UNCT was also able to mobilize US$1.5m from the SDG Trust Fund for a joint programme titled One-Stop-Shop for Sustainable Business that brought together UN Women, FAO and ITC to pool efforts in support the development of women owned/run Micro, Small, and Medium Enterprises (MSMEs) including cooperatives. While all three agencies have projects targeting the enterprise and trade facilitation sectors, the agreement was on pooling efforts and building on previous and current programmes for all three organizations, plus the joint work plans of the Ministry of Women’s Affairs, Ministry of National Economy and Ministry of Agriculture. A recently concluded evaluation noted that the project was seen as well designed and relevant by all participating stakeholders and was able to make substantial progress against both key outcomes while also noting that more could be done to improve the overall efficiency and effectiveness of the partnerships between the UN agencies.

## Promotion of Human Rights and Gender Equality

To what extent did the UNDAF make use of and promote human rights and gender equality standards and principles (e.g. participation, non-discrimination, accountability, etc.) to achieve its goal?

- One of the most notable achievements that have taken place under the auspices of the first UNDAF was the extent to which it has facilitated engagement with the international human rights mechanisms. The entry point for the UN was the ratification of seven core human rights treaties in 2014. This allowed OHCHR to work directly with the PA and National Human Rights Institutions (NHRI) and CSOs to raise awareness and support implementation of these treaties. OHCHR has worked closely with the PA to ensure the mainstreaming of human rights into the NPA. The UN put in place major capacity building efforts with line ministries on the obligations and reporting requirements. The UN has also worked with the PA and the Independent Commission on Human Rights (ICHR) in organizing national consultations on the draft State party reports under the various human rights treaties.

- Following the establishment of the UNCT Human Rights Treaty Support Group in 2015, OHCHR continued to lead the group to ensure coordinated and coherent approach to human rights treaty reporting and implementation. The group has been functioning as the main UN platform for information sharing and coordination of support to treaty reporting. The Treaty Support Group (in particular UN Women and OHCHR) conducted joint workshops in Gaza and the West Bank on civil society’s role in reporting and the implementation of human rights and the UN’s submission to the report under the Convention Against Torture. The Gender Task Force coordinated the writing of the annual Secretary General report on the Situation of and Assistance to Palestinian Women, which was presented in the Commission on the Status of Women 2017.

- Under the framework of the UNDAF, the HRBA became a guiding approach to a number of joint UN documents. These include the Joint UN Strategy for Hebron, the purpose of which was to define a UN joint response for the fulfilment of Human Rights for vulnerable and disadvantaged Palestinians (women, youth, and children living in Hebron) with specific focus on the rights to education, health, adequate housing, and an adequate standard of living. The  ‘One UN’ Approach to Spatial Planning in Area C of the occupied West Bank outlined a shared UN approach to address international humanitarian law concerns related to the Israeli planning regime in Area C, while taking stock of the achievements and potentials of an emerging Palestinian planning approach in Area C, responding to unmet needs and aspirations of the Palestinian population.

## Working with Civil Society

- While the UNDAF is a signed agreement between the UN system and the PA, partnering with civil society, the private sector and other stakeholders is often a critical part of the comparative advantage of the UN. Furthermore, the on-going restrictions on where the PA is able to work in the oPt has meant that local NGOs are often the primary source of basic services and underpin the resilience of the Palestinian people. The UN system has had working partnerships with a range of local and international NGOs that long predate the UNDAF and rely on local NGOs as key implementing partners especially in Gaza and Area C.

- However, it was noted that while NGOs were heavily involved in the planning and consultations leading up to the development of the CCA and UNDAF, there was no clear role for them within the UNDAF framework. More important, it was noted that the engagement of NGOs within the (limited) UNDAF processes was also not very strong and largely instrumental – i.e. while NGOs were often the vehicles through which the UN attempted to reach communities but the UNDAF never became a framework for mutual accountability with local NGOs. While there continue to be concerns that the UN and international NGOs on occasion “crowd out” local NGOs especially when it comes to funding, the UN has also been able to channel resources to the sector that would not otherwise be available / accessible locally.

- That said, there are practical examples of effective partnerships with NGOs at the sub-sector level. UNICEF works with some 28 NGOs working with children to allow for extended outreach to areas of restricted access to the PA, these include Area C and East Jerusalem of the West Bank, the Seam Zone, and the access restricted border area in Gaza,. Partnerships with civil society were particularly critical in programming for adolescents and child protection.

- Given the UN’s commitment to focusing on vulnerability and the continued importance of local NGOs to the work of the UN in Palestine, serious consideration should be given to forming a CSO advisory committee that would be part of national oversight and accountability structure. There is also scope for the UN to collectively make a more concerted effort to invest in civil society as a sector. This would include further strengthening the relationship with umbrella organizations such as the Palestinian Non-Governmental Organizations Network (PNGO) and the Association of International Development Agencies (AIDA) and more systematically including local NGOs in the UNDAF results groups. As noted earlier in this report, the reporting requirements and demands being placed on local NGOs in particular need to be streamlined and have a much greater focus on building capacities for long-term planning and financial management. Funds needs to be made available for training and investment that will allow NGOs to continue to act as  critical agents of change in Palestine.

## Conclusion

- The UNDAF has had some notable successes in helping to promote a more cohesive and effective UN in the State of Palestine. Both individually and collectively, the UN system has been able to leverage its comparative advantage grounded in neutrality and impartiality to help to provide critical developmental interventions in communities and geographic localities that are beyond the reach of most bilateral and multilateral donors and in some instances, the PA itself. The UN continues to play an important within the overall aid coordination architecture in the oPt and has increasingly begun to engage with common partners using a one UN approach (albeit not always anchored in the UNDAF itself).

- The UNDAF has been very effective as a vehicle for the UN to fulfill its normative mandates tied to the seven key human rights conventions that the State of Palestine signed and ratified in 2014. The highlighting of the rights and duties and the engagement with the international human rights mechanisms has been seen as one of the most notable achievements during the current cycle and has also helped to lay the foundation for the new UNDAF. At the project level, the UN has been able to develop a number of highly effective joint programmes and joint-programming modalities including the development of area based strategies that are likely to further enhance UN cohesion moving forward.

# Sustainability

- Sustainability is defined as the extent to which the benefits from a development intervention have continued or are likely to continue, after it has been completed. Assessing the overall sustainability of UN Interventions in the oPt is not an easy task given the many of the challenges identified during the course of the Evaluation linked to the lack of a resolution to the political situation regarding final Palestinian statehood and the daily challenges posed by the occupation.

## Contribution to National Development

- It is very difficult to talk about development programmes let alone sustainability when every aspect of life in the oPt is restricted by the occupation. Numerous restrictions—on movement, on access to large areas of the West Bank and the entirety of Gaza, and on the ability of Palestinians to build and develop in Area C and East Jerusalem—threaten both short and long-term prospects for human development. The occupation has resulted in a protracted protection crisis with some two million people—nearly half of all Palestinians including 70% of all residents of Gaza—requiring some form of humanitarian assistance in 2017.

- The capacities of the PA to act remains constrained due to limited fiscal and operational space. A decline in direct budgetary support has left government finances in jeopardy despite the Government’s efforts to reduce spending and improve tax collection. Official Development Assistance has declined significantly since 2013 and this has had a profound effect on the PA’s ability to meet the needs of its citizens let alone assume new financial obligations.

- Progress in ‘state-building’ that preceded Palestine’s recognition as a non-member United Nations Observer State in 2012, has lost momentum in the face of a disabling political environment and the stalled progress to statehood. Progress in building a culture of parliamentary democracy is also at risk as 10 years have now passed without a national election. The internal political and administrative rift between Gaza and the West Bank has impeded the development of both areas, slowed the reconstruction of Gaza and taken a large humanitarian toll on the population of Gaza.

- The ability of the PA to take on board new initiatives is likely to be further limited by the cost of potentially reabsorbing the public administration of Gaza within the operational budgets of line ministries and this makes assessing the long-term sustainability of UN programmes extremely challenging. Nonetheless, the UN’s commitment to ensuring the long-term sustainability of its support even under conditions of occupation and the focus on long-term development and building resilience are critical to the success of the UNDAF. Within that context, certain programmes are likely to be more sustainable than others. For instance, the initial investments in state-building activities through training of civil servants, modernizing and strengthening the legal framework, building institutions and infrastructure are more likely to endure. On the other hand, the impact of activities like service provision and livelihoods programmes are likely to dissipate within a certain time after the project ends. This last point speaks to a more general observation that the UN and PA are still in a process of building a partnership based on a shared long-term and programmatic approach to the key development challenges and a gradual movement away from a project-led approach that will take time to mature. The partnership will also need to evolve to reflect the State of Palestine’s middle-income status and the need to think about capacity development not simply within the framework of the current UNDAF and NPA but also in terms of the longer-term capacities that will be required if Palestine is to meet the SDGs and 2030 Agenda.

- As proposed in the previous section, a strong and healthy civil society is an essential part of a future Palestine that is able to meet the needs and aspirations of its citizens. The ability to work with and create space for a vibrant and independent civil society is a critical part of the UN’s comparative advantage both globally and in Palestine. The UN remains uniquely placed to support legislation and laws on the freedom of expression and assembly that can strengthen the independence of civil society organizations and their ability to hold duty bearers such as the UN and PA accountable.

## Lessons Learned

Which were the major factors that contributed positively or negatively to the progress towards the UNDAF outcomes and National Development Goals?

- A number of factors affected the overall effectiveness of the UNDAF not all of which are within the control of the UN. Foremost among these remains the fact that as long as the different UN agencies are accountable to separate Executive Boards or Membership Bodies each operating under individual strategic plans, the ability of the UN to coalesce at the country level remains constrained. Nonetheless, the evaluator was able to identify a number of very specific factors that have impacted the implementation of the UNDAF in the oPt.

### Leadership, UNCT Engagement and RCO support

- The biggest determinant of the success of the UNDAF process in the State of Palestine has been the commitment and efforts of the UNCT. Having made the decision to develop an UNDAF, successive Deputy Special Coordinators have been willing to invest time and resources to follow through to make it more than simply a paper exercise. In the case of the oPt, unlike in many other countries, the UNCT is fortunate to be supported by a large Coordination Office that has been able to push the UNDAF process forward even as the participation of agencies in common country processes has lessened. However, it is important to note that while the RCO can support improved coordination among agencies, it cannot substitute for actual coordination on the ground. Ultimately, UN reform only works if the agencies are willing to make a genuine commitment to working more cohesively and take concrete steps towards making it happen.

### Fragmentation

- The territorial fragmentation of the oPt coupled with the PA’s lack of access to Area C, Gaza and East Jerusalem created its own set of challenges. The UNDAF, however, was designed as framework to cover the full range of UN programmes in the State of Palestine including elements of the work being supported by UNRWA. At the same time, residents of Gaza and the West Bank (and within the West Bank, Areas A, B and C, and East Jerusalem) live under very different circumstances. In the case of the West Bank, the UN has at least had the advantage of working under the nominal authority of the PA and has been able to develop partnerships with line ministries that are grounded in the NPA and sectoral plans. However, even here, it should be noted that in implementing the UN has had to move towards an area based strategic approach to reflect the different challenges being faced in Hebron and East Jerusalem.

- Within this context, Gaza stands out almost as separate case outside the purview of the “regular” UNDAF. The 2014 conflict and reconstruction, the on-going blockade and the challenge of working in a situation where certain UN donors had a no-contact policy with Hamas created a unique set of challenges which, while nominally falling within the overall purview of the UNDAF priority areas, really required its own dedicated plan and approach. Even in instances where joint programmes are operating in both areas, the actual interventions themselves have taken on very different forms to reflect the very specific context.

### Lack of Prior UNDAF Experience

- It is important to recognize the unique situation in the oPt and the difficulties of even thinking about long-term development in a protracted crisis. The introduction of the UNDAF framework and processes that were developed with a conventional developmental setting in mind was always going to be challenging. Despite the attempts to think about medium-term planning, the UN in State of Palestine has been used to operating on a humanitarian footing that requires quick action and turnaround (and more importantly, works through very fixed and pre-defined arrangements).

- The UNDAF process, on the other hand, presumes time and resources that are considered luxuries in the most favourable of circumstances and almost non-existent in a situation where millions of people rely directly on the UN for food, nutrition, and clean water. In the circumstances, the UN in State of Palestine can point to far more success working jointly than is the norm for many countries and these successes—such as on joint assessments and joint plans—should certainly be captured in the results framework for the new UNDAF as a means of measuring “cohesion”.

### National Ownership

- A successful UNDAF requires a strong government architecture that is well managed and able to effectively coordinate the relationship between the UN and line ministries. In the case of the State of Palestine, the UNDAF was developed at a time when the Ministry of Planning and Development acted as the nodal ministry for the national development plan as well as for international development partners. Among other responsibilities, the MOPAD was able to act as a counterpart for the UN during the UNDAF process acting as a convener of different line ministries. Unfortunately, since the MOPAD was folded in the MOF, there was a vacuum within government around aid coordination. Thus, line ministries continue to exercise considerable latitude on how they wish to work and this has reduced the overall effectiveness of common frameworks such as the UNDAF.

### Communication and Advocacy

- The development of a clear and coherent set of messages around the UNDAF priorities for advocacy purposes would have helped to reinforce the view of a UN that was committed to acting and speaking with One Voice rather than simply as the sum of the individual mandates of the different UN agencies. The focus on the most marginalized is noted at various points in the UNDAF narrative but this has not been communicated particularly strongly in the UN’s work in the oPt. Equally, the UNDAF could have been used as a vehicle to highlight important themes such as Human Rights and Youth as particular priorities for the UN. The importance of raising awareness about the UNDAF cannot be overestimated. The overall lack of awareness about the UNDAF both in substance and as vehicle for the One UN among national counterpart and civil society was a major factor in why the UNDAF did not fully live up to the its full potential.

## Conclusion

- Across the board, the view was that UN agencies continue to be  valued partners to the PA and that in a number of sectors including Education, Children’s Health, Justice and Human Rights, this contribution continues to make a significant difference. The UNCT can point to significant progress towards developing a more cohesive One UN approach to the development agenda in State of Palestine through the UNDAF process despite some early setbacks. From all available evidence, the UN has found a variety of ways of coming together in support of common goals using a wide variety of approaches and definitions of joint programming. This has allowed the UN to flexibly respond to opportunities to work more closely together and thereby made the One UN experience in the oPt more demand-driven rather than mandated.

- However, it is also probably true that a more systematic approach would generate more opportunities for the UN to come together. Globally, UNDAFs have not included clear targets for measuring UN cohesion beyond a set of qualitative assessments in the form of the RC Annual Report but the UNCT may well wish to challenge the results groups to develop a set of internal metrics and indicators that would allow for a better measure of cohesion than is currently available.

- The UN has been most effective when it has leveraged its comparative advantage and convening power to focus on important gaps in the national development process—most notably around areas of policy coherence and strengthening implementation capacities at the local level—which continues to be a major challenge in Palestine.

- Given the considerable time and capital invested by the UNCT and the PA to develop the UNDAF, using it as a tool for guiding and sharpening the depth and quality of support being provided by the UN to national development priorities would have likely brought higher returns.

# Recommendations

- The primary aim of the recommendations is to provide the UN in Palestine and its national partners, in particular the PA, a set of actionable and time-bound proposals that would help to build on the considerable achievements of the 2014-2017 UNDAF process. The recommendations are broadly clustered using the evaluation criteria and were discussed and refined during a consultation between the UN and national counterparts held in January 2018. It is also acknowledged that the UNCT and partners will need to prioritize action based on time and resources but nonetheless, the recommendations have been crafted to make them achievable within the lifetime of the new UNDAF and should act as important benchmarks for measuring UN cohesion.

### Ownership

- There is a crucial need to convene the UNDAF National Steering Committee on a regular basis with senior representation from the PA to provide oversight and guidance over the UNDAF process from design through implementation and evaluation.

- Given the critical importance of a strong civil society in the oPt and the vital role they will continue to play as a partner to the UN system, it is strongly suggested that the UN establish a CSO Advisory Committee to the UNDAF process. This would build on precedents in other countries and would also very much be in line with the new emphasis on partnerships as a central pillar to the achievement of Agenda 2030.

- Donors in the oPt need to support the One UN concept financially and become more open to the idea of using funding mechanisms such as the UNDAF Fund as a more effective means of channeling resources. The continued reliance on project funding modalities along with other limits on the fungibility of resources reinforce traditional ways of working and thinking and act as a limitation on the flexibility of the UN to work more effectively as One UN with national partners

### Monitoring the UNDAF

- It is critical that the UNCT and PA actively monitor progress against UNDAF results in a fashion that builds on agency level reviews while at the same time informing the monitoring of progress against the National Policy Agenda.

- Furthermore, the monitoring of UNDAF results needs to be better integrated into the overall monitoring of sector results.

- UNDAF results must be anchored by a clear set of intermediate indicators that better capture the contribution of the UN to the achievement of natural priorities and are tracked properly through the life of the next UNDAF.

### Strengthening the One UN

- The next UNDAF should highlight those areas where the UN will work together under each pillar using a variety of joint programme modalities. These should serve as the “flagship” intervention(s) of the UN under the UNDAF and usefully build on the identification of 20 key vulnerable groups under taken in the CCA.

- The UN should significantly streamline its coordination architecture to minimize the number of working groups and to avoid unnecessary duplication. It is proposed that the UN engage a management consultant to review the existing coordination architecture including those for humanitarian emergencies during the rollout of the UNDAF to come up with lightest possible structure with clear term of references and accountability.

- The UNDAF Results groups should also be encouraged to set concrete and measureable targets to capture increased levels of “joint-ness” including number of joint work plans, joint meetings and so forth with common partners.

- It is critical for the UN and in particular UNCT members to raise awareness about and advocate for the UNDAF. The CCA, with its focus on the 2O most vulnerable groups, can and should be a central part of this message alongside the normative mandate and focus on human rights in the oPt.

# Annexes

List of People Interviewed

Palestinian Authority

|  | First Name | Last Name | Designation | Office |
| --- | --- | --- | --- | --- |
|  | Dr. Estephan | Salameh | Head of Policy and Reform Unit | Office of the Prime Minister |
|  | Shereen | Abu Al Rubbe | Director of International Relations | Ministry of Women’s Affairs |
|  |  |  |  | Ministry of Women’s Affairs |
|  |  |  |  | Ministry of Women’s Affairs |
|  | Daoud | Al-Deek | Assistant Deputy Minister for Planning and Administrative Development | Ministry of Social Affairs |
|  | Mohammed | Al-Hawwash | General Director of Counseling and Special Education | Ministry of Education and Higher Education |
|  | Dr. Mamoon | Jabr | General Director of Educational Planning | Ministry of Education and Higher Education |
|  | Ayoub | Elayan | Acting Director General for General Education | Ministry of Education and Higher Education |
|  | Nadia | Ashhab | Director of Monitoring and Evaluation |  |
|  | Hasan | Ashqar | DG of Planning and Policies | Ministry of Agriculture |
|  | Bashir | Baragouthi | National Policy Advisor | Ministry of Local Government |
|  | Abd Al-Kareem | Daragmeh | Deputy Assistant for Social Dialogue | Ministry of Labour |
|  |  |  |  | Ministry of Labour |
|  | Dr. Asad | Ramlawai | Deputy Minister | Ministry of Health |
|  | Jehad | Yasin | General Director | Ministry of Tourism and Antiquities |
|  | Youssef | Tartouri | General Director, Heritage | Ministry of Culture |
|  |  |  |  | Ministry of Justice |

United Nations

|  | First Name | Last Name | Designation | Office |
| --- | --- | --- | --- | --- |
|  | Robert | Piper | Deputy Special Representative, Resident and Humanitarian Coordinator | UNSCO |
|  | Ciro | Fiorillo | Head of Office | FAO |
|  | Azzam | Saleh Ayasa | Head of Programme | FAO |
|  | Rasha | El-Shurafa | Programme Officer | ILO |
|  | James | Heenan | Head of Office | OHCHR |
|  | Ole | Justesen | Associate Human Rights Officer | OHCHR |
|  | Ulziisuren | Jamsran | Special Representative | UN Women |
|  | Inas | Margieh | National Programme Officer | UN Women |
|  | Alla | Ayesh | Head of Monitoring and Evaluation | UN Women |
|  | Ahmad | El-Atrash | Senior National Urban Planner / Programme Manager | UN-Habitat |
|  | Sufian | Mushasha | Senior Policy Advisor | UNDP |
|  | Nasser | Al-Faqih | Team Leader for Poverty Reduction and Productive Capital | UNDP |
|  | Chikako | Kadama | Team Leader and Advisor Governance and Social Development Unit | UNDP |
|  | Ruba | El-Ghoul | Evaluation Officer | UNDP |
|  | Tap Raj | Pant | Head Education Unit | UNESCO Ramallah Office |
|  | Sonia | Ezem | Senior Programme Officer Education Unit | UNESCO Ramallah Office |
|  | Sarah | El-Attar | Education Officer | UNESCO Ramallah Office |
|  | Junaid | Sordish Wali | Head of Culture Unit | UNESCO Ramallah Office |
|  | Anders | Thomsen | Representative | UNFPA |
|  | Ziad | Yaish | Assistant Representative | UNFPA |
|  | Kumiko | Imai | Head Social Policy and PME | UNICEF |
|  | Meg | Aufette | Deputy Director (Programmes) | UNRWA West Bank Field Office |
|  | Subhra | Bhattacharjee | Planning, Monitoring and Evaluation Specialist | UNSCO |
|  | Julie | Crawford | Special Assistant | UNSCO |
|  | Shifa | Jayousi | Programme Officer | UNSCO |
|  | Sarah | Antoni | Programme Policy Officer | WFP |
|  | Peter | Holtsberg | Head of Programme | WFP |
|  | Munia | Abu El Hawa | National Professional Officer: Health Systems | WHO |
|  | Yousef | Muhaisen | National Professional Officer: Health Coordination | WHO |
|  |  |  | Gaza Office | WHO |
|  |  |  | Programme Officer | Sawasya Joint Programme |

Gaza Office

|  | First Name | Last Name | Designation | Office |
| --- | --- | --- | --- | --- |
|  | Ghada | Snounu | Coordination Officer | UNSCO |
|  | Heba | Zayyan | Head of Gaza Sub-office | UN Women |
|  | Amir | Yasin | Program Associate | WFP |
|  | Rula | Khalaf | Programme Policy Officer | WFP |
|  | Mohan | Peiris | Project Manager (Water and Sanitation Specialist) | UNICEF |
|  | Ruwan | Ubeysekara | Head of Gaza Sub-office | FAO |
|  | Basil | Nasser | Head of Gaza Sub-office | UNDP |
|  | Mahmoud | Abu Aisha | Monitoring, Evaluation and Reporting Associate | UNDP |
|  | Ashraf | Thomas | Human Rights Officer | OHCHR |

Gaza CSO Meeting Participants

|  | First Name | Last Name | Office |
| --- | --- | --- | --- |
|  | Yazdan | Al_Emawi | Al-Amal Rehabilitation Center |
|  | Abed Ar-Rahman | Qishta Muzanen | Baituna Society |
|  | Ahmed |  | PCOA |
|  | Riyad | Jneina | Palestinian Hydrology Group |
|  | Mohammed | Habboush | An-Najda Association |
|  | Saeb | Az-Zaanin | Alwafa hospital |
|  | Tariq | Al-Amour | Al-Fukhari Association |
|  | Abd-Almajeed | Turkia | Magahazi Center |
|  | Ibrahim | Mazrouq | POD |
|  | Areej | Khawaja | POD |
|  | Yassir | Abu Jame’ | Gaza Community Mental Health Program |
|  | Nahed | Khalef | PADR |
|  | Husein | Murtaja | Gaza Culture and Development Group |
|  | NIdaa | Abu Al-Ata | PARC |
|  | Dr. Suliman | Shahin | Union of Health Work Committees |
|  | Khaled | Dahlan | Union of Health Work Committees |
|  | Hania | Az-Zaanin | PDWSA |
|  | Riham | Shurafa | Al-Eidad Society |
|  | Wafa | Al-Ghousin | TCC |
|  | Naim | Kabaja | ASDC |
|  | Khalil | Matar | JRC |

West Bank CSO Meeting Participants

|  | First Name | Last Name | Designation | Office |
| --- | --- | --- | --- | --- |

Participants at Validation Workshop

Millennium Hotel, Ramallah 14 February 2018

|  | First Name | Last Name | Office |
| --- | --- | --- | --- |
|  | Dr. Bashir | Reyes | Prime Minister’s Office |
|  | Nuha | Tobasi | Prime Minister’s Office |
|  | Haleema | Said | PCBS |
|  | Rania | Abughaboush | PCBS |
|  | Mohammed | Qalalwa | PCBS |
|  | Mamoon | Jabr | MOEGE |
|  | Mohammed | Hawwash | MOEGE |
|  | Mohammed | Daraghmeh | MOC |
|  | Khalid | Mansour | MOC |
|  | Rola | El Belbissi | MINFO |
|  | Hiba | Yousef Rimawai | MOJ |
|  | Shereen | Abu Al Rab | MOWA |
|  | Dr. Yaser | Bozya | MOH |
|  | Sophie | Hede | UNICEF |
|  | Etona | Ekole | UNICEF |
|  | Kumiko | Imai | UNICEF |
|  | Marianne |  | UNICEF |
|  | S | Bajraktarovic | UNICEF |
|  | M | Pasic | UNICEF |
|  | Ole | Justesen | OHCHR |
|  | James | Heenan | OHCHR |
|  | Sama | Khali | UNOPS |
|  | Muwafaa | Abu-Ayyash | UNOPS |
|  | Ulzi | Jamsran | UN WOMEN |
|  | Alaeddin | Ayesg | UN WOMEN |
|  | M | Betaji | UNESCO |
|  | Hala | Tannous | UNESCO |
|  | Mohammed Abu | Hammad | UNECO |
|  | Sarah | El Attar | UNESCO |
|  | Junaid | Sorosh-Wali | UNESCO |
|  | S | Ezem | UNESCO |
|  | Roberto | Valent | UNDP |
|  | Geoffrey | Prewitt | UNDP |
|  | Yusef | Muhaisen | WHO |
|  | Arwa | Semier | WFP |
|  | Tharwat | Nashashibi | UNRWA |
|  | Majdi | Hamdan |  |
|  | Reem | Abu Al Rob |  |
|  | Subhra | Bhattacharjee | RCO |
|  | Katherine | Lester | RCO |

### Bibliography

Area Programme Document 2015-2016

Briefing Note for Countries on the 2016 Human Development Report, State of Palestine HDR 2016

Country Cooperation Strategy for WHO and the occupied Palestinian territory 2017–2020

FAO Mid Term Review of Programme Framework 2014-2017

Final Evaluation “Enhancing the Capacities of the Palestinian Authority in Mainstreaming Environment and Climate Change” Project General Consulting and Management, April 2017

Final Evaluation of SAWASYA Programme “Strengthening the Rule of Law: Justice and Security for the Palestinian People”, General Consulting and Management, April 2017

FINAL EVALUATION: Creating One-Stop-Shop for Sustainable Businesses Amer S. Madi, Man 2017

Food Assistance for the Food-Insecure Populations in the West Bank and Gaza Strip Standard Project 2016 WFP in the State of Palestine

Gender Scorecard United Nations Country Team (UNCT) State of Palestine Andrea Lee Esser, PhD, December 2014

Palestinian children and women in Jordan, Lebanon, the Syrian Arab Republic and the State of Palestine

Rapid Assessment of UNRWA Technical and Vocational Education and Training(Tvet) Programme, Engineer Ali Nasrallahand Dr. Nader Mrayyan July 2011

Support to the Role of Civil Society Organization and Youth in Local Public Oversight (RFQ-2015-174) Riyada December 2015

The Palestinian National Institute of Public Health (PNIPH) Review – Final Report, Oxford Policy Management February 2016

UN Women Country Portfolio Evaluation Final Report Palestine Strategic Note 2014-2017

UNDP – Community Resilience Development Program (CRDP) Evaluation Report World for Research and Development (AWRAD) October 2017

United Nations Country Team Occupied Palestinian Territory Common Country Analysis 2016: Leave No One Behind: A Perspective on Vulnerability and Structural Disadvantage in Palestine

United Nations Development Assistance Framework (UNDAF) Annual Review – Summary Note April 2015

United Nations Development Assistance Framework for the State of Palestine 2014-2017

United Nations Development Assistance Framework State of Palestine 2018-2022

United Nations Development Group Annual Reporting Strategic Summary Of Coordination Results ‐ Palestine 2014, 2015 and 2016

United Nations Population Fund Country Programme Document for the State of Palestine 2015-2017

WFP Summary Evaluation Report – State of Palestine Country Portfolio (2011–mid-2015)

WHO Right to Health/Advocacy Project Evaluation

The term “occupied Palestinian territory” refers as a whole to the geographical area of the Palestinian territory occupied by Israel since 1967. Consequent to the adoption of resolution 67/19 by the United Nations General Assembly on 29 November 2012, Palestine was accorded the status of non-member Observer State in the United Nations.

Briefing Note for countries on the 2016 Human Development Report: Palestine, State of

The UNDAF was originally developed for the period 2014-2016. In 2016 the Government formulated its National Policy Agenda. To ensure full alignment of the second UNDAF with the National Policy Agenda, it was decided to extend the current UNDAF to 2017 and defer the start of the second UNDAF by a year to 2018.

It should be noted that under the 2010 Guidelines, there is an expectation that the UNDAF would accommodate the bulk of UN interventions and explains why Palestine UNDAF has a very broad coverage rather than being more focused around a limited number of common areas of work.

The UNCT had the option of developing an outcome only UNDAF but opted for the additional level of planning down to the output level. These results then formed the basis for the results chain in the respective country programme documents and frameworks for the participating agencies. In the case of UNDP, UNFPA and to a lesser extent UNICEF, this extended to directly transposing UNDAF results (verbatim) into the CPD frameworks. Specialized agencies have much greater latitude on how they align with the UNDAF and there is no requirement to use specific language in the formulation of results. It should be noted that the new UNDAF 2018-2022 was developed to the Outcome Level to allow for greater flexibility in programming.

There continues to be a discussion about how best to capture the work and resources channelled through UNRWA in the UNDAF process given the particular mandate and focus on refugees even though they live under the nominal authority of the PA in the West Bank and Gaza. Over the course of the UNDAF process, this was resolved in part by drawing a distinction between UNRWA’s parastatal activities including the direct provision of health and education services from activities like infrastructure, institution-building, capacity development and livelihood support which have a longer term development impact. The on-the-ground collaboration between UNRWA and other UN agencies on, for example, school building with UNDP has been generally good.

These figures represent the original UNDAF budget prior the escalation of hostilities in Gaza and subsequent revisions.

It should be noted that Palestine is not recognized as a DaO self-starter by DOCO though increasingly that is a designation that applies to all countries and UNDAF processes.

Number of female participants in parenthesis

The six “priority areas” of the current UNDAF mirror the standard layouts for UNDAFs globally which speaks to a broader challenge of reconciling the need to accommodate the mandates of the agencies with the goal of creating a more cohesive UN approach at the country level. Even the new Palestine UNDAF 2018-2022 that is built on a very strong vulnerability analysis ends up mirroring this structure in two of the four strategic areas (Democratic governance and inclusive economic development).

This stems in part from the fact that successive iterations of the UNDAF guidelines has seen impact and outcome level results effectively collapsed into one set of very broad results usually tagged to national level indicators. Unfortunately, this trend has meant that the specific contributions of the UN system that would be best captured as a set of intermediate results linked to an HRBA analysis are not well reflected in the UNDAF results framework. This merely serves to exacerbate the focus on individual agency programmes and project that are captured at the level of outputs.

The subsequent decision to develop area based strategies for Hebron and E. Jerusalem would also suggest that there was a realization that adopting spatial [geographic focus] would be one way of leveraging the UN’s comparative advantage as a source of technical expertise and as a neutral convener working in partnership with a range of line ministries and local government actors.

The UNDAF M&E Group with technical support from UN Women did attempt to conduct baseline exercises to ensure that there was sex-disaggregated data for all relevant indicators during the first year of the UNDAF. Unfortunately, this information was not [tracked] updated during the life of the UNDAF.

The evaluation also found a number of clear examples (discussed later) where agencies have been able to take this once step further by identifying practical opportunities for collaboration.

This observation was made by a senior government official during one of the KIIs and confirmed directly or indirectly in subsequent interviews with both UN and PA staff.

The Conventions are: The International Covenant on Civil and Political Rights (ICCPR); The International Covenant on Economic, Social and Cultural Rights (ICESCR); The Convention on the Elimination of All Forms of Discrimination against Women (CEDAW); The Convention on the Rights of Persons with Disabilities (CRPD); The International Convention on the Elimination of All Forms of Racial Discrimination (CERD); The Convention against Torture and Other Cruel, Inhuman or Degrading Treatment or Punishment (CAT) and the Convention on the Rights of the Child (CRC)

http://www.unesco.org/new/en/unesco/worldwide/arab-states/palestine/

It should be noted, however, that this experience informed the design and roll out of the new UNDAF 2018-22 which was based on a country analysis with an explicit focus on vulnerability.

Available at: One UN approach to Spatial Planning in Area C

Attempts to standardize the collection of sex-disaggregated data through the M&E group partially addressed this problem but significant gaps remained.

For example, the evaluation of the UNDP Community Resilience Development Programme (CRDP) underwent significant adjustments at the activity and output level based on learning over the course of implementation and new emerging opportunities.

UNSCO is now coordinating joint resource mobilization efforts once again targeting donors from the Gulf. However, it appears that the approach is still using a project-based approach to soliciting support rather than a programme-based approach which focused on the overall needs of Hebron that will require a multi-sectoral effort.

The RC Annual Report requires UNCTs to report against specific metrics around the 5 Ones but these remain self-reported templates.

It is worth noting that the independent evaluation of the pilot DaO countries found that there were very few generalizable lessons across the 10 countries and that the local context was the most important determinant of what worked and what did not.

It should be noted that the original decision to develop an UNDAF in Palestine was not unanimous with a number of agencies questioning the utility of focusing on a development framework within the context of a protracted crisis and extreme political uncertainty. In hindsight, it appears this concern was not without foundation though as the narrative outlines, the reasons for choosing to develop an UNDAF was to send an important political message about Palestinian Statehood which should not be underestimated.

Even self-confessed UNDAF “skeptics” admitted that the process of developing the old UNDAF and similarly the decision to develop the new CCA around theme of vulnerability was ultimately the correct decision even if did not appear to be so at the time.

The UNCT also established Theme Groups to cover Monitoring and Evaluation, Youth and Gender as major crosscutting elements of the UNDAF.

For an agency such as the ILO with only two professional staff, participating in 3-4 outcome groups plus the 3 theme groups and the humanitarian cluster system was simply too much to expect and this inevitably led to attrition or choices having to be made [most often at the expense of the UNDAF].

The UN faces challenges working with donors that prefer a project approach to its support and are far less inclined to provide the type of support – i.e. pooled funding the UNDAF Fund – that would allow the UN to work together more cohesively under a programmatic framework that has longer-term goals.

The Gender Theme Group was felt to be less successful due in part to the lack of gender capacity within most agencies as well a mixed commitment / approach to gender mainstreaming that is discussed elsewhere in the report.

According to UN Women, all the UNDAF indicators were uploaded on to the DI platform and the M&E group did attempt to update the data in 2015 and 2016 but the large number of indicators and other technical issues resulted in the M&E Group opting for a different means of collating results.

This could be partly explained by the fact that not all of those who were interviewed participated in joint activities such as annual reviews that would more clearly articulate the common approach of the UNDAF.

The new UNDAF 2018-2023 was signed by the Ministry of Social Development on behalf of the PA whereas the first UNDAF was developed under the guidance of the Ministry of Planning. Efforts are underway to set up a high-level National Steering Committee NSC structure to oversee the roll-out of the new UNDAF.

UNRWA for instance provides coordination for UN staff from agencies to car pool into and out of Gaza or to ride in shuttle buses operated by UNRWA.

This figure is somewhat misleading since 95% of the social protection budget was to cover WFP’s food assistance programme compared to the more modest investments in upstream policy work that is nonetheless critical for development. It serves to illustrate just how difficult it is to get an accurate picture of the development budget when so much of the UN”s time and budget is spent on addressing the most basic of needs.

The Local Aid Coordination Secretariat (LACS) supports local aid coordination structure in the oPt to provide coherent technical assistance and financial support to the Palestinian people based on national priorities and in line with the OECD-DAC Paris Declaration on Aid Effectiveness. LACS is responsible for ensuring that the various local aid coordination bodies work smoothly together and increase aid effectiveness. LACS facilitates and provides technical support to the work of the Local Development Forum (LDF) and the Sector Working Groups (SWGs) .

The analysis found that baseline data was available for around 82 indicators, many of which will be utilized as outcome indicators in the upcoming UNDAF 2018-2022.