## Sheet1
Country: SRI LANKA; UNSDF 2018 - 2022 EVALUATION MANAGEMENT RESPONSE - Sri Lanka
Evaluation Title/Year: UNSDF 2018-2022 Evaluation of Sri Lanka / 2022 • Preparation of the management response: UNCT • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: RCO • Frequency of monitoring and updating: Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Strengthen the Comparative Advantages of the UN in Sri Lanka: Continue to Strengthen the comparative advantages of the UN in Sri Lanka, especially providing multi-sectoral technical support for systems building and convening partners around thematic areas/priorities and important issues related to development, human rights, peacebuilding, etc.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT acknowledges the UN’s system-wide comparative advantage is its ability to provide multi-sectoral technical support, convening power economic and social development, humanitarian operations, peacebuilding and human rights. UNCT acknowledges the multidimensional nature of Sri Lanka’s current crisis, and the need to ensure that each of these functions is represented appropriately in UNSDCF 2023-2027.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | UNCT to immediately respond to the crisis with a joint-up multisectoral offer of support in areas such as health, social protection, food security and macro-economic analysis. | 2022-2023 | UNCT
1.2 | Map technical support directly and indirectly provided to government by UN agencies, and identify gaps, opportunities for synergies and ways to improve efficiency. | 2023 | RCO & UNCT
1.3 | Align short-term humanitarian interventions with longer-term peacebuilding, development and human rights reform initiatives in the implementation of UNSDCF 2023-2027. | UNSDCF 2023-2027 life-cycle | UNCT
Recommendation 2: Strong Advocacy for The Human Rights Agenda Capitalize on the comparative advantage of the UN to bring human rights and peacebuilding issues to the attention of government, by ensuring that the RCO and all UN agencies further build on foundations the UN in Sri Lanka has in terms of the human rights-based agenda
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT acknowledges the importance of strong advocacy and programmatic mainstreaming for the Human Rights and Peacebuilding Agenda, and the shared responsibility of the UNCT in this regard. Advocacy and mainstreaming for the Human Rights Agenda should be reflected in the UNCTs internal and external engagement, as well as in the core principles of its programming.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Take steps to promote shared understanding of the Human Rights Agenda in Sri Lanka through a more prominent focus in UNCT meetings, and the monitoring and promotion of Human Rights-based principles in programme design. | 2022 and 2023 | RCO, UNCT, OHCHR
2.2 | Implement Human Rights Due Diligence Policy on UN Support to Non-UN Security Forces, and equip UNCT with appropriate tools and frameworks to ensure conflict-sensitive programming. | UNSDCF 2023-2027 life-cycle | RCO (HRA), UNCT, UNODC
2.3 | Maintain and actively participate in a human rights oriented thematic group/network as part of the UNSDCF implementation architecture | UNSDCF 2023-2027 life-cycle | RCO (HRA), UNCT
Recommendation 3: Create Clear Links between Framework Priorities and Agency Programmes: Create clear links between framework priorities and agency programmes by developing the upcoming 2023-2027 UNSDCF based on a common understanding of the change processes that need to occur to meet those priorities; and clearly link challenges to a set of driver priorities that speak to and articulate the contribution of UN agencies toward them.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT is aware of the design aspects of UNSDF 2018-2022, and has sought to more closely align UNSDCF 2023-2027 with UN Agency Country Programme documents.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | The Theory of Change and Strategic Prioritization process underpinning UNSDCF 2023-2027 involved extensive collaboration between UN agencies and key government partners. Strategic priorities and Outcomes were finalized ahead of the development of agency CPDs to assist with their alignment with UNSDCF 2023-2027. | UNSDCF 2023-2027 Development | RCO-UNCT
3.2 | Achieve CF and CPD alignment across all UN Sri Lanka agencies. WFP, UNDP, UNFPA and UNICEF have already been reviewed and approved by the RC. | UNSDCF 2023-2027 Development & its life-cycle | UN Agencies and RCO
3.3 | Outcome results groups under UNSDCF 2023-2027 to review activities and report annually on their contribution to collective outputs and outcomes under the CF. Annual Report to include review of the results matrix and identify gaps and opportunities to improve CF/Agency alignment. CF Mid-Term Review will also consider alignment and relevance in an evolving economic and social context. | UNSDCF 2023-2027 life-cycle | Outcome Results Group leads, UNCT and RCO
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: Support the UNSDCF through Joint Steering Committee and Regular Reviews. Support the 2023-2027 UNSDCF through an active and engaged Joint Steering Committee (and working-level Committee) to ensure oversight and monitoring through the meaningful buy-in and participation of all development stakeholders. This will include regular reviews to ensure the UNSDCF remains relevant and useful.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT acknowledges the importance of having a Joint Steering Committee (JSC), for effective implementation, review and reporting of the UNSDF 2018-2022. The following actions have been listed and few have already been actioned.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Establish a UNSDCF 2023-2027 Joint Steering Committee to be engaged regularly in the CF development process. The committee was set up during the initial stage of the CF development process and briefed on the CF development process, consulted during development of the CCA, strategic priorities and outcomes. | UNSDCF 2023-2027 Development | RC and UNCT, JSC
4.2 | Engaged and consulted Government, Donors and CSOs during the CF development stages – CCA, Strategic prioritization workshop and finalization of the CF. | UNSDCF 2023-2027 Development | RC, UNCT and the RCO
4.3 | Appraise JSC on annual results under UNSDCF 2023-2027 through an annual review meeting, including recommendations to maintain the relevance and coherence of UNDSCF outputs and the Results Matrix (RM) in line with economic and social developments as outlined in the CCA. | UNSDCF 2023-2027 life-cycle | RCO & UNCT
Recommendation 5: Better Leverage Multi-Stakeholder Partnerships, Especially with CSOs and VIOs Leverage multi-stakeholder partnerships more comprehensively, especially with CSOs and volunteer involving organizations (VIOs), integrating them into the official planning, implementation, and monitoring mechanisms within the cooperation framework at the Steering and Working/Operational committee level.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | CSO’s have been key partners to in implementing programme of UN agencies in Sri Lanka. They have been consulted for various reasons in many instances, however UNCT acknowledges there is space to further improve engagement with CSOs especially during the initial planning stages.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Engaged and consulted CSOs during the CF development stages – CCA and Strategic prioritization process | UNSDCF 2023-2027 Development | RCO and UNCT
5.2 | Engage with CSOs and VIOs annually as part of an extended programme of outreach for Outcome Groups under UNSDCF 2023-27. | UNSDCF 2023-2027 life-cycle | Outcome Group Leads
5.3 | Engage more systematically with youth-led CSOs on UNCT priorities and programming in line with Youth Score Card recommendations | UNSDCF 2023-2027 life-cycle | RCO & UNCT
Recommendation 6: Create Clear and Focused Priorities, Baselines, and Targets: Facilitate consensus-building work under the 2023-2027 UNSDCF by creating priority areas that are more focused and better defined from the outset, so that these are supported by common understandings of and approaches to development priorities. Based on this, identify, and define baselines and targets that reflect both the comparative advantage of the UN and its expected measurable contribution to sustainable development in Sri Lanka
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT has accepted this recommendation and has actioned it as part of the CF development process. It has consulted various stakeholders to ensure priority areas are captured accurately and are well defined to reflect national priorities.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Results Framework to stringently ensure a baseline and valid data source for each indicator. | UNSDCF 2023-2027 Development | RCO, Outcome Working Group Leads, M&E Group
6.2 | Indicator targets to be set in consultation with government as the targets would be national targets. Ensure it is realistic and achievable during CF cycle and is reflective of the current country context. | UNSDCF 2023-2027 Development | RCO, Outcome Working Group Leads, M&E Group
6.3 | UN agency CPD outcomes to align with the CF outcomes ensuring clear line of CF implementation | UNSDCF 2023-2027 Development & life cycle | RC and UNCT
6.4 | Support, improve and enhance data sources (DCS & Other) which can directly contribute towards reviewing the CF results Matrix. | UNSDCF 2023-2027 life-cycle | UNCT and Outcome Results Group Leads
Recommendation 7: Consolidate Knowledge-sharing and Increase Joint Action: Consolidate knowledge-sharing successes within Results Groups by creating incentives for moving towards further integration of knowledge activities building on initial successes in knowledge-sharing and collaboration in a way that leads to increased joint action, avoiding replication; this might for instance, include linking key performance indicators of agency staff in these groups to increased joint action.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT accepts this recommendation and commits to the use of Outcome Results Groups as a forum for quality assurance of desk-based and field-based assessments with a view to facilitating joint-agency involvement in the development of knowledge products, and ultimately to increase joint action.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Through their terms of reference, identify Outcome Results Groups under UNSDCF 2023-2027 as the primary forum for discussion and quality assurance of proposals for desk-based and field-based assessments and the generation of other relevant knowledge products. | UNSDCF 2023-2027 life-cycle | RCO, UNCT and Outcome Results Group Leads
Recommendation 8: Develop A Communications Strategy as Part of the Framework: Develop a clear strategic communications strategy around the 2023-2027 UNSDCF. Communicating as one under the UNSDCF can help make communication a strategic function that actively incorporates political analysis and pursues the ‘political’ objective of demonstrating the UN in Sri Lanka’s value-added and building support for the mission among the government and the public.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | Although a comprehensive communications strategy was developed retrospectively for the previous UNSDF by an external consultant – the recommendations were not fully implemented. There were concerted joint campaigns and communications activities covering the four drivers that yielded results.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Joint UNCG Communications Strategy to be developed to promote the UNSDCF and the subsequent results. | 2022 | UN Communications Group – Current Chair – UNICEF and RCO supporting as Secretariat
8.2 | Yearly monitoring of progress and priorities to support the implementation of the strategy | UNSDCF 2023-2027 life-cycle | UN Communications Group – Current Chair – UNICEF and RCO supporting as Secretariat
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 9: Raise Awareness about UNSDCF at All Levels: Increase efforts to raise awareness about the 2023-2027 UNSDCF among different stakeholders, especially at different levels of government, including greater efforts to sensitize donors and sell the benefits of the UNSDCF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | The UNCT is committed to strengthening the engagement and ownership of the Govt throughout the development and implementation of the new UNSDCF to ensure a coherent UN system-wide and whole of Govt approach at all levels, parties, and stages, thus increasing the effectiveness of the Govt- UN strategic cooperation.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Working closely with the Sustainable Development Council, UN Sri Lanka will have a public launch of the UNSDCF along with a press release and event | 2023 | UN Communications Group – Current Chair – UNICEF with RCO supporting as Secretariat
9.2 | To ensure continued reiteration of the role of the UNSDCF vis a vis stakeholders, a set of key messages will be developed and periodically updated and used by HoAs in their interactions with Government, donors, and other stakeholders and in public facing material | UNSDCF 2023-2027 life-cycle | RCO, UNCT, UN Communications Group – Current Chair – UNICEF with RCO supporting as Secretariat
Recommendation 10: Increased Agency Leadership and Ownership through Joint Workplans: Reinforce a sense of co-ownership of UN agencies in joint activities and further encourage agencies to take on a leadership role and accountability for joint results in agreed-up areas, as ‘the agency’ is where much of the technical sector-specific knowledge and capacities of the UN is housed.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | The current results group mechanism was formed to promote agency leadership and enhance agency joint programming. However, results groups were relatively new and were being implemented when this evaluation was conducted, limiting the opportunity to capture the results groups progress. The UNCT accepts this recommendation and hopes to continue its initiatives towards increasing agency leadership and JWP ownership.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Agencies have volunteered to co-lead the outcome groups and have extensively contributed towards developing the outcome narrative for the CF. | UNSDCF 2023-2027 Development | Outcome Results Group Leads
10.2 | Outcome groups will continue to co-lead the implementation of the CF joint work plans and aim to identify and strengthen opportunties for joint programming, aiming at a minumum of 15% in line with global guidance | UNSDCF 2023-2027 life-cycle | Outcome Results Group Leads
10.3 | Pursue opportunities for increased joint programming through the UN Sri Lanka SDG MPTF ("pooled fund") | UNSDCF 2023-2027 life-cycle | RCO, UNCT
Recommendation 11: Work with Donors to Pursue Joint Programming and More Flexible Funding: Build on increased perception of effectiveness of One UN approaches thanks to the UN's joint-up pandemic response, in order to work with donors to pursue more flexible funding and joint programmatic initiatives in other key priority areas, especially those identified by the 2023-2027 UNSDCF, utilizing more fully the RCO’s role as a key broker of new streams of funding for key programmes; this will require both the building of support among donors for pooled funding and strong coordination among agencies to avoid unnecessary project management overhead costs and other programmatic redundancies.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | UNCT acknowledges the need for flexibility in the mobilization and disbursement of resources under joint Programming initiatives. UNCT and RCO will continue to work towards providing clarity on the roles of responsibilities and financial management under joint programming initiatives, consistent with recent developments in global guidance for Joint Programme administration.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
11.1 | Engage donors to advocate for more flexible funding and funding that promotes joint programmatic initiatives among UN Agencies, including through the closer alignment of the UN Sri Lanka SDG MPTF with the UNSDCF | UNSDCF 2023-2027 life-cycle | RC, RCO, UNCT
11.2 | Outcome Results Groups focus on joint programmes as the key drivers to achieve common outcomes and increasingly engage donors in joint-up ways | UNSDCF 2023-2027 life-cycle | UNCT, Outcome Results Group Leads, RC, RCO

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030