## MR
Country ___VIET NAM_____; CF 2022 - 2026 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: ----2022-2026 CF Evaluation---------- / 2025/2026 • Preparation of the management response: UNCT, led by RCO • Approval of the management response: UNCT and JSC • Follow-up monitoring and updating of the management response’s implementation: UNCT, CF working groups, RCO • Frequency of monitoring and updating: Linh Bui Nguyen, RCO
Recommendation 1: Articulate the UN’s strategy in Viet Nam’s towards achieving an upper middle-income context in the next CF
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Articulate a system‑wide UN strategic positioning statement in the 2027–2031 CF aligned with Viet Nam's national priorities and international commitments, including transition toward UMIC and beyond. | During 2027-2031 CF design | RC, UNCT with PMT and RCO support Government
1.2 | Ensure a strong focus on Leave No One Behind and other UN programming principles (human rights–based approach, gender equality, etc.) is integrated across the CF outcomes and narrative, reinforcing UN’s commitment to equity as Viet Nam advances to UMIC. | During 2027-2031 CF design | RC, UNCT with PMT and RCO support Government
Recommendation 2: Focus on selective, high-impact priorities where the UN has clear comparative advantage
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Through broad consultations and analysis during CF formulation, identify a set of strategic priority areas for the 2027–2031 CF where the UN’s collective strengths and comparative advantages are greatest, as basis for identification of CF strategic outcomes | During 2027-2031 CF design | RC/UNCT (with PMT and RCO support) Government
2.2 | Streamline the CF structure by identifying a manageable number of mutually-enforcing and realistic Outcomes and their Focus Areas (during the CF design), and Outputs (during the JWP development), concentrating them around the agreed strategic priorities | During 2027-2031 CF and JWP design | RC/UNCT (with PMT and RCO support) Government
2.3 | Under each CF outcome, further identify Priorities for Collaboration that connect multiple Focus Areas, articulating how joint UN action across sectors and agencies will create systemic shifts beyond individual interventions, serving as basis for forming concrete joint initiatives within or across UNSDCF Results Groups during the implementation period. | During 2027-2031 CF design | RC/UNCT (with PMT and RCO support) Government
2.4 | Align agency programming instruments (e.g. CPDs) with the CF strategic priorities/outcomes to reinforce collective focus, greater synergy, and One UN coherence. | During 2027-2031 CF design, and agency programming instrument design | UN entities (lead)
Recommendation 3: Continue to ensure strategic and concentrated technical and financial support to high-impact priorities.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Develop a Multi-Year Funding Framework mapping UN agency resources against each outcome during CF design, as basis for development and implementation of a CF partnership and resource mobilization strategy. | During 2027-2031 CF | RC/UNCT (lead) (with PMT and RCO support)
| Develop and update CF Annual Joint Work Plan (JWP) mapping specific UN intervetions and resources against each CF output and outcome, with emphasis on formulating joint initiatives or joint programmes around the agreed Priorities for Collaboration. | During annual JWP design and implementation | Results Groups (lead), UNCT (clearance)
3.2 | Focus coordinated UN efforts in a select number of provinces or sub-national areas aligned with the CF Outcomes, Outputs, and Priorities for Collaboration. Develop joint sub-national workplans for these sub-national areas to promote synergy, peer learning, and scalable models. | Annually, during JWP design and implementation | Results Groups (lead), UNCT (clearance)
3.3 | Annually, Results Groups identify priority issues/joint initiatives under each CF Outcome for leveraging the UN’s convening power for unified high-level advocacy to promote reforms and ensure visibility of UN's collective contributions. For example, the RC and UNCT will engage in regular policy dialogues with Government and partners (e.g. annual high-level forums or JSC meetings). | Annually, during CF implemenation | RC, UNCT, Results Groups
3.4 | Establish an annual joint UN communications strategy that frequently packages and publicizes collective achievements and success stories in the above priority areas/joint initiatives, reinforcing a One UN image | Annually, during CF implemenation | Comms Team
Recommendation 4: Enhance jointness platforms for greater collective impact
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Set specific collective targets for joint initiatives each year in line with the Priorities for Collaboration (e.g. number of joint initiatives) and embed these targets in Results Group TOR, workplans, monitoring and reporting. | During Results Groups TOR design and CF implementation | Results Groups MEL Group
4.2 | Continuously apply the One UN approach to coordinate and advocate for UN work, particularly joint initiatives, across relevant development coordination platforms with development partners, government, and other stakeholders, in order to mobilize collective efforts and support (e.g. through JSC, DPG, IACG, DRRP) | During CF implementation | RC, UNCT (with RCO support)
4.3 | Encourage joint resource mobilization by presenting cohesive, multi-agency funding proposals to donors, and coordinate donor outreach through the One UN voice to secure financing for joint initiatives. | During CF implementation | RC, UNCT (with RCO support) Government
Recommendation 5: Embed flexibility and adaptability to respond to a dynamic context.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Leverage the Common Country Analysis (CCA) Update and Annual Horizontal Scanning as a dynamic tool: E.g. convene structured UN-GoV dialogues, including through JSC, on emerging trends and possible adjustment in the CF. | Annually, during CF implemenation | RC/UNCT, PMT, RCO
5.2 | Elevate Annual Results Reviews (including RGs and JSC reviews) and Reporting to be forward-looking reflection platforms, discussing opportunities and challenges, particularly for joint work and for CF course correction | Annually, during CF implemenation | RC/UNCT, Results Groups, RCO Government
5.3 | Quarterly Results Group Update to UNCT on RG progress, particularly on identification and implementation of joint initiatives within and across Results Groups, for improvement of One UN voice and efforts. | Quarterly, during CF implementation | Results Groups, RC/UNCT, RCO
5.4 | Quarterly PMT Technical Update and Advice to UNCT on any new developments in the country's contexts, possible UN entry points and/or possibilities for collaboration among Results Groups | Quarterly, during CF implementation | PMT, RC/UNCT, RCO
Recommendation 6: Deepen the joint UN-Government leadership and engagement
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Mobilize the Joint Steering Committee (JSC) as a platform for issues-based dialogue, partnerships and innovations with broader participation from ministries and stakeholders, as necessary, for strengthened UN-GOV leadership and engagement in CF implementation | During CF implementation | RC/UNCT Government
6.2 | Invite relevant Government and other counterparts to participate in the UN internal mechanism (e.g. Results Groups, Thematic Groups)'s technical discussions, as needed, on development gaps and solutions. | During CF implementation | RC/UNCT, Results Groups, Thematic Groups Government
6.3 | Strengthen joint UN-GoV technical leadership by incorporating sub-national authorities where relevant. For outcomes that largely involve local implementation, engage provincial government representatives through periodic consultations or by including them in relevant RG activities to ensure local ownership and feedback. | During CF implementation | RC/UNCT, Results Groups Government (sub-national level)
Recommendation 7: Expand inclusive platforms for partnerships and dialogue
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Strengthen and regularly utilize the Development Partners Group (DPG) and other development partner forums to ensure coherent support for CF priorities as well as joint advocacyy and knowledge exchange. E.g. schedule biannual DPG meetings or thematic workshops co-chaired by the RC to present CF progress, discuss emerging priorities, and coordinate funding strategies among UN, IFIs, and bilateral donors. | During CF implementation | RC/UNCT, RCO
7.2 | Establish or reinforce multi-stakeholder dialogue platforms that bring together Government, civil society, the private sector, and other partners around priority issues. E.g. organize annual roundtables facilitated by the UN as a neutral convenor, to allow open discussion among Government and other stakeholders. | During CF implementation | RC/UNCT, Results Groups, Thematic Groups, RCO Government
7.3 | Engage the private sector in CF implementation through structured partnerships. Eg. Develop a Private Sector Advisory Group or similar mechanism linked to the UNCT to advise on and co-create sustainable development initiatives, and leverage this group to mobilize private financing and technical expertise for CF priority areas. | During CF implementation | RC/UNCT, Results Groups, Thematic Groups, RCO
Recommendation 8: Reflect on and optimize CF coordination and governance mechanisms for greater coherence and effectiveness
Management response - Accepted/Partially Accepted/rejected : The CF governance structure comprises the JSC and the UN internal coordination architecture, to be outlined in the CF document. The detailed design and operationalization of each body within the UN internal coordination structure will be developed by the UNCT to ensure lean, fit-for-purpose, and results-oriented coordination that promotes One UN coherence across planning, implementation, monitoring, and reporting. It will align with UNSDCF guidance and remain flexible to adapt to evolving priorities and needs. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | Develop lean, purpose-driven CF coordination structures for the new CF, informed by a thorough review of the effectiveness of current mechanisms, particularly non-mandatory bodies, and clearly define their setup and roles. | Q3/2026 | RC/UNCT, RCO
8.2 | Strengthen Results Groups as the core operational coordination mechanism under the new CF. Update RG ToR to emphasize joint planning, joint resource mobilization, and shared monitoring/reporting responsibilities among agencies, including setting a target for a number of joint initiatives in line with the agreed Priorities for Collaboration. | Q3/2026 | RC/UNCT, Results Groups
8.3 | Enhance linkages between communications and MEL (Monitoring, Evaluation, Learning) functions, including on how M&E findings can be fed into communications materials. | During CF implementation | MEL Group, Comms Team
8.4 | Improve integration of Thematic Groups (TGs) into the CF coordination structure. E.g. assign TG focal points within each Results Group, invite TG leads to RG meetings | During CF implementation | RC/UNCT, Results Groups, Thematic Groups
Recommendation 9: Strengthen the Results Framework to enhance strategic focus and accountability.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Develop clear ToCs, including a system‑wide ToC for the overall CF and a dedicated ToC for each Outcome. These ToCs should clearly articulate the intended CF results in alignment with national development priorities and international commitments, the UN’s strategic positioning and comparative advantages, the agreed priority focus areas, the key priorities for collaboration, as well as the underlying assumptions and risks | During CF design | UNCT, RCO, PMT Government
9.2 | Streamline and sharpen the CF Results Framework (RF) to reflect the ToCs and to consist of robust indicators to measure the UN contribution to macro outcome-level results. Maximize the alignment between the CF Outcome indicators with agency country programme indicators | During CF design | UNCT, RCO, MEL Group Government
9.3 | Ensure that JWP consists of CF Outputs which have robust Output indicators to measure the UN attribution, in close linked with relevant Outcomes. Maximize the alignment between the CF Output indicators with agency country programme indicators | Q4/2026 - Q1/2027 | UNCT, RCO, MEL Group
9.4 | Utilize the strengthened RF and JWP indicator framework as a living management tool throughout implementation for review progress. Maximize the use of UNINFO database for CF M&E and reporting. | During CF implementation | UNCT, RCO, MEL Group

## detailed recommendations
Recommendation 1: Articulate the UN’s strategy in Viet Nam’s towards achieving an upper middle-income context in the next CF
As Viet Nam moves toward upper middle-income (UMIC) status, with Vietnam’s leadership bold vision and ambitious targets presented in the recent Party’s Resolutions, the next CF should consider articulating a clearer long-term strategy that defines the UN’s role, focus, and added value in this changing context. The CF narrative may highlight areas where the UN brings a distinctive comparative advantage, including normative work and promotion of international standards, policy advice and institutional capacity development, provision of technical knowledge and expertise, and facilitation of knowledge exchange and international networking.
While direct service delivery has been appropriate and effective during Viet Nam’s lower middle-income stage—especially for vulnerable populations insufficiently reached by public or private systems—its relevance is expected to diminish as national capacities strengthen. As it happens, the UN may wish to focus on leaving no one behind and reaching the “last mile,” and retain its convening role to support and coordinate the GoV and other stakeholders for direct service delivery. The UN may therefore wish to gradually reposition its support from downstream delivery toward upstream policy, systems, and institutional strengthening, ensuring its structure, scale, and approach remain responsive to Viet Nam’s evolving development context and aspirations to achieve UMIC status by 2030.
Linkages: | Key findings 1, 4, 6, 8, 28, 30
Priority level: | Critical
Responsibility:[1] | UNCT, GoV
Timeframe: | During the next CF design
Recommendation 2: Focus on selective, high-impact priorities where the UN has clear comparative advantage
Building on a clearly articulated long-term strategic positioning in the UMIC context, the next CF could consider identifying a strategic set of high-impact priorities where the UN system demonstrates distinctive comparative advantage and value addition. Streamlining outcomes and outputs would help reduce fragmentation, strengthen collective accountability, and enable the UN to deliver more visible and scalable results. Indicatively, potential areas of interest emerging from consultations with agencies and stakeholders may include:
· Advance climate action and a just, green transition: Provide policy advice, support system reforms, and foster partnerships that embed equity, job transitions, and resilience into climate responses, while connecting Viet Nam to JETP and global climate finance.
· Support inclusive digital transformation and data governance: Promote secure and rights-based digital ecosystems with universal access and strengthen governance and interoperable data systems to improve evidence-based decision-making.
· Promote gender-responsive care systems and social protection reform: Scale up reforms that expand care infrastructure, reduce unpaid care, and strengthen inclusive social protection with sustainable financing.
· Strengthen inclusive governance and civic space: Maintain principled engagement on sensitive issues, enhance rights-based policymaking capacity, and expand meaningful social partner participation.
· Enhance human capital and future-ready skills: Align education and training with labour market needs, emphasizing digital, green, and entrepreneurial skills, and ensuring equal access for marginalized groups.
· Engage the private sector for sustainable growth: Develop structured partnerships that promote ESG standards, impact investment, and blended finance, while supporting enterprises to meet international market requirements.
Linkages: | Key findings 2, 6, 8, 24
Priority level: | Critical
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design
Recommendation 3: Continue to ensure strategic and concentrated technical and financial support to high-impact priorities.
In connection with the Recommendation 2, in preparing the next CF, once high-impact priorities are identified, a concentrated approach could help reinforce strategic coherence and effectiveness, ensuring that collective resources and capacities are directed toward areas with the greatest transformative potential through policy advocacy, technical assistance, and capacity development.
In this context, the UNCT could explore ways to balance responsiveness to diverse demands with maintaining a strong strategic focus. Broader engagement across multiple sectors, provinces, or ministries may stretch available resources and reduce collective impact. Building on lessons from the current CF, a more clustered approach to sub-national engagement might be considered to promote synergy, shared learning, and scalability of results.
Continued proactive engagement, leveraging the UN’s convening power, in high-level policy dialogue would further strengthen the UN’s contribution in these areas. At the same time, enhancing internal coordination and communication among UN agencies could help present a more unified advocacy voice and improve visibility with development partners. Developing joint communication profiles that highlight the collective achievements of the UN system in these focus areas may also help demonstrate tangible impact and reinforce the UN’s role as a strategic, trusted partner in Viet Nam’s evolving development context.
Linkages: | As for Recommendation 2; and Key findings 10, 12, 23, 25
Priority level: | Important
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 4: Enhance jointness platforms for greater collective impact
Given the diversity of mandates and procedures across more than twenty non-resident and resident UN agencies, achieving effective jointness remains a continuing challenge. While each agency has its own priorities, there are clear areas of shared mandates and objectives where joint approaches could generate stronger results and greater efficiency. Facing downsizing development aid and a growing appetite for joint programming signalled by some donors, this modality could be seen as a viable financing tool that aggregates scare resources, leverages the UN’s collective expertise, and reduces transaction costs. Experiences under the current CF suggest that joint programmes perform best when driven by clearly defined common priorities.
In the next CF, the UNCT could consider different options to enhance jointness, particularly in programming and financing based on the comparative advantages and complementarities of agencies. This may begin with identifying and agreeing on priority areas where joint implementation and joint resource mobilization would bring the greatest value. The UNCT may also consider defining collective targets for joint programming, joint resource mobilization, and flagship initiatives, embedded these into the RGs. Such measures would help translate jointness from principle to practice, ensuring that collaboration across agencies delivers coherent, scalable, and cost-effective outcomes.
Linkages: | Key findings 13, 23, 24, 25, 26
Priority level: | Important
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 5: Embed flexibility and adaptability to respond to a dynamic context.
The next CF will operate in a rapidly evolving global and institutional environment, shaped by the retreat of multilateralism, intensified trade tensions, and uncertainty in development financing. Within the UN system, the ongoing UN80 reforms and the SWE on progress toward a “new generation of United Nations country teams” signal potential structural adjustments and shifts in coordination and accountability requirements. At the national level, institutional reforms and government restructuring continue to redefine priorities, policy directions, and implementation mechanisms at both national and sub-national levels.
To remain relevant and responsive in such a dynamic context, in preparation of the next CF, the UNCT, in close consultation with the GoV, could consider embedding stronger flexibility, adaptability mechanisms, and ways of working. While formal revisions of the CF document may remain procedurally complex, practical measures could be established to facilitate dialogue, identify gaps, and adjust priorities and workplans as contexts evolve. These may include light procedures for revising results indicators and resource allocations, along with a more strategic and forward-looking use of reflection platforms, notably the CA Update and ARRs, to support continuous learning and adaptation. In this regard, the UNCT and GoV might consider to:
• Ensure that findings from the CA Update are used proactively to trigger structured dialogues between the UN and the GoV at both strategic and operational levels, including discussion and endorsement through the JSC.
• Position ARRs as platforms for strategic reflection, highlighting not only achievements but also challenges, constraints, and proposed next steps, rather than serving primarily for reporting purposes.
• Use both the CA Update and ARRs to promote course correction, inform real-time decision-making, and reinforce the CF as a living, adaptive framework responsive to Viet Nam’s evolving development context and the ongoing UN reform direction.
Such an approach would help ensure that the next CF remains dynamic, evidence-based, and strategically aligned, while strengthening the adaptability of the One UN to contextual dynamics and emerging priorities.
Linkages: | Key findings 4, 5, 6, 11, 18
Priority level: | Important
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 6: Deepen the joint UN-Government leadership and engagement
As the CF is a joint framework between the UN and the GoV, active GoV participation and ownership are essential to achieving sustainable results. In the context of Viet Nam’s transition toward UMIC status, strengthened ownership will be critical not only for strategic alignment but also for ensuring domestic financing and policy leadership in advancing the joint UN–GoV development agenda. The ongoing institutional reforms and GoV restructuring also present an opportunity to explore new or strengthened modalities for GoV participation and leadership throughout the CF cycle.
In the next CF cycle, the UNCT and the GoV could consider jointly exploring options to deepen GoV engagement throughout the CF cycle, from design and oversight to implementation and monitoring. Engagement might extend beyond focal ministries such as MoFA and MoF to include other line ministries whose mandates align with CF priorities, as well as sub-national authorities. Possible directions may include:
· Enhancing the effectiveness of JSC deliberations by adopting more dynamic formats, such as extended agendas, technical sessions, or side events, with participation from relevant ministries to review results, identify bottlenecks, and coordinate solutions. Consolidating separate annual joint review processes between individual agencies and the GoV under the JSC platform would reinforce its strategic role and responsiveness.
· Encouraging active participation of GoV agencies in RGs as a means to strengthen joint planning and implementation. Although engagement of the GoV agencies in RGs has been a persistent challenge noted since the previous CF cycle, their participation remains possibly one of the most practical avenues to foster genuine joint planning between the UN and the GoV. Engagement may begin with participation in technical discussions to identify gaps and propose actions within relevant outcome areas, with potential for more structured or permanent involvement depending on interest and commitment as the RGs evolve.
Linkages: | Key findings 2, 9, 11, 13, 25, 27, 29, 30
Priority level: | Critical
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 7: Expand inclusive platforms for partnerships and dialogue
The next CF could consider broadening and deepening multi-stakeholder partnerships to reinforce the UN’s convening and coordinating role in Viet Nam’s evolving development landscape. Engagement with donors, development partners, social organizations, and the private sector should continue to be strengthened through inclusive platforms for dialogue, knowledge exchange, and co-financing. Such collaboration would help amplify the UN’s contribution to Viet Nam’s sustainable development agenda, support policy coherence, and mobilize complementary expertise and resources.
Leveraging the One UN voice through joint platforms, particularly the Development Partners Group (DPG), should continue and be further enhanced to strengthen joint advocacy on emerging national priorities, including those shaped by ongoing institutional reforms and GoV restructuring. The UNCT may also explore opportunities to establish or expand safe and constructive dialogue spaces involving the GoV, development partners, private sector, social partners, and other relevant stakeholders to engage on sensitive but essential governance issues, such as human rights, civic participation, and freedom of expression. These inclusive partnerships would help sustain trust, transparency, and shared responsibility for advancing Viet Nam’s SDG commitments under the next CF.
Linkages: | Key findings 9, 10, 12, 29
Priority level: | Important
Responsibility: | UNCT, GoV, development partners, and other related stakeholders
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 8: Reflect on and optimize CF coordination and governance mechanisms for greater coherence and effectiveness
To enhance coordination and governance throughout the CF cycle, the UNCT and the GoV could consider jointly reviewing and reflecting on the current CF governance structure to ensure it remains lean, purposeful, and outcome oriented. This reflection may help identify ways to avoid coordination fatigue, strengthen follow-through, and reinforce a more strategic and action-focused collaboration. Simplified coordination mechanisms and clearer role delineation could help reduce administrative burden while improving coherence and efficiency.
As part of this process, the UNCT and the GoV might explore several options:
· It may be useful to retain the PMT, which is not a mandatory structure under the UNSDCF Guideline, as a flexible, task-based arrangement to mobilize collective expertise for technically complex and strategic tasks such as the CA, CF evaluation, CF design, or strategic reviews. This could help maintain the UN’s relevance and responsiveness to an evolving context.
· The UNCT could consider strengthening the RGs as the core operational mechanism complementing the JSC’s strategic oversight role. This may involve revising the RGs’ ToR to clarify their mandate, refine the ways of working to foster genuine jointness in planning, resource mobilization, implementation, monitoring, and reporting. The RGs could also serve as dynamic forums for knowledge sharing, addressing implementation challenges, showcasing good practices, and promoting mutual learning.
· The UNCT may also wish to strengthen the linkages between communications and MEL functions, ensuring that communication products are grounded in evidence and lessons learned, thereby reinforcing coherent knowledge management and enhancing the visibility and credibility of the UN’s collective results.
· In addition, the UNCT could reflect on how to improve the interaction between RGs and TGs. A practical starting point could be to enhance the integration of cross-cutting issues, such as gender equality, youth, disability inclusion, and data, within RG discussions. Over time, the UNCT might explore options for embedding TGs into RG structure to better mainstream cross-cutting themes through joint planning, monitoring, and reporting.
Such reflections would help ensure that the CF’s coordination arrangements continue to evolve in a way that supports greater efficiency, integration, and collective impact, while respecting the operational realities and priorities of the UNCT and its GoV counterparts.
Linkages: | Key findings 11, 12, 13, 14, 15, 18
Priority level: | Important
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design, implementation, and monitoring
Recommendation 9: Strengthen the Results Framework to enhance strategic focus and accountability.
In developing the next CF, the UNCT, in consultation with the GoV, may wish to reflect on ways to strengthen the RF to ensure clearer causal linkages, sharper strategic focus, and more credible measurement of the UN’s collective contribution. A more coherent RF could serve as both a strategic tool for planning and a mechanism for collective accountability, reinforcing the UN’s role as a results-driven partner.
In this regard, the UNCT could consider:
· Streamlining outcomes and outputs in line with the agreed high-impact priority areas (as noted in Recommendation 2), to reinforce focus, coherence, and clarity of collective accountability.
· Developing a more coherent and results-oriented Framework that clearly establishes the linkages from output indicators to outputs, and from outputs to outcomes. This should be based on a well-articulated change logic and pathways of contribution, ensuring selected output indicators are sufficient to demonstrate achievement of each output, and that outputs collectively make a clear, justifiable, and measurable contribution to the corresponding outcomes.
Such reflection would help make the next CF Results Framework more focused, coherent, and evidence-based, while providing the UNCT and its partners with a stronger foundation for monitoring, learning, and demonstrating results.
Linkages: | Key findings 17, 18, 19, 20
Priority level: | Important
Responsibility: | UNCT, GoV
Timeframe: | During the next CF design
[1] In the recommendations presented in this section, indicative references to responsibility and timeframe are provided for illustrative purposes, to support reflection during the Management Response phase. Final decisions regarding ownership, sequencing, and timelines rest with UNCT management.

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030