## Indonesia
Country Indonesia; UNDAF / CF 2021 - 2025 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Independent Evaluation: United Nations Sustainable Development Cooperation Framework 2021-25, Indonesia/ 2025 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: DMEL • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1 (High Priority): Undertake a thorough ToC exercise for the next CF to underpin the results framework (and agencies’ programmes). 1.1. Hold strategic discussion(s) (internal and with partners) to define strategic CF priorities based on a shared ToC for the country’s sustainable development 1.2. Once the priorities are agreed upon, develop a programme-level ToC to define concrete outputs that the UN can deliver in the following five years (and how each agency can contribute) ensuring to distinguish between results and strategies to be adopted in order to achieve those results (including digitalization and innovation). 1.3. Agencies to consider, whenever possible, to adopt the CF as their country programme document/strategy, detailing how their organization will contribute to the realisation of the CF outputs. This will not only facilitate alignment but also reporting.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | We recognize the importance of understanding the views and priorities of various stakeholders. Therefore, the RC has proactively initiated bilateral meetings with key stakeholders—including ministers, high-level officials, civil society organizations (CSOs), the private sector, and academicians—since the early phase of the Cooperation Framework (CF) process, starting with the Common Country Analysis (CCA). This engagement will continue throughout the CF development process until its finalization. We received the preliminary draft of the evaluation in Q4 2024, providing us with an early insight into the findings and recommendations. We recognize the need to articulate the underlying assumptions, causal pathways, and expected outcomes to ensure strategic coherence in the design of the next Cooperation Framework and individual UN entity country planning frameworks. To address this, we initiated the formulation of the ToC through a strategic dialogue, ensuring that the approach is relevant to the Indonesian context. Through this, we identified strategic priorities, outcomes, and the critical areas for UN work that could best use our comparative strengths to make progress.This process was followed by the development of results frameworks and discussions on how different agencies will provide support in key areas. A summary of the ToC demonstrating the connections between UN focus areas, intended outcomes, and achievement of strategic priorities will be included in the Cooperation Framework. Agencies that have CPD to adopt, or at least refer, the CF when developing their country programme documents/strategies Additionally, it will be important to ensure that agencies integrate their work plans, derived from their CPDs, into UNINFO to strengthen alignment with the Cooperation Framework (CF).
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | RC to hold bilateral meetings with relevant stakeholders (ministers, high-level officials, CSOs, private sector, academicians). | Q3 2024 – Q1 2025 (The activity already started with the CCA process) | RCO
1.2 | Conducted UNCT leadership dialogue with Head of Agencies to identify the potential UN priorities. Based on the dialogue, develop a clear set of priorities. | Q4 2024 (completed) | UNCT/RCO
1.3 | Ensuring that the priorities align with the National Medium Term Development Plan (RPJMN 2025-2026) and National SDG Action Plan 2025-2030 | RCO | RCO
1.4 | Once the priorities are agreed upon, develop result framework. | Q1 2025 | UNCT/RCO
1.5 | Ensure that UN entities derive country planning documents from the agreed logic and priorities of the UN Cooperation Framework. Additionally, ensure that agency programs are integrated into the Joint Work Plan in UNINFO. RCO to facilitate meetings and provide technical support as needed. | Q1 2025-Q4 2025 | UNCT/RCO
Recommendation 2 (Medium Priority): Enhance effectiveness of pilot Projects. 2.1. Ensure that pilot projects, demonstration activities and service delivery interventions are linked to policy level work. RCO to create a mapping of relevant policies that are being adopted at national level (with or without UN support) and put them in matrix with connected UN interventions for relevant working groups’ consideration. 2.2. RCO to prepare, in consultation with UNCT and GoI, a guidance note on pilots to ensure consistency in approaches, linkages with national policies and alignment with local priorities.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We agree that linking pilot initiatives to policy-level work is essential to achieving tangible and sustainable results at scale. However, rather focus on mapping, we will prioritise ensuring that all pilot projects link to policy work to improve the coherence of the UN’s support to policy discussions in Indonesia, contribute to greater effectiveness of pilot initiatives and ensure scalability and sustainable impact.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | UN agencies should strengthen the connection between their pilot initiatives and policy-level efforts to ensure scalability and sustainable impact | Ongoing | Agencies
Recommendation 3 (High Priority): Establish area-based planning and implementation. 3.1. Identify in the CF geographical areas where the UN could jointly contribute, based on CCA findings and in consultation with GoI. 3.2. As part of the JWP planning process, prioritise provinces and districts where UN can have joint interventions. This could be done in consultation with the Ministry of Home Affairs and jointly agree how national priorities are relevant to the different local contexts and how the UN could/should support. 3.3. Establish light UN coordination structures at the provincial/district level as platform for UN agencies working in that area to interact, share information and identify opportunities for contributions (including tapping into UN agencies’ expertise that is not present on the ground) which will feedback to the national level to relevant WGs.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We agree on the importance of focusing UN efforts on the parts of the country where the need is greatest. The UN will prioritize Eastern Indonesia and the districts identified as being most disadvantaged, utilizing existing coordination structures to coordinate locally. Agencies with local presence will take coordination roles in the region.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Agencies with local presence in priority areas will convene relevant staff to coordinate efforts as necessary. | Q3 2025 | UNCT
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4 (Medium Priority): Monitoring framework needs to be defined alongside the ToC. 4.1. Outcome level indicators to be aligned to the SDG indicators and RPJMN indicators, but ensure that these are logically strongly linked to the CF outputs, that targets are set to the end of the cycle, and indicators are prioritised. 4.2. Output level indicators include baselines and, where feasible, quantified targets. There needs to be a system in place whereby the coordination groups and/or the RCO combine and ensure consistency across agencies’ reporting. 4.3. Include indicators that specifically track gender equality (such as using GII dimensions), the empowerment of women and girls and the wellbeing of vulnerable groups and disaggregation of data across the monitoring indicators by gender and other LNOB factors (e.g. place of residence).
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | We fully agree on the importance of having a well-defined monitoring framework. The Cooperation Framework will have outcome-level indicators that are aligned with the SDGs and the RPJMN, ensuring that our efforts contribute to broader national and global goals. Supporting output-level indicators will be jointly defined drawing from the global output indicator menu to ensure consistency in measurement across entities. We will enhance the monitoring system by improving data contributions from focal points and strengthening the coordination role of the RCO, ensuring more consistent updates to indicators and better tracking of the UN’s contributions. We also agree to include indicators that specifically track gender equality. While there are no dedicated indicators for persons with disabilities and young people, we aim to collect relevant indicators that can be disaggregated by age and disability status to the extent possible. This approach ensures that gender and LNOB analysis—particularly for youth and disability inclusion—are mainstreamed in the monitoring framework.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Develop outcome-level indicators that align with both SDGs and RPJMN, ensuring a clear logical connection to CF outputs. Set specific targets for the cycle's end and prioritize critical indicators for enhanced focus and accountability. | Q1 2025 | RCO/UNCT
4.2 | Identify and align UN agencies' CPD outputs with CF Outcomes as the foundation for developing output-level indicators for the CF, ensuring clearly defined baselines and quantifiable targets. Whenever possible, those indicators shall be drawn from the globally-agreed output indicator menu. Implement a system where coordination groups and/or the RCO collaborate to ensure consistency and coherence across all indicators. | Q1 – Q2 2025 | DMEL
4.3 | Integrate specific indicators for tracking gender equality (Such as Gender Inequality Index (GII)), to focus on the empowerment of women and girls and the well-being of vulnerable groups. Ensure comprehensive data disaggregation in monitoring indicators by key LNOB (Leave No One Behind) factors such as geography, gender, and disability status. | Q1 – Q2 2025 | DMEL/ Cross cutting groups (gender group and disability focal points for 2021-2025 CF and the new cross cutting group for new/2026-2030 CF)
4.4 | Organize targeted training sessions and provide continuous support for agencies on effectively using the monitoring framework, training that focus on adapting to new indicators and data disaggregation requirements. | Q3 2025 | DMEL
Recommendation 5 (High Priority): Expand engagement of UN staff in joint planning, implementation and reporting under the guidance of the RCO. 5.1. Ensure that relevant UN agencies’ programme staff are substantively involved in the design of next CF and related JWP in a joint manner and throughout its implementation (not just at the reporting stage), and fully familiarised with the programme level ToC. This implies that agencies’ focal points for the CCA/CF process provide briefings and coaching to relevant staff in their own organization. 5.2. Continue the good practice by RCO (with concerned agencies) to offer RBM trainings and specific sessions on how to interpret UNInfo data categories (markers, QCPR functions, available resources, etc). 5.3. Consider appointing a few “UNInfo champions” across agencies (led by RCO) to act as first- respondents to guide colleagues on how to classify their SOs and write narrative for reporting, including markers and QCPR functions, notwithstanding the need to have a UNInfo focal point in each agency. 5.4. Enhance the ‘quality assurance’ role of the RCO over the information inserted in UNInfo and the use of this information for drafting the annual reports.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We recognize the importance of engaging relevant UN staff in joint planning, implementation, and reporting as part of efforts to drive increased coherence across the UN’s work. However, we also recognise the need for the time and resource demands of engaging with coordination structures to be balanced with other priorities. The UNCT will remain the primary channel for accountability and information sharing on the design and implementation of the Cooperation Framework. This will be complemented by a revamped, reinvigorated, and focused set of coordination groups with nominated focal points from UN entities engaged at different levels.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | The UNCT will be substantively involved in all elements of the design of the Cooperation Framework, through regular consultations and the circulation of draft documents. UNCT members are encouraged to circulate drafts and consult internally within their entities throughout this process. DMEL focal points will be directly consulted as part of the definition of the results framework. Thematic groups will be substantively consulted on areas related to their respective areas of work. | Q1 2025 | UNCT, DMEL, thematic groups
5.2 | Organise RBM training on the key areas not covered by previous training. We will also update the UN Indonesia UNInfo Guide and conduct refresher sessions on how to interpret UNInfo data categories (markers, QCPR functions, available resources, etc.). | Q3 2025 | DMEL, RCO
5.3 | Enhance the quality assurance role of head of agencies over the information inserted in UNInfo by establishing clear guidelines; conducting regular audits and reviews; providing training and support. | 2025 | UNCT
Recommendation 6 (Low Priority): Address issues of perceived and actual inefficiencies in procurement and decision-making processes. 6.1. Consider to hold briefing sessions to implementing partners to explain how the UN procurement systems function and the rationale behind certain processes. 6.2. Look into potential inefficiencies in procurement process and undertake a diagnostic to identify factors and how to address them.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | We agree that improving operational efficiency, and effectively communicating the steps that we are taking to do so, is an essential part of the UN development system reform that the Cooperation Framework aims to take forward. However, we perceived that the recommendation for holding briefing sessions to implementing partners to explain how the UN procurement systems function and the rationale behind certain processes may not be applicable because each UN agency has its own procurement process and system, and there is no standardized UN procurement system. To improve operational efficiencies, we are raising ambitions through the Operations Management Team (OMT) on the Business Operations Strategy which identifies joint commitments across entities to minimise cost inefficiencies. During 2025 in particular, the UNCT in Indonesia will also move to reduce duplication through the establishment of Common Back Office shared services, and priority re-evaluation of cost-savings through Common Premises negotiations. As tangible efficiencies and savings are made, we will consider options for effectively and appropriately communicating these with relevant stakeholders.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Organizing a UN Supplier Day to attract new suppliers and expand supplier base to participate in the UN tendering process. | 2025 | OMT
6.2 | Improve UN procurement efficiency by increasing the number of Long-Term Agreements (LTAs) within each agency while applying the mutual recognition principle to facilitate cross-agency use. This strategy will optimize procurement processes, minimize duplication, and shorten lead times. Additionally, monitoring and evaluation mechanisms should be implemented to track efficiency gains as part of the UN Business Operations Strategy's annual reporting. | Q1 2025 | OMT
6.3 | Agree and begin rollout of Common Back Office shared services across UN entities. | Q1-Q4 2025 | UNCT, OMT
6.4 | Consider options for effective communication of operational efficiencies to relevant stakeholders | 2025 | RCO
Recommendation 7 (Medium Priority): Ensure CF funding and its sustainability. 7.1. RCO to lead on the development of a partnership strategy for joint resource mobilization, but also to define opportunities and parameters for the UN to partner with CSOs, Academia and private sectors. 7.2. RCO to continue to explore opportunities for joint funding and JPs, including for area-based programmes and programmes that need a cross-sectoral approach (such as food systems, digital transformation, energy transition, sustainable consumption) and ensure that responsibilities among participating agencies are clearly defined.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | As per guideline, RCO will develop partnership strategy for joint resource mobilization to support implementation of the Cooperation Framework. This will focus in particular on resourcing top-priority integrated One-UN offers, and exploration of the most appropriate structures and tools for financing such joint initiatives. This will build on ongoing work on the implementation of the UN Funding Compact.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | The RCO will lead the development of a partnership strategy for joint resource mobilization. This will focus on integrated One-UN offers defined in the Cooperation Framework. This strategy should include appropriate structures and tools for financing joint initiatives, identify opportunities and set clear parameters for UN engagement with CSOs, academia, and the private sector. | 2025-2030 | RCO, UNCT, Agencies
Recommendation 8 (High Priority): Revamp coordination structure differentiating between operational coordination and strategic guidance. 8.1. Consider establishing a Programme Management Team (PMT), to empower the SDG group, or to assign directly to the UNCT to take the task of overseeing the implementation of the CF. The group should regularly discuss advancements in each outcome areas, identify cross- fertilizations and give directions on how change in the context might affect the CF’s ToC – the group should interact with BAPPENAS (different directorates) in order to prepare for the JSC meetings. 8.2. Under this group, establish operational working groups to coordinate actions on issues that are beyond one agency’s mandate and that are captured in the CF (either at outcome or output level), monitor results and articulate reporting. These should interface, as needed, with the relevant government counterparts and be coordinated by a dedicated RCO staff.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The 2026-2030 Cooperation Framework will include a redesigned and reinvigorated coordination structure, building on the lessons learned from the 2021-2025 Cooperation Framework. This will include clearly distinguishing between strategic guidance and operational coordination functions. The UNCT will provide overarching strategic direction, while Results Groups will serve as platforms to address implementation and operational challenges on the ground for each outcome. In addition, Thematic Groups will be established to focus on technical-specific issues such as operation, communication, data, M&E and thematic LNOB issues, ensuring specialized attention and expertise are applied to key areas. This clear delineation of roles fosters effective coordination, enhances resource mobilization, and promotes efficient problem-solving across both strategic and operational dimensions. Reflecting feedback in the need to manage the time and resource requirements of engaging with coordination structures, a PMT-equivalent body is not anticipated as part of the new coordination structure.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
8.1 | UNCT will establish a clear set of coordination groups to ensure structured and clear channels for engagement with agreed terms of reference and membership across entities, including: a. Result Groups to coordinate actions on issues related to each CF outcome that extend beyond any single agency’s mandate, as defined in the CF. b. Thematic and Cross-Cutting Groups as needed. c. DMEL d. UNCG e. OMT | Q4 2025 | RC/RCO
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 9 (Medium Priority): Expand partnerships and engagement with civil society at national and local level. 9.1. Revamp the civil society advisory board (or thematic groups), ensuring that there is representation of CSOs active in the sectors related to 2030 Agenda and the LNOB principle. The group(s) should be a forum for the UN system to exchange views and identify areas of potential collaboration.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | To enhance civil society engagement, the UNCT will work with a network of Young SDG Influencers that are active in civil society and work with CSOs on pressing matters, including LNOB-related issues.With the increasing penetration of social media and the growing influence of young influencers in Indonesia, this represents an area that extends beyond the traditional approach of working with civil society . This will complement the existing engagement with civil society already undertaken by individual agencies as part of their mandates. The UNCT will ensure inclusive engagement of CSOs, including organizations of persons with disabilities (OPDs).
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
9.1 | Young SDG Influencers group to be established and regularly consulted throughout CF implementation. | Q2 2025 | RCO and UNCT
9.2 | UNCT will strengthen the engagement of organizations of persons with disabilities (OPDs). | 2025 | Disability inclusion team
Recommendation 10 (High Priority): Develop joint messages/position papers on issues that are key priorities for UN action in the country, to be used for joint advocacy, programming, partnership-building.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: …… |  | We agree on the importance of clear and consistent communication of key messages on priority issues in the country by UN entities. Through the UNCT, Result Groups, and UNCG, efforts will be invested to strengthen this under the next Cooperation Framework. Development of more in-depth position papers will be dependent on resource availability amongst relevant entities, and will be considered as part of annual joint work planning.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by DMEL
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
10.1 | Result Groups to discuss and identify priority issues as part of annual joint work planning process, with the aim of developing joint messages and/or position papers for new strategic areas. Then, a lead agency should be designated to coordinate and facilitate the division of responsibilities. RCO may also be involved in the development of joint messages or position papers in strategic areas. Additionally, Result Groups should amplify advocacy efforts for existing joint papers and proactively enhance coordination and UN joint work at scale. | 2026-2030 | Result Groups

## Sheet2 (hidden)
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030