## Management Response
MONGOLIA UNDAF 2017 - 2022 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: UNDAF 2017-2022/ 2022 • Preparation of the management response: RCO • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: RCO, M&E group • Frequency of monitoring and updating: Annually
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF UNSDCF 2023-2027
Recommendation 1: The UNCT and the Government should improve the design and usefulness of the UNSDCF as an instrument to capture a shared vision and mission in the context of SDGs.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments | Actions taken in 2023 | Month of monitoring | Year of monitoring
1.1 | to develop a Theory of Change (ToC) to ensure that outputs are sufficient for the achievements of the outcomes, with suitable indicators. | 2022-05-20 | UNCT, RCO | completed | The Theory of Change (ToC) was conducted for UNSDCF 2023-2027 to ensure that outputs were sufficient for the achievement of the outcomes, with suitable indicators that can capture all the UN contributions. UNSDCF 2023-2027 was signed in May, 2022 and now available to the public.
1.2 | to use the latest edition of the new guidelines for developing UNSDCF to improve the design and usefulness. | 2022-05-20 | UNCT, RCO | completed | For UNDAF 2017-2022, the Joint Work Plan (JWP) was not developed in a format recommended by DCO and all projects implemented by UN agencies were list in UN-info, which made it difficult to show common results. However, the JWP for the UNSDCF was developed in a format of recommended by DCO in the UNSDCF Guidelines to enhance it's design and usefulness.
1.3 | to develop output level indicators which are attributable to the UN Development System. | 2027-12-31 | UNCT, RCO, M&E group | ongoing | In order to formulate the indicators in a way that allows for effective monitoring and evaluation, Output indicators for UNSDCF were selected from a list provided by DCO with frequent discussions with UN agencies' M&E officers and focal points. Furthermore, Methodological note/Meta Data for output level indicators is being developed. | M&E group assessed the indicators' readiness to report in Oct, 2023 and agreed to finalize the Methodogical note as 22nd of Jan, 2024. | December | 2024
1.4 | to conduct an indicators validation exercise/evaluability exercise to ensure the suitability of the results matrix to measure results. | 2024-12-31 | RCO | ongoing | Evaluability exercise/forsight analysis will be conducted to ensure the suitabilility of the results matrix. | The Methodological note can be considered as a basic exercise for output level indicators' evaluability. The M&E group worked extensively on the note and agreed to finalize it on 22nd of Jan, 2024. | December | 2024
Recommendation 2: The Government should strengthen its ownership and strategic management of the next UNSDCF.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
2.1 | to ensure UNSDCF 2023-2027 is being designed in consultation with the Government and other national stakeholders in the strategic prioritisation process to collectively formulate the shared development vision and strategic priorities to build strong ownership. | 2022-05-20 | GoM, UNCT, RCO | completed | Strategic priorities of UNSDCF were jointly designed with the government and other stakeholders, ensuring its alignment with national priorities. The strategic priorities were approved by the National Committee for Sustainable Development (NCSD) chaired by the PM of Mongolia. The Government-UN Joint Steering Committee (JSC) was established to oversee UNSDCF implementation in coming five years.
2.2 | to ensure JSC meeting organize at least twice a year and engage with the government and relevant stakeholders in all the phases of the UNSDCF 2023-2027 implementation through active involvement in consultative processes and requesting their review and/or feedback on the progress. | 2027-12-31 | RCO | ongoing | Accroding to ToRs, the JSC meets at least twice a year to take stock of the progress and alignment of the UNSDCF with evolving national priorities and regional and international development contexts. | JSC meetings were held twice on 17th of March and 11th of December 2023. | December | 2024
2.3 | to ensure RGs organize 4 meetings annually (online or face to face) to prepare for key processes (JWPs, MYR, APR, Joint implementation), not relying solely on conducting work via email. | 2027-12-31 | RGs, UNCT, RCO | ongoing | As per the ToRs indicates, the RGs meet quarterly. RGs shared their meeting schedule in common calendar and the first meeting in 2023 is planned to be held in May. | On 5th of December 2023 all three RGs had the retreat. Besides that all RGs had 3 meetings. | December | 2024
Recommendation 3: The UNCT and the Government should contemplate creating an integrated funding framework in the next UNSDCF, and adequate funding instruments to ensure the scale of impact necessary for attaining the 2030 Agenda.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
3.1 | to develop Annual and Multi-Year Funding Framework based on the JWP, including operational and communications budgets (estimates are included for outcomes and outputs, and the costing of inputs and services based on agency standard costs). | 2023-12-31 | RMGs, RCO | completed | The Annual and Multi-Year Funding Framework is developed based on the JWP. |  | December | 2023
3.2 | to develop a Joint Resource Mobilization Strategy (JRMS) with clear actions based on the analysis of the development financing landscape in Mongolia and innovative financing opportunities. | 2023-12-31 | RMGs, RCO | ongoing | The Joint Resource Mobilization Strategy is being developed. | The JRMS is drafted by RCO and will be shared with UNCT and RGs for further improvement. | December | 2024
Recommendation 4: The UNCT and the Government should strengthen the sustainability of the UNSDCF.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
4.1 | to ensure UNSDCF is being designed in consultation with the government and other national stakeholders in the strategic prioritisation process to collectively formulate the shared development vision and strategic priorities to build strong ownership. | 2027-05-20 | GoM, UNCT, RCO | completed | Visioning and prioritization exercise was conducted jointly with the government and key government officials including the State Secretaries and Heads of Stratgeic Planning Departments of all line ministies and other government agencies participated to define the SPs and Outcomes of the CF in early November 2021.
4.2 | to ensure INFF is being implemented smoothly to contribute the sustainability of results. | 2025-12-31 | UNDP, UNCT, RCO | ongoing | UNRC requests PUNOs to ensure effective engagement with the respective government institutions for their adoption of the INFF strategy and its implementation. UNRC communicates with highest level of government officials in the MCSD for better coordination. | The concept note for INFF governance structure was developed and consulted with the National Stakeholders | December | 2024
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 5: UN agencies should implement the UNSDCF and increase their cooperation through the Outcome and Thematic Groups and use them to help the UNCT managing the UNSDCF strategically, with the RC/UNCT leadership.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
5.1 | to strenghthen internal cooperation and synergies among agencies involved in the implementation of UNSDCF to reach higher-level results, through RGs. | 2027-12-31 | RGs, RCO, Theme groups | ongoing | UN Result Groups (RGs) were set up on each of the strategic priority areas of UNSDCF. These RGs will ensure that respective outcomes will be achieved through the UN's collective and coherent efforts. * Thematic groups of (1) Human Rights, (2) Gender, (3) Youth are operational supporting the UNCT in implementing UNSDCF. * Support groups of (1) M&E group, (2) Communication group, (3) Resource Mobilization group, (4) Operational Management group are operational supporting the UNCT strategically implement and monitor UNSDCF. | Communication group developed the collective strategy and M&E group developed MEL plan to support RGs for UNSDCF's implementation. The Youth Thematic Group has updated the Terms of Reference in alignment with the UNSDCF for 2023-2027, which recognizes youth empowerment as a pivotal cross-cutting enabler for accomplishing the goals of the Cooperation Framework. Additionally, the Youth group has formulated a joint annual work plan. RGs held quarterly meetings to facilitate efficient communication among the contributing agencies. RG disseminated information from RCO swiftly among the member organizations. | December | 2024
5.2 | to rotate the agencies co-chairing the RGs to make them more dynamic and offer the agencies a sense of mission and achievements | 2027-12-31 | RC | ongoing | Agencies agreed to chair the RGs on rotational bases to increase the cooperation. | In 2023, UNICEF and UNFPA (co-chair) chaired RG-1, FAO and ESCAP (co-chair) chaired RG-2 and UNDP and ILO (co-chair) chaired RG-3. The chairpersonship will be rotated in 2024. | December | 2024
Recommendation 6: The UNCT should promote effective partnerships and strategic alliances around outcome areas, and with a variety of stakeholders, in order to enhance UNSDCF effectiveness.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) |  | Monitored by RCO, M&E group
|  |  |  | Status of implementation | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
6.1 | to involve NGOs and CSOs at a more strategic level in UNSDCF design and implementation. | 2027-12-31 | RGs, RCO | ongoing | NGOs and CSO were involved in the strategic level in UNSDCF design and are expected to be closely engaged in the implementation of UNSDCF. | Each organization are engaged with CSOs and NGOs suring the implementation phase. | December | 2025
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 7: The UNCT should ensure greater mainstreaming of the UNSDCF guiding principle Leave no one behind and Human Right-Based Approach under the leadership of the RC.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
7.1 | to ensure that the UNSDCF, as the successor to UNDAF indentifies precisely the vulnerable groups for addressing the principle Human Right-Based Approach and Leave No One Behind (LNOB). | 2022-05-20 | UNCT, HRTG, RCO | completed | The UNSDCF 2023-2027 has identified precisely the vulnerable groups for addressing the principle "Leave No One Behind". Those are (1) children and adolescents, (2) Rural poor and herders, (3) ethnic minorities, (4) unemployed and unskilled youth, (5) women and girls, vulnerable men, (6) persons with disabilities, (7) older persons, (8) urban poor and internal migrants, (9) sexual minorities and (10) victims of human trafficking.
7.2 | to train UN programme staff, government officials and other partners to build their capacities on LNOB, HRBA and GEWE. | 2027-12-31 | HRTG, OHCHR | ongoing | The training was organized for UN programme staffs in October, 2021. |  | December | 2025
7.3 | to ensure the Human Right Thematic group (HRTG) has more active engagement with related government stakeholders, CSOs. To ensure developing organic and active engagement with RGs and HRTG. | 2027-12-31 | RGs, HRTG, UNCT, RCO | ongoing | The Human Rights Theme Group (HRTG) is chaired by HRA at the UNRCO. The HRTG meets every quarter, calling additional ad hoc meetings as necessary |  | December | 2025
7.4 | to encourage RGs and HRTG to facilitate UN's collective work to issues of vulnerabale groups and Human Rights by capitalizing UN agencies' comparative advantages. | 2027-12-31 | RGs, HRTG, UNCT, RC | ongoing |  | In 2023, The HRTG had 4 meetings (quarterly). | December | 2025
Recommendation 8: The UNCT should ensure a greater mainstreaming of the UNSDCF guiding principle on gender equality and women’s empowerment.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
8.1 | to reflect GEWE as a cross-cutting principle (in terms of specific goals and targets set, gender disaggregated data and indicators.) | 2022-05-20 | RC, RCO | completed | Two output level indicators developed related to GEWE: (1) Number of women and young people engaged and participating in dialogue and decision-making and peacebuilding processes, with UN support, (2) Number of partnerships with women-led civil society organizations (CSOs) and other bodies and networks to advance women’s leadership and participation and gender equality under Output 4.4 of Outcome 4, UNSDCF. | At outcome level, a total of 5 of the 22 (23%) of indicators track changes in gender equality results. At output level, 20 of the 39 (51%) of indicators track progress towards GE results. This gives an overall figure of 25 of the 61 indicators, meeting the UNCT SWAP minimum requirements for this indicator.
8.2 | to increase collaboration between RGs and the Gender Theme Group (GTG) to regularly monitor the gender sensitivity and responsiveness of interventions implemented under UNSDCF and joint programmes among UN agencies. | 2027-12-31 | RGs, GTG | ongoing | GTG meets quarterly. RGs shall collaborate more with GTG to ensure the quality of gender mainstreaming across the joint programms. | In 2023, The GTG met more than 4 times. | December | 2025
8.3 | to encourage Gender Thematic Group (GTG) to facilitate UN's collective actions to Gender equality and women's empowerment (GEWE) capitalizing UN agencies' comparative advantages. | 2027-12-31 | RGs, GTG | ongoing | GEWE is a UNCT priority for 2023 to be focused on more closely. Joint programs on GEWE is necessary for UN agencies to accelerate implementation on SDG#5. | The UNCT-SWAP Gender Equality Scorecard assessment was conducted in Mongolia between September and October 2023. The GTG formed the basis of the Interagency Assessment Team (IAT), with additional members appointed to ensure representation from other relevant coordination mechanisms as per the guidance. The SWAP assessment process in Mongolia included four stages: Preparation, Self-Assessment, Action Planning, and finalization. The report was uploaded to the UNCT-SWAP Platform. | December | 2025
8.4 | to ensure the GTG has more active engagement with related government stakeholders, CSOs. To ensure developing organic and active engagement with RGs and GTG. | 2027-12-31 | RGs, GTG | ongoing | UN Mongolia incorporated critical GEWE issues across sections in the Voluntary National Report 2023, where inputs collected from local CSOs. On the occasion of international women's day March 8 of 2022, GTG has organized joint event with local CSOs and jointly discussed progress on gender equality and women's empowerment in Mongolia | Individual agencies are working in collaboration with GEWE CSOs and womens rights advocates on initiatives that foster GEWE the current cycle of CF. During the 16 days campaign against GBV, two leading agencies UNDP and UNFPA jointly organized events with national CSO. | December | 2025
Recommendation 9: The UNCT is invited to stregthen joint programming, resource mobilization and implement joint targeted programmes, while taking inco account geographic spread of UN interventions, integrated programming, and geographical targeting experiences.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
9.1 | to mobilize resources for, and implement targetted "joint programmes" reflecting complementarities amongst UN agencies to collectively work together on common national development priorities and where there is the possibility for higher-level results and reduced duplication of efforts in particularly strategic areas. | 2027-12-31 | UNCT, RCO | ongoing | UNCT has submitted 2 proposals to Joint SDG Fund in 2022. UNFPA and UNICEF have submitted a proposal to the Gobi Oyu Development Support Fund (DSF) on the second phase of the Integrated Support Programme in Umnugobi province for 2023-2027. | RGs drafted the concept notes for joint programmes. UNCT submitted expression of interest to SDG fund for UN Joint Programme (JP). | December | 2025
9.2 | to analyze and assess UN agencies capacities, comparative advantages (geographic spread, geographical targeting experiences) to increase synergies between UN agencies interventions. | 2027-12-31 | RCO, M&E Group, RGs | ongoing |  | All sub-outputs in UN-info are shown geographically in Data-portal. https://uninfo.org/location/107/programming | December | 2024
Recommendation 10: The UNCT and the Government should strengthen their use of effective Results-Based Management (RBM) and M&E systems to strategically monitor and manage the UNSDCF.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
10.1 | to formulate the UNSDCF result matrix with indicators and targets of different level (outcome and output) to permit performance monitoring and evaluation of impact. The UNSDCF result matrix shall demonstrate a causal logic relationship from input to results based on ToC. | 2022-05-20 | M&E group, RGs, RCO | completed | UNSDCF has outcome and output level indicators which allow to have performance monitoring and evaluation of impact.
10.2 | to develop Monitoring, Evaluation and Learning (MEL) Plan for the UNSDCF to promote coherence and consistency of the M&E plans of individual UN entities. | 2023-12-31 | M&E group, RGs, RCO | completed | M&E group will be working on this tasks. | M&E group developed the MEL Plan.
10.3 | to ensure the M&E group constantly supporting UNCT for UNSDCF's implementation against JWP' M&E Framework with the support of RCO. | 2027-12-31 | M&E group, RGs, RCO | ongoing | M&E group supported the RGs for JWP development of UNSDCF. The group meets frequently in first quarter due to planning and reporting processes and for the remaining period it meets quarterly. | M&E group met regularly (7 times) to support the RGs for JWP related tasks. JWP Reporting and Updating guidance is now developed. | December | 2024
10.4 | to strenghthen the group on Results Based Management (RBM) and overall Monitoring and Evaluation (M&E) capacity. | 2027-12-31 | RCO | ongoing | Needs analysis will be conducted. | End Year Reporting - Result based writing training was conducted twice by M&E group in November, 2023. In total, 38 UN staff attended the training. | December | 2024
Recommendation 11: The UNCT, the National Statistics Office, and ministries should strengthen collaboration, in view of improving national capacities for disaggregated data collection, analysis, dissemination and use, especially given their importance for measuring progress on the SDGs and next UNSDCF implementation.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
11.1 | to continue the support strengthening national capacities for disaggregated data collection, analysis and dissemination to measure the progress on SDG and UNSDCF's implementation. | 2027-12-31 | RGs, UNCT, RCO | ongoing | UN agencies continue supporting NSO and the ministries capacities in dissagregating the data collection, analysis and dissemination. In 2022, "Mapping SDGs Indicators" exercise was conducted in close cooperation with NSO. In addition, to support the implementation of UNSDCF "Measurement and Analysis of Economic Diversification in Mongolia" was conducted. | UNICEF and UNFPA started conducting Multiple Indicator Cluster Survey (MICS7) in cooperation with NSO. | December | 2024
Recommendation 12: The UNCT should continue its effort to reduce transaction costs where possible.
Management response - Accepted/Partially Accepted/rejected : …….. | [5 empty] | Accepted
If rejected or partially accepted, please provide an explanation: ………
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Status of implementation | Monitored by RCO, M&E group
[5 empty] | Comments (or action taken) | Actions taken in 2023 | Month of monitoring | Year of monitoring
12.1 | to endorse and sign off Business Operations Strategy (BOS) Annual Review | 2027-12-31 | OMT, UNCT, RC | ongoing | The Business Operations Strategy (BOS) is being reviewed annually. | The annual review for 2023 is completed in April, 2023. | December | 2024
12.2 | to ensure joint common activities in the area of Finance, Human Resources, Procurement, ICT will be facilitated to support and contribute to the UNSDCF implementation. | 2027-12-31 | OMT, UNCT | ongoing | OMT has been advised to explore opportunities for further enhancing business efficiency and reducing cost by optimizing and synergizing business operations. | Additional three common services were added into the BOS Annual Review. | December | 2024

## Sheet2 (hidden)
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030