Draft TOR UN CF 2021-2025

Final Evaluation

Terms of Reference for the Final Cooperation Framework Evaluation (2021-2025) UNCT Serbia

1.	Introduction

The Final Cooperation Framework (hereinafter CF) Evaluation is an external, independent exercise aimed at generating an independent assessment of results, successes, challenges, and lessons learned to inform the main stakeholders and feed into the next programming cycle.

The Final CF Evaluation in Serbia will be guided by the UNEG - DCO UNSDCF Evaluation Guidelines (July 2022). It will ensure accountability, support learning, and inform decisions to guide the design of the next CF cycle. The evaluation process will be transparent and inclusive (involving relevant stakeholders) with robust quality assurance. Evaluation results and recommendations will be derived from, and informed by, the conscientious, explicit, and judicious use of the best available, objective, reliable and valid evidence and data. CF evaluation will be managed by independent evaluators who exhibit professional and cultural competencies, and excellent understanding of the development context in the Republic of Serbia and the Western Balkan region.

  - Background – Country context

Serbia is a landlocked country situated in Southeast Europe with a population of 6.6 million people, according to the 2022 census. For the past 25 years Serbia has been facing unfavorable demographic trends: low natality rate, negative natural growth rate and , aging (with average age 42,9) and increase in share of population aged 65 years and over. According to the 2022 Census data, the total fertility rate (i.e. the number of live births per woman), slightly increased in 2022 to 1.63. Fertility and its growth are at the forefront of the government's focus and measures. Furthermore, the Government estimates further increase in the total fertility rate, projecting it to reach 1.75 by 2027. r. The 2022 Serbia National Human Development Report, shows that Serbia’s total population will continue declining in the future and that the state and society will have to formulate new responses to the demographic challenges ahead. Serbia has high levels of internal migrations from rural to urban areas and emigration, resulting in overall negative migration balance. In the decades preceding the current CF, Serbia struggled with lagging economic growth, underdevelopment of rural areas and regional disparities, relative high unemployment, low levels of investment and an increase in public debt. Since 2014, the Government of Serbia has initiated a series of stringent economic reforms and fiscal adjustments, combined with structural reforms, that aimed to curb public spending, foster fiscal stability and encourage economic growth. The government measures resulted in slow but steady economic growth since 2015, resulting in the relative improvement of the living conditions and lowering of the overall at-risk of poverty rate from 26.7% in 2015 to just over 20% in 2022.

Serbia’s development priorities are aligned with the 2030 Agenda, as well as with the strategic goal of EU membership, building on the strong synergies between the two processes. The Republic of Serbia was granted the status of EU candidate country in 2012 and accession negotiations started in 2013. To date, 22 out of 35 chapters have been opened and two chapters have been provisionally closed. Since 2021, Serbia has accepted the Europe Union’s revised enlargement methodology striving to align domestic regulations with the EU and adjusts reforms to the accession priorities set under the six EU thematic policy clusters. Since the onset of the international political crisis caused by the conflict in Ukraine and stalled negotiations with Kosovo, Serbia’s EU negotiations progress has been relatively dormant with no further progress since 2022.

In the past four years Serbia continued to implement reforms aimed at aligning its legal, political, and economic systems with EU standards. From 2021 to present, the EU Commission reported that Serbia made good progress in developing a functioning market economy, digital transformation, and sustainable energy development. Progress has also been noted on statistics, data collection, analysis and reporting, public access to institutional data, and agricultural reforms. Fiscal governance reforms have progressed well, particularly as regards the adoption of revised fiscal rules. Progress was achieved in several areas within the Internal market cluster, freedom of movement for workers through coordination of social security systems, and legislative alignment in free movement of goods with the EU.

Followong the adoption of the 2030 Agenda in 2015, Serbia established a national mechanism for its implementation: the Inter-Ministerial Working Group (IMWG) for the Implementation of the United Nations 2030 Agenda for Sustainable Development. Following the June 2020, and April of 2022 elections, the IMWG was not re-established, while the SDG coordination was entrusted to the Prime Minister’s Advisor on the SDGs and to some extent to the Ministry of EU Integrations. After the elections from December 2023, no SDG coordination body has been established so far (technical government in place). Enhanced capacity to work across silos and bring together different stakeholders will be especially important in following up on Serbia’s commitments in key multilateral frameworks – including most recently the outcomes of COP28, the Sustainable Food System Summit, the Transforming Education Summit, and Serbia’s reaffirmation of its commitment to the Agenda 2030 during the SDG Summit in September 2023.

While many challenges remain, Serbia is making progress towards the achievement of the 2030 Agenda in several key areas. The Progress report on the implementation of SDGs by 2030, published by the Statistical Office in April 2023 shows significant progress in SDGs 1 (No poverty), 3 (Health) and 5 (Gender) while certain regress or lack of data in noted by indicators in SDG 4 (Education), SDG 10 (Inequalities) and SDG 13 (Environment). According to the UNDP Insight Report from 2023, almost 25% of the SDGs are on track to be achieved in Serbia, against 18% at global level. According to the Human development report, Serbia's Human Development Index for 2022 is 0.805, which ranks it 65th on the list of 193 countries and territories included in the report. Over the past three years, Serbia’s HDI has remained relatively stable, with minor fluctuations. HDI for 2021 was 0.802, for 2020 - 0.804 and HDI for 2019 was 0.806. For now, Serbia’s HDI remains in the high human development category.

Many of Serbia’s development challenges were taken into consideration when formulating the CF 2021-2025, jointly by the UNCT and the Government of the Republic of Serbia; while the CF document specifically recognizes the EU integration process as the overarching priority for Serbia’ national development agenda.

1.2 Background - Cooperation Framework (2021-2025) Main Characteristics

The Government of the Republic of Serbia (GoS) and the United Nations Country Team in Serbia have jointly developed CF for the period 2021-2025 that was finalized and signed in February 2022. The CF was signed by the Government of the Republic of Serbia and twenty UN Agencies, Funds and Programmes active in the country. The framework articulates a collective vision and response of the UN development system to national development priorities and activities to be implemented in partnership with the GoS and in close cooperation with the international partners and civil society until 2025. This strategy was developed following an extensive Country Context Assessment and a comprehensive series of consultations with all relevant stakeholders. The key outcomes of the CF are fully aligned and contribute to the achievement of the SDGs, in complementarity with the six EU thematic policy clusters of the Negotiating Framework. The CF 2021-2025 process was designed to strengthen national ownership through the recognition, support, and advocacy of effective public policies, as well as reliance on domestic institutions, systems, and resources in the achievement of the Sustainable Development Goals and EU Acquis Chapters. The Cooperation Framework is based upon, and contributes to, the country’s development priorities that are primarily articulated through the National Programme for the Adoption of the EU Acquis (NPAA), The Economic Reform Program (ERP) 2021–2023 and Employment and Social Reform Programme (ESRP).

The CF envisages that, by 2025, significant progress will have been made towards the three strategic priorities defined by the CF: 1. Realizing the full potential of a green, sustainable and inclusive economy. 2. Placing well-being, social justice and human potential at the heart of systems, policies and practices. 3. Build trust and mutual accountability through the rule of law, the rights and duties agenda.

The implementation of CF was operationalized through the Joint National Steering Committee (JNSC) for strategic guidance and oversight and three Results Groups (RGs), each responsible for one CF strategic priority, tasked to develop and implement the annual joint work plans (JWPs) in cooperation with national counterparts.  The CF Results Groups are closely coordinating their work for effectiveness, in line with the provisions set in the Management and Accountability Framework (MAF). In support to the Results Groups on cross-cutting and operational issues, the CF also established a number of thematic and technical groups: Gender Thematic Group (supports gender mainstreaming throughout the CF), Human Rights and LNOB Group (implementation of human rights and LNOB principles and standards in the CF), Operations Management Team (OMT), Communication Group (enhancing joint communication), Monitoring and Evaluation Group (joint tracking and reporting of results), Ad-Hoc Inter-Agency Groups (Refugee and migration management, Humanitarian CT).

Primary responsibility for monitoring and assessing performance of the CF rests with the Joint National Steering Committee and UNCT based on the semi-annual (interim) and annual reporting provided by CF Results Groups. A Monitoring and Evaluation Group (MEG) of the UNCT provides technical advice to UNCT and JNSC, tracs the achievement of the CF Joint Work Plan output indicators and supports monitoring of the overall country progress related to SDG targets. All CF JWP progress data is managed and transparently reported through the UN Info platform. UN Info is an online monitoring platform providing open tracking of the United Nations contributions to the achievement of the SDGs in all countries where United Nations Country Teams operate.

The eight outcomes are defined by the CF to be achieved by 2025, under three Strategic Priorities in cooperation with the Government of the Republic of Serbia, the UNCT, the EU and other international and civil society partners:

| Strategic priority | Outcome |
| --- | --- |
| Strategic Priority 1 - Serbia harnesses the full potential of a green, sustainable and inclusive economy: increasing opportunities for all, and reducing risk. | 1.1 Serbia adopts and implements climate change and environmentally friendly strategies that increase community resilience, decrease carbon footprint, and amplify equitable benefits of investments. 1.2 Natural and cultural resources are managed in a sustainable way 1.3 Equitable economic and employment opportunities are promoted through innovation |
| Strategic Priority 2 - Well-being, social equity, and the human potential are at the heart of systems, policies and practices: everyone has equal opportunities, throughout their life, to achieve their full potential. | 2.1 Universal and inclusive access to quality health, social and protection services is improved 2.2 Skills, education and capabilities are enhanced to ensure equitable outcomes for all 2.3 Mobility and demographic transition become vectors for positive change and prosperity for all people |
| Strategic Priority 3 - Building trust and mutual accountability through the rule of law, rights and duties agenda: fostering transparency, fairness and effectiveness. | 3.1 All people, especially the more vulnerable, benefit from the realization of human rights, gender equality, social cohesion and enhanced rule of law in line with international commitments 3.2 All people benefit from effective governance and meaningful civic engagement |

The strategic priorities and outcomes reflect both the needs of the country and the UNCT’s comparative advantage in supporting the Government of Serbia to address them. The UNCT actions are framed in the larger setting of the United Nations Secretary General’s Call for the Decade of Action to accelerate the implementation of the SDGs. Each CF Strategic Priority and Outcome was further developed with the corresponding set of indicators containing baselines and targets, specifically designed to measure the progress toward results over the implementation period. The CF Results Matrix (Annex I to CF) represents an integral part of the document and a key reference point for the CF final evaluation.

The CF Theory of Change was developed with consideration to the three dimensions of social, economic and environmental progress whilst integrating the concepts of sustainability, inclusiveness and resilience into implementation. The prioritisation and development of CF Theory of Change was grounded in the international human rights standards and commitment reviews by the United Nations human rights mechanisms. ToC incorporated the identified needs for health security, improved well-being and equality for all, stronger resilience of society and the economy to future potential shocks, a green recovery with a triple objective to reduce pollution in the coming years, reach carbon neutrality by 2050, and create new sustainable jobs. Together with human rights and gender equality, these objectives embody a nexus of change and partnership that offered an effective pathway for the United Nations system in Serbia to make tangible, measurable contributions towards achievement of the 2030 Agenda.

Multiyear funding overview of the CF has projected 365 million USD as total required resources for the successful implementation of the intendent results framework. In the three-year implementation period (2021-2023) the UNCT Serbia has already secured 312 million USD of total available resources (85% of total funding coverage). Full annual funding overview of planned and delivered resources are available in the UNCT Serbia Annual Results Reports (2021-2023).

Based on the internal configuration exercise, a total of 20 UN entities committed to extend or deploy their mandates and capacities for the Cooperation Framework, de facto constituting the Serbia UNCT for the 2021-2025 period (in alphabetical order): FAO, ILO, IOM, ITU, OHCHR, UNICEF, UNCTAD,UNDP,UNECE, UNESCO, UN Women, UNEP, UNHCR, UN Habitat, UNIDO, UNDRR, UNOPS, UNODC, UNFPA, WHO. The number of UNCT entities has increased by one compared to the previous programme cycle (19). Two entities left (IAEA and UN WTO), while three new entities joined (ITU, UN DRR and UN Habitat). The continuity of the previous development work was ensured, while the new entities contribute with additional expertise and operational modalities.

2. Purpose and Objectives of the CF Evaluation

The Final CF Evaluation has two primary purposes:

- Promote greater learning and operational improvement. The evaluation will provide important information for strengthening programming and results at the country level, specifically informing the planning and decision-making for the next CF programme cycle and for improving UN coordination at the country level. The UNCT, host government and other CF stakeholders can learn from the process of documenting good practices and lessons learned, which can then be shared with DCO and used for the benefit of other countries.

- Support greater accountability of the UNCT to CF stakeholders. By objectively providing evidence of results achieved within the framework of the CF and assessing the effectiveness of the strategies and interventions used, the evaluation will enable the various stakeholders in the CF process, including national counterparts and donors, to hold the UNCT and other parties accountable for fulfilling their roles and commitments.

The overall objectives of the evaluation are to:

- Assess the contribution of the CF to national development results through evidence-based judgements using evaluation criteria (accountability). What difference did the CF intervention make in Serbia’s development as opposed to not having the CF?

- Identify the main factors that have affected the CF’s contribution; answer the question of why the performance is as it is; and explain the enabling factors and bottlenecks (learning).

- Reach conclusions concerning the UN’s contribution across the scope being examined.

- Provide actionable recommendations for improving the CF's contribution, especially for incorporation into the new CF programming cycle. These recommendations should be logically linked to the conclusions and findings of the evaluation and should draw upon lessons learned identified through the evaluation.

Evaluation will provide key information on achieved development results primarily to the Government of the Republic of Serbia, the United Nations Development System, and the UN Country Team in the Republic of Serbia. It will also be a key source of information for international institutions, donors, civil society organizations, and the Serbian public at large about the achievements of the Cooperation Framework between the United Nations Country Team in Serbia and the Government of the Republic of Serbia in the period 2021-2025.

3. Scope of the Evaluation

Programme scope: This evaluation will look at the Serbia’s UNSDCF 2021-2025 as a whole and its implementation instruments, specifically the implemented UNCT Serbia Joint Work Plans for 2021-2023 (three JWP rounds) and current JWP 2024 in implementation. The evaluation will pay special attention to the mainstreaming and application of the main CF programming principles in CF design and implementation: integrated and multidimensional programming approach (in line with five Ps and 2030 Agenda), Leaving no One Behind, Human Rights-Based Approach to Development, Gender Equality and Women’s empowerment, Resilience, and Accountability as specifically stated in the UNSDG Guidance on CF design.

The Evaluation Team will be expected to collaborate with and take into account the agency-specific programme evaluations for comprehensive coordination, including their contribution to the subject expertise, as it is assumed that the agency-specific programme evaluations, with its achieved results, contribute to attaining the overall UNSDCF assessment.

Time scope: The CF evaluation will cover the programme implementation period from January 2021 to September 2024.

Geographic scope: The evaluation will be conducted mainly in Belgrade where the key programme stakeholders are. However, during the inception phase, in consultation with the UNCT, the evaluation team will identify 2 to 3 regions with adequate programme representation for field visits.

4. Evaluation Criteria and Questions

The intended evaluation approach including the main evaluation criteria and questions must comply with the UNEG - DCO UNSDCF Evaluation Guidelines.

The questions presented in the table below are indicative suggestions to be finalized by the Evaluation Team during the Initial Phase and presented in the Inception report upon agreement between the Team leader and Evaluation Manager. The evaluation team will finalize the evaluation questions after consultations with the Evaluation Management Group. The final evaluation questions should be a reasonable number, generally not exceeding 15. They should clearly reflect the evaluation criteria as well as the indicative evaluation questions listed in these Terms of Reference. They should also take advantage of the results of the reconstruction of the intervention logic of the cooperation framework. The evaluation questions will be included in the evaluation matrix (see appendix) and should be supplemented by sets of hypotheses that capture the key aspects of the intervention logic associated with the scope of the question. Data collection for each of the assumptions will be guided by clearly formulated quantitative and qualitative indicators, also indicated in the matrix.

| Criteria | Evaluation questions |
| --- | --- |
| Relevance The extent to which the objectives of the CF are consistent with the needs and interests of the Serbian people, the needs and priorities of Serbia and its international obligations, Serbia’s EU integration agenda, the Sustainable Development Goals. | - Is the identification of the main development challenges, with their respective causes, clear in the CF? What has been CF relevance in contributing to the national development goals (EU Accession strategies, Economic and Social reforms) key development issues and achievement of the SDGs? - To what extent have the Serbia’s national, local authorities and civil society been taken into consideration, participated, or have become involved, at the design stage of the CF? - To what extent was the CF results matrix designed as a results-oriented, coherent, and focused framework? |
| Effectiveness: Assessment of the performance of CF support to Serbia’s development in terms of achieved of results. | - Is the CF likely progressing towards the attainment of the established outcomes, goals and targets as set in the CF results matrix? Have the outputs been achieved, and to what extent they contribute to the CF Outcomes? - Have the CF results responded to the needs and priorities of the target populations? To what extent did the CF interventions reach the vulnerable groups – (women, children, persons with disabilities, Roma communities, youth, older persons, low income families, LGBTI community)? To what extent have human rights principles and gender equality been effectively streamlined in the implementation of the CF? - How were risks and assumptions addressed during the implementation of CF outputs and activities? How well did the UNCT and CF stakeholders respond to unplanned situations (specifically Covid19) and what were the effects on CF implementation? |
| Efficiency: The extent to which the SDCF established and implemented clear procedures to provide coordinated support and the relationship of inputs (financial and staff) to the achieved results. | - How has the UN system mobilized and used its resources (human, technical and financial) and inter-agency synergies to achieve the planned CF results? - Compare efficiency achieved under joint programming and individual approach models? To what extent has the existence of the CF contributed to mobilization of national and donor resources. - The extent to which resource allocation took into account or prioritised most marginalised groups including women and girls. To what extent were adequate resources provided for integrating Human Rights and Gender Equality in the CF? |
| Coherence and Coordination: To what extent has the CF strengthened the coherence and coordination of support by UNCT members | - Post UN reform, to what extent have UN agency programs and work plans been effectively and meaningfully derived from the CF both in design and implementation? - To what extent has the CF fostered internal coordination? To what extent have the different UN agencies contributed to the functioning and consolidation of UNCT coordination mechanisms keeping in mind the spirit of the UN reform and adhering to it? - To what extent did the post reform Resident Coordinator office’s roles and responsibilities enable positive UNCT’s joint convening power and better coherence of the country team? |
| Sustainability: The evaluation will examine the sustainability of the CF results and benefits and explore whether CF outputs and activities develop/strengthen mechanisms to promote scaling up and replication of successful results. | - What are the main development changes achieved by CF that are likely to last? Which outcomes can be sustained without further interventions? - Has CF enabled innovative approaches embedded in institutional learning for national capacity development (government, civil society and NGOSs) to enable these actors to continue achieving positive results without the UN/development partners’ support? |
| Orientation toward Impact: The progress to impact criteria will be used to assess of the overall CF stakeholder contributions to the well-being of vulnerable groups, individuals, households and communities that could be credited to the CF implementation. | - What were the most significant changes in the well-being of citizens of Serbia (individuals, households and communities) that could be linked to the CF? - What unintended results – positive or negative – did the CF implementation produce? |

5. Evaluation Approach and Methodology

The evaluation should demonstrate whether or not the UN is making a difference in supporting governments and people to achieve the 2030 Agenda. The evaluation will therefore assess the UN’s contribution to the intended change defined in the CF ToC. A contribution analysis using a theory-based approach is a suggested evaluation perspective that can be considered.

The CF evaluation should use a participatory and consultative approach, whereby key CF stakeholders and national partners are engaged, and their views and feedback are collected and used at different stages of the evaluation process.

Theory of change analysis: During the inception phase or early in the data collection phase, the evaluation team will hold ToC meetings with the result or thematic groups to confirm a common understanding of the intervention logic and discuss the programmatic changes that occurred in the programme result chain during implementation as a response to emerging challenges and needs. The ToC analysis needs to include also cross-cutting issues such as gender equality and empowerment of women, human rights and non-discrimination (including disability inclusion), and environmental sustainability.

The theory of change analysis should be limited to the soundness of the “agencies’ and joint workplans” outputs contributions to the outcome level and SDG indicators. Evaluators will base their evaluation on the analysis and interpretation of the logical consistency of the results chain: linking program outputs to changes at a higher level of outcomes, based on observations and data collected during the process along the result chain. This analysis should serve as a basis for the judgment of the evaluators on the contribution of the current CF to the achievement of the outcome level results as targeted by the CF.

The analysis of the CF’s theory of change and the reconstruction of its intervention logic, if necessary, will therefore play a central role in the design of the evaluation, in the analysis of the data collected throughout the evaluation, in communicating results and in developing relevant and practical conclusions and recommendations.

Data Collection Methods: The evaluation will use a combination of document reviews, analysis of other quantitative secondary data, individual interviews with key informants and focus groups or other types of group discussion to collect data. The evaluation team will develop the evaluation methodology in accordance with the evaluation approach and design tools to collect appropriate data and information as strong, evidence-based answers to answer the overall evaluation questions. The methodological design will include: an analytical framework; a strategy for data collection and analysis; specially designed tools; an evaluation matrix; and a detailed work plan.  The methodological approach will account for existing UNCT evaluations (in the CF implementation period) and the synthesis of evaluative evidence e.g. project evaluations, agency-specific evaluations, CF Interim and Annual Reviews, UN Info data and other monitoring and reporting instruments.

The evaluation will use a combination of qualitative and quantitative methods, including document reviews, analysis of quantitative secondary data, individual interviews with key informants and focus groups or other types of discussion to collect data. The Independent External Evaluators shall be guided by Annex 1 (standard methodology section) of Appendix 2 (Terms of reference) of the UNSDCF Evaluation Guidelines - Engl - Revised July 2022 to develop the evaluation methodology. They shall also develop the necessary tools to collect data and information to answer the overall evaluation questions. The precise data collection methods should be identified following the analysis of availability of existing evaluative evidence and administrative data, logistical constraints (travel, costs, time, etc.) and ethical considerations.

Sampling approach:

A purposive sampling approach will be used to select programmes (joint workplans; joint programmes; UN agency programmes etc.) that will be covered in the scope of the CF evaluation. The selected programmes components should be representative of CF Outcome statements and have sufficient level of transformational intent (depth, breadth, and size) given the overall number of UNCT programmes in 2021-2023 (269).

The purposive sampling approach will also be used to target groups and stakeholders to be consulted. It is expected that the list of target groups will ensure adequate representation of beneficiaries, including civil society organizations with an emphasis on vulnerable groups, e.g people living with disabilities, and other marginalized groups. The selection will be informed by the portfolio analysis and stakeholder mapping undertaken during the inception phase of the evaluation. This analysis will yield information on the relevant initiatives and partners to be part of the evaluation. The evaluation team should clearly outline the sample selection criteria and process and identify any potential bias and limitations, including the steps towards addressing the limitations.

The sampling technique should ensure that the selected samples adequately reflect the diversity of stakeholders of the intervention and pay special attention to the inclusion, participation, and non-discrimination of the most vulnerable stakeholders. This process will enhance the credibility and technical adequacy of the information gathered.

Considering that the UNSDCF evaluation will coincide with agencies' specific country-programme evaluations, this evaluation will benefit from aspects of the methodology and data collection carried out as part of the UNSDCF and agency-specific programmes' evaluation, which will facilitate the advancement of the UN Reform Agenda implementation under leadership of the RC office. It will facilitate a better-coordinated approach between the evaluations, including a contribution of the available subject expertise that agency-specific evaluation teams will have.

The Final CF evaluation methodology must meet the UNEG Code of Conduct for Evaluation in the UN System and demonstrate effective use of the UNEG Guidance on integrating human rights and gender equality during all phases of the evaluation using the norms of the United Nations System Wide Action Plan for Gender Equality and Empowerment of Women (UN-SWAP 2.0).

6. Management Arrangements of the CF Evaluation

As per UNEG norms and standards, CF evaluations should involve all key stakeholders from the start, in order to bolster ownership and, consequently, use of evaluation findings:

The Evaluation Steering Committee (ESC) - the decision-making organ for the CF Evaluation bringing together representatives of the UNCT and national counterparts. The ESC supports the management of the evaluation and approves the evaluation deliverables (Inception Report, Final Report). In the specific implementation circumstances in the Republic of Serbia, the following arrangements will be considered: The role of the Evaluation Steering Committee will be performed by the CF Joint National Steering Committee due to adequacy of its composition. The CF Joint National Steering Committee will undertake the oversight of the final evaluation as one of its regular activities per the CF document.

Evaluation Management Group (EMG): composed of a staff member from the Resident Coordinator’s Office and five to seven UNCT Agency members (resident and non-resident).

The role of the CF Evaluation Management group will be undertaken by the members of UNCT Monitoring and Evaluation group. The group will serve as a key technical advisory entity for the CF Evaluation. The group will provide inputs on consultant’s selection process, inception report, main fact-finding mission, 	participate in the presentation of preliminary findings, review and comment on the draft evaluation report. Additionally, the Management Group may enable access to key informants during the evaluation process as necessary.

Evaluation Manager: The UNCT has designated an Evaluation Manager (UN Resident Coordinator’s Office Monitoring and Data Management Officer) who will assume the day-to-day responsibilities for managing the evaluation process as pertaining to all aspects of this ToR and serve as the focal point for ensuring the evaluation runs smoothly. The Evaluation Manager technically oversees the evaluation and reports regularly to the ESC and UNCT by organizing regular meetings. The Evaluation Manager works in close collaboration with DCO for quality assurance purposes and technical support.

DCO Evaluation Advisor supports the evaluation manager, the RC and the UNCT in quality assurance of all key products and liaise with UNEG. DCO is responsible for approving all evaluation products including the TOR, inception report, final report and other associated products. UNEG will be informed about the evaluation by the DCO, and may be engaged in exceptional circumstances.

7. Composition of the Evaluation Team

The evaluation team will consist of independent external consultants: Evaluation Team leader and one additional Team member – evaluation specialist.

The Evaluation Team Leader will conduct the evaluation process in a timely manner and communicate with the Evaluation Manager on a regular basis and highlight progress made/challenges encountered. The Evaluation Team Leader will be responsible for producing the inception report and the draft and final evaluation reports. In close collaboration with the Evaluation manager the Team Leader will take the lead role in conceptualization and design of the evaluation deliverables and shaping the findings, conclusions, and recommendations of the report.

The Team member will contribute to the evaluation process substantively through data collection and analysis. The Team member will share responsibilities for conducting desk review and interviews and conduct field visits identified and collect data. They will provide substantive input to the inception report, the presentation of preliminary findings as well as to the draft and final reports.

- Team Leader (external international) responsibilities:

- Develops an inception report and details the design, methodology (including the methods for data collection and analysis criteria for selection of projects, required resources), and work plan of the evaluation team.

- Directs and conducts the research and analysis of all relevant documentation;

- Decides the division of labour within the evaluation team and coordinates team tasks within the framework of the TORs;

- Oversees and quality assures the preparation of the report and takes a lead in the analysis of the evaluative evidence;

- Oversees the administration, and analysis of the results of the data collection exercise;

- Drafts the inception and evaluation reports, and coordinates the inputs from team members;

- Prepares for meetings with JNSC, ESC, UNCT and other stakeholder to review findings, conclusions and recommendations.

- Regularly briefs JNSC, UNCT, EM and EMG on the evaluation progress through informal sessions and finalizes the report based on feedback from the quality assurance process;

- Delivers and presents the final evaluation report.

B. Evaluation team member - specialist (external national) responsibilities:

The Evaluation Specialist will provide the expertise in the local development issues with sound understanding of the Serbian social and economic environment and Agenda 2023 in the national context. The evaluation specialist is expected to:

- Review relevant documents

- Participate in the design of the evaluation methodology ad provide inputs o the inception report

- Conduct an analysis of the outcomes, outputs, Join Work Plans

- Carry out fieldwork and data collection as per the Inception report and Terms of Reference

- Draft related parts of the inception and evaluation reports as agreed on the division of labor with the team leader

- Assist the Team Leader in finalizing the evaluation final report including incorporating suggestions received on draft related to assigned sections.

- Required skills and experience for the evaluation team members:

Evaluation Team Leader

- At least a master’s degree in a relevant field (international development, economics, political science, governance, social sciences or a related field);

- At least 10 years of working experience in evaluation of UN’s or other international organization strategic documents, UN agency country programme experince would be an advantage.

- Experience with participatory approaches, organizational assessments partnership strategies and capacity development;

- Knowledge of relevant human rights issues, including forced displacement, and ability to identify related problems in their political, ethnic, racial, gender equality and socio-economic dimensions;

- Ability to facilitate, evaluate and integrate information from a variety of sources and assess the impact on human rights and gender equality. Ability to incorporate gender perspectives in all aspects of the evaluation report;

- Regional expertise in the region of the Western Balkans; Specific experience in Serbia’s development context will be an asset.

- Proven experience as an evaluation team leader with ability to lead and work with other evaluation experts;

- Facilitation skills and ability to manage diversity of views in different development contexts;

- Ability to produce well written reports demonstrating analytical ability and communication skills

- Excellent command of English.

Team Member – Evaluation Specialist

- At least a master’s degree in a relevant field (international development, economics, political science, governance, social sciences or a related field);

- Minimum five years of relevant professional experience. Previous work with UN would be advantage;

- Strong data collection and analysis skills; Prior experience in working with multilateral agencies;

- Strong experience and knowledge in the UN programming principles including leaving no one behind LNOB, human rights, gender equality and women's empowerment, disability inclusion; forced displacement and statelessness, environmental sustainability and resilience, and accountability;

- In-depth knowledge and strong research record of country socio-economic development and environment context;

- Excellent timely delivery and time management;

- Process management skills such as facilitation skills and ability to negotiate with a wide range of stakeholders;

- Technical competence in undertaking complex evaluations which involve use of mixed methods;

- Knowledge of UN role, UN reform process and UN programming at the country level, particularly UNSDCF;

- Excellent command of English and Serbian language.

The evaluation will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’. The selected consultants are required to clearly identify any potential ethical issues and approaches to the evaluation, as well as the processes for ethical review and oversight of the evaluation process in their proposal.

7. Evaluation Deliverables

It is imperative that the evaluation method ensures that the perspectives of different stakeholders are captured, and recommendations are validated through the prism of nationally-owned priorities observing UNEG Evaluation Report Standards.

The evaluation team will proceed to structure the data gathering phase with close attention to the TOR and stakeholder analysis. Data collection methods must be linked to the evaluation criteria and evaluation questions that are included within the evaluation matrix. The precise data collection methods should be identified following the initial analysis of existing evaluative evidence and administrative data.

The key evaluation deliverables include:

- Inception Report, containing a preliminary analysis of the CF ToC or, in its absence, reconstruction of the CF ToC; an elaboration of the evaluation approach and methods, including the evaluation design matrix; and a detailed evaluation plan and timeline, including a tentative list of interviews to be arranged or plans for field visits.

- Preliminary findings report or presentation (following the fact-finding mission), in a template to be agreed with the Evaluation Manager.

- Draft and final CF Evaluation Report, including the Executive Summary and Annexes

- Power Point Presentation for UNCT Serbia outlining key findings and recommendations

Inception Report

Based on the desk review, The Evaluation Team will produce an Inception Report in line with the UNSDG CF Evaluation Template (CF Evaluation-Inception report template.docx) for the overall evaluation. The inception report should outline at a minimum the following issues:

-  A clear purpose and scope of the evaluation, which includes a clear statement of the objectives of the evaluation and an outline of the main issues to be examined. - An outline of the evaluation criteria and questions that the evaluation will use to assess performance.

- The evaluation methodology, including methods used for collecting data and their sources (must include the points in Chapter 5 above, as well as the additional data required, including a rationale for their selection). Data collection tools with an explanation of their reliability and validity. The methodology will take into consideration country-level data limitations.

- An evaluation matrix (in Annex to the report) which identifies the key evaluation questions, and an indication of how the team expects these questions to be answered.

-  Theory of Change analysis based on initial meetings as outlined in Chapter 5 (Evaluation Methodology).

Draft full report (no more than 60 pages excluding the Executive Summary and Annexes)

The full Evaluation Report covering the entire plan outlined in the Terms of Reference and inception report including the evaluation matrix, evaluation findings, conclusions, lessons and recommendations in full accordance with the CF evaluation report template 2021.docx.

A Power Point presentation of key findings, lessons and recommendations for the government counterparts and other stakeholders.

7.3 Follow-up and validation

The findings of the evaluation report will be reviewed jointly by Evaluation Steering Committee, (ESC), comprising UNCT and national stakeholders to ensure that the key recommendations are validated and incorporated into the design of new strategic framework. The UNCT will draft a management response outlining how the evaluation findings will be applied, including a timeframe and responsibilities for follow up.

Lessons learned from the evaluation will be extracted and disseminated by the UNCT in order to contribute to strategic planning, learning, advocacy and decision-making at all levels, including for the formulation of the CF successor document. The full evaluation report will be made public through the UNCT internet platform and shared in the form of electronic and hard copies to the key national stakeholders.

8. Quality Assurance

The Evaluation Steering Committee will provide oversight of the evaluation process, exercising quality assurance. The Evaluation Management Group will play an important role in providing strategic, methodological and substantive advice into the evaluation process as well as a peer review for the key outputs including the main report. Meetings of the EMG will be specified in the evaluation work plan.

The CF Evaluation ToR, Consultant Selection, Evaluation Inception Report and Final Report will be submitted to UN Development Coordination Office (HQ and Regional Office for ECA) for control review a, improvement/revision suggestions and final approval.

The selected consultants will be required to clearly identify any potential ethical issues and approaches to the CF evaluation, as well as the processes for ethical review and oversight of the evaluation process in their proposal.

9. Evaluation Process and Timeline of Deliverables, Estimated Working Days

The detailed implementation plan for the evaluation will be outlined in the inception report, but it is mandatory that the final Evaluation Report should be delivered by the second week of November 2024:

Tentative Evaluation Process and Timeline

| Activity | Timeframe | Lead and responsibility | Supervision |
| --- | --- | --- | --- |
| Recruitment of Consultants, Establishment of Evaluation Management Group | April 2024 | Evaluation Manager (EM), Evaluation Management Gorup (EMG) | Resident Coordinator (RC), UNCT, DCO Evaluation Advisor (EA) |
| Initial Desk review, establishment of Data repository | May 2024 | Evaluation Team Leader (ETL), EM | EMG |
| Initial meeting and discussions with UNCT, ESC and EMG | May 2024 | ETL, ES | UNCT, RC, EM, EMG, ESC |
| Full desk review including stakeholder analysis | First half of June 2024 | ETL, ES | EM, EMG |
| Drafting/ finalizing Inception Report, outlining evaluation design, initial synthesis and detailed additional data collection plan | June 2024 | ETL, ES | EG, EMG |
| Final Inception Report | 5 July 2024 | ETL, ES, EM | EMG, EA |
| Approval of the Inception Report | Mid July 2024 | EM, ESC | EA, ESC |
| Preparation of the field mission | July 2024 | ETL, EM | EMG |
| In-country field mission and presentation of the preliminary findings | September 2024 | ETL, ES, EM | EMG, RC |
| Finalization of First draft of full evaluation report | By 21 October 2024 | ETL, ES, EM | EMG, EM |
| Finalization of second draft, following feedback from UNCT and Evaluation Advisor | By 10 November 2024 | ETL, ES | EM, EMG, EA, RC |
| Presentation of the Final SDCF Evaluation findings and recommendations | 15 November 2024 | ETL, ES | EM, EMG, ESC |
| Dissemination of Final Report | December 2024 | RCO Serbia | RC |

Evaluation deliverables and estimated number of working days

| Deliverables | Estimated working days for the international expert | Estimated working days for the National expert |
| --- | --- | --- |
| Inception phase (desk review and UNCT, EMG meetings) | 10 days | 7 days |
| Inception report | 10 days | 5 days |
| Field phase data collection | 15 days | 15 days |
| Data analysis and First draft | 10 days | 10 days |
| Final draft | 5 days | 5 days |
| Final presentation event | 2 days | 2 days |
| Total | 52 days | 44 days |

10. Evaluation budget and payment schedule

Funding for the UNSDCF 2021-25 evaluation will be provided by the Special Purpose Trust Fund (SPTF) allocation to the Office of the Resident Coordinator.

Payments will be tied to deliverables as follows:

| No. | Deliverables/Outputs | Target Due Dates | Payment |
| --- | --- | --- | --- |
| 1 | Initial UNCT Meetings | May 2024 | 20% |
| 2 | Satisfactory completion of the inception report | July 2024 | 30 % |
| 2 | Submission of draft report | 21 October 2024 | 20 % |
| 4 | Submission and approval of final report and PPT presentation | 15 November 2024 | 30 % |

11. Administrative Issues

The Team Leader and National Team Member will be responsible for their own travel arrangements. No additional costs outside of the scope of this TOR will be covered. The consultants will have to possess their own computer and other technical equipment to complete the assignment. The documents produced during the period of this consultancy will be treated strictly confidential and the rights of distribution and/or publication shall solely reside with the United Nations Country Team in Serbia.

UNEG - DCO UNSDCF Evaluation Guidelines-English July 2022.pdf

Data derived from the UNCT Serbia Common Country Assessments (2021-2023).

UNDP Serbia, "Human Development in Response to Demographic Change” (2022).

References to Kosovo shall be understood in the context of UN Security Council resolution 1244 (1999).

See European Commission Serbia 2023 Report at https://neighbourhood-enlargement.ec.europa.eu/serbia-report-2023_en

https://www.stat.gov.rs/en-US/vesti/20230427

https://uninfo.org/location/62/documents

UNEG - DCO UNSDCF Evaluation Guidelines-Revised July 2022

United Nations Evaluation Group (2021). Norms and Standards for Evaluation. New York: UNEG.

There will be NO PRIMARY quantitative data collection. This means that there will NOT BE ANY QUANTITATIVE SAMPLING. Therefore, any quantitative analysis will be from desk review

PRIMARY data collection will only be qualitative. Therefore, no PRIMARY analysis will use quantitative methods.

https://www.unevaluation.org/document/detail/100

http://www.unevaluation.org/document/detail/1452