## Sheet1
Country Nigeria; UNDAF / CF 2018-2022 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Nigeria UNSPDF Evaluation / 2021 • Preparation of the management response: PMT • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: -RCO & M&E Group • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: The next UNSDPF/CF results framework should be streamlined, with fewer outcomes and outputs and accompanying indicators. This should include a consideration of how individual entity higher level objectives map onto the outcomes of the UNSDPF/CF, and better integrating the humanitarian response to complete the development-humanitarian-peace/security nexus. By extension, the DaO work planning process should also be streamlined to make it less cumbersome, reduce the number of activities and better align with state priorities.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | The current DaO workplanning process is not cumbersome (one day is assigned for reviewing achievements and the other day for planning) it is . However, reducing the number of activities and alining with state priorities will be the focus. UN Nigeria will still retain the current outcomes and results areas in the UNSDPF bearing in mind that this is the last year of implementaiton of the UNSDPF and the recommendaiton will be taken into consideraiton in the development of the new CF.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1 | Turning the current UNSDPF outcomes into outputs, while the result areas are the PF outcomes that contribute to Nigeria’s priorities. | 2022-06-01 | Participating UN Agencies & RCO | Since this is the last year of implementaiton of the PF the outcomes and outputs are maintianed | completed | June | 2022
2 | UN entities to map their higher level CPD objectives onto the PF outcomes. This way, all their activities including those that may be outside the DaO/JWPs would be aligned with the PF. | 2022-12-01 | Participating UN Agencies | Work in Progress | ongoing as expected | December | 2022
3 | Next CF should integrate the humanitarian response plan into to complete the development-humanitarian-peace/security nexus | 2022-06-01 | OCHA & RCO | This was taken into consideration in the devleopment of new CF | completed | June | 2022
4 | Undertake a comprehensive mapping of initiatives especially of non-UN entities, to see how these align with the PF, and feed these into the JWP to ensure better coherence | 2022-09-01 | RCO & Result Area group | Already working with UNEP on this | ongoing as expected | December | 2022
5 | Ensure that the JWPs have fewer activities which can be clustered around specific interventions | 2022-09-01 | RCO & Result Area group | Agencies were guided on what would count as activity in the JWP and are reviewing the JWP inline with the guidance | ongoing as expected | December | 2022
6 | Ensure prompt release of funds at the beginning of the implementation year to ensure that there is no rush towards the end of the year | 2022-12-01 | Participating UN Agencies | Agencies working on this | ongoing as expected | December | 2022
Recommendation 2: the UNCT to commission an evaluation of the DaO State approach, to look at the continuum from planning to coordination and implementation as well as reporting.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1 | Develop terms of reference for conducting the DaO State evaluation and secure interagency funding for the exercise. The evaluation should consider the effectiveness of the joint workplans, as well as coordination of planning, implementation, and reporting, including joint working among UN entities. | March/April 2022 | RCO & M&E | TOR developed & agencies contributed $50,000 | completed | June | 2022
2 | Conduct the DaO evaluation | August/Sept 2022 | RCO & M&E | DaO evaluation conducted, draft report submitted | ongoing as expected | October | 2022
3 | Consider including Borno, Adamawa, and Yobe States as part of DaO States given the huge humanitarian focus on these states. | 2022-12-01 | PMT & UNCT | The result of the evaluation will be used to inform decision on DaO | ongoing as expected | December | 2022
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 3: The evaluation endorses the recommendation from the 2019 UN country result report that suggested a focus on more joint programmes, partnership, and joint implementation to deliver on UN mandate in Nigeria. It is recommended that this suggestion is taken forward building on the existing joint programme initiatives
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
1 |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1 | Undertake a stocktake of the lessons from the current joint programmes around joint working, including any joint resource mobilisation | 2022-09-01 | RCO | The evaluation of the social protection will be conducted as well as the joint work planCOVID basket fund. This will enable UN to document lessons learned | ongoing as expected | December | 2022
2 | Develop a position paper on joint working and joint resource mobilisation, drawing on the experiences of the COVID-19 response plan and basket funds. | 2022-12-01 | RCO | The partnership group will develop the position paper | ongoing as expected | December | 2022
Recommendation 4: PMT working with agency leads, to consider including the activities of the M&E group and RA and outcome leads into their performance benchmarks.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1 | RCO/PMT to have frank discussions with agency heads about including coordination activities into the performance benchmarks of the staff members concerned | 2022-12-01 | PMT /UNCT | Yet to initiate the discussion | delayed | June | 2023
2 | Work with HR and line managers to decide how to incorporate these benchmarks | 2022-12-01 | PMT/UNCT | Yet to initiate the discussion | delayed | June | 2023
3 | Discuss these with the staff in a way that complements their skills and how these maps onto the UN staff members’ competency framework | Annually | Agency heads/HR | Yet to initiate the discussion | delayed | June | 2023
Recommendation 5: UNCT through the PMT should progressively strive to improve the collaboration between the various UN working groups.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | PMT regularly push for a common product that the groups will collectively produce | August 30th 2022 | PMT Chair | This is ongoing throught he policy advisory group, RA groyp, GTG, Disability Inclusion | ongoing as expected | December | 2022
5.2 | Results groups and M&E group to produce quarterly progress reports on implementaiton of the UNSDPF to PMT | Quarterly | Result Groups & M&E Group | The JWP is yearly joint plan and the RA present their progress report twice a year | ongoing as expected | December | 2022
5.34 | Initate annual PMT/UN Working Group Retreat (recognize and reward agencies who have demostrated uncommon committement to the new way of working). | Nov 30th 2022 | PMT Chair | This will not take place this year | cancelled
Recommendation 6: knowledge management and lesson learning should be systematized in the next CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Review the existing Knowledge Management and Lessosn Learnt Systems that is operational at the different agencies(SWOT) Anaysis. | 2022-12-01 | PMT | Not yet started | delayed | June | 2023
6.2 | Develop a Knowledge Management (KM) and learning strategy for the next CF based on the SWOT anaysis conducted. | November 30th 2022 | PMT/M&E | Not yet started | delayed | June | 2023
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 7: UNCT to reiterate the mainstreaming of UNDAF programming principles as well sustainability plans into the design and implementation of the next CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO & M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Increased involvement of traditional and religious leaders in the delivery of interventions | 2022-11-01 | UN Agencies | Involvment of traditional and religious leaders on going | ongoing as expected | December | 2022
7.2 | To ramp up PWD-related initiatives, focusing on the provision of technical skills and tools to support the needs of the PWDs | 2022-12-01 | Disability Inclusion group | The DI TWG secure seed funding to conduct some activities | ongoing as expected | December | 2022
7.3 | To build the capacity of implementing partners, as well as those of state government and local community should continue to be prioritized in the next phase of the PF | 2022-11-01 | UN Agencies | Capacity builidng on going | ongoing as expected | December | 2022
| To continue advocacy efforts for government partners to not only make budgetary provisions for the interventions but to secure long-term funding through the incorporation into their medium-term sector strategic plans | 2022-11-01 | UN Agencies | Advocacy to government on going | ongoing as expected | December | 2022
| To support initiatives towards medium term planning such as MTSS and Sector Development Plans (SDPs) and link up with other partners or partner projects that support these initiatives. | 2022-11-01 | UN Agencies | Support towards medium term planning on going | ongoing as expected | December | 2022
`

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030