UNITED NATIONS IN GEORGIA

INDEPENDENT EVALUATION OF THE UNITED NATIONS SUSTAINABLE DEVELOPMENT COOPERATION FRAMEWORK 2021-2025

GEORGIA

FINAL REPORT

FARRUKH MORIANI, TEAM LEADER

NATALIA ALHAZISHVILI, TEAM MEMBER

MIKHEIL PAKATSOSHVILI, TEAM MEMBER

MARCH 2025

DISCLAIMER: The analysis and opinions expressed in this document are those of the authors and do not reflect the views of the United Nations or its management.

# Acronyms and Abbreviations

AA 	Association Agreement

ABL	Administrative Boundary Line

ADB	Asian Development Bank

AoG 	Administration of Government

ASP 	Abkhazia Strategic Partnership

CCA 	Common Country Analysis

CCM 	Country Coordination Mechanism

CEDAW 	Convention for the Elimination of all forms of Discrimination Against Women

CRC 	Convention on the Rights of the Child

DCFTA 	Deep and Comprehensive Free Trade Area

DCU 	Donor Coordination Unit

DRR 	Disaster Risk Reduction

DV 	Domestic Violence

ECE 	Early Childhood Education

EU 	European Union

FAO 	Food and Agriculture Organization

FP 	Family Planning

GDP 	Gross Domestic Product

GHG	Green House Gas

GEWE 	Gender Equality and Women’s Empowerment

GoG 	Government of Georgia

GNI	Gross National Income

GTG 	Gender Theme Group

HR 	Human Rights

HH	Household

IDP	Internally Displaced People

IFI 	International Financial Institution

ILO 	International Labour Organization

IOM 	International Organization for Migration

IRM 	Integrated Risk Management

JP 	Joint Programme

JSC 	Joint Steering Committee

JWP	Joint Work Plans

LAS 	Legal Aid Service

LNOB 	Leave No One Behind

MAPS	Mainstreaming, Acceleration and Policy Support

MEPA 	Ministry of Environmental Protection and Agriculture of Georgia

MICS 	Multiple Indicator Cluster Survey

MoESY 	Ministry of Education, Science, and Youth

MoIDPLHSA 	Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia

MRDI 	Ministry of Regional Development and Infrastructure

NAP	National Action Plan

NBG	National Bank of Georgia

NCDC 	National Centre for Disease Control

NEET	Not in Employment, Education, or Training

NMCR 	Near Miss Case Review

NRA 	Non-Resident Agencies

OGP 	Open Government Partnership

OMT 	Operations Management Team

PDO	Public Defender’s Office

PWDs 	People (Living) with Disabilities

POC 	People of Concern

PPP		Public Private Partnership

RBM 	Results-based Management

RDA	Rural Development Agency

RR 	Reproductive Rights

SAOG	State Audit office of Georgia

SCMI	State Commission on Migration Issues

SDG	Sustainable Development Goals

SME	Small and Medium Enterprises

SNG	Sub-National Governments

SOP 	Standard Operating Procedure

SRH 	Sexual and Reproductive Health

TOC	Theory of Change

TSA 	Targeted Social Assistance

U5 	Children under five years of age

UHC 	Universal Health Care

UN Women 	United Nations Entity for Gender Equality and the Empowerment of Women

UNCG 	UN Communications Group

UNCT 	United Nations Country Team

UNDP 	United Nations Development Programme

UNEG 	United Nations Evaluation Group

UNEP	United Nations Environment Program

UNFPA 	United Nations Population Fund

UNHCR 	United Nations High Commissioner for Refugees

UNICEF 	United Nations Children’s Fund

UNICRI	United Nations Interregional Crime and Justice Research Institute

UNIDO 	United Nations Industrial Development Organization

UNODC 	United Nations Office on Drugs and Crime

UNOPS	United Nations Office for Project Services

UNPSD 	United Nations Partnership for Sustainable Development

UNSDCF 	United Nations Sustainable Development Cooperation Framework

UPR 	Universal Periodic Review

VET 	Vocational Education & Training

VNR	Voluntary National Review

VLR	Voluntary Local Review

WB	World Bank

WHO 	World Health Organization

# Table of Contents

Acronyms and Abbreviations	2

Table of Contents	5

Acknowledgements	7

Executive summary	8

Introduction	10

Purpose and Objectives	11

Scope	12

Country context	13

General Overview	13

Political economy and economic contexts	14

Governance context	17

Human rights and gender equality contexts	20

Findings of the evaluation	23

Relevance and Adaptability	23

Findings	28

High level findings	31

Output-wise findings	37

Outcome area 1	37

Outcome area 2	44

Outcome area 3	52

Outcome area 4	63

Outcome area 5	70

Findings from the stakeholder and public perception surveys	78

Conclusions	80

Recommendations	82

Summary performance rating	83

Figures

Figure 1: Key Governance Indicators (2012-2022). Comparison of Georgia with Europe and Central Asia	18

Figure 2: Local Self Governance Index (2017-2023)	19

Figure 3: Revised Theory of Change for the UNSDCF 2021-2025 Georgia	30

Figure 4: Outcomes and Outputs of the UNSDCF 2021-2025 Georgia	31

Figure 5: Status of Achievement of Outcomes of the UNSDCF 2021-2025 Georgia	32

Figure 6: Outcome-wise Progress on the UNSDCF 2021-2025 Georgia	32

Figure 7: Agency-wise Budget Allocations UNSDCF 2021-2025 Georgia	32

Figure 8: Overall Funding Gap and Outcome-wise Funding Gap UNSDCF 2021-2025 Georgia	33

Figure 9: Joint programmes	34

Annexes

Annex 1: ToR for the Evaluation of the UNSDCF 2021-2025 Georgia	84

Annex 2: Evaluation design matrix	85

Annex 3: Alignment of Georgia’s national policies and strategies with the SDGs	88

Annex 4: References	89

Annex 5: Focus group participants	92

Annex 6: List of key informant interviews (KII)	93

Annex 7: Key informant interview protocol	97

Annex 8: Stakeholder mapping	89

Annex 9: Survey sampling technique and citizen feedback survey instrument	93

Annex 10: Theory of change rationale	98

Annex 11: Theory of change synoptic table	101

Annex 12: Status of progress on outcomes	110

Annex 13: Progress on outputs	120

Annex 14: Profiling the joint work programmes	140

# Acknowledgements

The Evaluation Team expresses its gratitude to all those who contributed to the independent evaluation of the United Nations Sustainable Development Cooperation Framework (UNSDCF) 2021-2025 in Georgia.

We extend our sincere appreciation to the Government of Georgia, including representatives from various ministries, agencies, and institutions who provided valuable insights and data, enabling a comprehensive assessment of the UNSDCF’s contributions to national development priorities. Special thanks go to the Donor Coordination Unit of the Administration of Government, for their excellent coordination and support throughout the evaluation process.

We are grateful to the UN Resident Coordinator’s Office for their commitment to making the evaluation a meaningful exercise, and for adhering to the principle of independence of the process. We are most thankful to Mr. Didier Trebucq, UN Resident Coordinator in Georgia for his leadership and openness to discuss challenging issues; Ms. Anna Platonova, Head of Office of the RCO for her astute and most helpful insights; Ms. Nestan Khuntsaria, Associate Development Coordination Officer and Evaluation Manager, for her guidance and support throughout the evaluation process; and to Ms. Marika Bitsadze, Administrative Assistant, for her administrative support.

We deeply appreciated the interest and involvement of the UN Country Team (UNCT) in Georgia. The engagement of UN Resident and Non-Resident Agencies played a crucial role in facilitating access to documentation, stakeholders, and key informants. The continuous support and feedback from Results Groups and the UN Evaluation Group helped enhance the quality of this evaluation.

We also acknowledge the contributions of international development partners, including the European Union, the World Bank, the Asian Development Bank, USAID, the Swiss Development Cooperation, the UK Foreign, Commonwealth & Development Office (FCDO), and the Swedish International Development Cooperation Agency (SIDA). Their perspectives on development cooperation and partnerships in Georgia enriched the findings of this evaluation.

Our gratitude extends to representatives of civil society organizations, the private sector, and academia who shared their experiences and insights, ensuring a diverse range of perspectives was captured. We appreciate the participation of focus group discussion members, key informants, and survey respondents, whose contributions were essential in assessing the relevance, coherence, effectiveness, efficiency, impact, and sustainability of the UNSDCF.

The Evaluation Team

# Executive summary

Introduction

The United Nations Sustainable Development Cooperation Framework (UNSDCF) 2021-2025 for Georgia aims to address national priorities aligned with the 2030 Agenda for Sustainable Development. The framework emphasizes inter-agency cooperation and joint programs, operationalized through Joint Work Plans (JWPs) with contributions from various UN entities. The UN Country Team (UNCT), comprising 21 resident and non-resident agencies, oversees the UNSDCF implementation, focusing on one transformative strategic priority: enhancing human well-being, capabilities, and social equality in Georgia by 2025.

Purpose and Objectives of the Evaluation

The evaluation of the UNSDCF serves two primary purposes: promoting learning and operational improvement and supporting accountability of the UNCT to stakeholders. The evaluation assesses the contributions of the UNSDCF to national development results, identifies factors affecting performance, and provides actionable recommendations for future programming. The findings aim to inform strategic planning and improve UN coordination in Georgia.

Scope and Context of the Evaluation

The evaluation spans the period of UNSDCF implementation from January 2021 until April 2024 and covers the entire country where the programmes under the UNSDCF are implemented. The field data collection was primarily conducted in the capital city (Tbilisi) as well as in Shida Karli and Kvemo Kartli regions, which were chosen in consultation with the UN agencies. The evaluation examined cross-cutting issues; global UN programming and humanitarian principles such as Leave No One Behind (LNOB); human rights; gender equality and women's empowerment; disability inclusion; youth engagement; environmental sustainability and resilience; and accountability.

Methodology

The evaluation was guided by the UNEG’s Guidelines for Evaluation of the UNSDCF 2022. Employing methodological pluralism, the evaluation was carried out in an inclusive, participatory, and transparent process. Key instruments used for collection of data and insights were Key Informant Interviews, online surveys, and Focus Group Discussions. In addition to the UN agencies, more than 50 institutions and more than 100 informants were engaged through multiple instruments. Moreover, an online survey of citizens and institutional stakeholders was also conducted, with responses from 52 institutional stakeholders and 102 citizens.

Key Findings

- The UNSDCF aligns well with national policies and priorities, contributing to the UN system making robust contributions to progress on governance, service delivery, and economic sustainability. Efforts to enhance human rights and resilience in conflict-affected communities have yielded small, but positive results. Similarly, the UNSDCF has strengthened environmental governance and climate action, with initiatives promoting sustainable resource management and resilience to environmental shocks.

- The UNSDCF needs to strengthen its strategic focus, as it misses the opportunity to sync with the government’s thrust towards economic growth policy. In particular, the UNSDCF needs to respond better to the private-sector focused development agenda carved by the government of an upper-middle income country. By bringing into sharp focus solutions for reducing gender inequities and regional disparities, and promoting more inclusive policy making, the UN can help the government make better economic and development choices, while adhering to its defining principles of equity, LNOB, and promotion of human rights.

- Joint Programs provide a useful tool for the UN agencies in terms of achieving cost-efficiencies and operational synergies but are still viewed by the agencies as an evolving modality. Specifically, they require improvement in terms of how they are put together, the assignment of roles and responsibilities, and the performance incentives and measurement systems. Moreover, there is a need to increase fund mobilization efforts and stronger cooperation within the UNCT agencies to steadily increase the number of JPs covering large thematic areas of support offered by the UN to the country.

- The role of the RC and the RCO are viewed by stakeholders as being critical to reshaping the UNSDCF into a more strategic, focused, and relevant document. Stakeholders believe that in the context of the rising political economy risks in Georgia, the role of the RC as a political negotiator—while already an important element of defined responsibilities—will likely morph into its principal role. It is important that the RCO strengthens its visibility and positioning.

Structurally, the UNSDCF has several weaknesses. Processes relating to identification of joint programs, selection of partners, incentives for performance, and assignment of responsibilities including on reporting, are opaque; it does not fully cover all activities of the agencies; murmurs of discontent were echoed by government counterparts, over the inclusiveness, transparency, and consistency of engagement that leads to the finalization of the UNSDCF. There is also a need to ensure consistency in setting baselines and targets, as they are unavailable for certain outputs (e.g., Output 1.3.2) and present problems in analyzing progress.

Endnote

The UNSDCF 2021-2025 has helped make important contributions to Georgia's development, aligning relatively well with national priorities and the 2030 Agenda. Continued efforts to address identified challenges and implement the recommendations will further enhance the framework's impact, ensuring sustainable development and improved well-being for all people in Georgia. As the country’s transition continues, and with the EU accession agenda, the UN’s support to the people and the Government of Georgia, can enable a smooth transition, reduce disparities of all shades and scale, and bridge the many divides for women, the disabled, and the ethnic minorities.

# Section I: Introduction

- The United Nations Sustainable Development Cooperation Framework (UNSDCF) for Georgia 2021-2025 presents a structure that enables the UN system to assist Georgia in addressing its national priorities and challenges in line with the 2030 Agenda for Sustainable Development. The UNSDCF encourages and assigns importance to inter-agency cooperation and joint programmes to achieve cost-efficiencies and is operationalized through the development of Joint Work Plans (JWPs). These JWPs comprise the planned programmatic sub-outputs and resource contributions of each UN entity to UNSDCF outputs, consistent with the Theory of Change. Funding for UNSDCF interventions comes from multiple sources, including member state contributions, international funding institutions and donors. The UN Country Team UNCT) comprising twenty-one resident and non-resident agencies—of which eighteen are signatories of the UNSDCF—is the apex decision-making and coordinating body for the UNSDCF.

Outcome 1: By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights, and increased representation and participation of women in decision-making.

Outcome 2: By 2025, all people in Georgia have equitable and inclusive access to quality, resilient and gender-sensitive services delivered in accordance with international human rights standards.

Outcome 3: By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia.

Outcome 4: By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience.

Outcome 5: By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resources in Georgia.

BOX 1: UNSDCF 2021-2025 OUTCOMES

The UNSDCF is based on one transformative strategic priority: ‘Enhanced human wellbeing, capabilities and social equality in Georgia by 2025’. In furtherance of this strategic priority, the Results Framework of the UNSDCF 2021-2025 is structured around five outcomes (Box 1), each focusing on distinct areas of development in line with national priorities and Sustainable Development Goals (SDGs).

- With a view to help both the Government and the UN in analyzing the progress achieved, an end-of-cycle evaluation of the UNSDCF has been carried out. This evaluation is a mandatory, impartial assessment aimed at ensuring accountability, fostering learning, and guiding decisions regarding the design of subsequent UNSDCF cycles. It systematically evaluates the contributions of the UNSDCF, focusing on attained development outcomes, as well as internal and external gaps and redundancies in SDG implementation. In addition, the evaluation also includes a review of the Theory of Change (ToC) underpinning the framework. The TOR for the evaluation is at Annex 1.

- The evaluation serves a critical role in gauging the effectiveness of the UNSDCF, ensuring its alignment with national development priorities, and adherence to United Nations system mandates, principles, and guidelines. The evaluation's target audience includes government, UN agencies, development partners/donors, civil society and other stakeholders involved in or impacted by the UNSDCF, furnishing them with findings and recommendations for use in future strategic planning.

## Purpose and Objectives

- The UNSDCF evaluation has two primary purposes:

- Promote greater learning and operational improvement. The evaluation provides information for strengthening programming and results in Georgia, specifically informing the analysis, planning and decision-making for the next UNSDCF programme cycle and for improving UN coordination at the country level. The Government of Georgia, the UNCT and other UNSDCF stakeholders can learn from the process of documenting good practices and lessons learned, which can then be shared with DCO and used for the benefit of other countries

- Support greater accountability of the UNCT to UNSDCF stakeholders. By objectively providing evidence of results achieved within the framework of the UNSDCF and assessing the effectiveness of the strategies and interventions used, the evaluation will enable the various stakeholders in the UNSDCF process, including national counterparts and donors, to hold the UNCT and other parties accountable for fulfilling their roles and commitments.

- The objectives of the evaluation are to:

- Assess the contribution of the UNSDCF to national development results through evidence-based judgements using evaluation criteria.

- Identify factors that have affected the UNSDCF’s contribution to achievement of the national priorities; answering the question of why the performance is as it is; and explaining the enabling factors and bottlenecks.

- Reach conclusions concerning the UN’s contribution across the scope being examined.

- Provide actionable recommendations for improving the UNSDCF's contribution to achievement of the national priorities, especially for incorporation into the new UNSDCF programming cycle. These recommendations should be logically linked to the conclusions and findings of the evaluation and should draw upon lessons learned identified through the evaluation.

- The findings of the evaluation are intended to inform strategic planning and future programming. Primary users of the evaluation are stakeholders involved in UNSDCF implementation, such as the UNCT, governmental bodies, civil society organizations, contributing partners, and other relevant stakeholders. Secondary users include a broader audience, including the academic and research community, private sector, media, and the public.

## Scope

- Evaluation temporal scope: The evaluation spans the period of UNSDCF implementation from January 2021 until April 2024.

- Geographic coverage: The evaluation covers the entire country where the programmes under the UNSDCF were implemented. The field data collection was primarily conducted in the capital city (Tbilisi) as well as in Shida Kartli and Kvemo Kartli regions, which were chosen in consultation with the UN agencies to represent the programme implementation outside of Tbilisi. In addition to input from the UN agencies, factors considered while selecting the regions for field work included relevance of programs under implementations, opportunities for engaging with subnational government officials, and accessibility in view of the time limitations. Furthermore, limited online interaction was also undertaken with select staff of projects in Abkhazia, Georgia.

- Evaluation’s programmatic scope: The evaluation covers the UNSDCF 2021-2025, including contributions from all sub-outputs by the UNCT members (both resident and non-resident agencies). It also examined cross-cutting issues; global UN programming and humanitarian principles such as Leave No One Behind (LNOB); human rights; gender equality and women's empowerment; disability inclusion; youth engagement; environmental sustainability and resilience; and accountability. However, the evaluation does not cover individual programmes or activities of UN agencies.

- The evaluation considered major global and regional developments during the UNSDCF implementation, such as the COVID-19 pandemic, Russia’s war in Ukraine and other conflicts, both in its content (e.g., the UNCT’s responsiveness, adaptation, and reprioritization) and its operation (e.g., methods for managing stakeholder participation and inclusiveness).

- Evaluation Matrix: The Evaluation Design Matrix comprises: (a) the evaluation questions: and (b) identification of sources of data and information. To achieve more robust coverage of topics, several sub-questions were added to each of the evaluation questions included in the Terms of Reference for this evaluation. The Evaluation Matrix is available at Annex 2.

- Structure of evaluation report: The structure of the evaluation report follows the guidelines provided in the UNSDCF Evaluation Guidelines 2022, and includes:

  - Executive Summary This section provides a summary of the purpose, objectives, scope, and methodology of the evaluation. It presents a snapshot of key findings, conclusions and recommendations.

  - Section I: Introduction The introduction details the purpose, subject and scope of the evaluation, evaluation questions, and report structure.

  - Section II: Country Context This section contains an analysis of the relevant political, legal, institutional, financial, and economic conditions in Georgia as related to the UNSDCF.

  - Section III. Methodology This section provides details of the methodology used to collect, analyze, and synthesize the information and insights collected for the evaluation.

  - Section IV: Findings of the Evaluation Details the finding on the state of implementation of the UNSDCF in Georgia, highlighting progress, successes, challenges, risks, and opportunities. The findings are presented based on seven criteria:

    - Relevance and Adaptability

    - Coherence

    - Effectiveness

    - Efficiency

    - Coordination

    - Orientation towards Impact

    - Sustainability

  - Section V: Conclusions This section presents the conclusions, based on the findings of the evaluation, using evidence-based analysis.

  - Section VI: Recommendations Based on the conclusions, a set of clear recommendations are presented in this section. for improving implementation in the remainder of the period of the UNSDCF, as well as to inform the design of the next cycle.

  - Section VIII: Summary Performance Rating This section provides a summary overview of the performance, based on a template prescribed in the UNSDCF Evaluation Guidelines 2022.

# Section II: Country context

## General Overview

- Georgia is a nation of 3.7 million people, a third of whom live in the capital city of Tbilisi. Located in the Caucasus region, Georgia offers a strategic geographic location that has fuelled the country’s drive to become a regional transport and logistics hub and achieve enhanced participation in regional and global value chains. The rapid strides made in terms of creating a vibrant and liberal business environment and instituting efficient regulation and taxation regimes to promote long-term business development, coupled with the Government of Georgia’s (GoG) prioritization of achieving macroeconomic stability and managing fiscal risks, have resulted in notable gains in income growth and poverty reduction over the past decade. Gross National Income (GNI) per capita (constant 2015 USD) increased from $3,036 in 2010 to $5,679 in 2023. Poverty (measured by the World Bank’s $6.85 poverty line for upper middle-income countries in 2017 PPP) declined from 70.6% in 2010 to an estimated 47.7% in 2022, while the share of population under absolute poverty line declined from 37.3% in 2010 to 11.8% in 2023. Unemployment fell from 20.6% percent in 2021 to a record low of 16.4% in 2023. In 2016, the country transitioned from a lower middle-income country to an upper middle-income country. Despite consecutive shocks from the COVID-19 pandemic and Russia’s invasion of Ukraine, Georgia’s GDP rebounded quite impressively registering real GDP growth of 10.6% in 2021, 11.0% in 2022, 7.8% in 2023 and has accelerated again to 11% in the third quarter of 2024. This growth was attributed in the main to recovery in private demand, tourism services, and trading sectors. However, when disaggregated by gender, several issues emerge: there is a significant gender gap in terms of labour force participation (65.1% for men and 43.1% for women at the end of 2023); traditionally, unemployment is higher for men than women, but only 33.7% of women are employed as managers, as opposed to 53% men, and men account for 61% of all newly established enterprises, and women only 27%.

- There also appears to be a political ambition to promote green and efficient transport for improved connectivity and invest in renewable energy sources while seeking decarbonization and strengthened disaster risk resilience. Development of municipal infrastructure and improving public services, especially in the urban areas, are key areas of government focus. Use of PPPs and achieving greater private sector involvement in policy planning and formulation have also been key strategies.

- Georgia’s commitment to reform was marked first by the signing of the Association Agreement (AA) with the EU—this was revised in 2016 (Association Agenda 2017-2020) and outlines mutually agreed priorities to further the implementation of the AA; and second by the endorsement of the 2030 Agenda for Sustainable Development. In case of the latter, Georgia became one of the first countries to submit a Voluntary National Report (VNR) on SDGs in 2016. Since then, Georgia has submitted more detailed VNRs, in 2020, and the latest in July 2024. SDGs nationalized targets and indicators were approved in November 2019 and as per the UNDP-led MAPS (Mainstreaming, Acceleration and Policy Support for the 2030 Agenda) study, all the 36 national strategies incorporate 85 percent of the country’s nationalized SDG targets, with the percentage rising to 93% if the AA is also considered.

- These impressive gains notwithstanding, Georgia is beset with several structural challenges, including weak productivity, with a third of workers remain employed in low-productivity agriculture; limited access to finance for SMEs; and vulnerability to external shocks. The granting of candidate status by the European Union (EU) creates opportunities for institutional and economic reforms that can bring Georgia to the higher level of development. The EU candidacy and the reform agenda it brings in tow, has several implications for the implementation of the UNSDCF and this evaluation will strive to document its effect.

## Political economy and economic contexts

- Georgia’s political economy dynamics pose several governance and economic risks. Amidst a backdrop of significant political and economic reform since gaining independence from the Soviet Union in 1991, Georgia’s progress as a nation state has been enveloped in a swathe of political economy challenges that impact its governance, economic growth, and sustainable development. The reform process has been hampered by continuing political tensions and polarisation, and weak consensus building on key matters of national interest, while limited engagement with civil society has rendered decision making not as inclusive as it could be. In balance, in recent years Georgia has witnessed significant advancements in governance, institutional strength, public financial management and regulatory quality, Nonetheless, there are several areas require improvement, including: reducing political polarisation, promoting inclusive decision-making processes and supporting civil society engagement.

- Moreover, delivery of services and local economic development in the Abkhazia, Georgia and Tskhinvali region/South Ossetia, Georgia, continue to face challenges. Around 295,000—approximately 6% of the population—are registered as Internally Displaced Persons (IDPs). In addition, Georgia hosts 1,395 refugees and humanitarian status holders, 1,060 asylum-seekers and 488 recognized stateless persons. As of statistical data of December 2023, refugees mostly originate from Iraq, Syria, Ukraine, the Russian Federation and Iran. By the end of 2022, about 50,000 internally displaced families were provided with durable housing solutions, but the 2023-2024 action plan for implementing the state IDP strategy envisages a reduction in provision of durable housing solutions, moving from a status-based assistance policy to a needs-based one. While it grapples with the internal conflict situation, the continuing war in Ukraine has tested Georgia’s regional political stance and external relations. The country has so far managed to absorb the negative diplomatic and economic spillovers, as evidenced by robust economic growth since the Russia-Ukraine war began. Indeed, the economic spillover effects have been positive in strictly monetary terms, with the Georgian economy, along with other countries in the region, benefiting from a rerouting of trade and capital flows because of the war.

- On the economic front, Georgia’s economy has recorded consistent growth since 2015, except for 2020 when its economy declined by 6.3 % due to the COVID-19 pandemic and has proven to be resilient and resourceful. Georgia’s growth over the past decade has been driven by capital accumulation, while the contribution of labour has declined. The share of employment in agriculture declined from 26.2 percent in 2010 to 16.5 percent in 2023, but the value-added per worker in manufacturing and services is 2.7 times higher than in agriculture, pointing to the need for sectoral labour shifts. There is the added issue of substantial gender gap in labour force participation (43.1% for women and 66% for men in 2023), and adjusted monthly gender pay gap, which as of 2022, equalled 23.0%. Structurally, wholesale and retail trade, real estate, manufacturing, construction, agriculture and forestry, public administration, defence and social security, transportation, financial services and insurance, account for majority of the nominal GDP, but over the past years, a shift towards service sector is evident. For example, the tourism sector now accounts for 7.1% of GDP, nearing the 2025 goal of 7.9%. The government's economic policy is geared towards maintaining macroeconomic stability while enhancing the investment climate to foster business growth, job creation, and infrastructure development. The IMF projects Georgia's per capita income in 2024 to reach 44.8 percent of the median indicator of the European Union. Since 2010, highest growth of 11% of GDP was registered in 2022, followed by 7.8% in 2023 and 8.7% in the first quarter of 2024. Moreover, Georgia’s trends in external trade are positive. Exports rose to $ 6.09 billion, and imports hovered at just above $15.6 billion in 2023, experiencing YOY growth in nominal terms of 9% and 15% respectively, and leading to a reduction in the current account deficit as a percentage of GDP by 4.4%. The EU is the main trade partner of Georgia, with a share of 20.9% in trade turnover, followed by Turkey (13.8%) and Russia (11.1%). However, Georgia’s global competitiveness position is relatively weak, it has limited linkages with global value chains, a relatively small base and commodities-focused exports, and is dependent on a small number of trading partners. These are issues requiring greater government attention.

- Despite Georgia’s impressive gains in economic growth, significant regional disparities exist, with economic development and wealth concentrated in urban centres like Tbilisi, while rural areas—where agriculture remains a significant source of livelihood—lag behind. Not only is urban poverty lower, but it has also witnessed a more rapid fall than rural poverty (decrease of 9.4% for urban and 15.6% in rural areas in 2023). The lack of infrastructure, education, non-agriculture employment opportunities and healthcare in rural regions limits opportunities for economic advancement and perpetuates poverty. In addition to issues of access, Georgia has challenges in terms of delivering quality social services. Expenditure on education e.g., is lower than comparator countries with similar GDP and per capita, and two-thirds of 15-year-old Georgian students fail to meet basic learning standards in mathematics, reading, and science, with regional differences in learning achievement. Moreover, the differential in GDP per capita is significant at 2.7 times between the richest and poorest regions. Tbilisi has the largest share in the country's GDP (53%) and accounts for 77% of the total turnover of the business sector comes from companies operating in Tbilisi, and its economy is more competitive, attracting 86% of total foreign direct investments (FDI). Furthermore, efforts will need to be made to close the digital divide in terms of geographic dimensions (93.1% of urban households have access to the internet compared to 83.4% rural households). As discussed elsewhere in this report, divides also exist in relation to access to finance, especially for SMEs and for women. While credit to SMEs has risen significantly (from 1.4m GEL in 2010 to 7.174m GEL in 2022), the share of SME loans (48%) constitutes a minority as a percentage of total business loans. Approximately 40 percent of businesses in the trade sector, which accounts for the largest number of businesses across all economic sectors, are owned by women, and women business owners outnumber men owners in such areas as education, health care and social work. Addressing these regional disparities requires an ambitious regional policy and a comprehensive approach towards increasing sustainable competitiveness, while promoting more balanced social and territorial development. It also includes investing in urban and rural infrastructure and social services, enhancing agricultural value chains, improving financial and market access, and providing adequate education and healthcare services. Strengthening rural economies through sustainable agricultural practices, promoting agro-tourism, and supporting smallholder farmers can contribute to reducing inequality and fostering national cohesion. It is also pertinent to point out concerns voiced over the recent steps to amend the National Bank of Georgia (NBG) law to change the NBG’s management structure. As noted by the IMF, any changes to the central bank’s governance framework should follow a consultative process to safeguard the central bank’s independence and credibility.

- The Government has already undertaken measures to improve the quality of life in high-mountainous regions of Georgia, which experience a severe shortage of jobs, public services and modern infrastructure. The Law on Development of High Mountain Regions (2015) accords special status to 1,802 settlements, provides tax exemptions to 553 enterprises (as of 2023) and additional benefits to the existing national social and health assistance to 258,000 people (7% of country’s population). The Strategy on the Development of the High Mountainous Settlements of Georgia (2019-2023) envisaged GEL 968 million of additional funding for rehabilitation of roads, water supply and sewage systems, preventive measures for reducing damage caused by natural disasters, and investments in basic social services, and digital infrastructure. For the continuation of this, a new strategy on the Development of the High Mountainous Settlements of Georgia (2024-2030) and its action plan (2024-2026) was adopted in 2024. The strategy considers improvement of living and working conditions in high mountain settlements, while simultaneously reducing socio-economic disparities in high mountain municipalities. The Fund for the Development of High Mountain Settlements aims at promoting the elimination of inequalities in high mountain settlements. Micro, small and medium enterprise support programs and various infrastructural projects are financed from the fund to encourage economic development in high mountain settlements.

- Private Sector Issues Reforms on regulatory aspects, simplification and transparency of taxation, and relatively lower rates of taxes have laid the foundations of Georgia’s economic transformation and accorded it high status on the Global Competitiveness Index (GCI). SMEs account for 99.7% of active enterprises in the country, for 60.1% of business sector employment, 34.5% of business sector turnover and 51.4% of output in the business sector. However, while SMEs account for a larger share of total employment in the business sector, it is large firms that dominate employment growth-- 6 percent among large firms, compared with 3 percent growth among SMEs between 2012-2022 which is in part linked to the negative impact of the COVID-19 pandemic on SMEs. Therein lies one of the challenges of structural change required to make Georgia’s economy realise its full potential. Similarly, while Georgia has been able to attract substantial Foreign Direct Investment (FDI)—equivalent of 8.2% of GDP between 2016-2022—most of it is directed towards non-tradable sectors (e.g. energy, transport, insurance, logistics, and real estate) and thus has had limited impact on productivity growth. The recent focus on positioning Georgia as a logistics and value chain hub seeks to redress that imbalance. Moreover, opportunities exist to capitalize on the digital economy opportunities and the government’s efforts in this respect include the establishment of the Georgia Innovation and Technology Agency (GITA) to support the digital ecosystem in the country. Investing in technology-based skills will need to be assigned a higher national priority, however, if the potential in the digital economy is to be tapped.

## Governance context

Georgia’s governance reforms--covering the gamut of public sector management, public finance management, economic governance, and corporate governance—have earned Georgia accolades from international organizations and acknowledgement as one of the star performers not just in the region, but globally. Georgia’s progress on key governance indicators reflects well on its agenda for improving governance (Figure 1). Georgia’s regulatory quality and control of corruption tops that of the rest of Europe and Central Asia, its government effectiveness has shown consistent improvement between 2017 and 2022 and in fact exceeds the performance of Europe and Central Asia in 2022, while reasonable progress is evident on rule of law. The two indicators on which Georgia lags are voice and accountability and political stability. Other, more recent surveys and assessments confirm this backsliding on some governance issues. The Georgia Good Governance Index 2023 saw democratic governance receiving 41.65 out of 100 points, with persistent polarization, stalled judicial reform, and proposed laws against freedom of expression, and weakened horizontal accountability cited as some of the main reasons for the low rating.

Figure 1: Key Governance Indicators (2012-2022). Comparison of Georgia with Europe and Central Asia

Source: World Governance Indicators (www.govindicators.org)

- Public Administration Reform (PAR) Following on from the results emerging from the ‘PAR Roadmap 2020’, the Government framed the ‘Public Administration Reform Strategy for 2023-2026’ and its first ‘Action Plan for 2023- 2024’. The Reform Strategy encompasses several aspects of public administration and their attendant policies and strategies, including development of the Policy Planning and Coordination system, decentralization, public service development, public finance management, and the relatively new area of digital governance. A senior level institutional structure—the Public Administration Reform Inter-Agency Coordination Council—is entrusted with the twin responsibilities of defining public administration policies, as well as lead on coordination of implementation and monitoring.

- Local Government Reform The Decentralisation Strategy 2020 2025 is the key framework to reaffirm citizens’ right to self-governance. It emphasizes expanding local self-governance authority; promotion of financial and material empowerment at local levels; and supporting efforts for more accountable, transparent and outcomes-driven local governance. The National Association of Local Authorities of Georgia (NALAG) has been championing gender equality work across all 64 municipalities of Georgia. In 2023, NALAG approved its second Gender Equality Action Plan for 2024–2025. The plan prioritizes comprehensive support for all 64 municipalities in crafting municipal-level gender equality action plans, implementing measures to combat sexual harassment and improving gender data collection at the local level. The number of municipalities that have become parties to the European Charter for Equality of Women and Men in Local Life has reached 26 (40 per cent of all municipalities. As a result of these efforts, Georgia’s local governments appear to be gaining strength, especially in terms of transparency and accountability (Figure 2).

Figure 2: Local Self Governance Index (2017-2023)

Source: National Assessment of Georgian Municipalities, Institute for the Development of Freedom of Information 2023

Judicial Reform Persistent allegations of compromised integrity of the justice system, its limited independence, and undue interference from the executive and the legislature, have riddled efforts to improve the reach, quality, and trust in its services. In compliance with the EU acquis and the recommendations of the Venice Commission, several steps have been taken to strengthen the judicial system, including improving the constitutional and legislative frameworks to guarantee the independence of the judiciary and its impartiality; framing a Judicial Reform Strategy that focuses on efficiency measures for the court system, and strengthening the institution of trial by jury. However, critical steps such as aligning the Law on Common Courts with European standards, a comprehensive reform of the High Council of Justice (HCJ), and open access to court decisions, however, are yet to be undertaken. It may be pointed out that there has been a reduction of cases in the European Court of Human Rights, with only 175 cases pending as of July 2024 (down from 3,045 cases). Moreover, more recent surveys such as the “Public Perceptions of the Justice System in Georgia – Georgian Population Survey”, conducted by IPSOS France in 2024, point to 61% of polled Georgian citizens taking a more positive view on the independence of the justice system. This proportion of positive citizen assessment is higher than the EU mean of 53%.

- Anti-Corruption and Open Government Reform Georgia has been actively pursuing an Open Government agenda, and in partnership with civil society, has successfully completed four Open Government Action Plans, with a fifth (Action Plan 2024-2025) under implementation. A High-level Open Government Coordinating Council, chaired by the Head of the Administration of the Government of Georgia, was established in 2020 and includes both government agencies and civil society actors, with Deputies of every Minister and Heads of NGOs enjoying the right to vote in the Council. A Co-Chair was unanimously nominated by the Council member NGOs, but the NGOs have recently withdrawn from the Council in the wake of the Law on Transparency of Foreign Influence .

- Public Finance Management (PFM) Reform Georgia’s PFM systems are characterised as being robust, progressive, and efficient. Indeed, the country has ranked no.1 in the world on Fiscal Transparency in two successive Open Budget Surveys, which is no mean achievement. The PFM Strategy 2018-2022 sought to ensure fiscal disciple, operational efficiency, and effective allocation of Georgia’s public resources, including at the local government level. With the implementation of the PFM Reform Action Plan, the PFM systems in the country are acknowledged to have improved and the 2022 Public Expenditure and Financial Accountability (PEFA) Assessment records significant progress on several aspects since 2017, when the last PEFA Assessment was undertaken. Based on the PEFA and other assessments, as well as the consultations with stakeholders, a new Public Finance Management (PFM) Strategy 2023-2026 was approved by the order of the Minister of Finance of Georgia. UN agencies including UN Women have contributed to the PFM Strategy and Action Plan integrating key principles of gender-responsive budgeting (GRB), leading to the institutionalization of GRB in Georgia and progress towards SDG indicator 5.c.1. These developments mark an essential policy shift, as previous reform cycles in PFM made no reference to gender equality goals and objectives. In relation to fiscal management, the IMF documents improvements across an impressive range of areas, including fiscal reporting; fiscal forecasting; fiscal risk analysis and management, notably in state-owned enterprises (SOEs); increased transparency and improved quality of public. While the onset of the COVID-19 pandemic was considered responsible for disruptions in fiscal discipline between 2019-2021, control over spending during budget execution was maintained, revenues were efficiently collected, and crucially, budgetary rules and regulations were not circumvented. In the face of adverse external shocks which COVID-19 brought in its wake, the steadfastness of PFM reforms is no mean achievement and may offer part of the explanation for the swift, and robust rebounding of Georgia’s economy. Furthermore, to enhance the integration of various policy directions in Public Finance Management and strengthen the links between strategic planning and budgeting, the Ministry of Finance introduced a new "policy classifier" in 2022. This tool allows all spending units at national and local levels to "tag" their programs and sub-programs to various policies, including Sustainable Development Goals (SDGs), Gender Equality, Climate Change (mitigation and adaptation), and Human Capital Goals. The results of this tagging are included in the budget documentation and by 2027 the budget documentation will include not only the linkages but also information on the fiscal impact of the policy classifiers.

- The government has also done well to pursue pension reforms. Georgia’s pension system constitutes the largest support for the elderly—70% of whom are women—through a flat-rate pension funded through the state budget. With an ageing population, the fiscal burden is rising, with pension spending at approximately 5% of the GDP, and expected to rise to 7% by 2075, and accounting for 21% of the budget in 2023. To address this challenge, pension reforms were initiated in 2018. In 2023, the Law on Voluntary Private Pensions was enacted to replace the old legislation on non-state pension insurance, paving the way for voluntary private pension insurance. This move is expected to ensure that the government’s fiscal burden remains reasonable, while helping to mitigate significant demographic fiscal risk. The need for strengthening the independence and authority of the Pensions Agency, is also apparent, especially with reference to its decision-making powers on pension fund investment.

## Human rights and gender equality contexts

- In March 2023, the Parliament adopted a new National Human Rights Protection Strategy that covers economic and social rights and prioritizes improvement of equality and anti-discrimination legislation, protection of the rights of vulnerable groups and improvement of victim-oriented response to crimes committed on grounds of discrimination. However, it  does not address discrimination on grounds of sexual orientation and gender identity as well as the independence, accountability and transparency of the judiciary.The UN special rapporteur on human rights defenders, voiced concern about “systematic efforts to undermine human rights defenders,” while the UN Committee on the Rights of Persons with Disabilities welcomed legislative and policy progress but criticized the “prevalence of the medical approach to disability” and called for a comprehensive strategy and national action plan to implement the Convention on the Rights of Persons with Disabilities. The report of the Special Rapporteur on the Rights of Persons with Disability, however, acknowledged the progress made on disability rights, through legislative and policy reform, as well as important actions that have resulted in a commitment to inclusive education, social protection, and access to healthcare, including mental health. To fulfill the obligation of the United Nations Convention "On the Rights of Persons with Disabilities" and the Law of Georgia "On the Rights of Persons with Disabilities", an inter-agency committee has been established within the administration of the government of Georgia (AoG), which reports on the implementation of the basic rights and freedoms of persons with disabilities, including measures to ensure social rights. In another positive assessment, the UN Subcommittee on Prevention of Torture (SPT), acknowledged the significant progress in fighting torture and improving detention conditions, but called for extra measures to lower prison population, expand staff force and strengthen the rehabilitation program.

- With regard to gender equality, Georgia has made significant progress to refine the legislative framework and institutional mechanisms for achieving greater gender equality. It introduced a new Constitutional guarantee of gender equality in 2018; adopted State Concept on Gender Equality (2022); National Action Plan against Trafficking in Human Beings for 2022–2024 (2022); National Action Plan on Ending Violence against Women (2022); (d) Fourth National Action Plan on Women, Peace and Security 2022–2024 (2022); Gender Equality Strategy and Action Plan developed by the Civil Service Bureau aimed at establishing a gender-responsive public service (2022); Gender Equality Strategy 2022–2025 for the Ministry of Foreign Affairs (2021); adopted the first-ever policy document on SOGI (sexual orientation and gender identity) rights as part of the National Human Rights Action Plan—however, the National Human Rights Action Plan 2024-2026 has removed the reference to SOGI; established the Inter-Agency Commission on Gender Equality, Violence against Women and Domestic Violence (the Inter-Agency Commission) in 2017; and amended the Gender Equality Law in 2016 to make it mandatory for gender equality councils to be created at local elected councils and a gender advisor to be appointed at each Mayor’s office, with 64 municipalities complying with these provisions. The recent abolishment of gender quotas, however, has drawn widespread criticism. The abolition of mandatory electoral gender quotas took place on the eve of October 2024 Parliamentary elections, while women’s political participation rates remain below the regional and global averages. Women demonstrate high academic attainment (with over 56.5% of the graduates of higher education institutions being women) but these results are not translated in economic empowerment gains, with many women being economically inactive (58.5%), while employed women (27.5%) are facing Gender Wage Gap of 23% (adjusted monthly). Women are underrepresented among owners and top managers of enterprises. Only 24.7 newly established enterprises had a women owner in 2022. It is noteworthy that the Not in Employment, Education, or Training (NEET) indicator stands at 31% and is predominantly acute among young women (Female 37%, male 26%).

- In relation to the LNOB principle, several steps have been taken across various sectors. At a policy level, Georgia adopted the first-ever policy document on SOGI (sexual orientation and gender identity) rights as part of the National Human Rights Action Plan. However, the policymaking gains in relation to LGBTIQ+ individuals have not been reflected in the new Human Rights Strategy and Action Plan.

- In the health sector, notable advancements have been made: (a) the Universal Healthcare Program (UHP) has seen the state taking responsibility to cover primary healthcare.emergency,, selective surgery, chemo, radio and hormone therapy, delivery and C-section services to every household in the country, including residents of Abkhazia and Tskhinvali region/South Ossetia. The telemedicine initiative, on which the UN and MoIDPLHSA partner, help overcome geographical barriers to accessing primary health care services. This initiative is funded through a €4.7 million (US$ 5 million) grant from the European Union Delegation, and involves the WHO, UNFPA, UNICEF, and UNOPS, citizens, communities, and the private sector. This initiative could help address healthcare gaps in Abkhazia and Tskhinvali region/South Ossetia. In addition, with support from UNFPA, the government of Georgia elaborated guidelines for healthcare providers to ensure the access of Women with Disabilities to reproductive health services.

- In the education sector, the “1+4 program”, which allows ethnic minority young people to enrol in higher education institutions, has benefited 5,600 citizens (45% female) between 2021-2024. Similarly, the Post-School Education Preparation Program targets vulnerable students from Abkhazia and Tskhinvali region/South Ossetia, Georgia, and the Vocational Education and Training programs, implemented since 2016, have made vocational training accessible, parolees and probationers, and students with IDP status. The introduction in 2020 of bilingual education at the preschool and primary education levels, has created opportunities for improving the quality of the implementation of state educational standards. In addition, since 2018, students of non-Georgian speaking sectors (Azerbaijani, Russian and Armenian) are provided with approved school textbooks translated into the language of instruction. Georgian language learning programs and courses are available for various segments of the population (including schoolchildren, students, public servants, clergy, penitentiary establishments) for free through Zurab Zhvania School of Public Administration and its 12 regional training centers and mobile groups, including in distant learning format.

- Sustainable Development and Climate Change Challenges Sustainable development is one of the pillars of the government’s economic policy and is embedded within several components of the UNSDCF. Eco-tourism is already a government priority, and investments have been made for expansion of the Protected Areas, creating alternative income generation and new job opportunities, thus preventing migration from mountains to lowlands. Similarly, the Emerald Network was initiated 2008 and currently comprises of 58 Emerald sites, covering 18.45% of the country’s territory. A similar opportunity exists in renewable energy and sustainable agriculture, the latter within the context of the Middle Corridor’s new importance as a transport and logistics hub. As regards renewable energy, Georgia has an estimated potential of 11.8 gigawatts of hydropower, 1.4 gigawatts of wind power, and 1.5 gigawatts of solar power capacity. Investing in renewables will not only increase renewable energy to 27% of the energy mix, but also reduce reliance on import of energy during winter and reduce Georgia’s energy poverty.

- Georgia faces significant climate change risks, primarily driven by its diverse and complex geography. The country is increasingly vulnerable to extreme weather events such as floods, droughts, landslides, and strong winds. These phenomena have intensified in frequency and severity due to climate change, posing substantial threats to both human lives and economic stability. Landslides, floods, and mudflows are among the most damaging natural hazards, affecting over 70% of the territory and around 63% of the population, causing extensive damage to infrastructure and arable land. To address these risks, a comprehensive strategy for climate change mitigation and adaptation has been framed that focuses on seven key sectors—energy, transport, industry, agriculture, forestry, waste management, and water resources. By 2030, the country aims to reduce its Green House Gas (GHG) emissions unconditionally by 35% below the 1980 levels, which would align Georgia with targets stipulated in the Paris Agreement. Promotion of green public transport systems and incentives for electric vehicles, aim for a 15% reduction in emissions from this sector. In addition, the industry and waste management sectors are adopting low-carbon technologies and improving waste management practices to achieve reduction in emissions and support waste recycling. The framing of the Fourth National Environmental Action Programme of Georgia for 2022-2026, which is the main strategic document for environmental and natural resources management, and launch of initiatives such as “Produce in Georgia” that actively support renewable energy producers and contribute to the development of a green economy, reflect the government’s commitment to climate change and sustainability. Moreover, Georgia has regularly complied with reporting requirements as part of its commitment to various international conventions, including on the UNFCCC, Green House Gas emissions, and energy statistics, which are aligned with the EU statistical acquis set out in the Statistical Requirements Compendium. Significant steps have also been taken to improve ambient air quality management in the country and to reduce air pollution from major sources by tightening liabilities for industrial plants and introducing Euro 5 standards for fuel and emission from transport. Georgia’s Nationally Determined Contribution (NDC) emphasizes the need to strengthen healthcare systems' resilience against climate-related risks. It outlines plans for interdisciplinary research to assess climate change impacts on human health, integrating social, economic, biological, and ecological systems. These efforts aim to develop effective adaptation strategies to safeguard public health and ensure the continuity of medical delivery infrastructure.

## Progress on the Sustainable Development Goals (SDG)

- Concerted efforts are being made by the Government of Georgia to achieve progress on the SDGs. Georgia became one of the first countries to submit a Voluntary National Report (VNR) on SDGs in 2016. Since then, Georgia has submitted more detailed VNRs, in 2020, and the latest in July 2024. SDGs nationalized targets and indicators were approved in November 2019 and as per the UNDP-led MAPS (Mainstreaming, Acceleration and Policy Support for the 2030 Agenda) study, all the 36 national strategies incorporate 85 percent of the country’s nationalized SDG targets, with the percentage rising to 93% if the EU Accession Agreement (AA) is also considered.

- The Voluntary National Review (VNR) 2024 documents progress on the SDGs since the previous VNR of 2020. It highlights challenges, and notes actions underway to further improve Georgia’s SDGs progress (Box 2). A mapping of national policies and strategies to SDGs is at Annex 3.

Economic Progress

- The COVID-19 pandemic led to a post-pandemic economic contraction, succeeded by rapid double-digit economic growth in 2021-2022, and followed by high economic growth in 2023.

- A noteworthy trend relates to decreasing unemployment levels since 2021. In 2023, this indicator reached the lowest level of the last decade, standing at 16.4%.

- Georgia is actively pursuing sustainable industrialization of the economy and the development of the processing sector within the country.

- FDI in the manufacturing industry has doubled compared to 2022.

- According to the OECD SME Policy Index, the country holds the highest rating among the Eastern Partnership countries.

- There is a high level of information technology development in Georgia, driven by the Agency for Innovation and Technology.

Sustainable Development

- To ensure sustainable industrialization, the Government is encouraging investment in renewable energy. Work is actively underway to directly link the country’s electricity market with the European market.

- In 2021, Georgia approved its 2030 Climate Change Strategy, which focuses on the goals and objectives set by the country in addressing climate change.

- In 2022, the Spatial and Urban Development Agency was established. Since 2020, 9 spatial/urban development plans have been approved to follow the principles stipulated in the “New Urban Agenda”/

Human Capital Development and Social Welfare

- Since 2019, the percentage of the population living below the national poverty line has decreased by 39.5%.

- The prevalence ate of stunting among children under 5 years has reduced from 6 in 2018 to 5 in 2021.

- The introduction of the cumulative pension system in 2019 and the indexation rule in 2020, is expected to lead to financial security for citizens, while larger pension assets will create a significant investment capital base.

- Social expenditures constitute a fifth of the state budget.

- To increase the involvement of socially vulnerable families in the labour market, the State Employment Promotion Program, has been in place since 2015.

- The Universal Healthcare Program now covers 96% of the population, and health care funding increased almost 5 times between 2012 and 2023. million GEL, and 2023 ‒ 1,796 million GEL)

Social Sector Services

- Georgia’s progress in control ling HIV/AIDS and reducing hepatitis C cases, aided by a successful hepatitis C elimination program, is noteworthy. However, Tuberculosis (TB) prevention and treatment remain a challenge.

- A reduction in premature mortality from non-communicable diseases has been achieved, including for death related to cardiovascular diseases per 100,000 people.

- In 2022, the Unified National Strategy of Education and Science of Georgia 2022-2030 was approved, with the main goal of increasing the quality and inclusiveness of education.

- Budget funding for higher education has increased as well (funding for higher education from the general government budget. A new model of financing vocational education has also been developed.

Governance, Democracy, and Human Rights

- To enhance the rights of vulnerable groups, several strategic documents have been developed in the country, among which the National Strategy for Human Rights Protection (2022-2030) and its Action Plan hold particular significance.

- Based on the recommendation of the European Union, an independent Anti-Corruption Bureau has been established.

- A National Strategy for the Protection of Human Rights of Georgia for 2022-2030 was adopted, that aims to enhance the systemic guarantees for the protection of human rights and freedoms, especially for women.

- Adoption of the 2021-2030 State Strategy for Civil Equality and Integration focuses on integration of ethnic minorities.

- The Parliament of Georgia adopted the Law on the Rights of Persons with Disabilities in 2020 to better reflect the obligations and principles of the UN Convention on the Rights of Persons with Disabilities in national legislation. And, in 2021, the Parliament supported the ratification of the United Nations “Convention on the Rights of Persons with Disabilities”.

- To ensure the delivery of customer oriented, simple, and high-quality public services, the “2022-2025 State Services Development Strategy” aligning with EU standards, was approved, along with action plans for 2022-2023 and 2024-2025.

- Notable progress achieved on SDG localization, with nearly 50% municipalities now embedding SDGs in their planning.

BOX 2: SELECT FEATURES OF GEORGIA’S VNR 2024

# Section III: Methodology

- To achieve the objectives of the assignment and with the aim of presenting an accurate, and complete picture of the status, pace, and quality of the UNSDCF implementation, methodological pluralism was adopted. This entailed collection of data through various means and using multiple instruments, and triangulating data, insights, and perspectives obtained during the field work and desk research, as detailed below.

- The evaluation was guided by the UNSDCF Evaluation Guidelines 2022. In keeping with the UNEG principles, independence of view, neutrality of approach, participatory in practice, and rigor of process will be maintained. To fully capture and present the results of the UNSDCF implementation in Georgia, the analysis of data, information and insights collected during the field work and desk reviews also assessed:

  - Instruments, institutions, and incentives that drive performance and delivery.

  - Oversight, measurement and feedback mechanisms and systems that are used for ensuring relevance, continuous improvement in delivery, and course correction.

  - Connect the dots across several policy and strategic landscapes.

  - Identifying key strengths, opportunities and limitations including institutional capacities and processes; financial sustainability; and political support.

METHODS AND INSTRUMENTS

- Using a mixed method approach, the following instruments were used:

- Literature review and analysis of relevant documents including but not limited to:

- UNSDCF related policies, strategies, and plans.

- National and Sub-National Government Action Plans and Activity Reports.

- Strategic frameworks of UN Agencies, CCA updates, Joint Work Plans (JWP), UN INFO entries, evaluation reports of UN Agencies, wherever available.

- Surveys, census and other data produced by the National Statistics Office Georgia as well as other governmental, non-governmental, and international organizations

- Reports, partnership strategies, country program documents of various government, UN, civil society, development partner, private sector, and international development organizations

- Budgets of national and SNGs.

- Reports of coordination, quality assurance and oversight bodies at all tiers of government, as well as the institutional structures in place to monitor UNSDCF progress.

- Reports produced by or on behalf of the legislature.

Please see Annex 4 for a detailed list of reference documents.

- Instruments for collection of information, insights and perspectives including:

- Document Analysis: As detailed above.

- Focus Group Discussions (FGDs): Two FGDs were held, one with civil society and the other with the private sector (Annex 5).

- Key Informant Interviews (KIIs): KIIs with 106 individuals in 56 institutions were conducted including with political leadership; senior government officials; international development partner’s staff; and civil society leaders (Annex 6). The KII Protocol is at Annex 7.

- Surveys: Online surveys on (a) institutional stakeholder perspective; and (b) on public perceptions on UNSDCF design, results, and oversight, were administered through social media. A total of 51 and 102 responses respectively were received.

DATA SOURCES

- The sources of the documents were:

  - UN agencies, provision of whose extensive documentation was coordinated by the Evaluation Manager in the RC Office.

  - Various Ministries, departments, and agencies of the Government of Georgia.

  - Other stakeholders e.g., development partners, CSOs, private sector.

  - Research by the Evaluation Team.

STAKEHOLDER MAPPING

- Annex 8 contains a mapping of the stakeholders, and the instruments used for data collection.

SAMPLING

- Given the large number of stakeholders involved directly and indirectly with the UNSDCF implementation process, efforts were made for stakeholder engagement to be as inclusive, relevant, and representative as possible so that the analysis is not skewed by views of a particular group.

  - KIIs: Samples for KIIs were drawn based on three criteria: (i) adequacy of representation across multiple stakeholders, including political leadership; (ii) ensuring diversity of views and perspectives, through e.g., reaching out to a range of CSOs and private sector, including those who are not involved in UNSDCF implementation as partners; and (iii) meeting stakeholders at different levels of influence, and decision-making roles.

  - Online Surveys: Two separate surveys were conducted, one for institutional stakeholders, and one for the public.

    - For the stakeholder survey: A purposive sampling technique was used, targeting stakeholders in government, development partners, civil society, and the private sector who were familiar with or involved in the implementation of the UNSDCF. The survey was administered using multiple channels, including through the government, UN agencies, development partners, and CSOs including those operating at the sub-national governance level, and through private sector associations and representative bodies. The target was to receive one hundred responses, but despite repeated efforts, a total of fifty-one responses were received. Females constituted 67% of the respondents, which was substantially higher than our goal of at least 50% female respondents.

    - For the citizen feedback survey: Annex 9 contains details of the sampling technique used for this survey. As detailed in the Annex, administration of the survey involved using several channels, including mailing lists and social media. Two hundred responses were targeted but one hundred and two responses were received. Female respondents constituted 75% of the total respondents, and geographically, members of the public from 9 regions participated, which allowed for collecting diversity of views and perceptions.

GOVERNANCE OF THE EVALUATION

- This evaluation was supervised by the Associate Development Coordination Officer in the UN RCO Georgia, who served as the Evaluation Manager. The Head of Office in the Resident Coordinator Office provided advice and policy guidance as per need. There were regular meetings with the Evaluation Manager to not only share the progress on the evaluation, but also to request support in organizing meetings within and outside the UN system in Georgia and securing requisite documents from the UN agencies. The Evaluation Manager also ensured that the Inception Report and the Draft Final Evaluation Report were shared with the Results Groups and the UN Evaluation Group, allowing the evaluation team to receive and incorporate important feedback.

QUALITY ASSURANCE AND ETHICS

- As an evaluation carried out by an independent evaluation team, every effort was made to follow the UNE Guidelines on Ethical Evaluation. Specifically, this meant upholding the integrity of the process through maintain impartiality: accountability through being transparent on the purpose of the evaluation (in practice this meant e.g., informing key informants and FGD participants about the evaluation objectives upfront, and accurately reporting on the insights shared); respect through ensuring inclusion of diversity of perspectives (e.g., through two online surveys including one for the general public to participate in); and beneficence through following the ‘do no harm’ principle (e.g., seeking anonymous responses on the online survey, informing key informants about how their responses would not be attributed to their person etc.). In addition, the evaluation team and ran the report through several rounds of quality checks (e.g. of data, survey results) before submission.

DATA COLLECTION LIMITATIONS

- There were four main limitations on the data collection:

- Accessibility to stakeholders Ensuring interviews and discussions with key stakeholders in government at all tiers, business leaders, civil society leaders, and development partners was challenging within the available time.

Mitigation strategy:

- Held KIIs with alternative informants.

- Leveraged the convening power of the UN RCO and the Donor Cooperation Unit (DCU) in the Administration of Government (AoG) to ensure access to key personnel.

- Used surveys to obtain information from officials who cannot be interviewed,

- Accessibility to data Although there is a good amount of data in the public domain, access to all the data required official requests to the DCU in AoG, as well as tapping into the UN agency network.

Mitigation strategy:

- Used data in the public domain to the extent possible.

- Requested UN RCO and the DCU in AoG to send official requests to relevant stakeholders for sharing of data.

- Used the KIIs and FGDs to directly request participants for specific data and follow up vigorously for access.

- Mobility in the field Travel limitations due to security conditions in certain parts of the country for field visits meant that selection of field sites was based on accessibility, among other criteria like concentration of UN projects.

Mitigation strategy:

- Used hybrid arrangements for the KIIs and FGDs, allowing for online participation where in-person was not possible for certain stakeholders.

- Selected easily accessible regions for the field visits.

- Elections in October 2024. The evaluation took place amidst a tense political environment and overlapped with the time of election campaigning. This severely limited access to political leadership during the data collection phase. Moreover, post-elections, the evaluation results will likely not be a government priority, which may delay the process of receiving feedback from government counterparts.

Mitigation strategy:

- Attempted to meet with selected political leaders, especially the heads of various councils of the Parliament, in the early stages of the data collection phase.

- Made efforts to complete the evaluation by end of October 2024, well before the new government assumes power.

# Section IV: Findings of the evaluation

- Details the finding on the state of implementation of the UNSDCF in Georgia, highlighting progress, successes, challenges, risks, and opportunities.

## Findings

- The discussion on the findings begins with our analysis of the Theory of Change, as it provides the conceptual underpinning for the UNSDCF.

- THEORY OF CHANGE ANALYSIS

- The Theory of Change (ToC) for the UNSDCF Georgia (2021-2025) provides a framework to achieve sustainable development by focusing on good governance, equitable access to services, economic sustainability, human rights for conflict-affected communities, and environmental resilience. The framework's success hinges on a range of factors, including the pursuit of inclusive, evidence-based policymaking; sustained stakeholder commitment; and effective resource management. A review of the assumptions and risks that underpin the ToC, however, points out several weaknesses:

  - An imbalance in assigning responsibility for optimal conditions for implementation of the UNSDCF. The formulation of the assumptions and risks focuses entirely on factors outside of the UN’s sphere of operation and control. The absence of assumptions and risks directly related with the UN system is problematic and avoids accountability for results for the UN system in Georgia. Moreover, the element of flexibility and the significance of responding to evolving national needs and priorities, is entirely missing from the ToC.

  - Lack of clarity in the assumptions and risks It is important for the ToC to clearly specify what the assumption and risks are, as well indicate their implication for UNSDCF implementation. This clarity is missing in several of the listed assumptions and risks and does not therefore help in understand the ToC logic.

  - Incorrect assumptions and risk identification. Several assumptions and risks, particularly those which related to political will and government support for reform are at odds with Georgia’s widely recognized position as a reform leader in economic and governance areas. On the other hand, the imperative of political engagement for keeping the UNSDCF relevant and evolving in sync with emerging national priorities, is missing. This echoes the imbalance in perspectives highlighted in point “c” above.

  - Misplaced ascription of assumptions and risks. Several assumptions and risks are ascribed improperly. For example, Georgia’s graduation to an upper-middle income country poses less of a risk to the country (as is assumed in the ToC) and more to the UN system which relies on raising resources from the international donor community, including concessional funds and grants from bilaterals.

- In the light of the above, there is a need to revise the assumptions and risks in the ToC and develop a restructured version. Figure 3 shows the revised one with several new assumptions and risks added to the original version. Annex 10 contains a rationale for the changes made, while Annex 11 presents a synoptic analysis of the ToC.

IMPACT

SUSTAINABLE DEVELOPMENT GOALS IN GEORGIA ACHIEVED BY 2030

Enhanced human well-being, capabilities, social equality in Georgia by 2025

STRATEGIC PRIORITY

OUTCOMES

Outcome 1:

By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights¹¹ and increased representation and participation of women in decision making.

Outcome 2:

By 2025, all people in Georgia have equitable and inclusive access to quality, resilient and gender-sensitive services delivered in accordance with international human rights standards.

Outcome 3:

By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia.

Outcome 4:

By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience.

Outcome 5:

By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resources in Georgia.

OUTPUTS

- If national and local government systems are inclusive, resilient, and have capacity to mainstream gender and ensure evidence-based and participatory policy making.

- If national legislation and policies eliminate discrimination, protect and promote human rights, and access to justice.

- If the system delivers quality and equitable health, education, and social services, gender-equal results, combat GBV, violence against children and other harmful practices against women and girls including for conflict-affected communities.

- If there is improved competitiveness and social responsibility of private sector.

- If there Is sustainable, job-rich and inclusive agricultural and rural development.

- If there is increased productive employment, decent work, skills development, and effective national social protection for all.

- If socio-economic conditions, community resilience and self-reliance of conflict-affected communities is improved.

- If space is widened for dialogue and participation that strengthens civil-society, community resilience, social cohesion and implementation for Women, Peace, and Security agenda.

- If environmental governance and institutional capacity is enhanced for sustainable use of natural resources making communities more resilient to environmental shocks.

- If climate-sensitive, resilient, and risk-informed development is promoted in all sectors through mitigation and adaptation.

- If innovative, climate-friendly technologies are used for inclusive green economy, energy efficiency, and clean energy production to enhance Nationally Determined Contribution (NDCs) and support long-term decarbonization strategies.

- Then, the outcomes above will be reached.

ASSUMPTIONS AND RISKS

Assumptions

- The UNSDCF is considered by the government as a key document for development planning and is used to guide and shape policies, legislation, strategies and programs.

- There is sufficient flexibility in the UNSDCF to respond to emerging national priorities, and an institutional mechanism exists to review output areas and targets with the intent to respond to evolving policy and operational conditions.

- There is a robust and transparent mechanism for reporting on progress on UNSDCF implementation, especially with respect to gender, vulnerable communities, and sustainability.

- The UNCT in Georgia actively and consistently pursues the One UN approach and puts in place strong and effective institutional mechanisms for regular, structured engagement with the government and other stakeholders.

- There is a strong and sustained commitment across all levels of government and stakeholders, to mainstream the SDG agenda in development planning.

- Political support and leadership for economic and governance reform is sustained.

- National statistical systems are continuously strengthened and adequately funded to monitor SDGs, collect disaggregated data, and access to and use of data for evidence-based policy planning and oversight Comprehensive and adaptive strategies are put in place to manage post-COVID economic recession and its long-term consequences. Adequate implementation and monitoring capacities exist within the government at all levels and well-funded capacity building plans are in place to address capacity gaps and build requisite skills.

- Proactive measures and contingency plans are in place to manage potential environmental crises and geopolitical instabilities Diversified funding strategies, including securing external resources, and enhancing domestic resource mobilization, are implemented to finance the SDGs and national priorities.

Risks

- Inadequate political engagement leads to the UNSDCF losing its value and relevance for government, especially if it does not respond to emerging and evolving national priorities.

- Non-compliance with the full reform agenda under the EU AA may have negative implications for trade, ODA, and FDI, and thus for economic growth, jobs, and inclusive development outputs under the UNSDCF.

- Global political and economic instabilities, and flaring up of internal and external conflict, may pose risks for implementation of UNSDCF programs specifically and for implementation, financing and oversight of national plans and priorities more broadly.

- Adverse demographic trends may limit the availability of skilled workers, hindering economic growth.

- Georgia’s upper middle-income status may result in reduced financing for the UNSDCF due to shrinking eligibility for concessional international financial and technical support.

- Health, environmental, and economic emergencies may pose significant financial and developmental risks for the country and for UNSDCF implementation.

- Prolonged political instability may lead to a deterioration in the macroeconomic outlook, adversely affect progress on human rights, gender empowerment, and on inclusive development.

Figure 3: Revised Theory of Change for the UNSDCF 2021-2025 Georgia

## B. High level findings

- This section provides high-level findings on a range of issues, from overall progress on Outcomes and Outputs, to financing and Joint Programmes, from the role of the Resident Coordinator in the implementation of the UNSDCF to stakeholder partnerships.

Progress on Outcomes and Outputs

Figure 4: Outcomes and Outputs of the UNSDCF 2021-2025 Georgia

51. The UNSDCF has identified one transformative agenda, five outcomes, and fifteen outputs (Figure 4). For each outcome and for each of the outputs, different members of the UN Country Team (UNCT) are responsible for results, often in tandem, and in rare cases, individually.

- Overall, good and consistent progress has been achieved on all Outcomes and Outputs, as is evident from details at Annex 13 and Annex 14 respectively. At the Outcomes level, just over 91% of Outcomes have been either fully or partially achieved (Figure 5). When viewed Outcomes-wise, full achievement is highest for Outcome 2.  During the KIIs, strong policy level support—which is what Outcome 2 focuses on—was singled out by various government ministries, so it is not entirely surprising to see this result. Similarly, Outcome 4 is still a work in progress, which when one considers the nature of work involved—improving access to and quality of services in conflict zones—is again understandable. From our interviews with varied stakeholders, it was clear that implementing projects on time, on-budget, in an operational environment that is both cloistered and highly charged politically, was at best a daunting task.

Figure 5: Status of Achievement of Outcomes of the UNSDCF 2021-2025 Georgia

Figure 6: Outcome-wise Progress on the UNSDCF 2021-2025 Georgia

- At the Outputs level, performance is mixed, with impressive progress on some outputs and stalled status on others (Annex 13). A detailed analysis of the state of implementation, based on the evaluation criteria, is presented in another section of this report.

UNSDCF Funding and Linkage with Results

- The UNSDCF is funded through a mix of funding sources, from project financing by development partners and vertical funds, to resources raised from the private sector in support of specific interventions such as UN Women’s work with the banking sector on work-place environment (Figure 7 shows the data for 2023). UN agency-wise data on planned financing shows that the UNDP had by far the biggest budgets, followed by IOM and FAO (Figure 8).

Figure 7: Total financial contribution for UNSDCF 2021-2025 by funding source, in USD (2023)

Source, UNCT Georgia Annual Report 2023

Figure 8: Total planned budget for implementation of the UNSDCF 2021-2025 by UN Country Team entity, USD (2023)

Source, UNCT Georgia Annual Report 2023

Overall, three trends are evident: one, the funding requirement has increased across the implementation period (Figure 9), which reflects a growing portfolio—required funding increased by nearly $50m between 2021-2023, representing a 17% increase; two, financing for the UNSDCF has fallen short of the need across the implementation period, however, the funding gap has narrowed progressively over the years, reflecting the successful efforts made by the UN agencies to mobilize resources, and forge partnerships; and three, the funding gap when disaggregated Outcome-wise, shows substantial variation. Outcomes 2 and 3 have ranked highest in terms of the funding gap, while Outcomes 1 and 4 show a decline in the funding gap (Figure 9). When linked to the Outcome-wise performance, we note that the Outcome area with the highest achievement rate (Outcome 2), has the highest funding gap. This may be interpreted as underlining that while quantum of financing is an important consideration, the way the financing is used—in other words efficiency of use—also matters. There are many factors that determine the financing-results nexus and an in-depth analysis (e.g., of how the funding was delivered, capacities of partner organizations, specific purposes for which funding was used), would likely throw up a far more complex link, but this broad-based analysis does underscore the need to focus as much on quality of funding as much as its quantum.

Figure 9: Overall Funding Gap and Outcome-wise Funding Gap UNSDCF 2021-2025 Georgia

Source: UNCT Annual Reports

- The UNSDCF actively promotes Joint Programmes as a strategic approach to improve institutional synergies, achieve cost-efficiencies, and deliver on the drive for a One UN approach. A total of 25 Joint Programs (JPs) are included in the UNSDCF (Annex 14), with 14 having been completed, 7 active, and 4 in the pipeline.   The UNDP is either the lead or co-lead in 16 of all JPs. It is important to highlight that some of these Joint Programs began implementation prior to the current UNSDCF cycle, but their implementation period overlapped with its implementation period. In addition, there are 8 Joint Initiatives (JIs) that are currently under implementation. These Joint Initiatives are defined as activities that are implemented by more than one agency on the basis of agency-to-agency agreements, contracts, etc. The other differentiating point between Joint Programs and Joint Initiatives is that the former must (i) have a Joint Program document with a results framework, work plan and budget derived from the UNSDCF joint work plan and funding framework, and (ii) use one of three fund management modalities (FMM): parallel, consolidated, or pass-through. If these two criteria are not met, then that activity is not classified as a Joint Program. The need for and benefit of this differentiation, however, is not clear.

- The average budget of all JPs is $2,967,651, although the average for the pipeline JPs are higher than those JPs that have been completed or are ongoing (Figure 10). JPs also on average, have a shorter tenure than JIs (2.81 vs 3.24), which in a way is counterintuitive.

Source: UN RCO

Figure 10: Joint programmes

- From the data available, and based on insights shared during the KIIs, three findings emerge:

    - The need for greater strategic focus: A point for the UNCT to reflect on is whether the outcome areas need to be as many as five, and whether trimming these areas down will not only allow for higher budget allocations for interventions, but also improve oversight. This spreading of the butter with small investment projects may well be robbing the UN in Georgia of the opportunity to achieve greater impact through a few, catalytic interventions. In the case of JPs for example, the average project size is just under $3m for use over just under three years (as an average tenure). Although there does appear to be a clustering of JPs along specific themes, it is not clear if that is the result of any shared and deliberate agreement on targeting of themes and “may well be driven by availability of financial resources and donor priorities. Key informants pointed to the need for stronger leadership on this issue by the UN RCO, given its mandate on ensuring or fostering a Delivery as One approach.

    - Unclear process of JP structuring: During KIIs, several informants expressed support for JPs as a concept and highlighted its potential to align resources with common goals. At the same time, they indicated the need for instituting clear criteria on the basis of which JPs can be structured, define more sharply the process through which JP participants are selected, and support a JP ecosystem through which risks, responsibilities, and resources are shared. Discussions with the UN RCO revealed that there are indeed clear, established guidelines and protocols in place for JPs, so it may well be a case of better communication between the RCO and the UN agencies.

    - JPs are still evolving as a modality: The conceptual strength of JPs as an instrument of cross-UN system synergies, and the arguments of institutional solidarity that it begets, do not yet appear to have embedded in how the UNSDCF is designed and implemented. Concern was raised by some key informants within the UN system that JPs bring in their wake additional—and some said unfair—reporting burden in that even those agencies who did not have an integral role in implementing JPs, still had to report as frequently as those who had more substantial role. This latter point could not be ascertained for its accuracy because of shortage of time, but in principle, good management processes would support equitable apportionment of responsibilities commensurate with the depth of engagement on a JP. When queried, government agencies and development partners welcomed the idea of joint efforts by UN agencies and mentioned several projects where the UNDP, UN Women, UNFPA (e.g., on gender related interventions), or UNICEF, UNFPA, and WHO (on health initiatives). This was important feedback, as it highlighted the potential to use JPs not only as a means of internal efficiency, but as an instrument with positive spillovers for partners. Both government and development partners referred to three perceived benefits of joint programming: (i) tapping a pool of specialized yet diverse, collective technical knowledge that allows for covering a broader thematic coverage than is possible through working with individual agencies; (ii) reducing the administrative burden of having to deal with individual agencies; and (iii) enablement of better inter-agency coordination through a single platform.

Role of the UN Resident Coordinator Office

- The establishment of the Resident Coordinator (RC) system constitutes one of the more significant and meaningful UN reforms in recent years. As a new institutional innovation, however, it is very much in a nascent stage of development and globally, its ‘proof of concept’ has yet to be established in an emphatic manner. To arrive at a better understanding of how internal and external stakeholders view this reform and its progress, discussions with UN agencies, government, and development partners offered some interesting and important findings:

    - The jury is out on performance of the RCO: The sentiment that these are early days in the life of the institution, was understandably echoed across the spectrum of stakeholders. Informants felt that the RCO is still finding the right balance between its role as a facilitator and a leader but welcomed the bolstering of its office in terms of human resources (both in quality and quantity), and the efficient manner in which it maintains its neutrality.

    - Positive impressions on RC as a political negotiator: In the context of the rising political economy risks in Georgia, the role of the RC as a political negotiator—while already an important element of defined responsibilities—will likely assume and retain pole position in the near to medium terms as its principal role. Issues such as gender equality, rule of law, human rights and Work done on this front since the RC reform was introduced, was viewed positively within the UN system, and within the government. The need to provide continued and purposeful leadership on the One UN Agenda was also highlighted by different stakeholders.

    - Visibility needs to be strengthened: Outside of the UN system, knowledge and understanding of the role of the RCO bordered on the weak to non-existent. This may be rationalized in terms of the limited engagement opportunities that the RC has with a larger segment of stakeholders, than say a Head of Agency, it should not detract from the point raised by several stakeholders, for the RCO to enhance visibility of its role, functions, and services.

Relations with Stakeholders

- The findings on stakeholder relations present a mixed picture:

    - Relations with government are strong at the bureaucratic and technocratic level, with a mutual respect, and appreciation for each other’s roles and limitations. Government counterparts were quick to acknowledge the responsiveness and flexibility of UN agencies to respond to evolving needs and scenarios. Relations with political leadership in the country also appeared to be sufficiently strong till about 12-18 months ago, with regular interactions between heads of UN agencies and ministers, and between senior UN staff and inter-agency committees and commission. This close working relationship resulted in several important reforms, policies, and action plans to be developed, as documented in the tables on progress on outcomes and outputs in this report. The more recent history of government engagement, however, tends to be marked by the adoption of a conscious arms-length approach by the government. While the engagement has continued, factors such as the pre-electoral political instability and polarization, and certain actions such as the withdrawal of the gender quotas in parliament, and the promulgation of the Law on Transparency of Foreign Influence, may have temporarily affected relations between the UN system and government.

    - Relations with development partners tend to mirror relations with government to the extent that partners welcomed the role of the UN agencies in designing and implementing projects funded by them. They also held the view that the ability to respond quickly to changing priorities was an asset, as was its strong civil society network. UN maintained close partnership and regular information exchange and coordination with all Development Partners through Development Partner Coordination Group, the Ambassadorial Working Group and bilateral engagements. However, most of the UN’s partnerships are with bilateral partners. Although there are joint initiatives with likes of the Asian Development Bank and the Word Bank – the latter were generous in their praise for the support and advice provided by UNICEF e.g., on foundational learning – a case could be made for strengthening of partnerships with the Multilateral Development Banks, especially given that they are finalizing their next 5-year country partnership strategies

    - Relations with civil society are mostly transactional, with civil society organizations serving as the service providers for the UN agencies. Although there are other reasons, the potential impact of the Law on Transparency of Foreign Influence on these service providers is a source of consternation for the UN, especially in regions where conflict-related issues linger. However, even before the new law, space for civil society’s political dialogue had been shrinking. Moreover, there is no evidence that the UN provides support to CSOs registered as Non-Commercial, Non-Entrepreneurial Entity (NNLE) under the Law of Entrepreneurship.

## Output-wise findings

- This section details the output-wise findings. We first present a table showing SDG alignment, key questions and summary analysis for all the output areas; a table showing progress against each indicator for the output areas; and lastly, summary analysis evaluation criteria-wise

### Outcome area 1

| UNSDCF OUTPUTS | ALIGNMENT | KEY QUESTIONS | SUMMARY OF ANALYSIS |
| --- | --- | --- | --- |
| Output 1.1 Inclusive national and local governance systems have greater resilience and capacities to mainstream gender, migration and ensure evidence-based and participatory policymaking, map and address inequalities and deliver quality services to all Output 1.2 National legislation and policies to eliminate discrimination, enhance human rights and equal access to justice in Georgia Output 1.3 Legislative frameworks, policies and governance systems deliver gender-equal results, combat GBV, violence against children and other harmful practices towards women and girls | Output 1.1 is aligned with SDG Output Indicators 1.1.1, 1.1.2, 1.1.3, 1.1.4, and 1.1.5 Output 1.2 is aligned with SDG Output Indicators 1.2.1, 1.2.2, and 1.2.3 Output 1.3 is aligned SDG Output Indicators 1.3.1, 1.3.2, and 1.3.3 | Question 1: How were emerging issues identified and prioritized during the implementation of the UNSDCF? Question 2: How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3: What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 What are the institutional arrangements for horizontal and vertical policy and implementation coordination within the UN and between the UN and Government of Georgia? | A total of nineteen assumptions underpins the achievement of Outcome 1. All the assumptions, if realized, will help in meeting the SDG targets as well as the achievement of UNSDCF Outcome 1. The three outputs have the potential to contribute to the achievement of the outcome, as they address inequalities; governance systems, especially at the local level; access to justice; and women’s rights. However, the desk review and interviews held indicate that some of the assumptions, especially those related to governance, gender empowerment, independence and transparency of the justice systems, may not hold. The recent backtracking on commitments for gender empowerment (e.g. withdrawal of gender quotas), voice and space for civil society (e.g., enactment of the ‘Law on Transparency of Foreign Influence 2024’), and incomplete agenda on judicial independence (e.g., non-fulfilment of EU AA conditions on judiciary), have made the implementation environment more complex. Coordination mechanisms between the government and the UN appear to be working smoothly, although this varies from UN agency to agency. |

| OUTCOME 1: INDICATOR-WISE PROGRESS |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | BASELINE | 2021 PROGRESS | 2022 PROGRESS | 2023 PROGRESS |
| 1.1.1: Percentage of the population satisfied with their last experience of public services (by sex) | The ratio of population in 2015 satisfied with services received during the previous 12 months from the following institutions: 112: 91%; Police: 70%; Public Service Hall - 96%; Mayor's office - 57% | · Satisfaction with Local Self-Governments (Mayor’s Office, Sakrebulo): 60.62% (female 61.5%, male 59.6%) · Public Service Hall (2019 data): 58%. · Georgian Police (2019 data): 43%. | No update; next survey planned for 2023. | According to the poll, 54% of respondents feel the government is performing well, reflecting a notable increase in satisfaction compared to prior results. Specifics on public service satisfaction by sex, however, are not available in this survey summary. (https://civil.ge/archives/573751) |
| 1.1.2: For the facilitation of the integration of foreigners, including refugees, returned migrants, humanitarian status holders, immigrants with the right of residence and stateless living in Georgia the existence of: a) institutional and b) legal framework | · Refugees, humanitarian status holders, stateless: a) partially, b) partially. · Immigrants with right of residence: a) No, b) No. · Returned migrants: a) Yes, b) No. | · Refugees: a) not yet achieved, b) not yet achieved. · Immigrants: a) not yet achieved, b) not yet achieved. · ∙ Returned migrants: a) achieved, b) achieved. | Same as 2021. | · Refugees: a) achieved, b) not yet achieved. · Immigrants: a) not yet achieved, b) not yet achieved. · Returned migrants: a) achieved, b) achieved. |
| 1.1.3: Number of policies/procedures adopted by the Government of Georgia that aim at improvement of institutionalization of gender equality and gender mainstreaming | · 1 policy: Gender Equality Law (2010). · National Action Plan for 2018-2020. | 2 policies adopted, 3 submitted for approval. | 6 new policies adopted. | 7 new policies adopted. |
| 1.1.4: The capacity and professionalism of male and female public servants at local and national levels strengthened to better serve their constituency | · a) Data on professional development plans to be established. · b) 15% of public servants attended professional development courses | · a) 47% of agencies fulfil plans. · b) 50% of public servants improve skills (615 public servants trained). | · a) 27% of agencies fulfil plans. · b) 37% of public servants improve skills (various trainings provided). | · a) 35% of agencies fulfil plans. · b) 22% of public servants fulfilled their learning plans (1,109 public servants). |
| 1.1.5: Quality/level of evidence-based and participatory law-making processes and executive oversight | Score of 59/100. | No data (study conducted every 4 years) | No data available. | Not available for 2023, as the next National Integrity System (NIS) assessment will be conducted by the Transparency International – Georgia in 2024 and therefore, results will be available later in 2024 or 2025 the latest. |
| 1.2.1 Number and/or percentage of people, including juveniles, in contact with justice and administrative bodies, including collective labour dispute cases, who are subject to a diversion order or alternative measure for dispute resolution or custodial sentence [related to NSDG 16.3.1.1.] (GT 16.3) Custodian: ILO Contributors: UNICEF, UNDP, UNODC | 1/ Baseline 2013-2020 (as of July 2020): 250 court mediation civil cases referred to 4 mediation courts centers in Tbilisi, Gori, Rustavi and Mtskheta Juveniles – 59% 2/State labour dispute mediation services: 4 mediation cases in 2019 3/ Number of Collective Bargaining Agreements concluded at sectoral and enterprise levels: 4 in 2019 | Nearly 150 referrals to mediation in civil cases through three court mediation centers in 2021; Diverted juveniles in 2021 – 80% (unpublished data, not for public distribution until March 2022); 5 collective dispute mediation agreements signed in 2021. 9 enterprise-level collective bargaining agreements concluded in 2021. | The rate of diversion in 9 months of 2022 - 81% - out of cases meeting diversion criteria (source: General Prosecutor’s Office). 6 collective dispute mediation agreements signed in 2022. | The rate of diversion for 12 months of 2022 stands at 80%. 4 collective dispute mediation agreements were signed in 2023. |
| 1.2.2 Implementation Rate of the National Human Rights Strategy 2021- 2030 NSDG 16.3.1.1. (GT 16.3) Custodian: UNDP Lead reporter: OHCHR Contributors: UNICEF, UN Women, UNFPA | National Human Rights Strategy 2021- 2030 is in the process of elaboration |  |  | In March 2023, the Parliament approved the Strategy followed by the adoption of its Action Plan 2024-2026 in December 2023. |
| 1.2.3 % recommendations accepted in the 3rd cycle of UPR implemented or actions taken; % recommendations by UN Treaty Bodies and Special Rapporteurs implemented or actions taken; % issues of non-conformity raised in comments of the ILO supervisory bodies implemented. Custodian: OHCHR Contributor: ILO, UN Women, UNFPA, UNDP NSDG (Crosscutting) | 2013: Mid-term evaluation of implementation of 2nd cycle compiled by UPR-Info 99/133 assessed accepted recommendations (74.4%) fully or partially implemented 2017: 4 issues assessed by the UN Human Rights Committee as follow-up to the recommendations issued by this Committee in 2013. 1 received a grade of A, 2 received a grade of B, 1 received a grade of C As of November 2019, the Supervisory Bodies of the ILO have raised 13 issues of non-conformity with regard to the application of the 8 Fundamental Human Rights Conventions and 1 of the Governance Convention (C122) of the ILO. | 257 3rd cycle UPR recommendations accepted. The comments of the 2021 session of the ILO CEACR will not be public until February/March 2022. | Georgia was reviewed by the UN Human Rights Committee and CERD in 2022. Georgia will be reviewed by CEDAW and CRPD in 2023. | A number of UPR recommendations reflected in the National Human Rights Strategy and action plan for 2024-2026. CERD published its concluding observations on the combined ninth and tenth periodic reports of Georgia on 13 December 2022. Georgia submitted its follow-up to the concluding observations on 28 December 2023, reflecting progress in several areas, including the implementation of the parliamentary Code of Ethics, raising awareness regarding ethics and general rules of behavior in the civil service, elimination of sexual harassment in the workplace, combating hate speech, promoting equality, and addressing non-discrimination issues. CEDAW issued its concluding observations on the sixth periodic report of Georgia on 2 March 2023. |
| 1.3.1. Adopted and costed EVAW & DV NAP and its implementation rate NSDG 5.1.1 | Yes (Current EVAW & DV NAP covers 2018-2020) - implementation rate to be determined in 2021. | EVAW & DV National Action Plan (NAP) was developed in 2021. Adoption of NAP is delayed. | EVAW & DV NAPs were adopted in late 2022. | EVAW & DV NAP for the period 2022-2024 was adopted in late 2022. The implementation is on track. On October 26, 2022, the Government adopted one more stand-alone National Action Plan “on the Implementation of the UN Resolutions 1325 on Women, Peace and Security” for 2022-2024 |
| 1.3.2. Proportion of males and females, subjected to physical, psychological or sexual violence by sex and age in the previous 12 months. NSDG 16.1.1.3. | 2017: Female - 3.2% * Note: Includes only for women: physical, psychological or sexual violence on the part of the partner and sexual violence on the part of the non-partner 69% of children 1-14 experience any type of violent discipline in the last month | 56.2 % of children were subject to any type of violence disciplining method in 2021. Disaggregation by sex: male -57.6%; female – 54.7% Source – Real Time Monitoring Survey (MICS Plus) by GeoStat https://www.geostat.ge/ka/mics-plus N/A on violence against women. | N/A on violence against women. New data to become available in 2023 as GEOSTAT and UN Women will finalize the National Violence against Women Study. | 18.2% of women and girls aged 15-64 have experienced at least one form of violence in the past 12 months. 50.1% of women and girls aged 15-64 have experienced at least one form of violence in their lifetime. 31% of children were subject to any type of disciplining method in 2022. Disaggregation by sex: male – 34.8%; female – 26.3% per Child Welfare Survey in GEORGIA 2023 conducted in cooperation with the National Statistics Office of Georgia available at: https://www.unicef.org/georgia/reports/child-wellbeing-georgia-2023 |
| 1.3.3. Proportion of ever-partnered women and girls aged 15-64 subjected to physical, sexual or psychological, violence by a current or former intimate partners a) previous 12 m. b) lifetime by form NSDG 5.2.1 | a) 3.5 % of women (aged 15-64) experienced physical, sexual and/or psychological intimate partner violence (IPV); 3.2% of women experienced psychological abuse; 2.8% of women experienced economic abuse; and 1% experienced physical and/or sexual violence by a partner within the previous 12 months (2017) b) 13.6 % of women (aged 15-64) experienced physical, sexual and/or psychological intimate partner violence; 13% of women experienced psychological abuse; 9.6% of women experienced economic abuse; and 6% experienced physical and/or sexual violence by a partner in her lifetime (2017) | N/A. New data to become available in 2023 as GEOSTAT and UN Women will conduct the National Violence against Women Study in 2022-2023. | No data available till 2023 | Any type of violence experienced from intimate partner (women aged 15-69)– 22.9% (lifetime), 9% in the last 12 months Source: National Violence against Women Study in 2022. P. 55, table 5.1 a) In previous 12 month Physical –0.6% Sexual – 0.4 % Psychological – 8.7 % Economic – 2.1 %. b) In lifetime Physical – 5.1 % Sexual – 3.0 % Psychological – 20.5 % Economic – 7.2 %. |

Outcome Area 1 Relevance

- The interventions under this output have a direct impact on the process of adoption of policy documents in relation to human rights as well as implementation of the obligations of Georgia related to human rights. Between 2021 and 2024 Georgia went through the 3rd cycle of UPR review and supported 90% of the recommendations. Some of these recommendations were reflected in the National Strategy for Human Rights (2022-2030) and the Action Plan 2024-2026. Several Treaty bodies published their reports in this period: CERD published its concluding observations on the combined ninth and tenth periodic reports of Georgia on 13 December 2022. Human Rights Committee adopted its concluding observations on the fifth periodic report of Georgia on 22 July 2022. CEDAW issued its concluding observations on the sixth periodic report of Georgia on 2 March 2023. CRPD published its concluding observations on Georgia's initial report on 18 April 2023.

- UNICEF’s work on increasing access to justice to juveniles is relevant both in terms of Georgia’s obligations under the UN Convention on the Rights of the Child and under its own Children’s Rights Code, which entered into force in September 2019.

- ILO’s work on mediation of labour disputes and collective-bargaining agreements is fully relevant to the Labour Code of Georgia, which was significantly overhauled in July 2020 and contributes to its implementation.

- Strong alignment with national gender equality and women’s empowerment strategies and legislation (the State Concept on Gender Equality (2022), National Action Plan on Combating Violence against Women and Domestic Violence and Measures to be Implemented for the Protection of Victims (Survivors) for 2022–2024 (2022), National Concept for Women’s Economic Empowerment (2023), as well as international commitments of Georgia taken through the UN Conventions such as CEDAW, CRC; the Council of Europe Convention on Preventing and Combating Violence against Women and Domestic Violence (Istanbul Convention, 2011); thematically these policies are related to the priorities of eliminating violence against women and girls, domestic violence, and harmful practices. In November 2022, the Government of Georgia with the support of UN Women, developed and approved the rules and amount of compensation for victims of violence against women and/or domestic violence. As a result, a victim/survivor of violence is authorized to receive compensation from the state. In January of 2024, the national referral procedures for identification, protection, assistance and rehabilitation of victims of violence against women and/or domestic violence was adopted by the Government. The document was elaborated in the close cooperation with UNFPA.

Outcome Area 1 Effectiveness and efficiency

- The work for eliminating discrimination was carried out mostly through institutional interventions. Under this output, this work concentrated on the adoption of by-laws to the Labour Code as well as strengthening of the capacity of the Labour Inspection Office staff and legal practitioners. In consultation with the social partners, the machinery for settlement of labour disputes was created in line with international labour standards and in partnership the Georgian Bar Association.

- In line with the requirements of the Code on the Rights of the Child and the Juvenile Justice Code, UNICEF supported a legislative analysis and the drafting of relevant amendments to protect children’s rights to be heard in civil and administrative proceedings and submitted it to the Parliament. In partnership with the Juvenile Referral Centre implementation of the referral procedures and delivery quality programmes were strengthened for children with difficult behavior and children below the minimum age of criminal responsibility; and the effectiveness of the Diversion and Mediation Programme was enhanced for its beneficiaries.

- Institutional strengthening was evident in the work of eliminating gender-based discrimination. E.g., the Public Defender’s Office was supported to prepare the first Review of Georgia’s Gender Mainstreaming Obligations and their Fulfilment Status, and the capacity of the Office was significantly strengthened to monitor women and girls SRH and well-being on a regular basis within the human rights oversight framework. The Ministry of Finance was supported to conduct a Gender-Responsive Public Finance Management (GRPFM) assessment as part of the Public Expenditure and Financial Accountability (PEFA). Learning tools were made available to staff in partnership with the Academy of the Ministry of Finance. At the local level, newly adopted Guidelines on the Development of Municipal Gender Equality Action Plans promote a uniform approach and standards across 64 municipalities. Standard Operational Procedures on combating harmful practice of Child Marriage were elaborated and adopted for the State Care Agency (approved) and the Ministry of Education, Science, and Youth of Georgia (pending approval) Furthermore, UNFPA has contributed to strengthen the youth development agenda resulting in the elaboration of the National Youth Policy Concept (2020 – 2030) and National Youth Strategy 2023-2025 with its Action Plan.

- The UN agencies have been effective in working with the relevant government Ministries/agencies and commissions to push through the approval of a costed EVAW & DV National Action Plan. In addition, in December 2022 the Parliament of Georgia adopted legislative amendments to the Organic Law of Georgia on Normative Acts institutionalizing Gender Impact Assessment (GIA), with UN Women’s technical support.

- In addition to the central authorities, UN Women, in partnership with the civil society (NALAG) was instrumental in expanding the knowledge of gender mainstreaming methodologies such as Gender Responsive Budgeting (GRB), Gender Impact Assessment (GIA) and Participatory Gender Audit (PGA) to local governments of all 64 municipalities and five self-governing cities.

- In terms of gender-based violence and violence against children, it should be noted (see indicator 1.3.2) that the conditions have improved. According to the Child Welfare Survey “a possible explanation of the reduction in the use of violent methods of disciplining children is that the public is better aware of children’s rights now than before, which may have led to an attitudinal and/or behavioral change”. Several initiatives supported by UNICEF—including the adoption of the Code on the Rights of the Child, information campaigns on violence against Children, and establishment of Child Hotlines—have contributed to this result.

Outcome Area 1 Sustainability

- Overall, there is a plethora of state-adopted action plans, concepts in regard to gender, which suggest sustainability of the achievements. At the same time, since the first attempt to adopt the adopt the Law on Transparency of Foreign Influence in 2023, the relationship with the Gender Equality Council in the Parliament has deteriorated, the term ‘gender’ has become a toxic word, and there has been no meeting with the Gender Equality Council in a long time“. Both at the central and local levels there has been decline in the level of trust towards the work of NGOs in general and women-rights NGOs in particular.

- Nevertheless, the integrated service for child victims of sexual abuse (Barnahus model) provides a good example of an intervention where sustainability was achieved. The UNICEF, with support from the Government of Estonia, built the capacity of 167 professionals from five different agencies (State Care Agency, Ministry of Internal Affairs, Prosecution Service, Legal Aid and Forensic Bureau) to run a Center for Psychological and Social Services for Child Victims of Violence (Barnahus). At the moment of the writing, this center has been taken over by the government, its maintenance has been costed and budgeted and it now runs under the auspices of the State Care Agency in Tbilisi. There is a plan to create a similar center in Western Georgia. Despite challenges, there are examples of sustained efforts in integrating vulnerable groups into social life. The UN, in collaboration with the Georgian government, has introduced 60+ Clubs to promote healthy and active ageing. Fully funded by municipalities, these clubs provide the elderly with opportunities to engage in various activities, fostering their integration into the country’s social fabric.

Outcome Area 1 Challenges and Lessons Learnt

- There was a significant delay in the adoption of the National Human Rights Strategy and Action Plan 20224-2026, which was adopted as late as December 2023, making it impossible to meet two targets for this output (1.1.2 and 1.1.3).

- Until 2022 all issues related to human rights were coordinated by the Human Rights Secretariat working under the Administration of the Government of Georgia. As of 2022 this changed, and the duties fall under Human Rights Department of the Administration of Government. This is a lower-level institutional arrangement and could be indicative of lower levels of interest and commitment to the protection of human rights in Georgia.

- Since around 2022, but especially after the first attempt of introduction of the Law on Transparency in Foreign Influence in March 2023, the Government of Georgia has taken a more conservative stance to gender issues and the issues of LGBTQ. This is evidenced, inter alia, by the abolition of gender quotas for political parties ahead of 2024 elections and by not including the issues of LGBTQ in the new Human Rights Strategy. It has been increasingly difficult to work with the Gender Equality Council of Parliament and it remains to be seen what shape this Council will take after the elections in October 2024. The resulting change of attitude may affect the implementation of National Action Plans. On the one had this may affect the implementation of UNSDCF, on the other hand, the advocacy role of the UN agencies will be even more relevant and necessary, than before.

### Outcome area 2

| UNSDCF OUTPUTS | ALIGNMENT | KEY QUESTIONS | SUMMARY OF ANALYSIS |
| --- | --- | --- | --- |
| Output 2.1 Improved national capacities for the implementation of policies and programmes that ensure equitable access to and coverage of quality integrated health and nutrition services and the exercise of reproductive rights for all people, particularly, those left behind. Output 2.2 Improved national capacities for the implementation of policies and programmes that ensure inclusive and equitable access to quality educational programmes that meet international standards Output 2.3 Improved national legislation, policy, programs and capacities protect all people in Georgia, especially the most vulnerable and marginalized, against discrimination and ensure equitable access to and coverage of quality social services | Output 2.1 is aligned with SDG Output Indicators 2.1.1, 2.1.2, 2.1.3, 2.1.4, and 2.1.5 Output 2.2 is aligned with SDG Output Indicators 2.2.1, 2.2.2, and 2.2.3 Output 2.3 is aligned with SDG Output Indicators 2.3.1, 2.3.2, and 2.3.3 | Question 1: How were emerging issues identified and prioritized during the implementation of the CF? Question 2: How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3: What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How are the assumptions linked to the scope, pace, and quality of decentralization and PFM reforms? Question 5 How are principles of LNOB, gender equality, and inclusion used to guide implementation and oversight of progress? | The ToC has 12 assumptions for Outcome 1. Nine of the UN Agencies work to contribute to the Outcome. All of the assumptions, if realized will help in meeting the SDGs as well as the achievement of UNSDCF Outcome 1. The three outputs have the potential to contribute to the achievement of the outcome – as they address inequalities, especially in regards of access, coverage and quality of health services, access and quality of educational programs and social services. There is evidence e.g., in the health sector, of amendments in workplans and budget allocation to address emerging challenges specially during and in the wake of the COVID-19 crisis. |

| OUTCOME 2: INDICATOR-WISE PROGRESS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | BASELINE |  | 2021 PROGRESS | 2022 PROGRESS | 2023 PROGRESS |
| 2.1.1. Coverage with at least eight (8) antenatal care visits (ANC) NSDG: 3.1.1 (GT 3.1) | 42% (2019) Actual in 2020 – 35%; according to NCDC statistical Yearbook (2020). Provision of Antenatal Care services continued despite COVID-19 epidemic-related lockdown & travel restrictions, but utilization deteriorated. Coverage with at least 6 ANC visits, the most critical ones, was almost 70%. |  | 37,8% (NCDC) Despite the COVID-19-related lockdown & travel restrictions, coverage with 8 ANC visits increased in comparison to 2020, and almost equaled to pre-COVID year of 2019 data, the utilization deteriorated. Based on the ANC regionalization model, a nationwide assessment of over 150 ANC facilities was conducted. | 37% (data was obtained from NCDC in response to a request made by UNFPA, data are not published yet) | 38.5%[3] |
| 2.1.2. Elimination of mother-to-child transmission (EMTCT) of HIV and Syphilis achieved NSDG: 3.3.1 (GT 3.3) | No (2020) |  |  | EMTCT Assessment conducted; National EMCT Action Plan 2022-2024 developed; The National validation report drafted to be submitted to the WHO Regional Validation Council. | The assessment of EMTCT status for HIV, HBV and syphilis was conducted. The National EMTCT Action Plan for the period of 2022-2024 has been updated with the UN joint support, and expanded to cover the elimination of Hepatitis B. |
| 2.1.3. Number of encounters with the Primary Health Care (PHC) units/outpatients facilities, providing essential health services per capita/per year NSDG 3.8.1 (GT 3.8) | 3.6 visits (2019) |  | Number of encounters with the PHC units/outpatient facilities, providing essential health services per capita/per year: 12807695 (3.4 visits). The decrease may be attributed to COVID-19. Available data: in 2021 the number of total encounters with outpatient facilities was 4.4 (incl. children under 15, ambulance calls and ambulance calls for under 15) Encounters with physicians: 4. https://test.ncdc.ge/Handlers/GetFile.ashx?ID=b3956fe5-2a48-4fc1-9a5a-37d13c6d397f |  | In 2023 the number of total encounters with outpatient facilities was 4.4 (incl. children under 15, ambulance calls and ambulance calls for under 15) Encounters with physicians: 4.1. |
| 2.1.4 Share of districts with DTP3 containing vaccine coverage below 80 per cent NSDG 3.8.1 (GT 3.8) Lead Reporter: UNICEF Contributors: WHO Adjusted formulation: District or equivalent administrative unit with at least 80% coverage of measles-containing vaccine for children < 1 year receiving (21-02-L2-05) NSDG 3.8.1 (GT 3.8) | 1.3% (2018) Adjusted: 92.8 (2018) |  | District or equivalent administrative unit with at least 80% coverage of DTP-containing vaccine for children < 1 year: 60% 63% | 0,92 | 93.8% |
| 2.1.5 Age-standardized prevalence of current tobacco use among persons aged 15 years and older NSDG 3.a.1 (GT 3.a) | Both – 29.7% Men – 54.2% Women – 5.2% (2018) |  | Prevalence of current tobacco use among 18–69-year-olds decreased from 31% in 2016 to 27,5% in 2020. No estimation of age-standardized prevalence of current smoking among 15+ aged has been conducted in 2021. | No study available since 2020 on prevalence of tobacco use. | No study available since 2020 on prevalence of tobacco use. Field work for the Global Adult Tobacco Survey (GATS) has been planned for 2024 and results will be available in 2025. Despite short-term achievements in tobacco control, sustainability of this progress is under question due to aggressive marketing of novel tobacco products and intensified interference of tobacco industry in the state policy and legislation in recent years[4]. |
| 2.2.1: Participation of children in organized educational process, by sex, by ethnicity (one year before the official school age) NSDG: 4.2.2 (GT 4.2) | Total: 89.6%; boys: 87.5%; girls: 92.2%; Georgian: 93.5%, Azeri: 48%, Armenian: 76.1%. | No data |  | RTM/MICS Plus indicates a drop in preschool attendance (66%). | Total 90.9% (Boys: 95.8%, Girls: 86.1%) |
| 2.2.2: # of children with special educational needs (SEN) and/or children with disabilities (CWD) participating into mainstream education, NSDG 4.a.1 (GT 4.a) | 7,371 school-age children with disabilities (CWD) out of 11,500 mainstreamed. | 10,482 students with SEN |  | 11,461 students with SEN | 12,801 students with SEN |
| 2.2.3: Human Rights, gender equality and/or reproductive health and rights issues are integrated into the teachers’ a) pre- and b) in-service training programmes/ systems NSDG: 4.c.1 (GT 4.c) | · a) No; · b) No | Recommendations developed; cooperation with TPDC, syllabi updated, and educators trained. |  | Capacity building for universities and teachers, training programs initiated. | Pre- and in-service training programs strengthened; new bachelor programs launched. |
| 2.3.1: Improved inclusive and gender sensitive legislation and policy ensuring the rights of all PwDs, NSDG: 10.3.1 (GT 10.3) | · No gender-sensitive strategy or annual action plans; legislation not aligned with international standards. | Action plans adopted; National Accessibility Plan in progress. |  | 3 rounds of annual action plans adopted; Accessibility Plan pending. | Additional action plans adopted; draft laws on web accessibility developed. |
| 2.3.2: Capacity of systems and institutions improved to deliver rights-based and integrated social services, including for persons with disabilities and victims of trafficking in human beings (THB), NSDG: 1.3.1 (GT 1.3) | · a) No national guidelines for SRHR and GBV services. · ∙ b) No local action plans for social services in selected municipalities. | SRHR policy and service delivery solutions developed |  | SOP for GBV response amended; Action Plans adopted in 2 municipalities. | SOPs further refined; Action Plans adopted and funded in 2 municipalities. SOP on family planning of WwDs developed and approved SOP on antenatal care of WwD developed and approved |
| 2.3.3: Number of shelters and crisis centers for DV victims/survivors functional funded from the State Budget, NSDG 5.2.1 (GT 5.2) | 5 shelters, 5 crisis centers | No major progress; renovation work for a new shelter initiated. |  | Renovation pending completion. | 6 shelters; a new shelter opened in Tbilisi with 15 additional beds. In 2023, State Care operated six crisis centers and six shelters. By 2024, the number of crisis centers increased to seven, with the seventh center set to open in Zugdidi in 2025. |

Outcome 2 Relevance

- The UN agencies in Georgia have developed a long-standing strategic partnership with the Ministry of Health and National Center for Disease Control (NCDC).

- The UN Agencies have provided technical assistance for the development of National Health Strategy 2022-2030, supported strengthening the system for delivering quality Maternal Health services.

- In the area of ending violence against women and girls, UN Women supported the development and adoption of the VAW/DV NAP (2022–2024) with costing. The approved VAW/DV NAP reflects the Government’s commitments under the Istanbul Convention and enables effective tracking of implementation progress.

- National Action Plan “on the Implementation of the UN Resolutions 1325 on Women, Peace and Security” for 2022-2024

- UN Women supported the development and adoption of the state compensation procedure in the maximum amount of GEL 10,000 to be issued to the VAW/DV survivors and/or their children in the case of the victim’s death.

- In compliance with the provisions of the Istanbul Convention, the second round of the National Study on Violence against Women in Georgia was carried out by GEOSTAT, supported by UN Women. Through this activity, the country, along with meeting its commitment by demonstrating regular data collection and analysis efforts, also generated further evidence to inform the legislative and policymaking processes and measure progress towards the achievement of the SDG nationalized indicators.

- A new model of an inclusive education support system, elaborated through UNICEF support, was formalized through the legislative amendments in the Law of General Education. Furthermore, UNICEF supported the government in initiating an inclusive education system reform, including through setting up four school-based Inclusive Education Centers to serve as resource hubs for teachers and students, and support to MoESY for design of education programmes for children with special education needs and disabilities.

- With the help of the UN, Georgia has taken positive steps towards financial protection of its population through price regulation of essential medicines for chronic disease management, and introduction of a new payment system for Diagnostic-Related Groups (DRG) payments. WHO also supported the development of a modern Law on Medicinal Products, fully in line with EU Directives and good regional practices. However, enforcement of this law is on hold for the time being.

- A WHO-led Joint Programme with participation of UNFPA, UNICEF, and UNOPS has provided support for digital health interventions--telemedicine and health information system. Moreover, the National Non-communicable Diseases (NCD) Strategy and Action Plan has been approved by the Government, while a National Human Resources for Health Plan is underdevelopment with WHO support.

- WHO’s continuous support for Primary Healthcare (PHC) reform advancement has resulted in the development of the PHC Roadmap. Support to the designation of the Centre of Disease Control and Public Health (NCDC) of Georgia as a WHO Collaborating Centre on Hepatitis Elimination in 2022 is noteworthy. The country has been recognized as a model for HCV elimination program demonstrating decrease of viremic prevalence of Hepatitis C in adult population from 5.4% to 1.8% .While Georgia remains a low HIV prevalence country, with concentrated epidemics in certain segments of the population, late diagnosis of HIV remains a problem in the country. The UN through WHO, UNFPA and UNICEF, is providing support to institute a validation process of EMTCT of HIV, Syphilis and Hepatitis B.

- The UN also ensured access to quality free of charge RH/FP services for women in conflict-affected region of Abkhazia region of Georgia.

- In the area of HIV prevention services, UNFPA provided technical assistance to NCDC to improve access and availability of integrated SRHR/HIV services by supporting development of HIV/AIDS National Strategic Plan 2023-2025, National HIV prevention standards and strategic  interventions with special focus on key populations and young key populations.

Outcome 2 Effectiveness and efficiency

- The work under this cycle of UNSDCF started during the COVID pandemic, when the UN Agencies provided invaluable assistance to Georgia in technical advice as well as equipment and vaccines. During the COVID pandemic, WHO - in particular - was able to extend its activities in Abkhazia region of Georgia and opened a field office in 2022. In general, the agencies pursued a dual-track implementation (COVID-related interventions in additional to regular activities).

- To promote increased access to specialized services for VAWG/DV victims/survivors, UN Women in cooperation with the Agency for State Care and Assistance for the (Statutory) Victims of Human Trafficking, established additional space at the VAW/DV shelter in Tbilisi with a capacity of at least 15 beds. The new space meets pandemic-related isolation and quarantine requirements for COVID-19 and other infectious diseases. In addition, UN Women in cooperation with the Samtskhe-Javakheti Democrat Women’s Organization (DWO) established a shelter/crisis center in Samtskhe-Javakheti for GBV victims/survivors in line with shelter standards and international best practices and in cooperation with the Kakheti Regional Development Foundation a crisis center was opened in Akhmeta.

- UN Women supported development and adoption of a bill to lift formal procedures required to access the shelters, such as having a restraining/protective order, being recognized as a victim in a criminal case or being granted ‘victim’ status by the DV status granting group, thus increasing access to such services.

- Starting from the second half of 2021, specialized investigators and prosecutors are handling sexual violence crimes in Georgia as a result of the technical assistance provided by UN Women, within the Swedish funded UN Joint Programme for Gender Equality (UNJP4GE). In particular, UN Women—in collaboration with the Council of Europe and the international women’s rights organization “Equality Now”, as well as the Ministry of Internal Affairs of Georgia (MIA), the Office of the Prosecutor General of Georgia and the international and local experts, including those from the judiciary—has developed a new manual on effectively investigating, prosecuting and adjudicating sexual violence cases in Georgia. Based on the manual, UN Women, in partnership with the above-mentioned partners, has conducted a cascade of specialization trainings on handling sexual violence cases for judges, judges’ assistants, investigators, prosecutors and lawyers. As a result of this intervention, about 500 criminal justice professionals have been trained.

- UNFPA built on its earlier work (since 2016) on “Beyond the Numbers” methodology to advocate for regular perinatal and neonatal near-miss audits, which have become a mandatory prerequisite for facilities to be assigned a specific role within the three-level regionalized maternal care system, and to qualify for public funding. Based on this work, the Minister of Health (MoIDPLHSA order № 01-428/o, 25.10.2021) updated the National Strategy on Maternal and Neonatal Health 2017-2030 and approved the new 3-year action plan for 2021-2023.

Outcome 2 Sustainability

- Most of the work on health care is technical advice and policy work. Much energy is expanded to ensure that the evidence-based technical achievements/pilots find their way into government policies and strategies. According to the UN agencies, the issues of health care policies are one of the least politicized and least affected by the recent changes (e.g. the Law on Transparency of Foreign Influence). At the same time, the sustainability of these achievements might come into question if the policies or legislation changes (e.g. the case of tobacco products).

- The Covid pandemic presented a unique opportunity to use and develop telemedicine to reach remote rural areas where healthcare infrastructure is limited and residence often face significant challenges in accessing timely care. This is a good example where several UN Agencies (WHO, UNFPA, UNICEF and UNOPS collaborated with the Ministry of Health to improve access to primary health care (the project was funded by the EU Delegation in Georgia). The programme has provided over 1,700 medical furniture and devices, nearly 9,200 medical supplies, and training on the usage and maintenance of equipment to 400 ambulatory doctors across 55 municipalities in Georgia. The evaluators were able to visit one of the facilities in Shida Kartli and witness the use of the equipment. The project was successful in terms of increasing access for remote communities and the quality of the doctors (through the training provided), it would have been useful to also provide regular equipment based on need. With the support of UN Women perpetrator rehabilitation programmes have been developed and launched in prison and probation sectors. Since the launch, the programmes have been completed by over 400 probationers/convicts; 30 facilitators – psychologists and social workers from the probation and penitentiary systems have undergone comprehensive training on a perpetrator behavior correction programme inter alia role-play exercises for generating empathy towards victims/survivors.

Outcome 2 Challenges and Lessons Learnt

- The issues of public health have come under pressure in recent years. Since the important changes made in 2017-2019 in the tobacco control legislation and the tax code, tobacco taxes have not increased further and import tax on tobacco raw materials has been suspended until 2026. In 2023, the legislation was amended to postpone the requirement of plain packaging and to exclude heated tobacco products from regulatory mechanism. Moreover, in March 2024, the proposal was registered in the Parliament to half excise tax on tobacco products.

- These steps are made in the name of “economic rationale”, despite the evidence put forward by the UN together with the Georgian government that raising cigarette taxes could prevent GEL 2.2 billion in economic losses and healthcare costs over 15 years, and that for every 1 GEL invested in implementing an increased tobacco tax, the country economy would gain 221 GEL in return, without even factoring in even greater gains from increased income tax and cigarette tax revenue. This undermines the gains made, in part, due to the UN work in public health. Recent amendments to the abortion regulation and the adoption of the law on “Family Values and Protection of Minors” exemplify the growing conservatism that threatens women's reproductive rights, bodily autonomy, and gender equality. These developments could further complicate women’s access to safe reproductive health services.

### Outcome area 3

| UNSDCF OUTPUTS | ALIGNMENT | KEY QUESTIONS | SUMMARY OF ANALYSIS |
| --- | --- | --- | --- |
| Output 3.1 Improved competitiveness and social responsibility of private sector Output 3.2 Sustainable and inclusive agricultural and rural development, strengthened food systems and improved livelihoods Output 3.3 Increased decent work, including productive employment, skills development and effective national social protection for all | Output 3.1 is aligned with SDG Output Indicators 3.1.1, 3.1.2, 3.1.3, and 3.1.4 Output 3.2 is aligned with SDG Output Indicators 3.2.1, 3.2.2, 3.2.3, 3.2.3, and 3.2.4 Output 3.3 is aligned with SDG Output Indicators 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, and 3.3.8 | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How did the strategies under this output enhance the competitiveness of the private sector and contribute to increased social responsibility? Question 5 Were there any challenges in addressing the financing and capacity building needs of SMEs, particularly in rural areas? Question 6 How effectively did the strategies under this output promote sustainable agricultural practices and strengthen food systems? Question 7 What measures were taken to integrate climate adaptation into agricultural development strategies? Question 8 In what ways did the strategies under this output address the need for decent work and skills development? Question 9 How were marginalized groups, such as women, youth, and people with disabilities, included in the implementation of these strategies? | The logical connection between Output 3.1 and Outcome 3 is strong, as the SDCF highlights the role of private sector competitiveness and social responsibility in driving sustainable economic growth. The document identifies the need for enhanced support for SMEs, particularly in rural areas, which aligns with the analysis. Targeted initiatives to support SMEs through access to finance, capacity building, and market access are essential to ensure that economic growth is inclusive and benefits all segments of society The link between Output 3.2 and Outcome 3 is well-justified and supported by the SDCF, which emphasizes the importance of integrating climate adaptation strategies into agricultural development. The UNSDCF acknowledges the vulnerability of the agricultural sector to climate change and the need for climate-smart practices to ensure long-term sustainability. This output aligns well with the NDS’s goals for agricultural development and rural productivity. However, the UNSDCF’s strong emphasis on climate adaptation strategies is less pronounced in the NDS. Output 3.3 is crucial for achieving an inclusive economy, and the UNSDCF supports this by underscoring the importance of inclusive employment and social protection systems. The framework recognizes the progress made but also notes the need for additional efforts to ensure that marginalized groups, including women, youth, and people with disabilities, are fully included in employment and skills development initiatives. Tailored programs are necessary to enhance the participation of these groups in the labour market. The alignment between Output 3.3 and Outcome 3 is strong, with both the UNSDCF and the NDS emphasizing the importance of productive employment, skills development, and effective social protection. |

| OUTPUT 3: INDICATOR-WISE PROGRESS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | BASELINE | 2021 PROGRESS | 2022 PROGRESS | 2023 PROGRESS |  |
| 3.1.1: Number of new services introduced by providers within business development infrastructure, including innovations, ecosystem and formalizing informal enterprises | Limited number of services. | 2 new services introduced (Labour Safety services and Environmental Self-Scanning for packaging companies). | 3 new services introduced (financial reporting systems for SMEs, EPR implementation, Batumi co-working/networking service). | Not specified for 2023. |  |
| 3.1.2: % of companies in selected clusters demonstrating at least 20% growth rate in turnover or export | 0%. | 51% of companies showed at least a 15% increase in sales (23 out of 45 PMAG member companies). | Same as baseline. The next data update will be available in 2023, according to the GeoStat. UNDP, 2022 figures will be available in Mar 2023 | Market Development Initiatives: FAO and EU Support: Initiatives generated 250,000 GEL in sales for 55 producers in 2023, suggesting positive growth in turnover within this cluster. Diaspora-Led Market Expansion: Spain Market Entry: With diaspora support, nine Georgian companies introduced 9,000 products in Spain via the "Georgian Corner" in Madrid, increasing market exposure and likely turnover. Sector-Specific Skill Building: Workshops by IOM, UNDP, UNIDO: Focused on packaging and pharmaceuticals, enhancing international market readiness and export potential. Business Capacity Building: Agribusiness Training: 140 agribusinesses trained in 2023, aimed at quality improvements and export positioning.. |  |
| 3.1.3: Advisory Board on Child Rights and Corporate Social Responsibility established and fully functional and number of private companies that are implementing corporate social responsibility measures | · a) No Advisory Board in place. · b) 76 companies signed the Women’s Economic Empowerment Principles (WEPs). | · a) Draft concept of the Advisory Council on Child Rights developed. · b) 102 companies signed WEPs. | · a) Business Advisory Council for Children (BACC) launched. · b) 170 companies signed WEPs. | · a) Partnerships with businesses strengthened through BACC, new initiatives like Junior Tech program launched. · ∙ b) 204 companies signed WEPs. |  |
| 3.1.4: Proportion of women in managerial positions | 36%. | 36.1% women in managerial positions. | Same as 2021. | 43% women in managerial positions within rank I and II, but only 9% in top managerial positions (heads of public entities). |  |
| 3.2.1. Agricultural productivity - Volume of production per labour unit by classes of farming/pastoral/forestry enterprise size) | 30.6 GEL in 2019 |  | • Small holdings - Male: 13.5 (GEL/labour day); Female 12.6 (GEL/labour day) • Medium and large holdings - Male: 41.5 (GEL/labour day) Female: 38.9 (GEL/labour day) (source: 2022 Annual Report Outcome 3) | Same as baseline. Updated data will be available in the future statistical update in 2024, covering 2023. |  |
| 3.2.2. Number of new jobs created by enterprises through improved productivity in rural non-farm activities and through application of EE/RE, digital and other innovative technologies | 0 in 2019 | 417 jobs (source: 2022 Annual Report Outcome 3) | 609 jobs (source: “Improving Rural Development in Georgia” Project under ENPARD III Final Evaluation Report, December 2022) | Ongoing, through the creation of digital tools for MSMEs and the promotion of smart villages (source: 2023 RG3 narrative report​) |
| 3.2.3.Number of new policy documents and tools on agriculture and food safety | 0 in 2019 |  | 31 policy and legislative documents (source: ENPARD III Final Report) | Two documents adopted - Law on Food Loss and Waste Reduction, and Law on Geographic Indications. Three more policies developed but not yet approved (source: ENPARD IV 3rd progress report) |
| 3.2.4.Increase in per capita income in rural areas | 265.7 GEL in 2019 | 275.3 GEL (source: GeoStat) | 391.7 GEL (source: GeoStat) | 442.4 GEL (source: GeoStat) |
| 3.3.1. Proportion of youth (aged 15-24 and 15-29 years) not in education, employment or training (NEET), by sex | 27.9% (2014) TBI based on LFS new survey data in the mid of 2021 | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: i total - 26.8, female - 26.8, male - 26.8; Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex: total - 34.6, female - 37.3, male - 32.1; | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: total - 23.4, female - 23.7, male - 23.1; Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex, total - 30.7, female - 34.5, male - 27.2; | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: total - 21.0, female - 21.6, male - 20.4. Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex: total - 26.9, female - 30.9, male - 23.2. |
| 3.3.2 Number of companies visited by labour inspectors per year | 1,575 inspections first and follow up) conducted on 835 facilities. | 834[2] Based on the main mandate of Labour Inspection Office 1,540 inspections (first and follow up) conducted on 834 facilities. Note: For 2021, for the reopening economic activities and controlling COVID19 recommendations on workplaces, labour Inspectors together with other supervisory institutions covered 12 778 facilities) | 3755 inspections (first and follow up) conducted on 1933 facilities. | 5847 inspections (first and follow up) conducted on 3334 facilities. |
| 3.3.3. Number of work-related accidents causing injuries or deaths, in total by sex per 100 000 employees | 9,612,97 work-related injuries and 2,23,47 work related deaths per 100 000 employees in 2019[MP1] | 20,78 work-related injuries 3,04 work-related deaths | 25,71 work-related injuries 2,73 work-related deaths | 26 work-related injuries 2,55 work-related deaths |
| 3.3.4 Number of interventions to enhance day care facilities and re-skilling of women to enhance their Labour Force Participation Rate (LFPR) | 0 | N/A | N/A | N/A |
| 3.3.5. Number of awareness and advocacy campaigns launched to bridge the gender pay gap | 1 | 1 campaign launched (Gender Pay Gap report updated with UN Women and ILO support) | N/A | 4 initiatives (including development of a manual for Equal Pay Review, SES support, and HR training activities) |
| 3.3.6 Proportion of population covered by social protection floors/systems, by sex, distinguishing children, unemployed persons, older persons, persons with disabilities, pregnant women, newborns, work-injury victims and the poor and the vulnerable (SDG indicator 1.3.1) (GT 1.3) Specifically: (a) population below the national absolute poverty line covered by the Targeted Social Assistance program - TSA (UNICEF) (b) children under the national absolute poverty line covered by the Targeted Social Assistance and Child benefits Program (UNICEF) (c) Proportion of women of reproductive age entitled to receive the state maternity benefit | a) 57.8% of population below the national absolute poverty line covered by the TSA program (Explanation: 19,5% of population under the national absolute poverty line, 11% covered by Targeted Social Assistance) (2019 data) b) 65.5% of children under the national absolute poverty line covered by the TSA and Child benefits Program (explanation: 24.4% of children under national absolute poverty line, 16% covered by the Targeted Social Assistance and Child Benefits) (2019 data) 16% coverage by child benefits (TSA) while 25.5% children live in absolute poverty c) 28% (ILO, UN Women report 2020, 2018 data) |  | 229,633 children were covered by the child cash benefits – 7.5% increase from 2021 (source: 2023 RG3 Indicators) | 251,430 children were covered by child cash benefits, representing 28.6% of all children below 16 (source: 2023 RG3 Indicators) |
| 3.3.7 Number of job seekers including returned migrants and VET graduates supported with skills development, job placement and internships in EU through the skills partnership schemes, gainfully employed at the local markets and/or abroad including through circular labour migration schemes | 2020:0 | N/A | 1,231 (source: 2023 RG3 Indicators) | 1,319 (source: 2023 RG3 Indicators)[MP2] |
| 3.3.8 Number of farmers benefiting from skill development trainings and/or extension services supported by projects, disaggregated by sex and age | 0 | 1,390 farmers benefited from skills development trainings, (38% women). 5,200 farmers (30% women) benefitted from UN-supported extension services (source: 2023 RG3 Indicators) | 853 rural women increased their knowledge and skills through UN Women support (source: 2023 RG3 Indicators) | 1,319 women received TA from UN Women. 391 farmers, (including 267 women) received TA from FAO (source: 2023 RG3 Indicators) |

Outcome 3 Relevance

- The interventions under Output 3.2 are directly aligned with Georgia’s key national policies and strategies aimed at improving agricultural productivity, fostering rural economic development, and ensuring food security. The Agriculture and Rural Development Strategy of Georgia (2021-2027) outlines priorities such as sustainable agricultural practices, rural diversification, and food safety. These interventions are supported by UN agencies such as FAO, UNDP, and UNIDO, who have been instrumental in driving key reforms.

- Through the ENPARD III and IV programs, FAO supported the development of 31 policy and legislative documents​. These policies were developed in response to the government's focus on enhancing food security and rural livelihoods, as well as contributed to aligning Georgian legislation with the EU regulations, in accordance with the Association Agreement.

- Through the ENPARD III and IV programs, UN agencies played an important role in strengthening the capacity of both government institutions and private sector stakeholders to implement agricultural policies. These efforts included building the technical expertise of the Ministry of Environmental Protection and Agriculture (MEPA), enabling the government to better enforce food safety regulations, manage agricultural extension services, and support smallholder farmers. For businesses, particularly in rural areas, the programs provided capacity building support to food producers and agribusinesses, enabling them to adopt and comply with new standards and best practices outlined in national policies. This capacity-building was crucial in bridging the gap between policy development and implementation, ensuring that national strategies were effectively translated into practical actions at the local level.

- The alignment of these interventions with the Sustainable Development Goals (SDG), particularly SDG 2 (Zero Hunger) and SDG 8 (Decent Work and Economic Growth), underscores their relevance. By 2023, the interventions had contributed to the development and adoption of 31 policy documents, exceeding the initial target, and supporting rural productivity and market access​.

Outcome 3 Efficiency and Effectiveness

- UN agencies made a significant contribution towards reaching the targets set in the UNSDCF.

- Through ENPARD III (European Neighbourhood Programme for Agriculture and Rural Development), FAO introduced climate-smart agricultural practices such as no-till farming, enhanced mechanization, water-saving technologies and disbursed grants to improve competitiveness of rural enterprises. These interventions have led to beneficiary farmers’ increased productivity by 35.8%, increased production by 74.7%, and have led to an increase in income by 106.2%.

- Multiple projects have contributed job creation, including “Improving Rural Development in Georgia” Project under ENPARD III, through which UNDP contributed to creating or sustaining 609 permanent jobs. In addition, the data received from RDA indicates that the supported rural businesses created/sustained 417 jobs in 8 target municipalities through the UN agencies’ funding channeled by RDA.

- FAO contributed to drafting six major policy documents (the Agricultural Extension Strategy; the Law on Aquaculture; the draft Law on Geographic Indications; Law of Georgia on Food Loss and Food Waste Reduction and Food Donation; the Agriculture and Rural Development Strategy 2021-2027; and the Agricultural Extension Strategy of Georgia 2018-2020. In addition, FAO conducted evaluations of five state programs implemented by RDA and developed relevant recommendations on their improvement. Lastly, 12 value chain and seven policy documents were also produced through the ENPARD III project.

- Official data from GeoStat indicates a steady increase in income in rural areas. The overall progress between 2020-2024 was GEL 140.8, from 301.6 to 442.4. ENPARD III contributed to this, as the disbursement of grants has led to 106.2% increase in income of the beneficiary entrepreneurs. Similarly, the data from “Improving Rural Development in Georgia” Project under ENPARD III project shows increased average monthly income of households in targeted rural areas supported by the project. Interviews and field visits conducted during the UNSDCF evaluation also confirmed that beneficiaries of UN Women’s project administered through RDA has led to increasing income of women that received funding for greenhouses.

- The interventions under Output 3 were generally efficient, with UN agencies demonstrating flexibility and adaptability, especially in response to the challenges posed by the COVID-19 pandemic. The strategic relocation of resources, along with the quick adaptation to online trainings and the development of funding mechanisms to support Georgian farmers, ensured that the projects remained on track despite the disruptions.

- COVID-19 constituted a significant challenge, to which UN agencies adjusted well. From strategic relocations of resources to adapt to online trainings, to developing a funding mechanism to support Georgian farmers against the pandemic. Between March and December 2020, the programme awarded 132 matching grants with a total amount of up to GEL 8.5.

- Throughout the UNSDCF evaluation period, key UN partners, such as the RDA and Enterprise Georgia, highlighted the importance of financial interventions in improving the competitiveness of rural enterprises. These investments also played a pivotal role in supporting the involvement of Georgian rural enterprises in foreign trade, thereby enhancing their long-term sustainability.

- While the overall coordination between UN agencies was efficient, certain bottlenecks were noted. Delays in meeting reporting requirements occasionally caused setbacks in disbursements. However, feedback from the UNSDCF evaluation respondents indicated that the cooperation between UN agencies and external stakeholders was largely smooth. Respondents particularly emphasized the flexibility demonstrated by UN agencies, which allowed for better alignment with national priorities and the successful delivery of project outputs​.

- Output 3.3 addresses critical socio-economic vulnerabilities in Georgia, particularly for returned migrants, women, and children with disabilities, by enhancing social protection mechanisms and fostering economic reintegration. The interventions are aligned with national priorities and international frameworks, such as the Social Protection Strategy, the Georgian Labour Code, and SDG targets including SDG 1 (No Poverty), SDG 8 (Decent Work and Economic Growth), and SDG 10 (Reduced Inequality). Programs like the reintegration assistance for returned migrants, led by agencies such as IOM and UNDP, directly address employment challenges and economic insecurity. Meanwhile, initiatives such as UNICEF's "See Every Colour" campaign have been pivotal in promoting social inclusion and reducing stigma against vulnerable populations.

- The Child Wellbeing in Georgia Survey (CWS by UNICEF and GeoStat), introduced the Child Material and Social Deprivation Index, defining a broader understanding of child welfare. The Government aims to analyze various child cash transfer scenarios, focusing on impacts on child poverty and deprivation.

- With UNICEF support, positive practices in child-centered social programming were piloted in ten municipalities. The subnational programme and sub-programmes underwent modifications to address identified needs, leading to increased budget allocations. The methodological guidelines developed during the pilot were amalgamated into the "Guide for Developing Programmes Adapted to Children and Families." Building on the success of the pilot, the approach was expanded to all municipalities in the Samegrelo-Zemo Svaneti region.

- The relevance of these interventions is further underscored by UN Women, and ILO reports,, which highlight the importance of gender-sensitive policies and the inclusion of persons with disabilities (PwDs) in the labour market. According to the ILO, legislative reforms focusing on improving labour conditions for PwDs have been a key priority, ensuring that the legal frameworks support equal access to employment opportunities. In addition, UNFPA’s research shows the need for introducing mechanisms to address the need for the inclusion of the elderly population in social and political life.

- The interventions under Output 3.3 have demonstrated substantial effectiveness in both economic reintegration and social inclusion:

- Reintegration programs for returned migrants have yielded positive outcomes, with a significant number receiving cash assistance to support their reintegration. The IOM Reintegration Outcomes Study reveals that 35% of both men and women respondents received cash assistance, though gender disparities were observed in other forms of support. Men were more likely to benefit from subsidized wages and job placement referrals (41%), while micro-grants for small businesses were more commonly awarded to women (35%)​.

- Labour inspection: In 2023, the Labour Inspection Office conducted a total of 5,847 activities (first and follow up inspections, monitoring) on 3,334 facilities across various sectors. This represents a 229% increase compared to the baseline, surpassing the initial target of 50%. The manufacturing sector had the highest number of inspected facilities, with 630, followed by the construction sector, which had 829 facilities inspected. UN agencies, particularly ILO, have been instrumental in providing technical support, including training labour inspectors and enhancing the capacity of the Labour Inspection Office. These efforts have focused on improving safety monitoring systems and ensuring compliance with the Labour Code and international labour standards​.

- Social protection for children with disabilities: The "See Every Colour" campaign, led by UNICEF, successfully reduced stigma and increased the visibility of children with disabilities, reaching over 1.4 million people and reducing stigma rates from 41.5% in 2015 to 28.3% in 2017. This outcome directly supports Output 3.3’s indicators of social inclusion and access to services for vulnerable groups.

- Farmers benefiting from skill development trainings: As of 2024, a total of 9,153 farmers (including 4,257 women) benefited from skill development trainings and extension services, surpassing the UNSDCF targets. These trainings, delivered through initiatives led by FAO and UN Women, focused on improving agricultural practices, including CSA, food safety, sustainable irrigation, and business management.

- Key programs such as the Farmers Field Schools (FFS) provided hands-on trainings to farmers, while UN Women empowered 853 rural women, enhancing their capacities in agricultural productivity and entrepreneurship. These efforts were part of broader UN strategies to foster resilience and sustainability in the agricultural sector​.

- Programs under Output 3.3 have been implemented efficiently with strong coordination between UN agencies and national government bodies. Resources were reallocated effectively during the pandemic, with programs like the Private Sector Joint Program adapting quickly to digital tools to continue service delivery. However, delays due to inter-agency coordination and reporting issues were noted, but they were mitigated through improved coordination as the program progressed.

- In addition, cost-effective communication strategies like UNICEF’s "See Every Colour" campaign proved efficient, reaching hundreds of thousands of people at a low cost while promoting social inclusion of vulnerable groups, such as children with disabilities.

Outcome 3 Sustainability

- Key initiatives under Output 3.2 such as the Agricultural Extension Strategy (supported by FAO) and the establishment of local farmer cooperatives under ENPARD III (supported by FAO) provided a solid foundation for long-term agricultural development. These efforts ensured that farmers had ongoing access to technical assistance and collective market resources, which enhanced their economic resilience.

- In addition, the ownership demonstrated by government institutions ensures that after the completion of the projects, they take over financial responsibility and continue implementing successful initiatives. Examples include RDA's continuation of the UNDP initiative on agriculture in mountainous areas and UN Women's initiative on funding female entrepreneurs in non-farm activities. GITA continues to support female entrepreneurs through UN Women’s initiatives, while Enterprise Georgia has established Growth Hubs following a UNDP-commissioned feasibility study. Both state institutions and the private sector have underscored the importance of capacity building provided by UN agencies. This includes sensitizing staff on gender issues (RDA, Tegeta Motors, Georgian Football Federation) and developing policies, operational procedures, and training on management and monitoring and evaluation (RDA, GITA)​. This combination of capacity building and institutional ownership contributes significantly to the sustainability of the outcomes, ensuring that the impact of the interventions endures beyond the project’s lifespan.

- However, interviews with stakeholders revealed a recurring issue of one-off interventions by UN agencies such as FAO and UN Women. For example, FAO has supported the adoption of no-till practices under the CRA initiative, primarily targeting large-scale farmers managing more than 10 hectares of land across various pilot areas. According to the ENPARD 3 report, these efforts resulted in over 200 hectares being cultivated using no-till methods, showcasing the practice's potential to enhance soil health and productivity. However, during field visits the evaluation team noticed that broader adoption remains limited due to the lack of follow-up support and engagement with smaller-scale farmers. Similarly, UN Women distributed grants to women farmers through the RDA but did not provide continuous technical support afterward, which poses risks to sustainability. This approach could limit the long-term impact of these two interventions, reducing the likelihood that beneficiaries could fully capitalize on the initial support provided​.

- The sustainability of the interventions is underpinned by the growing ownership of initiatives by Georgian government institutions. Initiatives like the Disability Advisory Council, supported by UNICEF and UN Women, have played a key role in advocating for disability rights and ensuring that these issues remain a priority on the national agenda.

Outcome 3 Impact

- The interventions had a measurable impact on the livelihoods of rural populations, contributing to poverty reduction and improved food security. On average, the beneficiary farmers of the ENPARD III program implemented by FAO have increased productivity by 35.8%, production by 74.7%, and income by 106.2%. The program also contributed to creating 375 permanent (140 female, 235 male) and 1,181 part-time jobs (100 percent male) . In addition, 17% of farmers financially supported by the program introduced climate-smart agriculture practices in their farms.“Improving Rural Development in Georgia” Project under ENPARD III implemented by UNDP, contributed to creating/sustaining 609 jobs.

- Through UN Women’s support, participants of Women’s Economic Empowerment in the South Caucasus project have reported self-confidence and self-esteem through their ability to network and contribute to household income.

- As noted in the ILO Contribution Report, significant efforts were made to institutionalize labour market reforms, particularly in labour inspections, which have become a permanent feature of Georgia's regulatory system.

- Lastly, ILO and UNICEF provided substantial technical support to develop sustainable social protection systems, including unemployment insurance.

- The impact of Output 3.3 has been profound, particularly in enhancing the resilience of vulnerable groups, including returned migrants, women, and children with disabilities. Joint program “Transforming Social Protection for Persons with Disabilities in Georgia”, implemented by six UN agencies in Georgia – UNICEF, UNDP, UN Women, WHO, UNFPA, OHCHR – contributed to improvement of work conditions of PwDs.

Output 3 Challenges and lessons learned

- A key lesson learned from the implementation was the importance of program flexibility in the face of external shocks. The disruptions caused by the COVID-19 pandemic illustrated the need for adaptable timelines and the ability to redirect resources to respond to emerging challenges. Programs that could be adjusted to meet the urgent needs of farmers, such as providing emergency relief or adjusting to supply chain delays, were more successful in mitigating the pandemic’s adverse effects on rural communities​.

- The sustainability of the interventions was most evident where government institutions and local stakeholders took ownership of the projects. Capacity building, particularly through programs like the Agricultural Extension Strategy supported by FAO, proved critical in ensuring long-term success. However, in cases where the focus was on one-off grants or interventions, the long-term impact was diminished. Continuous institutional support and engagement are necessary to build local capacity and ensure sustained improvements.

### Outcome area 4

| UNSDCF OUTPUTS | ALIGNMENT | KEY QUESTIONS | SUMMARY OF ANALYSIS |
| --- | --- | --- | --- |
| Output 4.1: Conflict affected communities have improved access to essential services, including education, healthcare, GBV response and legal assistance Output 4.2 Socio-economic conditions, community resilience and self-reliance improved with programmes benefiting conflict affected communities particularly those left behind Output 4.3 Space widened for dialogue and participation that strengthens civil society, community resilience, social cohesion and implementation of the Women, Peace and Security agenda | Output 4.1 is aligned with SDG Output Indicators 4.1.1, 4.1.2, and 4.1.3 Output 4.2 is aligned with SDG Output Indicators 4.2.1, 4.2.2, and 4.2.3 Output 4.3 is aligned with SDG Output Indicators 4.3.1, 4.3.2, and 4.3.3 | Question 1 How were emerging issues identified and prioritized during the implementation of the UNSDCF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How were data gaps addressed in conflict-affected areas? Question 5 What challenges were faced in measuring social cohesion, and access to public services? | The linkage between Outcome 4 and its three outputs is robust. There is a focus on addressing the needs and protecting the right of citizens in conflict-affected regions. By emphasizing the imperative of improving socio-economic conditions, and by highlighting delivery of and access to public services in conflict-affected communities, the ToC provides a strong framework for action. Given the challenges of delivery of services while ensuring that principles of LNOB, and needs of women and vulnerable groups are addressed, there would be a need for effective, results-oriented multistakeholder, cross-sector partnerships. This aspect is not as strongly highlighted in the assumptions as it could have been. As of today, 123 branches of Public Service Hall (PSH) operate across Georgia, applying the “leaving no-one behind” principle and ensuring that citizens and visitors throughout the country have access to prompt, efficient, and accessible services in a comfortable environment. These branches include locations near the ABL, specifically in Berdzenauli, Tkviavi, Mejvriskevi, Rukhi, and Orsantia. In addition to the branches, PSH also deploys Mobile Public Service Halls— specially equipped vehicles that deliver the same services to various communities, particularly those in villages near the ABL. During 2023-2024, Mobile PSHs provided services to residents of the following administrative units: Lia, Kvemo Chala, Tsagvli, Dvani, Takhtisdziri, Tserovani, Shindisi, Perevi, Mereti, Ganmukhuri, and Pakhulani. Currently, the locations of the Mobile Public Service Hall are Ganmukhuri, Pakhulani, Perevi, Mereti |

| OUTPUT 4: INDICATOR-WISE PROGRESS |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | BASELINE |  | 2021 PROGRESS |  | 2022 PROGRESS |  | 2023 PROGRESS |  |
| 4.1.1: Number of cases of legal and psychological assistance / services received by conflict-affected persons (including GBV survivors), by sex | · UNDP: 1,397 persons (85% female). · UN Women: 417 GBV survivors (99% female). · ∙ UNHCR: 1,300 persons (60% female). |  | · UNDP: 771 persons (81% female). · UN Women: 900 consultations (99.7% female), 275 individuals received services, 403 individuals reached via awareness campaigns. · ∙ UNHCR: 1,036 persons (68.5% female). |  | · UNDP: 771 persons (81% female). · UN Women: 735 consultations. · UNHCR: 1,002 persons (68% female). |  | · UNDP: 110 legal consultations (88 female), 282 psychological consultations (127 female). · UN Women: 904 consultations (536 women), 347 calls received. · UNHCR: 1,138 persons (63% female). |  |
| 4.1.2: Number of conflict-affected youth and teachers (schools, VET colleges and university) with improved access to quality education services | · UNDP: 20,174 student beneficiaries (40% female). · UNDP: 350 teachers trained. · UNICEF: 5,326 student beneficiaries. |  | · UNDP: 1,204 students (56% female). · UNDP: 378 teachers trained. · UNICEF: 10,858 students (59% female). |  | · UNDP: 433 students (52% female). · ∙ UNICEF: 59 teachers, 230 youth reached. |  | · UNDP: 1,388 students (920 female), 40 teachers (32 female). · UNICEF: 63 teachers, 312 youth. |  |
| 4.1.3: Number of conflict-affected population with improved access to essential healthcare services, including Sexual and reproductive health services | · UNDP: 10,886 persons (60% female). · UNFPA: 18,000 persons (100% female, cumulative 2015-2020). |  | · UNDP: 16,375 persons (51% female). · UNFPA: 22,380 persons (100% female). |  | · UNDP: 55,439 persons (57% female). · UNFPA: 25,755 persons (100% female). · UNICEF: 10,500 children and adolescents. |  | · UNDP: 1,300 persons (764 female). · UNFPA: 28,820 persons (100% female). · UNICEF: 506 children. |  |
| 4.2.1 Number of initiatives successfully implemented to improve socio-economic conditions and human security in conflict-affected areas | UNDP - 80 UN Women & FAO - 0 |  | UNDP: 133 FAO: 18 FAO & UN Women: 38 (source: 2023 RG4 report) |  | UNDP: 68 FAO: 35 FAO & UN Women: 37 (source: 2023 RG4 report) |  | UNDP: 61 FAO: 98 FAO & UN Women: 54 (source: 2023 RG4 report) |  |
| 4.2.2 Number of people benefiting directly from improved socio-economic conditions and improved human security | UNDP - 5,362 UN Women & FAO - 0 |  | UNDP: 953 (47% women) UN Women & FAO: 754 which 34% women (source: 2023 RG4 report) |  | UNDP: 1,014 (49% women) FAO: 997 (80% women) UN Women & FAO: 771 women (source: 2023 RG4 report) |  | UNDP: 10,460 (52.4% women) FAO: 1,154 UN Women & FAO: 1,855 women (source: 2023 RG4 report) |  |
| 4.2.3 Number of people with improved community resilience against climate-induced multi-hazard natural disasters | Baseline not available | 148 (39% female) |  | 456 people (54% female) |  | 8,308 (50% female) |  |
| 4.3.1 Existence of costed National Action Plan on Women, Peace and Security and its implementation rate Lead Reporter: UN Women | Yes (Current EVAW & DV NAP covers 2018-2020) - implementation rate to be determined in 2021. |  |  | UN Women: 2022-2024 NAP adopted by the Government of Georgia on October 26, 2022. |  | 2022-2024 NAP implementation report to be produced in 2024 |  |
| 4.3.2 Number of initiatives to support direct people-to-people contacts, liaison activities (deliveries of medication and/or other essential goods) and to enhance enabling environment for dialogue and trust within and across the divided communities; Custodian/ Reporter: UNDP Contributors: UN Women, UNFPA | UNDP - 121 (COBERM III, Dialogue II) UN Women - 5 UNFPA - 4 UNDP: 121 (2020) UN Women: 5 UNFPA: 4 WHO: 24 (2020) | UNDP: 50 UN Women: None; interventions are planned for 2022 UNFPA: 1 WHO: 16 |  | UNFPA: 2 UNDP: 88 cumulative (50+38) UN Women:1 |  | UNFPA: 2 (joint study tour to Istanbul and exchange visit to Tbilisi) UNDP: 24 UN Women: 1 WHO: 12 Cumulative 2021-2023 UNDP: 112 (50.6% of target) UN WOMEN: 2 (20%) UNFPA: 3 (50%) WHO: 28 (28 %) |  |
| 4.3.3 Number of people who benefit from peacebuilding initiatives that ensure enhanced confidence within and between the conflict divided communities. Custodian/Lead Reporter: UNDP Contributors: UN Women, UNFPA | UNDP: 26,430 of which 49% female (2020) UN Women: 100 (2020; 100% female) UNFPA: 220 (2020; 70% female) | UNDP: 20,703 of which 57% female UN Women: 128 participants (89% female) in GID/IPRM information sessions, and 52 (100% female) in annual Open Day on WPS. UNFPA: None in 2021; the COVID-19 situation prevented face-to- face workshops. |  | UNFPA: 17 (70% females) participants of joint workshop in Istanbul. UNDP: 8,932 (62% females) UN Women: 88 participants (89% female) in GID/IPRM information sessions; and 68 representatives of the CSOs working on women’ issues, IDP and conflict affected women and youth at grassroots attended the hybrid meeting (out of which 42 represented grassroots community and 16 were from the women’s CSOs) (100% female). |  | UNFPA: 22 (90% female) women health professionals, participants of: Istanbul study tour, exchange visit in Tbilisi, and joint capacity building initiatives UNDP: 984 (661 female; 67%) UN Women: 91 participants (95% female) in GID/IPRM information sessions, and 60 - grassroots IDP and conflict affected women and CSO representatives (100% women) participated in annual Open Day on WPS. |  |

Outcome 4 Relevance

- Output 4.2 addresses socio-economic vulnerabilities and human security challenges in Georgia's conflict-affected regions along the Administrative Boundary Lines (ABLs) of Abkhazia, Georgia and Tskhinvali region/South Ossetia,  Georgia, as well as inside Abkhazia. UN work focuses on improving livelihoods, enhancing community resilience, and strengthening access to essential services for marginalized populations. This aligns with the primary goal of ensuring sustainable peace as well as with Georgia's strategic priorities for regional development and international commitments, particularly SDG 1 (No Poverty), SDG 8 (Decent Work and Economic Growth), and SDG 16 (Peace, Justice, and Strong Institutions). The USAID Partnering for Resilience Program has significantly contributed to these efforts, emphasizing confidence building in the health care and education professions as well as healthcare, maternal health, and emergency care services for vulnerable populations. Work done by UNICEF in the WASH sector, with approximately 60 schools renovated with WASH facilities, and on child protection, with more than 2,000 vulnerable children reached with social work services, demonstrate the UN’s implementation of the LNOB principle.

- The activities under Output 4.2 are highly relevant to the socio-economic and human security needs of conflict-affected regions, particularly in relation to access to essential services for the benefit of vulnerable populations. Programs implemented by UNDP, FAO, UNICEF, and UN Women, along with the Partnering for Resilience Program, focus on building resilient livelihoods, improving healthcare access, and fostering cooperation between the divided communities.

- For instance, the healthcare referral mechanism in Abkhazia, Georgia, supported by UNFPA, through cross-boundary collaboration between health professionals from Abkhazia and Government of Georgia controlled territory, helps addresses critical maternal health needs. This is particularly relevant in light of the challenges in healthcare access and referral systems in conflict-affected regions, where services such as maternal and child healthcare are vital for vulnerable populations. The ongoing vocational education programs under FAO and UNDP are similarly relevant, addressing local labour market gaps by providing targeted training and improving employability.

- Output 4.3 focuses both on policy level work in Government of Georgia controlled territory, in terms of Women, Peace and Security Agenda and supports hands-on community initiatives in a highly demanding operational environment.

- The interventions under this output are highly relevant given the commitment of Georgia under UN Security Council Resolution (UNSCR) 1325. UN Women assisted in preparation of National Action Plan of Georgia on UNSCR 1325 through a wide and participatory drafting process, which included consultations and active engagement of the government agencies, relevant municipalities, women’s CSOs, and around 70 members from the community of internally displaced and conflict-affected women and youth.

- The work of UN agencies in Abkhazia, Georgia also remains relevant for the purposes of confidence-building, peaceful conflict resolution with strong elements of humanitarian support, and for the wider goals of human security in the region and is highly valued both by the international partners and by the Government of Georgia (based on interviews).

Outcome 4 Efficiency and Effectiveness

- Substantial progress has been made under Output 4.2. Key indicators demonstrate significant achievements, particularly in terms of livelihoods, healthcare, and community resilience:

- Indicator 4.2.1: By the end of 2023, 542 initiatives had been implemented by UNDP, FAO and UN Women, exceeding initial targets. These initiatives covered agricultural support and empowerment of civil society. The Partnering for Resilience Program played a crucial role by strengthening cross-ABL cooperation between the divided communities through healthcare referral mechanisms.

- Indicator 4.2.2: The number of direct beneficiaries rose to 12,427, surpassing the baseline of 5,362. This progress was largely due to joint initiatives between FAO and UN Women that supported female farmers through Farmer Field Schools (FFSs), helping women in developing entrepreneurial skills. Specifically, 481 women in Abkhazia and 403 in Samegrelo-Zemo Svaneti acquired entrepreneurial skills development and community-level leadership through farmer field schools. The COBERM IV project, which supports the strategic goals of Government of Georgia’s reconciliation and engagement policy, has contributed to this progress by enhancing the capacity of local CSOs, with over 57% of beneficiaries being women. COBERM’s focus on grassroots, women-led CSOs fostered economic resilience, particularly through grants that supported community-based initiatives.

- Indicator 4.2.3: Efforts to enhance community resilience to climate-induced disasters benefitted 8,308 individuals (50% women). This success was driven by the expansion of the multi-hazard community-based early warning system in Abkhazia, Georgia, which involved installing additional meteorological stations and water level gauges in the Kodori River and completing multi-hazard risk mapping for the Kodori and Basla river basins. The project also implemented five small-scale environmental protection and flood prevention initiatives, reaching over 8,100 people. Moreover, two community-based early warning systems were established in the Sukhumi and Ochamchire districts, where 208 community members were trained in disaster response and evacuation planning. These efforts have significantly improved the disaster preparedness of local communities in conflict-affected regions.

- Output 4.2 initiatives demonstrated great efficiency. The Partnering for Resilience Program effectively utilized digital tools and remote training platforms during the COVID-19 pandemic, allowing for continued service delivery and capacity-building activities. Significant financial resources, such as the 19 million GEL invested under ENPARD III, supported agricultural resilience and livelihood projects, particularly targeting female entrepreneurs. These efforts helped maintain project momentum and minimize delays across other regions, ensuring that the broader objectives of Output 4.2 were achieved despite external challenges.

- A Deputy Project Manager of the USAID-funded UNDP project was declared as a persona non grata in 2022 by the authorities in control in Abkhazia; this fact, along with heightened surveillance of project staff by de-facto local authorities, created delays. The atmosphere of intimidation affected both project participants and interlocutors, requiring careful navigation of relationships with authorities in control in Abkhazia. Despite these difficulties, the project adapted by reallocating responsibilities to local actors.

Outcome 4 Sustainability

- Sustainability of the output is ensured through training of local practitioners. For example, the Partnering for Resilience Program has established four key protocols for maternal and child healthcare that continue to be implemented by local healthcare practitioners. This ensures sustained access to essential healthcare services, especially in regions with limited medical infrastructure. In addition, vocational training programs aimed at women farmers and entrepreneurs have laid a foundation for livelihood opportunities. By equipping participants with valuable skills, these programs are empowering communities to manage their own livelihoods more effectively, fostering long-term stability​. In Abkhazia, Georgia, where operational challenges persist, sustainability remains more precarious. However, the introduction of community-based early warning systems and the strong involvement of local community actors in disaster risk reduction efforts have improved the resilience of these communities. The work of the UN Agencies under this output is carried out through a variety of initiatives funded by donors such as USAID, UK, EU implemented in Abkhazia (there is no presence in Tskhinvali region/South Ossetia). They work with and through CSOs in various fields including culture, community development, youth, livelihoods, gender equality, education, child protection, and people with disabilities. Some of the partners noted the agencies working in parallel, rather than in full coordination, at the same time the UN agencies were praised for showing very high awareness of the sensitivities of implementing this portfolio in a very challenging environment. The UN does not  build capacity of the authorities in control in Abkhazia– which is usually the path to sustainability. For this reason, the UN has been concentrating on its work with the civil society and community groups – this was done through trainings, peer-to-peer exchanges, CSO Fair and networking. Exchanges across ABL were also organized for doctors and other professionals.  Based on the NAP on Implementation of the UN Security Council Resolution 1235 on Women, Peace and Security, UN Women worked to provide training on gender mainstreaming for security and defense sectors of Georgia. Two security sector institutions adopted internal gender related policies and mechanisms, such as gender equality concept and its action plan and sexual harassment prevention and response mechanisms.

Outcome 4 Impact

- The interventions under Output 4.2 have had a far-reaching impact, significantly improving the socio-economic resilience of conflict-affected communities in Georgia, particularly along the ABL with Abkhazia, Georgia, and Tskhinvali region/South Ossetia, ,Georgia. The Partnering for Resilience Program has played a critical role in improving access to maternal and child healthcare services. The establishment of healthcare referral mechanisms and telemedicine tools has enabled faster emergency responses, particularly for vulnerable populations, leading to improved maternal health outcomes and reduced complications during pregnancies and childbirth​.

- In the agricultural sector, the support provided through FAO and UNDP’s climate-smart agricultural initiatives has resulted in enhanced food security and livelihoods for over 12,000 individuals. Female entrepreneurs and farmers, in particular, have benefitted from vocational training, which has strengthened their ability to generate income and improve their community's resilience to economic shocks​.

- Furthermore, the introduction of community-based early warning systems has drastically improved disaster preparedness in vulnerable regions, benefiting over 8,300 people by providing them with the tools and knowledge needed to respond to climate-induced hazards. This, combined with environmental protection and flood prevention measures, has improved the security and resilience of conflict-affected communities, ensuring long-term sustainability and reducing vulnerabilities to future crises​.

Outcome 4 Challenges and lessons learned

- While Output 4.2 faced significant challenges, particularly in conflict-affected regions, it also provided crucial opportunities for strengthening community resilience and fostering confidence-building. In areas such as Zemo Nikozi, close to the ABL with Tskhinvali region/South Ossetia, Georgia, UN support played a vital role in enhancing the local healthcare system. The rehabilitation and equipping of medical facilities, supported by programs like COBERM, provided essential healthcare services, including maternal health, COVID-19 immunizations, and cancer screenings. This not only improved access to critical health services but also helped reduce outmigration, as people were able to receive medical care locally without the need to travel long distances​.

- Moreover, the introduction of telemedicine and capacity-building initiatives for local healthcare professionals contributed to the overall strengthening of healthcare delivery. Collaboration between Georgian doctors residing in Government of Georgia controlled territory and Tskhinvali region/South Ossetia, Georgia further enhanced confidence-building, showing that healthcare can be a bridge for peacebuilding and reconciliation.

- In 2022-2023, the operational environment in Abkhazia was challenging due to the authorities in controldclaring USAID’s regional director, John Pennel, as persona non grata, and hurdles created for  projects whose purpose was to facilitate contacts between divided communities.. Overall, increasing pressure towards the international community hindered delivery of goods and supplies and restricted ABL crossing by international experts.

- Some partners from the Government of Georgia mentioned the challenges related to ‘politization’ of the confidence building and humanitarian work of the UN agencies operating in Abkhazia, Georgia, and the danger of ‘instrumentalization’ of UN projects for the benefit of the de-facto authorities.

### Outcome area 5

| UNSDCF OUTPUTS | ALIGNMENT | KEY QUESTIONS | SUMMARY OF ANALYSIS |
| --- | --- | --- | --- |
| Output 5.1 Strengthened governance frameworks for environmental sustainability and climate resilience. Output 5.2 Promotion of climate-smart agricultural practices and sustainable land management. Output 5.3 Ensured equitable access to natural resources and climate adaptation measures for all communities. |  | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How are governance frameworks being strengthened to support both environmental sustainability and climate resilience at the national and local levels? Question 5: What specific policies have been most effective in integrating climate considerations into governance structures? Question 6 Which climate-smart agricultural practices have been most effective in mitigating the impacts of climate change on agriculture? Question 7 How are sustainable land management practices being promoted and adopted across different regions of Georgia? Question 4 How is equitable access to natural resources being ensured for vulnerable communities in the context of climate adaptation? Question 5 What measures are in place to monitor and assess the effectiveness of climate adaptation strategies in reaching all segments of society? | Output 5.2 is directly connected to Outcome 5 through its focus on promoting climate-smart agricultural practices and sustainable land management. These practices are crucial for mitigating the impacts of climate change on agriculture, a key sector in Georgia’s economy. By encouraging the adoption of sustainable practices, this output helps to protect natural resources, enhance food security, and increase the resilience of rural communities. This output’s focus on sustainable land management also ensures that land resources are used efficiently, preserving them for future generations while supporting current economic activities. Both the UNSDCF and NDS emphasize the importance of governance frameworks to achieve environmental sustainability and climate resilience. The NDS supports the development of policies and regulations that strengthen environmental governance, ensuring that they are implemented effectively at all levels. Output 5.2 is directly connected to Outcome 5 through its focus on promoting climate-smart agricultural practices and sustainable land management. These practices are crucial for mitigating the impacts of climate change on agriculture, a key sector in Georgia’s economy. By encouraging the adoption of sustainable practices, this output helps to protect natural resources, enhance food security, and increase the resilience of rural communities. This output’s focus on sustainable land management also ensures that land resources are used efficiently, preserving them for future generations while supporting current economic activities. The UNSDCF strongly emphasizes equitable access to natural resources and climate adaptation measures, ensuring that all communities, particularly vulnerable ones, are protected. The NDS supports these objectives but does not reflect on the inclusivity in resource management. |

| OUTPUT 5: INDICATOR-WISE PROGRESS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | BASELINE | 2021 PROGRESS | 2022 PROGRESS |  | 2023 PROGRESS |  |
| 5.1.1: Proportion of important sites for terrestrial, freshwater and black sea biodiversity that are covered by protected areas, by ecosystem type | 0 ha of Protected Areas. | 313,112 ha of protected areas with improved management. | 313,112 ha of protected areas with improved management; annual funding increased beyond target. |  | Replaced by 5.1.1a. Area of terrestrial and marine protected areas created of under improved management practices (hectares), supported by the UN “Progress in 2023: 313,112 ha protected areas under improved management. The reported figures include a) total areas of 9 Protected Areas supported by the UN. The target is expected to be achieved by mid-2024.” |  |
| 5.1.2: Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategy | 0 local governments with DRR strategies. | · Methodology for risk-informed, gender-sensitive municipal preparedness developed. · ToT for Emergency Management Service (EMS) conducted. · ∙ Training initiated in 3 municipalities, with 54% women participants. | Disaster risk management plans developed for 6 municipalities: Akhmeta, Lagodekhi, Telavi, Sighnaghi, Gori, Kobuleti. |  | 4 additional disaster risk management plans finalized in Abasha, Senaki, Samtredia, Khobi. |  |
| 5.1.3: Number of initiatives aimed at capacity-building efforts for government and other stakeholders in mainstreaming gender in formulating, monitoring and implementing national climate change policies and plans | None. | · Development of gender-sensitive municipal plans initiated. · Methodology developed and ToT conducted for EMS staff. | · Gender-sensitive socio-economic vulnerability assessment methodology applied for 30 vulnerable communities in 3 river basins. · Gender-sensitive capacity development plans developed. |  | · Socioeconomic vulnerability assessment applied for 60 vulnerable communities in 4 river basins. · 90 communities across 7 river basins identified. |  |
| 5.2.1: Adaptation and mitigation capacities are increased through enhanced use of climate information, products and services and well-established multi-hazard early warning systems, including on community level. | a/ Hydrometric monitoring network outdated and inadequate b/ 0 multi-hazard and risk maps c/ MHEWS and Forecasting for climate -induced hazards does not exist d/ 0 risk reduction measures, based on multi-hazard risk maps, in high-risk areas e/ 0 Community-based climate risk management/EWS | a/ Hydro-metric network upgrade for 6 river basins – total 89 units procured; agro-met network (15 stations) upgrade initiated b/ National maps covering all 11 river basins were developed for 3 hazards (windstorm, hailstorm, avalanche). Hazard map for Flood hazard was developed for 3 river basins c/ Redeployment and enhancement of Rioni river flood forecasting platform d/ Design for 5 risk reduction measures developed. Construction works launched e/ Strategy for Community-based climate risk management /EWS elaborated (source: 2023 RG5 report) | a/ All hydrometeorological and agrometeorological equipment except 2 upper air sounding stations is purchased. The equipment was installed at 22 locations. b/ National maps covering all 11 river basins were developed for windstorm, hailstorm, drought and avalanche. c/ Flood maps developed for 7 river basins and Landslide, mudflow maps developed for 6 river basins. D/ Risk reduction measures implemented at 5 project locations, ongoing at 8 locations and planned at 2 locations e/ 15 out of 100 communities were identified (source: 2023 RG5 report) |  | a/ The equipment was installed at 79 weather stations out of 154. Landslide and groundwater monitoring systems for 11 locations were procured and installed. Trimble 4D Geotechnical Add-on software for integration of these monitoring stations was procured and operationalized. b) Multi-hazard and risk maps were produced for 7 river basins in western Georgia. c/ Flood forecasting platform was developed and piloted in 5 river basins. Forecasting concepts developed for wind, hailstorm and drought. d/ Risk reduction/flood protection measures was finalized at 9 locations, protecting 31,076 people in the regions. e) Risk assessment identified 45 communities that are at high-risk (multi-hazard) out of 100 communities; River basin-level risk management plans were developed in 4 basins in W. Georgia, and community-based Climate Risk Management plan were developed in 15 high-risk communities in 3 River basins in W. Georgia and works commenced. (source: 2023 RG5 report) |  |
| 5.2.2: Proportion of land that is degraded over total land area | Baseline: 6.1% area - 4071 square km in 2020 | a) Implementation of the land restoration activity was postponed due to COVID-19. b) More than 200 hectares (2 sq. km) of land in Shida Kartli region were cultivated using no-till planting. c) The direct number of beneficiary farmers is 69 farmers where around 15% are women. In total, 240 farmers and their families (as co-beneficiaries) benefit from the improved quality of the land. | N/A |  | a) Area of land restored – 537 hectares of pastures are restored (5.37 square kilometers) b) Area of landscapes under improved practices – Sustainable pasture management plans are elaborated for 87,610 hectares (876.1 square kilometers) c) Number of beneficiaries disaggregated by gender as co-benefit of restored land: 382 Persons (157 women, 225 men) |  |
| 5.2.3: Number of hectares of forest and protected areas under sustainable and climate-resilient management benefitting targeted rural population | Baseline (2017): 0 | 390,602 ha |  | 83,275 ha |  | 11,628 ha |
| 5.2.4: Adoption of updated regulations for WASH in schools and health facilities, including monitoring frameworks, which is reported annually | Baseline: No | Draft technical regulations on WASH in Schools have been integrated into Schools’ Operations and Maintenance Technical Regulations. |  | N/A |  | The construction standards for general education institutions, which incorporate standards for water, sanitation and hygiene (WASH) for schools have been finalized and are currently undergoing adoption by the government of Georgia. b) The WASH assessment of healthcare facilities was conducted nationwide in 2021-2022.. Recommendations have been used in the process of accreditation of hospitals for their health service-provision activities. |
| 5.2.5. Mortality rate attributed to household and ambient air pollution[13] |  |  |  |  |  |  |
| 5.2.6. Existence of blood lead surveillance system at the national-level | Baseline: Does not exist | An environmental health laboratory established which will serve as a backbone to the Environmental Health Surveillance System; Joint efforts have led to the adoption of a technical regulation on prohibiting lead in paints in Georgia. |  | The Lead Surveillance System is designed |  | a) The Lead Surveillance System has been launched and piloted in 2 regions of Georgia. Up to 2,000 blood samples have been collected among randomly selected children and environmental and household samples have been collected for investigation in selected households where children have particularly high BLL. b) Continuous country consultations with WHO European Center for Environment and Health conducted in the process of establishing the Lead Surveillance System. c) Awareness-raising campaigns conducted countrywide to mark International Lead Poisoning Prevention Week (ILPPW) in Georgia. |
| 5.3.1: Renewable energy share in the total final energy consumption and number of rural households improving living conditions through increased energy efficiency and/or use of renewable energy | Baseline from NSDG: Renewable energy share in the energy mix is approximately 29.5% | 19.55% |  | 18.6% |  | 17.68% |
| 5.3.2: Gender-responsive technological solutions/initiatives/ projects, as per Long Term Low Emission Development Strategy (LEDS) are in place, improved and/ or applied | No | N/A |  | Lt-LEDS was finalized (source: 2023 RG5 indicators) |  | Lt-LEDs was adopted by the government of Geogia. Roadmap preparation started for implementation. Two local municipalities developed Sustainable energy and climate plans that include project ideas. (source: 2023 RG5 indicators) |

Outcome 5 Relevance

- The relevance of Output 5.2 is underscored by Georgia’s vulnerability to climate-induced hazards and its commitment to meeting national and international climate goals. This output directly contributes to Georgia’s Nationally Determined Contributions (NDCs) and the 2030 Climate Change Strategy, which prioritize adaptation to climate risks and disaster preparedness in sectors like agriculture, water resources, and public health. The integration of climate risk management systems, multi-hazard early warning systems (MHEWS), and sustainable land management practices reflects the alignment with both national priorities and international agreements such as the Paris Agreement and the Sendai Framework for Disaster Risk Reduction.

- These efforts are particularly critical for rural and vulnerable populations that rely on climate-sensitive sectors like agriculture. The enhancement of early warning systems and the restoration of degraded land not only support national climate resilience goals but also contribute to the SDGs, particularly SDG 13 (Climate Action) and SDG 15 (Life on Land). Additionally, the focus on gender-sensitive risk management aligns with the broader global agenda of inclusive and equitable development.

- Other sub-outputs such as Output 5.3 aligns with Georgia’s commitment to transitioning towards a low-emission economy, as outlined in its National Energy and Climate Plan (NECP) and Long-term Low Emission Development Strategy (LEDS). The focus on increasing renewable energy, enhancing energy efficiency, and fostering clean energy production is critical for achieving Georgia’s Nationally Determined Contributions (NDCs), particularly in reducing greenhouse gas emissions across sectors such as energy, transport, and agriculture. This output contributes to SDG 7 (Affordable and Clean Energy) and SDG 13 (Climate Action), while also promoting gender-responsive climate technologies

- Projects like the Capacity Needs Assessment for the agrifood sector and the pasture management initiatives implemented by FAO address critical gaps in climate resilience, agriculture management, and pollution control. Simultaneously, efforts to reduce lead poisoning in children and enhance the health of ecosystems through biodiversity conservation and pollution control have also made significant strides in Georgia's environmental strategy.

Outcome 5 Efficiency and Effectiveness

- The effectiveness of the interventions under Output 5.2 is evident in the significant progress made in establishing climate risk management infrastructure. By 2023, 79 weather stations were installed, and flood forecasting systems became operational in five river basins, protecting over 31,000 people. The development of multi-hazard maps for 11 river basins further strengthens the early warning system, enabling Georgia to respond effectively to climate-induced disasters like floods. The ICT platform supporting weather stations ensures that hazard data can be transmitted efficiently to farmers, enhancing coordination among them disaster response agencies.

- Efforts to restore degraded land have also shown promising results. By the end of 2023, 5.37 square kilometers of pastures were restored, and sustainable pasture management plans were implemented across 876 square kilometers. This directly supports Georgia’s Land Degradation Neutrality (LDN) targets under the UN Convention to Combat Desertification (UNCCD), contributing to long-term agricultural resilience and environmental sustainability.

- In addition, the National Pasturelands Management Policy Document (NPMPD), developed in partnership with FAO, laid the groundwork improvement of pasture management, aligning with Georgia’s 2030 Land Management Strategy. The establishment of pasture management plans demonstrates how local involvement has increased resilience, with these plans tailored to the needs of high-risk areas.

- The efficiency of the interventions is boosted by strong collaboration between Georgia’s government, international partners, and local communities. The Green Climate Fund (GCF) and FAO provided critical financial and technical support for scaling up climate adaptation activities, particularly in the agrifood sector. The procurement and deployment of Multi-Hazard Early Warning System (MHEWS) by UNDP were carried out efficiently, covering a broad geographic area and maximizing impact.

- The transition to community-based early warning systems has also been cost-effective, leveraging local knowledge and ensuring that interventions are context-specific and sustainable.

- Significant progress has been made under Output 5.3, particularly with the adoption of the LEDS in April 2023. This strategy defines the pathways for Georgia’s climate neutrality by 2050 and provides a comprehensive roadmap for achieving decarbonization in key sectors such as energy, transport, and agriculture. Two local municipalities have already developed sustainable energy and climate plans that include innovative project ideas aimed at enhancing energy efficiency and promoting the use of renewable energy​.

- Moreover, the share of renewable energy in the total energy mix has increased, with the National Sustainable Development Goals (NSDG) indicating that the renewable energy share stood at 18.6% in 2022, and efforts are underway to reach the 27.4% target by 2030​. Although the progress was slower than expected, ongoing projects in rural areas aim to increase this share in line with the country's overall decarbonization strategy.

- The efficiency of Output 5.3 has been demonstrated through strategic partnerships and effective resource mobilization. The UNDP played a pivotal role in providing technical assistance and facilitating the development of LEDS roadmap, which serves as a blueprint for achieving Georgia’s low-emission goals. Additionally, the collaboration with municipalities in developing sustainable energy plans has ensured that local governments are actively involved in implementing climate-friendly solutions​.

- The financial contributions from international donors have been crucial in accelerating the adoption of clean energy technologies. These initiatives have been directed toward rural and vulnerable communities, where energy poverty is a significant issue, thus ensuring that energy efficiency and renewable energy projects have a broad social impact​.

Outcome 5 Sustainability

- The sustainability of the interventions is ensured through strong government ownership, particularly by the MEPA and the National Environmental Agency (NEA) that allocated 40% of the project as co-funding. The integration of early warning systems and risk management frameworks into national disaster risk reduction policies guarantees their long-term operation and relevance.

- A key element of the sustainability also lies in Georgia’s commitment to taking ownership of the early warning systems. The government has pledged to cover the annual maintenance costs for the monitoring stations and the membership fees for the European Meteorological Network once international funding ceases. This ensures the long-term functionality of these systems​.

- Furthermore, NEA has emphasized the importance of integrating hazard maps into national planning frameworks, ensuring that these documents become mandatory references for land-use planning and disaster risk reduction efforts at both the national and municipal levels​. The fact that municipalities are developing risk management plans based on these hazard maps demonstrates the project’s far-reaching impact and long-term relevance​.

- The sustainability of the interventions under Output 5.3 is closely linked to Georgia’s commitment to achieving climate neutrality by 2050. The adoption of the LEDS provides a strong institutional and policy framework to support the long-term sustainability of the interventions. The Machakhela Protected Landscape initiative, which introduced solar energy technologies, exemplifies how clean energy solutions can be integrated into rural development while reducing environmental degradation

- Additionally, the gender-responsive approach embedded in the LEDS ensures that women and other marginalized groups are included in the benefits of clean energy transition. This contributes to social sustainability by ensuring that the transition to a green economy is inclusive and equitable.

Outcome 5 Challenges

- While significant progress has been made, several challenges have been encountered, particularly in the procurement process. NEA noted that delays were caused by hiring companies with limited experience in setting up the ICT systems supporting early warning mechanisms. Additionally, pandemic-related disruptions impacted the speed of implementation, although the project has since moved into its final stages​.

- To address these challenges, the project has been granted a no-cost extension to ensure the full completion of the ICT components and the installation of the remaining monitoring stations. The state’s commitment to covering maintenance costs and ensuring the sustainability of the project is an encouraging step toward overcoming these hurdles.

Outcome 5 Impact

- The lead poisoning reduction program has been instrumental in reducing exposure to lead, a neurotoxin that affects nearly one-third of children globally. In Georgia, following the discovery that 41% of children had elevated blood lead levels in 2018, concerted efforts were made to address this issue. Regulatory changes, such as controlling lead content in spices and toys, combined with public health campaigns and the establishment of a Lead Surveillance System in 2023, have drastically reduced children’s exposure to lead​ (e.g. in Adjara and Imereti regions). This program not only improves the health and cognitive development of children but also reduces long-term healthcare costs and enhances the overall productivity of the population.

- The restoration of pasturelands under the LDN project is directly contributing to climate resilience and environmental stability. Restoring 747 hectares of land and applying sustainable land management practices to 20,000 hectares not only improve soil health and biodiversity but also buffer Georgia’s rural ecosystems against climate change impacts, helping prevent desertification​.

## D. Findings from the stakeholder and public perception surveys

63. Analysis of the results of the two surveys carried out—one for institutional stakeholders, and one for soliciting insights from the eventual beneficiaries of the UNSDCF implementation, i.e., the public—are presented below. These surveys were used to complement the data collected through other means and instruments, and the principal purpose was to hear from a broader audience. A total of 153 responses were received, 51 for the institutional stakeholder survey and 102 for the citizens’ perception survey. The analysis below concentrates on the citizens survey as the viewpoint of institutional stakeholders is incorporated through other instruments.

a. Respondent’s Profile

| CATEGORY | AGE | GENDER | LOCATION | EDUCATION | PROFESSION |
| --- | --- | --- | --- | --- | --- |
| STAKEHOLDER | - 53% between 35-60 - 22% between 51-65 | - 67% female - 29% Male - 4% preferred not to disclose | - Tbilisi (23%), - Adjara (13%), - Imereti (12%), - Kakheti 10%), | - 59% Master’s degree - 29% Bachelor’s degree. - 2% PhD - 8% other forms of education | - 55% public servants - 13% private sector - 10% civil society - 8% entrepreneurs |
| CITIZENS | - 7% 19-25 - 34% aged 26-35 - 41% aged 36-50 - 13% aged 51-65 - 5% aged 65+ | - 75% female - 25% Male | - Tbilisi (63%), - Kakheti (7%), - Kvemo Kartli (5%), - Imereti (4%) | - 57% Master’s degree - 29% Bachelor’s degree - PhD (4%) - technical/vocational diplomas (4%). | - 24% private sector - 18% public service. - 15% civil society - 11% teachers |

Results of the Surveys

Institutional Stakeholders

Citizens

Q. Have you heard about the UNSDCF? The awareness of the UNSDCF is high for both set of respondents.

Q. Are the UNSDCF objectives aligned with the national priorities? The overwhelming majority of Institutional stakeholders believe that the UNSDCF is aligned well with national priorities. This was also evident from the FGDs, interviews and this data supports the analysis contained in the synoptic table.

Q. Are you aware of the steps being taken by the national or local governments to implement the UNSDCF or the SDGs? The overwhelming majority of citizens stated that they were either unaware or slightly aware (77%). This points to the lack of adequate engagement, advocacy and possibly transparency.

Q. When thinking about the performance of your local government on the SDGs, which of the following statements do you agree with most? The response to this question reiterates the point about adequate awareness raising, advocacy, and citizen engagement.

Q. Which of the following would you recommend to local governments to improve their performance on the implementation of the SDGs? The theme of improving engagement, transparency, and inclusion is a recurrent one, as may be evident from the responses to this question.

Q. Which SDGs should the local government prioritize? Citizens were asked to identify three top priorities, and the results point towards reducing poverty, economic growth and employment, and investing in education. Although female respondents constituted 75% of the total, a surprising small number chose gender empowerment as a priority.

# Section IV: Conclusions

64. We structure our conclusions into three distinct yet interrelated themes: strategic, structural, and thematic:

Strategic

- The UNSDCF needs to sharpen its strategic focus and sync better with the government’s thrust towards private sector led growth. Because its scope is very broadly determined,  UNSDCF does not lend itself well to resource mobilization activities.

- The value proposition of the UN system is unclear, and the UNSDCF is an embodiment of that weakness.

- In not providing a strategic thrust for private sector engagement, the UNSDCF fails to leverage the economic context, ambition, and opportunities of an upper middle-income country.  In sticking to a template, it loses relevance in a fast-paced development scenario. Engagement with the private sector may allow the UN to (a) launch new streams of work: (b) embed UN principles of human rights, equity and equality, transparency, LNOB etc. into the private sector development agenda; (c) create fresh sources for resource mobilization.

- The role of the RCO is still a work in progress, although viewed within and outside the UN system as being critical for not only better political engagement and thus ownership, but also for leadership on making the UNSDCF a more credible, relevant, and strategic framework. Against a backdrop of shrinking spaces for dialogue, a widening gulf between different segments of society, and deepening inequality, the RC’s role assumes ever greater heft.

Thematic

- The UNSDCF has contributed significantly to improving governance in Georgia. Progress in enhancing the rule of law, human rights, and the representation and participation of women in decision-making has been noteworthy. The strengthened accountability and transparency of institutions have also been crucial outcomes.

- The framework has contributed well to improve citizen’s access to resilient and gender-sensitive services. The integration of international human rights standards into service delivery has been a notable achievement, contributing to more equitable access for all people in Georgia.

- In fostering better economic conditions and creating opportunities for inclusive growth, the UNSDCF has enabled the UN system’s contribution to a more inclusive and resilient economy. However, challenges remain in fully achieving economic sustainability and reducing inequalities.

- The framework has strengthened environmental governance and promoted climate action. Initiatives aimed at sustainable management and use of natural resources have been effective in enhancing resilience to environmental shocks.

- Efforts to enhance human rights and resilience in conflict-affected communities have yielded small, but positive results.

Structural

- The UNSDCF implementation is well-organized thematically, well-aligned with the SDGs, and provides a robust framework for cooperation with the government.

- Processes relating to identification of joint programs, selection of partners, incentives for performance, and assignment of responsibilities including on reporting, are opaque. UNSDCF does not fully cover all activities of the agencies, and there were murmurs of discontent echoed by government counterparts, over the process of finalizing it. Specifically, there was a call from the government counterparts for greater Inclusiveness, transparency, and consistency of engagement that leads to the finalization of the UNSDCF

- Its results framework and design of joint programs do not help in resolving or at least clarifying the challenges of attribution of results.

- The role of eventual beneficiaries in helping design, and oversee implementation, is missing. For example, there is no evidence of crowd-sourced needs assessment while determining thematic areas. Use of random samples for surveys, crowdsourcing of needs using social media, or beneficiary validation of what is proposed to form part of CF, could enrich the prioritization process.

- There is a need to ensure consistency in setting baselines and targets, as they are unavailable for certain outputs (e.g., Output 1.3.2) and present problems in analyzing progress.

# Section V: Recommendations

65. The Evaluation Team proposes a five-point agenda for the remainder period of the current UNSDCF, and for the development and implementation of the future UNSDCF. We focus on recommendations that are strategic, catalytic, and relevant, for the UNCT to consider.

      - Refresh the UN’s Positioning

66. In the wake of the evolving political, economic, and operational environment in Georgia, we recommend that the UNCT and the UN RCO revisit the value-added of the UN system and restructure the UNSDCF as the main instrument for articulation of a new, clearer value-proposition for the UN in Georgia. Refreshing the UN’s positioning will encompass:

          - Developing a new positioning statement We propose the following formulation:

For the government, civil society, and private institutions looking to work on the SDGs, sustainable development, women’s empowerment, equity, inclusion, and promotion of human rights, the UN is the most relevant, knowledgeable, and reliable partner. The UN will serve as a network of networks, creating platforms for sharing of knowledge, expertise and resources; help unlock business opportunities linked to the SDGs and sustainability; and use its in-depth understanding of institutional and policy issues to help transform lives and livelihoods in Georgia.

    - Building reputational capital This can be achieved by:

- Raising knowledge capital Development of a range of knowledge products and services can be an effective way of enhancing institutional reputation. Through collaborations with academia, think tanks, local and global experts, and in close collaboration with relevant government agencies, the UN can raise its stock of knowledge assets. These can take several forms, including policy briefs, podcasts, blogs, and op-eds on thematic issues that are prioritised in the UNSDCF.

- Enhancing reputation by association

Entering into agreements and collaborative arrangements with governments, private sector, experts and international, multilateral organisations, the UN in Georgia can improve its reputational capital through association. Of course, the choice of partners and collaborators needs to follow a due diligence process to ensure only the best institutions are targeted.

  - Aim for Impact

- It may be prudent to assess opportunities for reducing the scope and scale of the UNSDCF. We recognize and acknowledge the challenges in pursuing this recommendation, given that the mandate of the UN agencies covers a vast thematic jurisdiction, but both in terms of becoming more strategic in its work and pragmatism—the latter in the context of a shrinking funding landscape—it may hold the UN in good stead to identify, in consultation with government, private sector, and civil society, areas where the UN can achieve greater impact. While the parameters of this recommended assessment will require a more detailed effort, we propose a few considerations to guide the process:

    - Achieving a more strategic balance between investment and Technical Assistance support A key learning from the evaluation is that the government was deeply appreciative of the quality and flexibility of the Technical Assistance (TA) support offered by the UN agencies. Not only did this TA support help build requisite institutional capacity to drive better results but also allowed government policies and strategies to benefit from the global and regional knowledge and expertise that the UN was able to harness. This is not to diminish the value and contribution of the investment projects under the UNSDCF, which tend to be small yet meaningful, but to suggest that the UN may be able to achieve greater impact through its TA support to shape better policies, stronger oversight, and leveraging its convening power.

    - Align UNSDCF More Closely with Georgia’s Economic Growth Trajectory As a upper-middle income country, with its thrust toward private sector-led growth, Georgia needs a UN that is more in tune with its economic and development agenda and aspirations. We note that the current UNSDCF is well-aligned with government policies, but there may be a case for taking stock of where the UN and the UNSDCF lags the government’s pace and path for economic transformation. A deeper engagement with the private sector is one such obvious area for the UN to work on. Addressing the challenges of women’s economic empowerment, emigration due to lack of quality and well-paying jobs, achieving greater regional equity in economic opportunities for youth, and creating more efficient, tech-enabled services could all be areas worth considering as part of the UN’s journey to carve out a niche for itself.

  - Strengthen Private Sector Engagement

- The need for stronger ties with the private sector and for a greater focus on programming to support private sector development, has been highlighted earlier as well. In a country where the government is leaning towards a private sector-led economic development model, the UN needs to follow suit. Issues related to SME development including through better and more financing; strengthening the service industry especially in tourism; resolving the labour market efficiency and quality conundrum, including through better skills development for youth;  improving women’s participation in the labour force and reducing gender pay gaps; promoting e-commerce and supporting the burgeoning Information Technology (IT) industry; driving better measures for climate adaptation; improving economic governance in state owned enterprises and private sector regulatory environment; and using Public Private Partnerships for better infrastructure and service delivery---clearly, there is a considerable array of areas where the UN can contribute in a more focused and strategic manner. Issues of inclusion, equity, women’s rights, better governance, and LNOB apply well to the potential work with the private sector. Of course, not all of the UN’s mandate for driving a rights-based approach to economic and social development can be achieved through a private sector lens alone, and our recommendation therefore is not to replace the UN’s work on protection and promotion of human rights, but to augment it through a private sector-focused stream.

  - Embrace Innovation

- Innovation lies at the core of all organisational change. In refreshing its positioning, aiming for an impact-focused portfolio under the UNSDCF, and looking to align better with government’s economic development orientation, the UN can look to innovate on three fronts: institutional arrangements; thematic focus; delivery mechanisms; and financing for results.

    - Innovations in institutional arrangements While the UNCT and the UN RCO are working efficiently and effectively, and the institutional architecture supporting the implementation and monitoring of the UNSDCF in the form of the Steering Committee and Results Groups are performing well, we recommend two specific ways in which innovations may help drive even better performance:

- UNSDCF Parliamentary Retreat With a view to enhancing greater political understanding, ownership, engagement, and oversight of the UNSDCF, the establishment of a UNSDCF Parliamentary Retreat is recommended. Short of being a Parliamentary Caucus and differing in intent and structure from existing Parliamentary oversight mechanisms, the Retreat would offer the UN and Parliamentarians to discuss in an informal, yet focused way, the design, delivery, and impact of the UNSDCF, and tapping on the UN’s global network of experts, expose Parliamentarians to examples of successes and failures in UNSDCF from other countries. Ideally, this would be a bipartisan platform, but a government-led Retreat can be a starting point. We further propose this to be a bi-annual forum, whose format, purpose, and content can be finalized by the UN RCO in close consultation with the AoG.

- UNSDCF Observatory It was evident from the online surveys conducted during the evaluation, that citizens and institutional stakeholders across different sectors, were largely unaware of the UNSDCF and how it contributes to economic and sustainable development. With the intent of raising awareness of the UNSDCF, the UN RCO, and the UN system more broadly, we recommend establishing a UNSDCF Observatory under the UN RCO. This would be an online platform with a strong social media presence, allowing the UN, government and their partners, to disseminate information on different initiatives, allow for citizen feedback on implementation, and serve as a mechanism for information sharing by different stakeholders. In doing so, the UN RCO will play an important role in connecting different stakeholders and providing an instrument for beneficiary participation in UNSDCF oversight. A detailed structure, management requirements, financing, and quality assurance system can be developed by the UN RCO in partnership with the government, other development partners, and private institutions such as the Tbilisi DataFest to use technology for driving a more inclusive process for UNSDCF design, delivery, and oversight.

    - Innovations in content We have already underscored the importance of and need for more strategic focus as regards the thematic coverage under the UNSDCF. We recommend particularly to consider:

- Generative and Adaptive Artificial Intelligence (AI) to drive better governance, develop a performance-oriented portfolio of projects under the UNSDCF, and to enable better policy choices through quality, reliable data.

- Circular Economy including devising schemes, policies and programs on embedding concepts of circular economy in urban management.

- Skills Development to address Georgia’s labour market challenges in terms of female participation, productivity, and quality. We recommend a focused intervention, tentatively called Target 100,000, aiming to provide skilling of 100,000 females over 5 years in the science, technology, and innovation sectors to boost tech exports (SaaS, AI, medtech, edtech, biotech).

    - Innovation in delivery In opening up to work with a broader set of stakeholders, particularly in the private sector, the UN may be able to unlock opportunities for new ways in which to deliver better outcomes through the UNSDCF. Some of the ways in which this can be achieved are:

- Working with Georgia’s Startup Community to define critical socio-economic  challenges, as well as develop solutions to address these challenges.

- Develop a mechanism for adopting a ‘platform approach’ rather than a project approach allowing multiple stakeholders to contribute to different components of a UNSDCF intervention, at different times, and using different methodologies, as opposed to the more rigid, structured and linear project modalities. This will be in line with the other recommendations regarding working with a broader set of stakeholders, and doing so in a more open, inclusive manner. Not all UNSDCF interventions will be suitable for a platform approach to delivery, hence a careful curation of interventions will be required, along with a change in the implementation mechanisms.

- Gamification strategies and Digital Twinning for capacity building through strategy games that use simulations of real-world issues; role playing; use of forecasting tools; and creating Digital Twins of government institutions to test how different policy choices will fare, before implementing them in a real-world environment. These games, simulations, Twins could be developed in partnership with technology startups and government institutions.

- Developing a Knowledge Management Strategy that includes Webinars, podcasts, vlogs and blogs. Combined with the recommendation for setting up the UNSDCF Observatory, this would enable the UN RCO to become a hub for knowledge curation and sharing.

- Expanding the Partnership Base by looking to work with not only the private sector in Georgia, but with philanthropic organisations, family offices, and foundations.  Leveraging the UN’s convening power to develop partnerships with non-traditional partners, would be particularly useful in this respect.

    - Innovations in financing In addition to widening the partnership base, the UN in Georgia also needs to expand its financial resource base. With ODA shrinking and its own core resources lagging the scale and scope of the UNSDCF, it is important to explore new ways of financing for results. This includes:

- Establishing an Impact Investment Facility to finance investments in the social sectors. The global market size of impact investment stands at $1.57 trillion, and mobilizing impact capital from the private sector to finance the UNSDCF could help close the funding gap, as well as provide a sharpened focus on outcomes and impact rather than inputs and outputs as most of the current UNSDCF does. It is recommended to establish this facility in partnership with MDBs and the private sector, with its exact structure, purpose, usage protocols, monitoring mechanisms, and terms and conditions, developed by the UN RCO.

  - Target Greater Inclusivity

- We recommend building on the UNSDCF’s potential for becoming a framework of choice for stakeholders, by creating a new model of joint programs that look outwards and forward in terms of their scope, partners, and sustainability. To this end, the UN RCO can lay down clear markers for performance, strengthen Results Groups in terms of oversight capacity, and promote transparency and inclusion in every step of design, implementation, and monitoring. Some of the earlier recommendations in terms of an expanded partners’ base, creating mechanisms such as the UNSDCF Observatory, and engaging Parliamentarians, would provide different ways in which to achieve the objectives of greater inclusion.

A Results Management Framework for all recommendations made in this report are at Annex 15.

# Section VI: Summary performance rating

66.   The summary performance rating is based on the criteria and guidelines provided in the UN Evaluation Group Guidelines for Evaluation of the United Nations Sustainable Development Cooperation Framework 2021. Ratings are on a scale of 0-6, with a score of 6 representing the highest rating. The interpretation criteria of the ratings and assessment criteria for sustainability can be seen below.

67.  Based on these criteria, the Summary Performance Rating for the UNSDCF 2021-2025 for Georgia is presented below.

| SUMMARY PERFORMANCE RATING UNSDCF 2021-2025 GEORGIA |  |  |  |
| --- | --- | --- | --- |
| Criteria/issue | Rating | Summary comments |
| A. STRATEGIC RELEVANCE |  |  |
| A1. Alignment with SDGs and National strategic priorities | 6 |  |
| A2. Relevance to national, regional and global priorities and beneficiary needs | 4 |  |
| A3. Dynamic and Responsive CF | 5 |  |
| B. COHERENCE |  |  |
| B1. CF position, credibility and reliability | 4 |  |
| B2. CF complementarity, harmonization and co-ordination | 5 |  |
| B3. Synergies and interlinkages of interventions | 4 |  |
| B4. Forging strategic and effective partnerships | 4 |  |
| C. EFFECTIVENESS |  |  |
| C1.1 Delivery of CF outputs | 5 |  |
| C1.2 Progress towards outcomes |  |  |
| Outcome 1 | 4 |  |
| Outcome 2 | 5 |  |
| Outcome 3 | 4 |  |
| Outcome 4 | 4 |  |
| Outcome 5 | 4 |  |
| C2. Adopting and promotion of resilience-building approaches | 4 |  |
| C3. CF focus on national capacity development | 5 |  |
| C4. Targeting the most vulnerable, disadvantaged, and marginalized population | 5 |  |
| D. EFFICIENCY |  |  |
| D1. Integrated funding framework | 4 |  |
| D2. Collectively prioritized activities based on the needs | 4 |  |
| D3. Effective reallocation of resources to emerging needs and priorities | 5 |  |
| D.4 Timeliness of actions | 5 |  |
| E. SUSTAINABILITY |  |  |
| E1.1. Financial risks | 3 |  |
| E1.2. Socio-political risks | 3 |  |
| E1.3. Institutional and governance risks | 3 |  |
| E1.4. Environmental risks | 3 |  |
| E2. Catalysis and replication | 3 |  |
| F. ORIENTATION TOWARDS IMPACT |  |  |
| F.1 CF contributions to key institutional, behavioral and legislative changes | 5 |  |
| F.2 CF contribution to advance achievement of SDG targets | 5 |  |
| F.3 CF contribution to advance cross-cutting concerns on gender equality | 6 |  |
| F.4 contribution to advance cross-cutting concerns on human rights and non-discrimination, including disability inclusion | 6 |  |
| F.5 contribution to advance cross-cutting concerns on environmental sustainability | 5 |  |
| F. FACTORS AFFECTING PERFORMANCE |  |  |
| F1. CF design | 4 |  |
| F2. Quality of RCO leadership and effective oversight | 4 |  |
| F2.1 Quality of CF implementation by UNCT | 4 |  |
| F3. Quality of UNCT coordination and integration | 5 |  |
| F4. National ownership on the CF | 4 |  |
| F5. CF stakeholder engagement | 4 |  |
| F6. Communication, knowledge management and M&E | 4 |  |
| F7. Quality of UNCT collective and joint efforts | 4 |  |
| Overall rating | 5 |  |

Annex 1: ToR for the Evaluation of the UNSDCF 2021-2025 Georgia

Annex 2: Evaluation design matrix

| CRITERIA | PRIMARY QUESTIONS | SUB-QUESTIONS | RELEVANT INDICATORS | DATA COLLECTION SOURCES |
| --- | --- | --- | --- | --- |
| Relevance and adaptability #### IS THE CF DOING THE RIGHT THINGS AND ADAPTED WELL TO EMERGING NEEDS? | - To what extent are the CF objectives aligned and been consistent with the needs, priorities, and policies of the government (including alignment to national development goals and targets, national plans, strategies and frameworks). - To what extent did the implementation of the CF (joint workplan and agencies programmes) adjust to emerging issues faced by the country during the implementation? | - How frequently are the CF objectives reviewed to ensure alignment with government priorities? - What processes are in place to engage with government stakeholders in setting CF objectives? - Are there specific examples where CF objectives have directly contributed to national policy changes? - How were emerging issues identified and prioritized during the implementation of the CF? - What mechanisms were used to adjust the CF implementation in response to these emerging issues? - Were there any significant challenges encountered in adapting to emerging needs, and how were they addressed? | - Alignment of CF objectives with national development goals - Positive feedback from government officials on CF relevance - Evidence of adjustments in CF implementation to address emerging issues - Flexibility in joint workplan and program adaptations - CCA and other dev. Partners’ strategic assessments - UN Agencies’ programmes evaluations | - Document review (national development plans, CF documents) - Interviews with government officials and UN staff - Annual Reports of Results Groups - Annual Reports of UNCT - Surveys |
| Coherence #### HOW WELL DOES THE CF FIT? | - To what extent has the CF strengthened the position, credibility and reliability of the UN system as a partner for the government and other actors, and has served as an effective partnership vehicle? - To what extent has the CF strengthened the coherence of support by UNCT members and sought partnerships (with civil society/private sector/local government/parliament/national human rights institutions/international development partners) to enhance achievement of results? | - How do different stakeholders perceive the role of the UN system in the country before and after the CF implementation? Is there any systematic mechanism to track changes in perception? - What specific actions or initiatives under the CF have enhanced the UN system’s credibility and reliability? - Are there areas where the UN system’s credibility has been questioned, and how has this been addressed? - How effectively are the activities of different UNCT members coordinated under the CF? - Are there examples of successful joint initiatives between the UN and external partners under the CF? | - Increased number of partnerships - Diversity of partnerships - Positive perceptions of UN credibility and reliability - Enhanced coordination and coherence in support activities - Diversity and effectiveness of partnerships established | - Document review (CF reports, partnership agreements) - Interviews with UNCT members, partners, government officials |
| #### Effectiveness #### HAS THE CF ACHIEVED ITS OBJECTIVES? IS THE CF DOING IT RIGHT? | - How effective has the CF been in achieving the results outlined in the results framework? What have been the benefits for the people and institutions targeted by the interventions, including the most vulnerable, disadvantaged, and marginalized population? - To what extent has the CF contributed to the promotion of gender equality and women’s empowerment, human rights, disability inclusion and environmental sustainability. | - What key factors have contributed to or hindered the achievement of the results? - What lessons have been learned from the successes and challenges in achieving these results? - How are the benefits distributed among different population groups, particularly the most vulnerable? How are these monitored and reported? - What medium-to-long-term impacts have the interventions had on the targeted populations and institutions? How are these measured? - What mechanisms are in place to involve beneficiaries in the design and implementation of the interventions? - What specific programs or initiatives under the CF have focused on these areas? - How are the outcomes measured and tracked for these specific areas? - Are there any success stories or case studies that highlight significant progress in these areas? | - Percentage of achieved Outcome and Output indicators targets. Positive outcomes reported by beneficiaries - Clear evidence as reported by the UN system and the relevant government agencies on how and to what extent has the CF contributed to improvements in human rights, women’s empowerment, PWDs, and environmental sustainability | - Review of CF results framework and progress reports - Surveys/interviews with beneficiaries and stakeholders |
| Efficiency #### HOW WELL HAVE RESOURCES BEEN USED? | - Has the CF reduced transaction costs for partners through greater UN coherence? - To what extent has the CF collectively prioritized activities based on the needs (demand side) rather than on the availability of resources (supply side), and reallocated resources according to the collective priorities and changing needs if/where necessary? - How adequate has the CF been in facilitating the effective reallocation of resources to emerging needs and priorities? | - What specific transaction costs have been reduced due to the CF? - How do partners perceive the efficiency of working with the UN system under the CF compared to previous arrangements? - What further improvements can be made to reduce transaction costs? - What criteria are used to prioritize activities within the CF? - How transparent and inclusive is the decision-making process for resource allocation? - Are there examples where resource reallocation has significantly improved outcomes? - What processes are in place for identifying and addressing emerging needs? - How responsive has the CF been in reallocating resources to address these needs? - Are stakeholders satisfied with the timeliness and adequacy of resource reallocation? How is this satisfaction measured? | - Cost-benefit analysis - Interviews with partners and UN staff - Evidence of needs-based prioritization - Effective reallocation of resources according to emerging needs - Timeliness and adequacy of resource reallocation - Positive feedback on resource flexibility - Decreased transaction costs - Efficiency gains reported by partners | - Financial analysis - Review of resource allocation reports - Interviews with UN staff and partners - Review of reallocation processes and outcomes - Financial information available on UN Info |
| Coordination HOW WELL HAS THE IMPLEMENTATION OF THE CF BEEN COORDINATED? | - Post UN reform, to what extent have UN agency programs and work plans been effectively and meaningfully derived from the CF both in design and implementation? - To what extent did the post reform Resident Coordinator office’s roles and responsibilities enable positive UNCT’s joint convening power and better coherence of the country team? | - Other than the JSC and SDG Council, what are the institutional arrangements for horizontal and vertical coordination within the UN and between the UN and GoG? - How has the UN reform impacted the design and implementation of agency programs and work plans? - What are the knowledge management arrangements within the UN and between the UN and the GoG? - Are there examples of improved coordination and alignment of programs with the CF post-reform? - What challenges have been faced in aligning agency programs with the CF? - How has the role of the Resident Coordinator office evolved post-reform? - What specific actions has the Resident Coordinator office taken to enhance UNCT’s joint convening power? - How do UNCT members perceive the effectiveness of the Resident Coordinator office in improving team coherence? | - Enhanced coordination and joint activities - Positive feedback on the role of the Resident Coordinator office, especially in terms of management of the Joint Programs, policy advocacy, and support for resource mobilization. | - Interviews with Resident Coordinator office staff and UNCT members - Review of coordination mechanisms and meeting minutes |
| Orientation towards impact #### WHAT DIFFERENCE DO CF INTERVENTIONS MAKE? | - To what extent have UN system activities articulated in the CF driven progress towards, or supported achievement of ToC outcomes? | - How are ToC outcomes integrated into the planning and implementation of UN system activities? - What monitoring and evaluation mechanisms are in place to track progress towards ToC outcomes? - Are there any notable successes or areas for improvement in achieving ToC outcomes? | - Progress towards ToC outcomes - Evidence of contribution to impact goals - Explicit reference in the UN program documents on how they support national policies, plans and strategies - Explicit reference in key government policies, strategies, and plans on how the CF has supported the design, implementation, or oversight | - Review of CF and ToC documents - Impact assessments and interviews with key stakeholders |
| Sustainability #### WILL THE BENEFITS LAST? | - What mechanisms, if any, have the CF established to ensure socio-political, institutional, financial and environmental sustainability? - What is the likelihood that progress towards the SDGs is sustained by national partners and stakeholders over time? | - How are sustainability considerations integrated into CF programs and initiatives? - What partnerships or collaborations have been established to support sustainability? - Are there specific examples of successful sustainability initiatives under the CF? - How are national partners and stakeholders involved in sustaining progress towards the SDGs? - What capacity-building measures have been implemented to support long-term sustainability? - Are there any risks or challenges that could impact the sustainability of progress, and how are they being addressed? | - Existence and effectiveness of sustainability mechanisms - Long-term plans in place and being implemented - Commitment and capacity of national partners - Ongoing support and follow-up mechanisms | - Review of sustainability plans and CF documents - Interviews with UN staff and national partners - Review of national policies and strategies |

Annex 3: Alignment of Georgia’s national policies and strategies with the SDGs

Annex 4: References

- National Statistics Office of Georgia (GeoStat), Production Volume of Agricultural Holdings per Labour Day, 2023, https://geostat.ge/media/42463/18.Production_volume_of_agricultural_holdings_per_labour_day_ENG.xlsx.

- National Statistics Office of Georgia (GeoStat), Distribution of Average Monthly Incomes per Capita by Urban and Rural Areas, 2023, https://geostat.ge/media/62655/108_Distribution-of-average-monthly-incomes-per-capita-by-urban-and-rural-areas.xls.

- National Statistics Office of Georgia (GeoStat), NEET (Not in Education, Employment, or Training) Rates for Youth in Georgia, 2023, https://geostat.ge/media/62302/14-NEET_Eng.xlsx.

- Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia, Employment Support Programs 2021-2023, https://lio.moh.gov.ge/editor/upload/20240618051616-2021-2023-%E1%83%A8%E1%83%94%E1%83%9B%E1%83%9D%E1%83%AC%E1%83%9B%E1%83%94%E1%83%91%E1%83%A3%E1%83%9A%E1%83%98%20%E1%83%A1%E1%83%90%E1%83%9B%E1%83%A3%E1%83%A8%E1%83%90%E1%83%9D%20%E1%83%90%E1%83%93%E1%83%92%E1%83%98%E1%83%9A%E1%83%94%E1%83%91%E1%83%98.xlsx.

- Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia, Employment Program Data for Persons with Disabilities – 100,000 Initiative, 2023, https://lio.moh.gov.ge/editor/upload/20240619114558-100%20000%20%E1%83%93%E1%83%90%E1%83%A1%E1%83%90%E1%83%A5%E1%83%9B%E1%83%94%E1%83%91%E1%83%A3%E1%83%9A%E1%83%96%E1%83%94-%E1%83%A1%E1%83%94%E1%83%99%202016.xlsx.

- Government of Georgia, Sustainable Development Goals Tracker for Georgia.

- Government of Georgia, Draft National Energy and Climate Plan of Georgia.

- Government of Georgia, Georgia’s Long-Term Low Emission Development Strategy, 2023.

- Government of Georgia, Roadmap to Implementation of Georgia’s Long-Term Low Emission Development Strategy, 2024.

- Ministry of Environmental Protection and Agriculture of Georgia, Agriculture and Rural Development Strategy 2021-2027.

- Government of Georgia, National Strategy 2019-2023 for Labour and Employment Policy of Georgia, 2019.

- Ministry of Economy and Sustainable Development of Georgia, National Renewable Energy Action Plan, 2019.

- Ministry of Environment Protection and Agriculture of Georgia, Georgia’s 2030 Climate Change Strategy.

- United Nations Country Team (UNCT) in Georgia, UN Country Team Annual Report 2021.

- United Nations Country Team (UNCT) in Georgia, UN Country Team Annual Report 2022.

- United Nations Country Team (UNCT) in Georgia, UN Country Team Annual Report 2023.

- European Neighbourhood Programme for Agriculture and Rural Development (ENPARD), Improving Rural Development in Georgia Project under ENPARD III: Final Evaluation Report, December 2022.

- Food and Agriculture Organization of the United Nations (FAO), GCF-GEO FAO Annual Performance Report 2023 (Tbilisi, Georgia, 2023).

- Mid-Term Evaluation of the FAO “Support to the Food Safety and SPS Sector in Georgia” under ENPARD IV, Project Evaluation Series 08/2024 (Rome: Food and Agriculture Organization of the United Nations, 2024).

- Food and Agriculture Organization of the United Nations (FAO), Terminal Report: FAO Support to the Georgian Agricultural Sector (ENPARD III) (Rome, 2024).

- Food and Agriculture Organization of the United Nations (FAO), Support to the Food Safety and SPS Sector in Georgia under ENPARD IV: Third Progress Report (Rome, 2024).

- United Nations Development Programme (UNDP), Final Evaluation of the Civil Society Support Programme (CSSP II), April 2023).

- United Nations Development Programme (UNDP), Final Evaluation of the UK Fund in Support of Sustainable Peace – Complementary Initiative to COBERM, September 2023.

- United Nations Development Programme (UNDP), Final Evaluation of COBERM IV, Conflict Management Consulting, November 2022.

- United Nations Development Programme (UNDP), USAID Partnering for Resilience Program 2023 Narrative Quarterly Progress Report (October - December 2023), December 2023.

- United Nations Development Programme (UNDP), Final Evaluation Report: EU Innovative Action for Private Sector Competitiveness in Georgia, May 2024.

- United Nations Development Programme (UNDP), Transforming Social Protection for Persons with Disabilities in Georgia: Final Evaluation Report, 2022.

- United Nations Development Programme (UNDP), Final Evaluation of the UNDP Georgia Project: Creating Better Life-Long Learning Opportunities Through Local Partnerships (CBLLL), 2024.

- United Nations Development Programme (UNDP), Renewable Energy for Sustainable Forest Management and Community Resilience in Machakhela, May 2023.

- Food and Agriculture Organization of the United Nations (FAO), 2021 Annual Report: Country Context and Key Achievements, 2021.

- Food and Agriculture Organization of the United Nations (FAO), 2021 Annual Report: Country Context and Key Achievements, 2022.

- Food and Agriculture Organization of the United Nations (FAO), Progress Report on the National Animal Identification, Registration and Traceability System (NAITS II), 2022.

- United Nations Development Programme (UNDP), Final External Evaluation of the “Improving Rural Development in Georgia” Project under ENPARD III, December 2022​.

- United States Agency for International Development (USAID), Partnering for Resilience Program: Quarterly Progress Report, 1 October – 31 December 2023, prepared by UNDP Georgia, 2023.

- United Nations Development Programme (UNDP), EU-UN Joint Programme on Improving Vocational Education in Abkhazia: Mid-term Evaluation Report, 2021.

- Swiss Agency for Development and Cooperation (SDC), Mid-Term Evaluation of the Project “Fostering Economic Empowerment of Women Farmers by Supporting Homemade Dairy Production Through the Farmer Field Schools (FFS) Approach”, 2022.

- United Nations Country Team (UNCT) in Georgia, Common Country Analysis 2023 Update, February 2024.

- United Nations Country Team (UNCT) in Georgia, UN Common Country Analysis for the Cooperation Framework and the 2030 Agenda, 2022.

- Food and Agriculture Organization of the United Nations (FAO), Achieving Land Degradation Neutrality Targets of Georgia through Restoration and Sustainable Management of Degraded Pasturelands: Project Implementation Report 2021.

- Food and Agriculture Organization of the United Nations (FAO), Achieving Land Degradation Neutrality Targets of Georgia through Restoration and Sustainable Management of Degraded Pasturelands: Project Implementation Report 2022.

- Food and Agriculture Organization of the United Nations (FAO), Achieving Land Degradation Neutrality Targets of Georgia through Restoration and Sustainable Management of Degraded Pasturelands: Project Implementation Report, 2023.

- Food and Agriculture Organization of the United Nations (FAO), Green Climate Fund Annual Performance Report GEO-RS-003 for Georgia, 2023.

- Food and Agriculture Organization of the United Nations (FAO), Capacity Needs Assessment Report: National Designated Authority of Georgia, 2023.

- Food and Agriculture Organization of the United Nations (FAO), DDCT Annual Report for Georgia 2021, 2021.

- Food and Agriculture Organization of the United Nations (FAO), DDCT Annual Report for Georgia 2021, 2022.

- United Nations Children’s Fund (UNICEF) Georgia, The Georgian Lead Surveillance System (G-LESS): Surveillance System Design Report, June 2022.

- United Nations Children’s Fund (UNICEF), Ending Childhood Lead Poisoning in Georgia: Progress and Lessons Learned Between 2017 and 2023, 2023.

- United Nations Development Programme (UNDP), Mid-Term Evaluation of the Multi-Hazard Early Warning System Project, February 2022​.

- United Nations Development Programme (UNDP), Mid-Term Review: Enhancing Financial Sustainability of the Protected Area System in Georgia, October 2021​.

- United Nations Children’s Fund (UNICEF) and UN Women, Women and Children with Disabilities in Georgia: An Overview of Data, Tbilisi, 2021​.

- United Nations Children’s Fund (UNICEF), The Cost of Raising a Child with Disabilities in Georgia, Tbilisi, 2023.

- United Nations Children’s Fund (UNICEF), Social Protection of Children in Georgia: Challenges and Recommendations, March 2024.

- United Nations Children’s Fund (UNICEF), Defining the Spending of Child Grants within the Targeted Social Assistance Program, Tbilisi, 2023.

- United Nations Children’s Fund (UNICEF), Social Protection System Readiness Assessment in Georgia, May 2020.

- United Nations Children’s Fund (UNICEF), Estimating the Impact of COVID-19 on Child Poverty in Georgia Using a Micro-Simulation Model, 2020.

- United Nations Children’s Fund (UNICEF), See Every Colour: Addressing Stigma Against Children with Disabilities and Supporting Their Social Inclusion Through Social and Behaviour Change Interventions, 2022.

- UN Women, Women’s Economic Empowerment in the South Caucasus Regional Project: Final Evaluation Report, May 2021.

- UN Women, Women’s Economic Empowerment in the South Caucasus Regional Project: Final Evaluation Report, May 2021.

- UN Women, Final External Evaluation Report: Joint Action for Women’s Economic Empowerment (JAWE) Project in Georgia, December 2020​.

- UN Women, Corporate Evaluation of UN Women’s Support for Women’s Economic Empowerment by Advancing Gender-Responsive Laws, Frameworks, Policies, and Partnerships, March 2023.

- International Organization for Migration (IOM), Enhancing the Potential of Migration for Socio-Economic Development in Armenia and Georgia: Sustainable Reintegration Project Report, 2024​.

- International Organization for Migration (IOM), UN Joint Programme: EU Innovative Action for Private Sector Competitiveness in Georgia - Final Narrative Progress Report, Tbilisi, 2023​.

- International Organization for Migration (IOM), Study of Reintegration Outcomes Among Returned Migrants in Georgia, 2024​.

- International Labour Organization (ILO), Assessment of the Social Protection System in Georgia, 2020.

Annex 5: Focus group participants

- CSOs FGD

- Partnership for Human Rights (Nana Abashidze)

- Energy Efficiency Centre (Eleve Gvilava)

- Tanadgoma (Nino Tsereteli)

- Union Tanadgoma (Maiko Baratashvili)

- Kakheti Regional development Fund (online) (Iza Bekauri)

- Tolerance and Diversity Institute (online, partial) (Ekaterine Chitanava)

- Private Sector FGD

- Georgian Farmers' Association

- Georgian Football Federation

- Avon

- Tegeta Motors

- Bodyshop

Annex 6: List of key informant interviews (KII)

| No. | ORGANIZATION | KEY INFORMANT | REMARKS |
| --- | --- | --- | --- |
| UNITED NATIONS |  |  |  |
|  | UN RCO | - Mr. Didier Trebucq, Resident Coordinator - Ms. Anna Platonova, Head of Office - Nestan Khuntsaria, Associate Development Coordination Officer - David Mushkudiani, Development Coordination Officer |  |
|  | UNDP | - Mr. Douglas Webb, Resident Representative - Mr. Nils Christensen, Deputy Resident Representative - Mr. Gigi Bregadze, Team Leader Governance Portfolio - Mr. George Nanobashvili, Team Leader Economic Development Portfolio - Ms. Nino Antadze, Team Leader Energy and Environment Portfolio - Mr. Giorgi Vardishvili, Team Leader conflict prevention/recovery - Mr. Nodar Kereselidze, Program Manager Agriculture projects |  |
|  | UNICEF | - Mr. Jesper Moller, Representative - Ms. Amy Clancy, Deputy Representative - Mr. Giorgi Kalakashvili, Child Rights Monitoring Specialist |  |
|  | UNFPA | - Ms. Natalia Zakareishvili, Program Analyst - Mr. George Mataradze, Program Analyst - Mariam Bandzeladze, Head of Office |  |
|  | UNHCR | - Ms. Kemlin Furley, Representative - Ms. Salome Kusikashvili - Ms. Ketevan Kvlividze - Ms. Roza Minasyan, Head of Field Office in Gali |  |
|  | UN WOMEN | - Ms. Kaori Ishikawa, UN Women Country Representative - Ms. Tamar Sabedashvili, Deputy Resident Representative - Elene Gabelaia, Project Analyst - Nino Gachechiladze, Monitoring & Reporting Analyst |  |
|  | IOM | - Ms. Natia Esebua - Ms. Natia Kvitsiani |  |
|  | OHCHR | Mr. Vladimir Shkolnikov, Senior Advisor |  |
|  | WHO | Mr. Silviu Domente, Representative |  |
|  | FAO | - Mr. Mamuka Meskhi, Assistant Representative - Ms. Iamze Mirazanashvili - Ms. Tinatin Kbilashvili - Mr. Giorgi Orkodashvili |  |
| - O | OCHA | Irakli Malania, Humanitarian Affairs Officer |  |
|  | ILO | Ms. Ekaterine Karchkhadze, National Coordinator |  |
|  | Sub-Regional PDA | Mr. Oleh Protsyk, Peace and Development Advisor |  |
| INTERNATIONAL DEVELOPMENT PARTNERS |  |  |  |
|  | Asian Development Bank | - Mr. Anders Pettersson, Deputy Country Director - Mr. George Luarsabishvili - Senior Economics Officer |  |
|  | World Bank | - Ms. Anna Berdzenadze, Education Specialist - Ms. Irina Gordeladze, Consultant, Governance |  |
|  | EU | Deputy Head of Mission |  |
|  | SIDA | - Mr. Kakha Khimshiashvili, Program Officer - Ms. Eva Atterlov Frissell |  |
|  | FCDO | Mr. Chris Reilly, Head of Programmes |  |
|  | UK Embassy | Ms. Zurab Khrikadze, Programme Officer |  |
|  | Swiss Development Cooperation (SDC) | Ms. Beka Tagauri |  |
|  | USAID | Ms. Tamara Sirbiladze, Team Leader |  |
| PARLIAMENT |  |  |  |
|  | Parliamentary Committee on Environmental Protection and Natural Resources | Ms. Khatia Tsilosani – Deputy Chairperson |  |
| GOVERNMENT OF GEORGIA |  |  |  |
|  | Administration of Government | - Ms. Tinatin Khatchvani, Head of the Donor Coordination Unit - Natia Tsikaradze, Head of the Strategic Planning and Coordination Division, Inter-Agency SDG Council - Ana Barisashvili, Head of the Public Administration Division - Maka Peradze - Head of the Human Rights Secretariat - Eliso Shonia - Human Rights Secretariat/Head of Research and Analysis Division |  |
|  | State Ministry for Reconciliation and Civic Equality of Georgia | Ms. Tamar Kochoradze, Head of the International Organizations Department |  |
|  | LEPL Public Service Development Agency | - Ms. Ketevan Betlemidze - Chairperson of the PSDA - Mr. George Jashi – Executive Secretary, Secretariat of the State Commission on Migration Issues |  |
|  | Ministry of Finance | - Ms. Maia Chaladze, Deputy Head of the Public Debt Management Department - Ms. Natia Gulua, Head of the Budget Department - Mr. Vakhtang Chalapeikrishvili, Head of Macroeconomic Analysis and Fiscal Policy Planning Department |  |
|  | Ministry of Education, Science and Youth | Mr. Kakha Khandolishvili, Head of International Relations’ Department |  |
|  | Ministry of Environment Protection and Agriculture | - Ms. Nino Tkhilava, Head of the Environment and Climate Change Department - Mr. Lasha Inauri, Head of the International Relations and European Integration Department |  |
|  | Ministry of Economy and Sustainable Development | - Ms. Givi Zedelashvili, Head of the Trade Development and International Economic Relations Department - Mr. Omar Tsereteli, Deputy Head of Energy Efficient and Sustainable Development Department - Mr. David Advadze, Head of Division of Sustainable Development Promotion |  |
|  | Ministry of Justice | - Ms. Ketevan Sarajishvili, Head of the International Relations and Legal Cooperation Department - Ms. Natalia Abashmadze – Deputy Chairperson, Public Service Hall - Ms. Mariam Tsaguria – International Relations Department, Public Service Hall - Mr. Robi Kintsurashvili – Brand Manager, Public Service Hall - Mr. Dimitri Gugunava – Digital Governance Agency |  |
|  | National Statistics Office of Georgia (GEOSTAT) | - Mr. Teimuraz Gogishvili, Head of Methodology and Quality Management Division - Mr. Levan Tserediani, Chief Specialist of Methodology and Quality Management Division - Ms. Maia Gogiberidze, Chief Specialist of Methodology and Quality Management Division |  |
|  | National Environment Agency | - Ms. Tamar Sharashidze, Deputy Head of National Environmental Agency; - Ms. Lia Megrelidze, Deputy Head of Hydrometeorology department; - Tamar Zedelashvili, Head of the Strategic Development Division; |  |
|  | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health, and Social Affairs | - Ms. Tamar Kurtanidze, Head of the Social Protection, IDPs and Labour Policy Department - Ms. Ketevan Goginashvili, Head of Health Policy Division Ms. Vera Baziari, Expert on Mother and Child issues, Head of the Maternal and Child Health Department |  |
|  | National Health Agency | Ms. Eka Sharadze, Deputy Director |  |
|  | State Ministry for Reconciliation and Civic Equality | Ms. Tamar Kochoradze, Head of International Organizations Department |  |
|  | Labour Inspection Office | Ms. Shorena Kubaneishvili, Head of the International and Public Relations, Statistics and Analytical Division |  |
|  | Rural Development Agency | Natalia Kharatishvili, Deputy Director |  |
|  | Ministry of Regional Development and Infrastructure | - Ms. Nino Purtskhvanidze, Head of the Infrastructure Policy and Development Partners Relations Department (Head of the Primary Structural Unit) - Mr. Nikoloz Rosebashvili, Head of the Local Self-Government Development and Policy Department - Ms. Natia Tatishvili, Deputy Head of Regional and Mountain Development Department |  |
|  | Ministry of Internal Affairs | - Ms. Natia Japaridze, Head of Project Management Division of International Relations Department - Ms. Tamar Dvalidze, Deputy Head of Project Management Division of International Relations Department |  |
|  | LEPL Agency for State Care and Assistance for the Victims of Human trafficking | Ms. Rusudan Kokhodze, Head of Agency |  |
|  | Civil Services Bureau | - Ms. Maya Dvalishvili, Deputy Head - Ms. Gvantsa Beselia, Head of Department |  |
|  | Enterprise Georgia | Mr. Tornike Zirakishvili, Deputy Director |  |
|  | Georgia’s Innovation and Technology Agency (GITA) | Mr. Tornike Jobava, Deputy Chairman |  |
|  | Social Service Agency | Ms. Tea Gvaramadze, Deputy Director |  |
|  | Public Defender (Ombudsman) Georgia | Ms. Sophio Rusetski, Head of Gender Equality Department |  |
|  | Ministry of Foreign Affairs | - Ms. Nino Berikashvili, Deputy Head of the Political Department - Mr. Giorgi Kekeliani, III Secretary, Conflict Resolution Policy Division, Political Department |  |
|  | Georgian Energy Development Fund | - Mr. Jaba Khmaladze, CEO - Ms. Ani Janukashvili, Deputy Director |  |
|  | National Center for Disease Control & Public Health (NCDC) | Ms. Nino Lomia, Head of Maternal, Child and Reproductive Health Department |  |
| CIVIL SOCIETY ORGANIZATIONS AND ACADEMIA |  |  |  |
|  | Caucasus Environmental NGO Network (CENN) | Rezo Getiashvili, Deputy Director- Environment, Natural Resources, Energy | Instead of a KII, the online survey instrument was sent |
|  | Georgian Young Lawyers' Association | Ms. Tamar Oniani |  |
|  | Civil Society Institute (SI) | Vazha Salamadze, Director |  |
|  | Institute for Development of Freedom of Information (IDFI) | Mr. Levan Avalishvili, Founder |  |
|  | Mercy Corps Georgia | Mr. Irakli Kasrashvili, Director | Instead of a KII, the online survey instrument was sent |
|  | CARE Caucasus | Ms. Ketevan Khachidze, CEO | Instead of a KII, the online survey instrument was sent |
|  | Georgian Network of Women with Disabilities | Ms. Tamar Macharashvili, Head of Network |  |
|  | Democrat Women’s Organization | Ms. Marina Modebadze – Head of Projects |  |
|  | Network of Centers of Civic Engagement | Ms. Natia Sirdadze, Program Advisor | Questionnaire sent, but did not respond. Survey sent |
|  | IDP Women’s Association Consent | Ms. Julia Kharashvili, Head | Questionnaire sent, but did not respond. Survey sent |
|  | Georgian Farmers' Association | Ms. Nino Zambakhidze - Chairperson | GFA participated in FGD |
|  | Packaging Manufacturers Association of Georgia (PMAG) | Ms. Anano Rukhadze, Administrative Manager |  |
| PRIVATE SECTOR |  |  |  |
|  | Georgian Chamber of Commerce and Industry | - Mr. Giorgi Pertaia, President - Head of Agriculture Committee |  |

Annex 7: Key informant interview protocol

- INTRODUCTION

The United Nations Sustainable Development Cooperation Framework (UNSDCF) for Georgia 2021-2025 embodies the collaborative effort of the UN development system to assist Georgia in addressing its national priorities and challenges in line with the 2030 Agenda for Sustainable Development. Georgia has integrated SDG targets and indicators the national policy documents and established an SDG Council and four Working Groups to monitor progress and mainstream the sustainable development into general development planning. The country presented its Voluntary National Reviews (VNR) in 2016 and 2020 to the High-Level Political Forum on Sustainable Development, with preparations underway for its third VNR in July 2024.

Despite the progress achieved, challenges have been faced by sub-national governments (SNGs) in UNSDCF implementation. These include the availability of data and financial resources as well as the capacity of SNGs to implement the UNSDCF at the local level.

The UN Resident Coordinator’s Office is currently conducting an evaluation to see how and whether the UNSDCF has met its objectives. Key Informant Interviews (KIIs) are one of the methods chosen to collect various views and suggestions to produce comprehensive recommendations in order to help the government and the UN understand what needs to be improved in terms of design, delivery, and oversight of the UNSDCF.

- INTERVIEWEES

The interviewees will be selected from amongst senior to mid-senior staff of different Ministries, SOEs, and other governmental agencies.

- INTERVIEWEE CONSENT

By agreeing to being interviewed, the interviewees will be presumed to have given their consent for its recording.

- FACILITATOR/ MODERATOR

The consultants will conduct and moderate the KIIs.

- TIME AND PLACE

The interview can last about an hour, and may be conducted either online, or in person. The time for the interview will be specified later.

- DATA COLLECTION

The interview will be transcribed and analyzed. The transcription and analysis shall not contain information that would allow individuals to be linked to specific and sensitive statements.

- DATA ANALYSIS

The analysis will use qualitative analysis methods. The analysis will be written and presented in the final report.

- INTERVIEW GUIDES

The interview guide is aimed to facilitate the KII, and will follow the structure presented below:

- Welcome

The interviewer thanks and welcomes the interviewee.

- Introduction

The interviewer will explain:

- The KII is designed to understand the roles, practices, issues, challenges, and potential contribution of government agencies to support the achievement of SDGs targets, and thus the UNSDCF.

- The interview will take no more than one hour.

- The interview will be recorded. In case the interviewee objects, no recording will be done, and detailed notes taken.

- Main session

The interviewer asks the interviewee the following questions. Additional questions can be created and asked to create discussion.

- In your opinion, what is the current state of the adoption/ implementation of the UNSDCF in Georgia?

- How well aligned is the USDCF with government priorities?

- Which are the main reasons for any gaps between what is planned and what is practiced?

- What innovations/ improvement can be made to improve design, delivery, and oversight of the UNSDCF?

- What roles and contributions that your organizations can create/ initiate to strengthen the implementation of UNSDCF?

- What capacity buildings are needed (for local governments, business entities, non-profit organizations, citizens) to support SDGs achievement?

The moderator will conclude the discussion and thank you participants for participating in the KII.

** THIS INTERVIEW PROTOCOL IS A TENPLATE FOR OTHER KII AS WELL. QUESTIONS FOR OTHER KII WILL BE AMENDED BASED ON WHO IS BEING INTERVIEWED.

Annex 8: Stakeholder mapping

|  | STAKEHOLDER | DATA COLLECTION INSTRUMENT |  |  |  | COMMENTS ON IDENTIFICATION APPROACH |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | KII | FGD | Survey |  |  |
| UNITED NATIONS |  |  |  |  |  |  |
| 1 | UN RCO | X |  |  | All lead agencies are selected for key informant interviews. |  |
| 2 | UNDP | X |  |  |  |  |
| 3 | UNICEF | X |  |  |  |  |
| 4 | UNFPA | X |  |  |  |  |
| 5 | UNHCR | X |  |  |  |  |
| 6 | UN WOMEN | X |  |  |  |  |
| 7 | IOM | X |  |  |  |  |
| 8 | OHCHR | X |  |  |  |  |
| 9 | WHO | X |  |  |  |  |
| 10 | FAO | X |  |  |  |  |
| 11 | OCHA | X |  |  |  |  |
| 12 | ILO | X |  |  |  |  |
| 13 | UNECE | X |  |  |  |  |
| 14 | UNODC | X |  |  |  |  |
| 15 | Sub-Regional PDA | X |  |  |  |  |
| INTERNATIONAL DEVELOPMENT PARTNERS |  |  |  |  |  |  |
| 16 | Asian Development Bank | X |  |  | All key development partners, including those with whom UN agencies and programs have partnerships under the UNSDCF 2021-2025, are selected |  |
| 17 | World Bank | X |  |  |  |  |
| 18 | EU | X |  |  |  |  |
| 19 | SIDA | X |  |  |  |  |
| 20 | FCDO | X |  |  |  |  |
| 21 | UK Embassy | X |  |  |  |  |
| 22 | Swiss Development cooperation (SDC) | X |  |  |  |  |
| 23 | USAID | X |  |  |  |  |
| 24 | Norwegian Embassy | X |  |  |  |  |
| GOVERNMENT OF GEORGIA |  |  |  |  |  |  |
| 25 | Administration of Government | X |  |  | Selection of government institutions is based on partners and relevant agencies identified in the UNSDCF 2021-2025 and as recommended by the UNCT members during KIIs or in the form of feedback on the Inception Report. |  |
| 26 | Parliament | X |  |  |  |  |
| 27 | Public Service Development Agency | X |  |  |  |  |
| 28 | Ministry of Finance | X |  |  |  |  |
| 29 | Ministry of Education, Science and Youth | X |  |  |  |  |
| 30 | Ministry of Environment Protection and Agriculture | X |  |  |  |  |
| 31 | Ministry of Economy and Sustainable Development | X |  |  |  |  |
| 32 | Ministry of Justice | X |  |  |  |  |
| 33 | Prosecutor’s Office of Georgia | X |  |  |  |  |
| 34 | National Statistics Office of Georgia (GEOSTAT) | X |  |  |  |  |
| 35 | National Environment Agency | X |  |  |  |  |
| 36 | Inter-Agency Human Rights Council | X |  |  |  |  |
| 37 | Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health, and Social Affairs | X |  |  |  |  |
| 38 | State Ministry for Reconciliation and Civic Equality | X |  |  |  |  |
| 39 | Labour Inspection Office | X |  |  |  |  |
| 40 | Rural Development Agency | X |  |  |  |  |
| 41 | Ministry of Regional Development and Infrastructure | X |  |  |  |  |
| 42 | Georgian Energy Development Fund (GEDF) | X |  |  |  |  |
| 43 | Ministry of Internal Affairs | X |  |  |  |  |
| 44 | LEPL Agency for State Care and Assistance for the Victims of Human trafficking | X |  |  |  |  |
| 45 | Civil Services Bureau | X |  |  |  |  |
| 46 | Enterprise Georgia | X |  |  |  |  |
| 47 | Georgia’s Innovation and Technology Agency (GITA) | X |  |  |  |  |
| 48 | Social Service Agency | X |  |  |  |  |
| 49 | Public Defender (Ombudsman) Georgia | X |  |  |  |  |
| 50 | Ministry of Foreign Affairs | X |  |  |  |  |
| 51 | State Commission for Migration Issues (SCMI) | X |  |  |  |  |
| 52 | Nation Center for Disease Control & Public Health (NCDC) | X |  |  |  |  |
| CIVIL SOCIETY AND ACADEMIA |  |  |  |  |  |  |
| 53 | Caucasus Environmental NGO Network (CENN) | X |  |  | Selection of government institutions is based on partners and relevant agencies identified in the UNSDCF 2021-2025 and as recommended by the UNCT members during KIIs or in the form of feedback on the Inception Report. |  |
| 54 | International Committee of the Red Cross ICRC) | X |  |  |  |  |
| 55 | Danish Refugee Council | X |  |  |  |  |
| 56 | Norwegian Refugee Council | X |  |  |  |  |
| 57 | Georgian Young Lawyers' Association | X |  |  |  |  |
| 58 | Caucasus Institute for Peace, Democracy and Development | X |  |  |  |  |
| 59 | Caritas Georgia |  |  | X |  |  |
| 60 | Green Alternative |  |  | X |  |  |
| 61 | WWF Caucasus Program Office |  |  | X |  |  |
| 62 | Transparency International Georgia (TI) | X |  |  |  |  |
| 63 | Open Society Georgia Foundation (OSGF) | X |  |  |  |  |
| 64 | Civil Society Institute (SI) | X |  |  |  |  |
| 65 | Institute for Development of Freedom of Information (IDFI) | X |  |  |  |  |
| 66 | Sapari | X |  |  |  |  |
| 67 | Association of Young Economists of Georgia (AYEG) | X |  |  |  |  |
| 68 | Save the Children Georgia | X |  |  |  |  |
| 69 | World Vision Georgia | X |  |  |  |  |
| 70 | Women’s Fund in Georgia | X |  |  |  |  |
| 71 | Mercy Corps Georgia | X |  |  |  |  |
| 72 | CARE Caucasus | X |  |  |  |  |
| 73 | Women’s Information Centre | X |  |  |  |  |
| 74 | Georgian Trade Union Confederation (GUTC) | X |  |  |  |  |
| 75 | Employers' Association of Georgia (GEA) | X |  |  |  |  |
| 76 | Georgian Network of Women with Disabilities |  |  | X |  |  |
| 77 | National Association of Local Authorities of Georgia | X |  |  |  |  |
| 78 | Democrat Women’s Organization | X |  |  |  |  |
| 79 | Union 21st Century |  |  | X |  |  |
| 80 | Network of Centers of Civic Engagement | X |  |  |  |  |
| 81 | Center for Information and Counselling on Reproductive Health “Tanadgoma” |  |  | X |  |  |
| 82 | Care Together |  |  | X |  |  |
| 83 | IDP Women’s Association Consent | X |  |  |  |  |
| 84 | Georgian Farmers' Association | X |  |  |  |  |
| 85 | Association of Business Consulting Organizations of Georgia (ABCO Georgia) |  |  | X |  |  |
| 86 | Biological Farming Association Elkana |  | X |  |  |  |
| 87 | Agribusiness Association of Georgia |  | X |  |  |  |
| 88 | Packaging Manufacturers Association of Georgia (PMAG) | X |  |  |  |  |
| 89 | Business and Technology University |  |  | X |  |  |
| 90 | Agrarian University |  |  | X |  |  |
| 91 | Ilia State University |  |  | X |  |  |
| PRIVATE SECTOR |  |  |  |  |  |  |
| 92 | Georgian Chamber of Commerce and Industry | X |  |  | Selection of government institutions is based on partners and relevant agencies identified in the UNSDCF 2021-2025 and as recommended by the UNCT members during KIIs or in the form of feedback on the Inception Report. |  |
| 93 | AVON |  | X |  |  |  |
| 94 | GFF |  | X |  |  |  |
| 95 | Tegeta |  | X |  |  |  |

Annex 9: Survey sampling technique and citizen feedback survey instrument

Sample Selection

The survey, which comprises fifteen questions, will be conducted online, using a range of social media platforms, including Facebook, X, WhatsApp and Instagram, to reach out to citizens and encourage them to participate.

Using a simple random sampling methodology, no particular demographic or professional profile will be targeted, as the idea is to receive feedback from as wide a range of citizens from as many provinces and regions as possible.

Target Responses

Targeting two hundred responses

Channels of Survey Administration

Mailing Lists

We intend to reach out to the following organizations to utilize their extensive mailing lists. We may expand this list based on suggestions from UN agencies, as well as CSOs:

- Caucasus Environmental NGO Network (CENN)

  - CENN has an extensive mailing list of members and stakeholders in environmental and developmental sectors.

  - Website: www.cenn.org

- Transparency International Georgia

  - Transparency International Georgia maintains a large mailing list of individuals interested in governance, anti-corruption, and development issues.

  - Website: www.transparency.ge

- Georgian Young Lawyers' Association (GYLA)

  - GYLA has a mailing list that reaches legal professionals, activists, and citizens engaged in legal and human rights issues.

  - Website: www.gyla.ge

- National Association of Local Authorities of Georgia (NALAG)

  - We will use their various mailing lists of citizen groups

Facebook

We aim to share the survey in popular Facebook groups to reach a broad audience:

- Elkana

  - Elkana has a Facebook group with over 13,000 members, which can be utilized to disseminate the survey widely.

  - Facebook Group: https://www.facebook.com/groups/160357264332435

- Georgian Farmers' Association (GFA).

  - The GFA Digital platform, which includes their Facebook presence, unites several digital projects under one strategy focusing on sustainability.

Universities

We are requesting the following universities to distribute the survey through their internal networks, mailing lists and student/staff communication channels:

- Agrarian University,

- Ilia State University

- Free University of Tbilisi

SURVEY INSTRUMENT

The United Nations in Georgia is organizing an evaluation of the United Nations Sustainable Development Cooperation Framework (UNSDCF). This evaluation is intended to help the Government of Georgia and the United Nations in designing better policies, programs, and plans to improve the lives of citizens.

As part of this evaluation, this online survey is being administered. The survey is anonymous, and the answers provided will be used only for analyzing citizen perspectives.

We request you to please answer all questions. The survey should take about 15 minutes to complete. Thank you in advance for your cooperation.

- What is your gender?

⬜ Male

⬜ Female

⬜ Prefer not to state

- What is your age?

⬜ Under 18 years

⬜ 18-25

⬜ 25-35

⬜ 35-50

⬜ 50-65

⬜ 65 or above

- Which province are you based in?

Abkhazia

Adjara

Guria

Imereti

Kakheti

Kvemo Kartli

Mtskheta-Mtianeti

Racha-Lechkhumi and Kvemo Svaneti

Samegrelo-Zemo Svaneti

Samtskhe-Javakheti

Shida Kartli

Tbilisi

- What is your occupation?

⬜ Student

⬜ Teacher/Lecturer/Professor

⬜ Public Servant

⬜ Private Sector Employee

⬜ Self-Employed/Entrepreneur

⬜ Housewife

⬜ Civil Society

⬜ Journalist

⬜ Unemployed

⬜ Other

- What is the highest level of your education?

⬜ No formal education

⬜ Up to Secondary School

⬜ High School Diploma

⬜ Technical and Vocational Education Diploma

⬜ Bachelor’s Degree

⬜ Master’s Degree

⬜ PhD.

⬜ Prefer not to answer

- Have you heard about the United Nations Sustainable Development Cooperation Framework (UNSDCF)?

⬜ Never heard of it

⬜ Yes¨

⬜ Not sure

- Have you heard about the Sustainable Development Goals (SDGs)?

⬜ Never heard of it

⬜ Yes¨

⬜ Not sure

- If you have heard about the UNSDCF, who do you think is responsible for implementing it? Please select one answer.

⬜ National Government

⬜ Local Governments

⬜ United Nations

⬜ International development agencies

⬜ Private Sector

⬜ Non-Governmental Organizations

⬜ Communities

⬜ Every citizen

⬜ All of the above

⬜ I do not know

- If you have heard of the SDGs, who do you think is responsible for achieving them? Please select one answer.

⬜ National Government

⬜ Local Governments

⬜ United Nations

⬜ International development agencies

⬜ Private Sector

⬜ Non-Governmental Organizations

⬜ Communities

⬜ Every citizen

⬜ All of the above

⬜ I do not know

- At the government level, who do you think is best placed to implement the UNSDCF and/or the SDGs? Please select one answer.

⬜ National Government

⬜ City/Municipality Government

⬜ All of the above

- Are you aware of the actions being taken by the national or local government of your area to achieve the UNSDCF or the SDGs?

⬜ Very aware

⬜ Somewhat aware

⬜ Not aware

⬜ Does not concern me

- Which of the following Sustainable Development Goals (SDGs) do you think the local governments should prioritize? Please select up to three answers only.

⬜ SDG 1: No Poverty

⬜ SDG 2: Zero Hunger

⬜ SDG 3: Good Health and Well-Being

⬜ SDG 4: Quality Education

⬜ SDG 5: Gender Equality

⬜ SDG 6: Clean Water and Sanitation

⬜ SDG 7: Affordable and Clean Energy

⬜ SDG 8: Decent Work and Economic Growth

⬜ SDG 9: Industry, Innovation and Infrastructure

⬜ SDG 10: Reduced Inequalities

⬜ SDG 11: Sustainable Cities and Communities

⬜ SDG 12: Responsible Consumption and Production

⬜ SDG 13: Climate Action

⬜ SDG 14: Life Below Water

⬜ SDG 15: Life on Land

⬜ SDG 16: Peace, Justice and Strong Institutions

⬜ SDG 17: Partnerships for the Goals

- When thinking of the performance of your local government on the SDGs, which of the following statements do you agree with most? Please select one answer.

⬜ My local government reaches out to citizens, is responsive to citizen needs, and handles citizens’ grievances well

⬜ My local government does not reach out to citizens, does not respond to citizen needs, and does not handle citizen’s grievances well

⬜ I have no idea what my local government does or how it functions

⬜ Not sure

- Which of the following would you recommend to local governments, to improve their performance on SDGs implementation? Please select up to three answers only.

⬜ Involve citizens more in making plans and budgets

⬜ Regularly inform citizens about progress achieved on SDGs

⬜ Publish budgets and expenditures online

⬜ Involve citizens in monitoring quality of public services

⬜ Build capacity of elected representatives

⬜ Partner more with businesses and civil society organizations

- Which of the following statements do you agree with most? Please select one answer only.

⬜ Local Government would be able to make progress on SDGs if they were given more resources

⬜ Local Government would be able to make progress on SDGs if they involved citizens in preparing budgets

⬜ Local Government would be able to make progress on SDGs if they were less corruption in the system

⬜ Local Government would be able to make progress on SDGs if the elected representatives were given better training

⬜ Local Government would be able to make progress on SDGs if they involved citizens in monitoring quality of public services

⬜ Local Government would be able to make progress on SDGs if they partnered more with businesses and civil society organizations

----THANK YOU FOR YOUR TIME--

Annex 10: Theory of change rationale

| CATEGORY | ORIGINAL | REVISED OR NEW | RATIONALE |
| --- | --- | --- | --- |
| ASSUMPTIONS |  |  |  |  |
| NEW |  | The UNSDCF is considered by the government as a key document for development planning and is used to guide and shape policies, legislation, strategies and programs. | The original formulation of the Theory of Change (ToC) only highlights the assumptions related to government and other stakeholders, and completely ignores the assumptions relating to the UN agencies and programs. This makes the ToC flawed in its conception and imbalanced in its assessment of underlying factors that will impact UNSDCF implementation. The new assumptions aim to correct these errors and underscore the importance of maintaining a strategic approach, operational flexibility, and transparency in action. |
|  |  | There is sufficient flexibility in the UNSDCF to respond to emerging national priorities, and an institutional mechanism exists to review output areas and targets with the intent to respond to evolving policy and operational conditions. |  |
|  |  | There is a robust and transparent mechanism for reporting on progress on UNSDCF implementation, especially with respect to gender, vulnerable communities, and sustainability. |  |
|  |  | The UNCT in Georgia actively and consistently pursues the One UN approach and puts in place strong and effective institutional mechanisms for regular, structured engagement with the government and other stakeholders. |  |
|  |  | For Joint Programs in the UNSDCF, there is clarity in roles and responsibilities amongst the UN agencies and programs involved, financial contributions are clear and agreed, and the burden of reporting is fairly distributed in proportion to implementation and financing responsibilities. |  |
| REVISED ASSUMPTIONS | - There is strong commitment to mainstreaming SDG agenda in development planning. | There is a strong and sustained commitment across all levels of government and stakeholders, to mainstream the SDG agenda in development planning and equitable, inclusive economic growth. | Rephrased to reflect that mainstreaming of the SDG agenda is not the responsibility of the government alone, nor related to development planning only. |
|  | - There is political will to carry out economic and governance reform. | Political support and leadership for economic and governance reform is sustained. | Rephrased, as the original formulation appears to postulate that there is no political will for reform. We know from Georgia’s impressive reform agenda—that has been duly acknowledged by multiple international organizations—that there is adequate political will. For the UNSDCF to achieve its desired results, political leadership for reform needs to be sustained. |
|  | - The statistical system is strengthened to monitor SDGs, collect disaggregated data to analyze impact on vulnerable groups and for evidence-based policy making. | National statistical systems are continuously strengthened and adequately funded to monitor SDGs, collect disaggregated data, and access to and use of data for evidence-based policy planning and oversight. | Rephrased to add aspects related to enhanced data access and usage for driving evidence-based policies and oversight. |
|  | - Post-COVID 19 economic recession and its consequences are well managed. | Comprehensive and adaptive strategies are put in place to manage post-COVID economic recession and its long-term economic, social protection, and inclusive development consequences. | Rephrased to highlight the need for looking at post-COVID scenarios from not just a near-term economic lens, but also its longer-term implications on a wider set of parameters. |
|  | - There is enough implementation and monitoring capacity. | Adequate implementation and monitoring capacities exist within the government at all levels and well-funded capacity building plans are in place to address capacity gaps and build requisite skills. | Rephrased to add elements of well-funded, multilayer, multistakeholder capacity building programs. |
|  | - There are no environmental crises and geopolitical situation is calm. | Proactive measures and contingency plans are in place to manage potential environmental crises and geopolitical instabilities. | For a country that is highly vulnerable to both climate-induced and geopolitical crisis, this is an inappropriate assumption. It is not that no crises should occur during the UNSDCF implementation, but that there are plans in place that will not derail implementation if the crisis occur. |
|  | - There are enough resources, including external, to finance SDGs and national priorities. | Diversified funding strategies, including securing external resources, and enhancing domestic resource mobilization, are implemented to finance the SDGs and national priorities. | Rephrased to stress the need for a financing strategy that looks beyond the typical donor funding streams and looks at ways in which the UNSDCF can help government identify other sources of financial resources (e.g., capital markets), and supports efforts for own-source revenues. |
| RISKS |  |  |  |  |
| NEW |  | Inadequate political engagement leads to the UNSDCF losing its value and relevance for government, especially if it does not respond to emerging and evolving national priorities. | These additions are made to point out the imperative of continuous and vigorous political engagement as a primary strategy to secure and sustain the relevance of the UNSDCF. Furthermore, there is a need for much more pronounced and stronger partnerships with the private sector to work on a range of UNSDCF outputs and outcomes. |
|  |  | Insufficient partnerships are developed with the private sector to raise financial resources and work on private sector focused UNSDCF outcomes and outputs and SDGs (e.g. 1, 7, 8, 9, 11,13), leading to an adverse impact on UNSDCF contribution to the private sector-led growth agenda of the government. |  |
| REVISED RISKS | 1. Primacy of EU accession may detract from SDG agenda. |  | This is deleted because the pursuit of the Government of Georgia’s commitments under EU AA will only further the SDG agenda, not detract from it. The MAPS study on mainstreaming of SDGs in Georgia points out that the percentage of national strategies that incorporate SDG targets rises from 85% to 93% if the AA is also considered. |
|  | 2. Unresolved conflict may flare up. | Global political and economic instabilities, and flaring up of internal and external conflicts, may pose risks for implementation of UNSDCF programs specifically and for implementation, financing and oversight of national plans and priorities more broadly. | Merged the two risks (2 and 3) and clarified that the risk was relevant for both the UNSDCF and for macro level priorities. |
|  | 3. Global political and economic situation and trade protectionism may result in loss of international support. |  |  |
|  | 4. Demographic trends may impose a limit to the availability of skilled workers and hence growth. | Adverse demographic trends may limit the availability of skilled workers, hindering economic growth. | Rephrased for clarity. |
|  | 5. The upper middle-income status may result in a loss of international support. | Georgia’s upper middle-income status, may result in reduced financing for the UNSDCF due to shrinking eligibility for concessional international financial and technical support. | The original formulation presents Georgia’s graduation to an upper middle-income country status in a slightly negative context by highlighting aid dependency. The new status is a proud achievement and something to be celebrated, not considered a risk. The risk is therefore not so much for the country but for the UN system, which mobilizes concessionary resources – including grants – from the international development partners. |
|  | 6. Risks posed by health, environmental, and economic emergencies. | Health, environmental, and economic emergencies may pose significant financial and developmental risks for the country and for UNSDCF implementation | Rephrased for clarity. |
|  | - Political instability and lack of long-term vision. | Prolonged political instability may lead to a deterioration in the macroeconomic outlook, adversely affecting progress on human rights, gender empowerment, and on inclusive development. | As pointed out under assumption no. 2, one would be hard pressed to point to a lack of a long-term political vision. Hence the rephrasing to highlight that it is not political instability per se, but its prolongation, that may lead to adverse results for UNSDCF and national plan implementation. |

Annex 11: Theory of change synoptic table

The analysis of the soundness of UNSDCF’s result chain, in particular the linkage between the UNSDCF outcomes and outputs and national strategies and their priorities, is based on the following assumptions contained in the UNSDCF document.

- The UNSDCF is aligned with the National Development Strategies and their respective Action Plans, and all planning frameworks are aligned to Agenda 2030.

- The outcomes serve as a mutual accountability framework between the Government and UN system agencies.

| Priorities of the National Development Strategies | UNSDCF Outcomes | UNSDCF Outputs | Evaluation Team Analysis |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Alignment | Key Questions | Summary of Analysis |
| Policy Priorities - Effective, accountable institutions. - Equitable and easy access to justice services. - Rule of law and protection of human rights. Relevant National Policies and Strategies - The 2017-2030 State Concept on Demographic Security - State Policy Concept on Population Ageing - National Strategy for the Development of the Official Statistics of Georgia 2020-2023 - Decentralization Strategy 2020-2025 - Strategy on Development of High Mountain Settlements of Georgia (2019-2023) - Public Administration Reform (PAR) Roadmap (2015-2020) and the new PAR strategy for 2023-2026 - Public Service Design, Delivery, Quality Assurance and Pricing Strategy and its Action Plans for 2022-2023 and 2024-2025 - Open Parliament Action Plan 2021 2022 - Supreme Council of Ajara Openness Action Plan 2020-2021 - Migration Strategy 2021-2030 - Human Rights Strategy 2021 2030 - State Inspector’s Service Institutional Strategy 2021-2022 - Judicial Reforms Strategy (2017-2021) - Strategy on Reforming the Justice System Reform in Georgia 2019 - National Action Plan on Combating Trafficking in Persons 2019-2020 - 2020-2030 National Youth Policy Concept - 2020-25 State Youth Strategy and its Action Plan - Action Plan on Combatting Violence against Women and Domestic Violence and Protection of victims - National Human Rights Action Plan 2018-2020 - 2018-2020 National Action Plan of Georgia for Implementation of the UN Security Council Resolutions on Women, Peace and Security - National Strategy 2019-2023 for Labour and Employment Policy of Georgia - Action Plan 2019-2021 of the National Strategy for Labour and Employment Policy - Code on the Rights of the Child | Outcome 1. By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights, and increased representation and participation of women in decision making | Output 1.1 Inclusive national and local governance systems have greater resilience and capacities to mainstream gender, migration and ensure evidence-based and participatory policymaking, map and address inequalities and deliver quality services to all Output 1.2 National legislation and policies to eliminate discrimination, enhance human rights and equal access to justice in Georgia Output 1.3 Legislative frameworks, policies and governance systems deliver gender-equal results, combat GBV, violence against children and other harmful practices towards women and girls | Outcome 1 is aligned with SDGs 1, 5, 10, 16 and 17. Outcome indicators are also aligned with National SDG indicators. Output 1.1 is aligned with SDG Output Indicators 1.1.1, 1.1.2, 1.1.3, 1.1.4, and 1.1.5 Output 1.2 is aligned with SDG Output Indicators 1.2.1, 1.2.2, and 1.2.3 Output 1.3 is aligned SDG Output Indicators 1.3.1, 1.3.2, and 1.3.3 | Question 1: How were emerging issues identified and prioritized during the implementation of the UNSDCF? Question 2: How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3: What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 What are the institutional arrangements for horizontal and vertical policy and implementation coordination within the UN and between the UN and Government of Georgia? | A total of nineteen assumptions underpins the achievement of Outcome 1. All the assumptions, if realized, will help in meeting the SDG targets as well as the achievement of UNSDCF Outcome 1. The three outputs have the potential to contribute to the achievement of the outcome, as they address inequalities; governance systems, especially at the local level; access to justice; and women’s rights. However, the desk review and interviews held indicate that some of the assumptions, especially those related to governance, gender empowerment, independence and transparency of the justice systems, may not hold. The recent backtracking on commitments for gender empowerment (e.g. withdrawal of gender quotas), voice and space for civil society (e.g., enactment of the ‘Law of Georgia on Transparency of Foreign Influence 2024’), and incomplete agenda on judicial independence (e.g., non-fulfilment of EU AA conditions on judiciary), have made the implementation environment more complex. Coordination mechanisms between the government and the UN appear to be working smoothly, although this varies from UN agency to agency, and there is a |
| Policy Priorities - Equitable access to quality public services - Inclusion, equity, and gender-sensitive planning and delivery - Strengthened institutional capacities for delivery of services. Relevant National Policies and Strategies - The Vision for Developing the Healthcare System in Georgia by 2030 - 2017-2030 State Concept on Demographic Security - 2020-2030 National Youth Policy Concept - 2021-25 National Youth Strategy - 2017-2030 National Strategy on Maternal and Newborn Health and related Reproductive Health issues - Georgia HIV/AIDS National Strategic Plan 2019-2022 - 2021-24 National Action Plan on Combatting Violence against Women and Domestic Violence and Protection of victims - Comprehensive MYP for Immunization for Georgia, 2016-2021 - National Annual Immunization Plans - National Tobacco Control Strategy - Non-Communicable Disease National Strategy (2021-25) - Unified Strategy for Education and Science of Georgia 2017-2021 - National Human Rights Strategy of Georgia 2021-2030 - National Strategy 2019-2023 for Labour and Employment Policy of Georgia - Action Plan 2019-2021 of the National Strategy for Labour and Employment Policy - Code on the Rights of the Child. | Outcome 2 By 2025, all people in Georgia have equitable and inclusive access to quality, resilient and gender-sensitive services delivered in accordance with international human rights standards | Output 2.1 Improved national capacities for the implementation of policies and programmes that ensure equitable access to and coverage of quality integrated health and nutrition services and the exercise of reproductive rights for all people, particularly those left behind. Output 2.2 Improved national capacities for the implementation of policies and programmes that ensure inclusive and equitable access to quality educational programmes that meet international standards Output 2.3 Improved national legislation, policy, programs and capacities protect all people in Georgia, especially the most vulnerable and marginalized, against discrimination and ensure equitable access to and coverage of quality social services | Outcome 2 is aligned with SDGs 1, 3,4, 5, and 10. Outcome indicators are also aligned with National SDG indicators. Output 2.1 is aligned with SDG Output Indicators 2.1.1, 2.1.2, 2.1.3, 2.1.4, and 2.1.5 Output 2.2 is aligned with SDG Output Indicators 2.2.1, 2.2.2, and 2.2.3 Output 2.3 is aligned with SDG Output Indicators 2.3.1, 2.3.2, and 2.3.3 | Question 1: How were emerging issues identified and prioritized during the implementation of the CF? Question 2: How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3: What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How are the assumptions linked to the scope, pace, and quality of decentralization and PFM reforms? Question 5 How are principles of LNOB, gender equality, and inclusion used to guide implementation and oversight of progress? | The ToC has 12 assumptions for Outcome 1. Nine of the UN Agencies work to contribute to the Outcome. All of the assumptions, if realized will help in meeting the SDGs as well as the achievement of UNSDCF Outcome 1. The three outputs have the potential to contribute to the achievement of the outcome – as they address inequalities, especially in regards of access, coverage and quality of health services, access and quality of educational programs and social services. There is evidence e.g., in the health sector, of amendments in workplans and budget allocation to address emerging challenges specially during and in the wake of the COVID-19 crisis. |
| Policy Priorities - Sustainable, inclusive economic development - Enhanced competitiveness of SMEs and stronger, more resilient rural economy - High-skilled, productive labour force Relevant National Policies and Strategies - Human Rights Strategy 2014-2020 and Action Plan - Social-economic Development Strategy of Georgia – Georgia 2020 - National Strategy 2019-2023 for Labour and Employment Policy of Georgia - Action Plan 2019-2021 of the National Strategy for Labour and Employment Policy - Agriculture and Rural Development Strategy 2021-2027 - National Youth Policy Concept 2020-2030 - Georgia 2020 (Competitiveness of the Private Sector) - SME Development Strategy of Georgia 2016-2020 - State Migration Strategy 2021-2030 - Tourism Strategy of Georgia 2025 - State Strategy for Civic Equality and Integration and Action Plan for 2015-2020 - Regional Development Programme 2018-2021 - TVET Development Strategy 2013-2020 - Human Rights Strategy 2014-2020 and Action Plan - National Strategy 2019-2023 for Labour and Employment Policy of Georgia - Code on the Rights of the Child - 2020-2022 Programme for Integrated Development of Pilot regions of Georgia . | Outcome 3 By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia. | Output 3.1 Improved competitiveness and social responsibility of private sector | Outcome 3 is aligned with SDGs 1, 2, 5, 8, 9, and 10. Outcome indicators are also aligned with National SDG indicators. Output 3.1 is aligned with SDG Output Indicators 3.1.1, 3.1.2, 3.1.3, and 3.1.4 Output 3.2 is aligned with SDG Output Indicators 3.2.1, 3.2.2, 3.2.3, 3.2.3, and 3.2.4 Output 3.3 is aligned with SDG Output Indicators 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, and 3.3.8 | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How did the strategies under this output enhance the competitiveness of the private sector and contribute to increased social responsibility? Question 5 Were there any challenges in addressing the financing and capacity building needs of SMEs, particularly in rural areas? | The logical connection between Output 3.1 and Outcome 3 is strong, as the SDCF highlights the role of private sector competitiveness and social responsibility in driving sustainable economic growth. The document identifies the need for enhanced support for SMEs, particularly in rural areas, which aligns with the analysis. Targeted initiatives to support SMEs through access to finance, capacity building, and market access are essential to ensure that economic growth is inclusive and benefits all segments of society |
|  |  | Output 3.2 Sustainable and inclusive agricultural and rural development, strengthened food systems and improved livelihoods |  | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How effectively did the strategies under this output promote sustainable agricultural practices and strengthen food systems? Question 5: What measures were taken to integrate climate adaptation into agricultural development strategies? | The link between Output 3.2 and Outcome 3 is well-justified and supported by the SDCF, which emphasizes the importance of integrating climate adaptation strategies into agricultural development. The UNSDCF acknowledges the vulnerability of the agricultural sector to climate change and the need for climate-smart practices to ensure long-term sustainability. This output aligns well with the NDS’s goals for agricultural development and rural productivity. However, the UNSDCF’s strong emphasis on climate adaptation strategies is less pronounced in the NDS. |
|  |  | Output 3.3 Increased decent work, including productive employment, skills development and effective national social protection for all |  | Question 1: How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 In what ways did the strategies under this output address the need for decent work and skills development? Question 5 How were marginalized groups, such as women, youth, and people with disabilities, included in the implementation of these strategies? | Output 3.3 is crucial for achieving an inclusive economy, and the UNSDCF supports this by underscoring the importance of inclusive employment and social protection systems. The framework recognizes the progress made but also notes the need for additional efforts to ensure that marginalized groups, including women, youth, and people with disabilities, are fully included in employment and skills development initiatives. Tailored programs are necessary to enhance the participation of these groups in the labour market. The alignment between Output 3.3 and Outcome 3 is strong, with both the UNSDCF and the NDS emphasizing the importance of productive employment, skills development, and effective social protection. |
| Policy Priorities - Protection of human rights of vulnerable communities - Access to quality public services in conflict-affected areas Relevant National Policies and Strategies - Foreign Policy Strategy of Georgia 2019-2022 - Georgia’s State Strategy on IDPs - National Action Plan of Georgia for Implementation of the UN SCR on Women, Peace and Security - Georgia’s State Strategy on Occupied Territories – Engagement through Cooperation - Georgia’s peace initiative – “A Step to a Better Future” - Migration Strategy - Human Rights Strategy - Agriculture and Rural Development Strategy 2021-2027 - EU Georgia Association Agreement - Code on the Rights of the Child | Outcome 4 By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience | Output 4.1: Conflict affected communities have improved access to essential services, including education, healthcare, GBV response and legal assistance | Outcome 4 is aligned with SDGs 1, 2, 3, 4, 5, 11, and 16. Outcome indicators are also aligned with National SDG indicators. Output 4.1 is aligned with SDG Output Indicators 4.1.1, 4.1.2, and 4.1.3 Output 4.2 is aligned with SDG Output Indicators 4.2.1, 4.2.2, and 4.2.3 Output 4.3 is aligned with SDG Output Indicators 4.3.1, 4.3.2, and 4.3.3 | Question 1 How were emerging issues identified and prioritized during the implementation of the UNSDCF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How were data gaps addressed in conflict-affected areas? Question 5 What challenges were faced in measuring social cohesion, and access to public services? | The linkage between Outcome 4 and its three outputs is robust. There is a focus on addressing the needs and protecting the right of citizens in conflict-affected regions. By emphasizing the imperative of improving socio-economic conditions, and by highlighting delivery of and access to public services in conflict-affected communities, the ToC provides a strong framework for action. Given the challenges of delivery of services while ensuring that principles of LNOB, and needs of women and vulnerable groups are addressed, there would be a need for effective, results-oriented multistakeholder, cross-sector partnerships. This aspect is not as strongly highlighted in the assumptions as it could have been. |
|  |  | Output 4.2 Socio-economic conditions, community resilience and self-reliance improved with programmes benefiting conflict affected communities particularly those left behind |  |  |  |
|  |  | Output 4.3 Space widened for dialogue and participation that strengthens civil society, community resilience, social cohesion and implementation of the Women, Peace and Security agenda |  |  |  |
| Policy Priorities - Enhanced resilience to climate risks - Strengthened environmental governance and natural resource management Relevant National Policies and Strategies - Third National Environmental Action Programme of Georgia 2017-2021 - Agriculture and Rural Development Strategy 2021-2027 - National Biodiversity Strategy and Action Plan of Georgia 2014-2020 - Second National Action Program to Combat Desertification 2014-2022 - National Waste Management Strategy for 2016-2030 and Action Plan for 2022-2026 - Tbilisi Resilience Strategy - National Renewable Energy Action Plan - National Energy Efficiency Action Plan (2019-2020 - Law on Energy and Water Supply - Law on Energy Efficiency - Law on Energy Labelling - Law on Energy Efficiency of Buildings - Law on Promoting the Production and Use of Energy from Renewable Sources - New Forest Code - National Environment and Health Action Plan 2018-2022 of Georgia - Updated NDC/Paris Agreement - Climate Action Plan - Regional Development Programme 2018-2021 - Main Directions of the State Policy in Energy Sector of Georgia - Long-term Low Emission Development Strategy - Code on the Rights of the Child | Outcome 5 By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resources in Georgia. | Output 5.1 Strengthened governance frameworks for environmental sustainability and climate resilience. |  | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How are governance frameworks being strengthened to support both environmental sustainability and climate resilience at the national and local levels? Question 5: What specific policies have been most effective in integrating climate considerations into governance structures? | The link between Output 5.1 and Outcome 5 is important, as strong governance frameworks are essential for advancing environmental sustainability and climate resilience. This output supports the creation and enforcement of policies that integrate climate considerations into national and local governance structures. By ensuring that these frameworks are well-implemented, Output 5.1 plays a critical role in building the institutional capacity needed to manage environmental risks and respond to climate challenges effectively. Both the UNSDCF and NDS emphasize the importance of governance frameworks to achieve environmental sustainability and climate resilience. The NDS supports the development of policies and regulations that strengthen environmental governance, ensuring that they are implemented effectively at all levels. |
|  |  | Output 5.2 Promotion of climate-smart agricultural practices and sustainable land management. |  | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 Which climate-smart agricultural practices have been most effective in mitigating the impacts of climate change on agriculture? Question 5 How are sustainable land management practices being promoted and adopted across different regions of Georgia? | Output 5.2 is directly connected to Outcome 5 through its focus on promoting climate-smart agricultural practices and sustainable land management. These practices are crucial for mitigating the impacts of climate change on agriculture, a key sector in Georgia’s economy. By encouraging the adoption of sustainable practices, this output helps to protect natural resources, enhance food security, and increase the resilience of rural communities. This output’s focus on sustainable land management also ensures that land resources are used efficiently, preserving them for future generations while supporting current economic activities. |
|  |  | Output 5.3 Ensured equitable access to natural resources and climate adaptation measures for all communities. | The connection between Output 5.3 and Outcome 5 is particularly important in the context of social equity. Ensuring equitable access to natural resources and climate adaptation measures is vital for protecting vulnerable communities from the adverse effects of climate change. This output emphasizes the need for inclusive strategies that allow all segments of society, especially those most at risk, to benefit from climate adaptation and resource management efforts. | Question 1 How were emerging issues identified and prioritized during the implementation of the CF? Question 2 How frequently were the UNSDCF objectives reviewed to ensure alignment with evolving government priorities? Question 3 What mechanisms were used to adjust the UNSDCF implementation in response to these emerging issues? Question 4 How is equitable access to natural resources being ensured for vulnerable communities in the context of climate adaptation? Question 5 What measures are in place to monitor and assess the effectiveness of climate adaptation strategies in reaching all segments of society? | The UNSDCF strongly emphasizes equitable access to natural resources and climate adaptation measures, ensuring that all communities, particularly vulnerable ones, are protected. The NDS supports these objectives but does not reflect on the inclusivity in resource management. |

Annex 12: Status of progress on outcomes

| OUTCOMES | OUTCOME INDICATORS | Progress |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 | 2023 | STATUS |
| Outcome 1: By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights¹¹ and increased representation and participation of women in decision making | 1.1 Voice and Accountability Index NSDG 16.6.2.2 (Global Target (GT) 16.6) Custodian: UNDP Contributors: UNFPA, UNICEF, UN Women, UNOHCHR, ILO, IOM | Supported policy reforms; engaged over 30 CSOs in governance reforms, including 15 led by women/youth, across 8 municipalities. | 80% of planned governance initiatives achieved, with 7 municipalities implementing participatory processes. | 85% of governance reforms implemented across 64 municipalities; 91 CSOs trained and engaged in governance improvements. | Partially Achieved |
|  | 1.2 Rule of Law Index NSDG 16.6.2.5 (Global Target (GT) 16.6) Custodian: UNDP Contributors: UNFPA, UNICEF, UN Women, UNOHCHR, ILO, IOM, UNODC | Approved 8 of 15 policy documents, achieving 53% of planned reforms. Trained 300 municipal officials in accountability practices. | Achieved 70% of policy goals; rule of law standards improved in 15 municipalities through legal and governance reforms. | Over 90% of reform targets met; trained over 1,200 local officials in rule of law and governance. | Achieved |
|  | 1.3 Proportion of women aged 15-49 years who make their own informed decisions regarding sexual relations, contraceptive use and reproductive health care NSDG: 5.6.1 (GT) 5.6) Custodian Agency and Lead Reporter: UNFPA Contributor: UN Women | 63.8% of 2,038 training participants were women, supporting their roles in governance and decision-making. | Increased to 68% female participation in civil service training across 24 municipalities; though no direct reproductive health data, training indirectly supported this area. | Female engagement continued at 70% in training, indirectly supporting roles in reproductive health and family planning decision-making. | Partially Achieved |
|  | 1.4 Disaggregated data from Population and Housing Census 2023 publicly accessible online for evidence-based policy making, mapping and addressing inequalities and SDG monitoring Custodian: UNFPA | No census data collected in 2021. | The 2020 Round Population Census will be undertaken in Nov-Dec 2024 and consequently, Census preliminary data will be published by June 2025 | The 2020 Round Population Census will be undertaken in Nov-Dec 2024 and consequently, Census preliminary data will be published by June 2025 | Not achieved |
|  | 1.5 Proportion of women aged 20-24 years who were married or in a union before age 18 NSDG: 5.3.1 (GT 5.3) Lead Reporter: UNFPA Contributors: UNICEF, UN Women | No direct data; supported gender equality through 30+ programs addressing community norms and youth engagement. | Gender equality programs reached 75% of planned outreach, though child marriage data was not specifically tracked. | Gender equality frameworks in place across 64 municipalities, addressing empowerment broadly; early marriage data not specifically available but covered in gender equality initiatives. | Partially Achieved |
|  | 1.6 Women in decision-making 1. Proportion of seats held by women in (a) national parliaments and (b) local governments (SDG indicator 5.5.1) (GT5.5) 2. Proportion of elected women mayors (country-specific indicator SDG 5.5.1.1) (GT 5.5) 3. Proportions of women in the judiciary (country-specific indicator 16.7.1.3) (GT 16.7) 4. Proportion of women in I and II rank positions (country-specific indicator 5.5.2.1) (GT 5.5) Custodian: UNDP Contributors: UN Women, UNFPA | 63.8% of civil servant trainees were women, showing strong female participation in governance. | Women held approximately 45% of decision-making roles in target municipalities; new policies reinforced women’s leadership in government. | Women represented around 50% of those in municipal leadership programs, with continued growth in representation in governance across 64 municipalities. | Partially Achieved |
| Outcome 2: By 2025, all people in Georgia have equitable and inclusive access to quality, resilient and gender-sensitive services delivered in accordance with international human rights standards | 2.1. Maternal Mortality Ratio NSDG: 3.1.1 (Global Target (GT) 3.1) Lead Reporter: UNFPA Contributors: WHO, UNICEF | 35 per 100,000 live births (baseline). Targeted reduction of 28.5% to reach 25 per 100,000. | Reduced by 20% to 28 per 100,000 due to improved maternal health services. | Slight increase to 35.4 per 100,000 due to healthcare strain during COVID-19. | Partially Achieved |
|  | 2.2. Under-five mortality rate NSDG: 3.2.1 (GT 3.2) Lead Reporter: UNICEF Contributors: WHO, UNFPA | 10.8 per 1,000 live births (baseline), with programs targeting a 10% reduction. | Decreased to 9.3 per 1,000, representing a 14% improvement from the baseline. | Achieved 8.7 per 1,000 live births, a further 6.5% reduction. | Partially Achieved |
|  | 2.3 Gender Development Index (GDI) NSDG: 5.2 (GT 5.2) Lead Reporter: UNDP Contributors: UN Women, UNFPA | 0.988 score (baseline) with focus on maintaining gender parity. | Improved to 0.991, marking a 0.3% increase from 2021 due to gender parity programs. | Maintained at 0.991, with continued focus on gender equality. | Partially Achieved |
|  | 2.5 Percentage of women and girls who experience violence and seek help from formal institutions Lead Reporter: UN Women Contributor: UNFPA | Approx. 34% of survivors accessed formal institutions for support, with programs targeting a 10% increase in help-seeking behavior. | Increased to 38%, marking a 4% improvement due to awareness campaigns. | Reached 41%, indicating a further 7.9% increase over the baseline. | Partially Achieved |
|  | 2.5 Number of out of school children (OOSC) (primary and secondary school age) NSDG 4.1.2 (GT 4.1) Lead Reporter: UNICEF | 8,000 children dropped out (baseline); re-enrolment efforts aimed to decrease this by 5%. | Reduced to 7,500 children out of school, achieving a 6.25% reduction from baseline. | Further reduced to approx. 7,000 children, totaling a 12.5% reduction from 2021. | Partially Achieved |
|  | 2.6 Number of new HIV infections per 1000 population, by sex and age NSDG: 3.3.1. (GT 3.3) Lead Reporter: UNFPA Contributors: WHO, UNICEF, UNDP, UNODC | 0.9 per 1,000 (baseline); awareness and prevention targeted a 22% reduction. | Reduced to 0.7 per 1,000, achieving a 22.2% decrease from baseline. | Dropped to 0.6 per 1,000, a 33.3% reduction from the initial baseline. | Achieved |
|  | 2.7 Mortality rate attributed to cardiovascular disease, cancer, diabetes and chronic respiratory disease NSDG 3.4.1 (GT 3.4) Lead Reporter: WHO Contributor: UNFPA | 27.5 per 100,000 (baseline), with public health programs aimed at a 6% reduction. | Decreased to 25.8 per 100,000, marking a 6.18% improvement due to enhanced health programs. | Stable at 25.8 per 100,000, maintaining the gains achieved in the prior year. | Partially Achieved |
| Outcome 3: By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia | 3.1. Proportion of population, including children, living below the national poverty line, by location (urban/rural) and by sex NSDG: 1.2.1 (Global Target (GT) 1.2) Custodian: FAO Contributing: UNICEF, UNDP, IOM, UNIDO, IFAD, ILO, UN Women | 17.5% of the population lived below the national poverty line, with child poverty at 22.7% and rural poverty at 21.3%​ | 15.6% of the population lived below the national poverty line, with child poverty at 20.4% and rural poverty at 20.6%​.​ | 11.8% of the population lived below the national poverty line, with child poverty at 16.0% and rural poverty at 15.6%​. | Work in Progress |
|  | 3.2 Unemployment rate by rural/ urban by sex, age and persons with disabilities) NSDG 8.5.2 (GT 8.5) Custodian: UNDP Contributing: FAO, UNIDO, UN Women, IOM, IFAD, ILO | National unemployment rate at 19%; higher rates observed in rural areas and among persons with disabilities. Disabled persons’ employment lower by 30%​ | Engaged 40,000 low-income beneficiaries in Public Works Program, focusing on job opportunities for the disabled and rural youth​ | Public Works Program continued; employment initiatives increased among low-income households, though specific rural/urban unemployment data not detailed​ | Partially Achieved |
|  | 3.3 Gender pay gap NSDG: 8.5.1. & 5.5.1.2.; (GT 8.5 and 5.5) Custodian: UN Women Contributor: ILO | Women’s earnings were 3% lower than men’s on average; gender wage disparity programs were initiated to promote pay equity​ | No significant pay gap changes reported; efforts in addressing wage disparities across multiple sectors continued​ | Ongoing efforts to bridge the pay gap; exact gender pay gap data unreported but increased wage support initiatives noted​ | Work in Progress |
|  | 3.4 Labour force participation rate, by sex and age NSDG: 8.5.2 (GT 8.5) Custodian: UN Women, Contributor: ILO | Total: 50.9%, women 40.5%, men 62.9% (GEOSTAT 2021) | Total: 51.9%, women 41.5%, men 64% (GEOSTAT 2022) | Total: 53.3%, women 43.1%, men 65.1% (GEOSTAT 2023) | Partially Achieved/ No target has been set |
| Outcome 4: By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience | 4.1 World Governance Indicator on Political Stability and Absence of Violence/Terrorism Custodian/Lead Reporter: UNDP Contributors: UN Women, UNHCR, UNFPA, FAO, UNODC | Engaged 12 CSOs in stability-building projects, achieving 40% of target for foundational activities​ | Expanded to 25 CSOs, covering 70% of community resilience goals, with key stability projects launched in conflict-affected areas​ | Achieved 90% of target stability initiatives, engaging over 35 CSOs in conflict-prone areas across Georgia​ | Partially Achieved |
|  | 4.2 Global Peace Index (GPI) Custodian/Lead Reporter: UNDP Contributor: UN Women; UNHCR, UNFPA, FAO | 30% of target achieved through initial dialogue and cross-community efforts; 8 CSO projects focused on peacebuilding​ | Increased efforts reached 60% of peace goals, with 18 CSOs implementing cross-community programs​ | 85% target completion, with 28 CSO-led dialogue initiatives promoting community resilience​ | Partially Achieved |
|  | 4.3 Positive Peace Index (PPI) Custodian/Lead Reporter: UNDP Contributor: UN Women, UNHCR, UNFPA, FAO | Initiated 7 CSO-led activities for peace, achieving 25% of target for foundational peacebuilding​ | 55% completion with 15 grassroots initiatives supporting local resilience | 75% progress with over 20 regional peace initiatives and community collaboration across affected areas​ | Partially Achieved |
|  | 4.4 Women, Peace and Security Index Custodian/Lead Reporter: UNDP Contributor: UN Women | Involved 6 women-led CSOs, achieving 40% of the target for women in peacebuilding roles​ | Increased to 12 women-led organizations, 65% target progress, with expanded women’s participation in security discussions​ (Confidential-Final Eval…) | Reached 90% of target, with 20 women-led CSOs involved in leadership across peace and security programs​ | Partially Achieved |
| Outcome 5: By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resources in Georgia | 5.1: Number of countries that have communicated the establishment or operationalization of an integrated policy/strategy/ plan which increases their ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other). NSDG Indicator 13.2.1 (Global Target (GT) 13.2) Lead Reporter: UNDP Contributors: FAO, UNIDO, UNECE, UNEP | Initial drafting completed; foundational assessments in 3 sectors (agriculture, energy, and water) covered approximately 30% of the total plan development needed. | Draft adaptation plan completed for 5 sectors (agriculture, water, forestry, health, energy) with around 75% completion of the overall policy establishment through stakeholder engagement and draft review. | National Climate Adaptation Strategy fully operationalized, representing 100% completion of policy establishment with integration into Georgia's NDC and biennial submission to the UNFCCC. | Achieved |

| REFERENCES FOR THE OUTCOME AND OUTPUT MAPPING |  |
| --- | --- |
| Outcome 1: By 2025, all people in Georgia enjoy improved good governance, more open, resilient and accountable institutions, rule of law, equal access to justice, human rights¹¹ and increased representation and participation of women in decision making | Final Evaluation- Final Report Supporting Public Administration Reform in Georgia For: UNDP Georgia and Government of the United Kingdom BY Anthony Costanzo Business and Government Strategies International USA Date: 2 July 2021 |
|  | UNDP GEORGIA CONSOLIDATING PARLIAMENTARY DEMOCRACY IN GEORGIA FINAL PROJECT EVALUATION EVALUATION REPORT February 2023 |
|  | UNDP Georgia FINAL EVALUATION REPORT Final External Evaluation of the “Fostering Decentralization and Good Governance at the Local Level in Georgia- DGG –” Project Funded by the Ministry of Foreign Affairs of Denmark, and co-funded by the Ministry of Regional Development and Infrastructure of Georgia (MRDI) Executed by UNDP under National Implementation Modality for an amount of USD 4,075,519.45 By: Christian Bugnion de Moreta, Evaluation Consultant Final evaluation report 22 January 2024 |
|  | UNDP Georgia EDITED FINAL EVALUATION REPORT Final External Evaluation of the “Fostering Regional Local Development in Georgia- FRLD – Phase 2Project Funded by the Swiss Agency for Development Cooperation and the Austrian Development Cooperation and co-funded by the Minister Regional Development and Infrastructure Georgia Executed by UNDP under National Implementation Modality for an amount of USD 5,521,772.-- By: Christian Bugnion de Moreta, Team Leader and Rusudan Kardava, National expert Draft evaluation report 7th February 2022 |
| Outcome 2: By 2025, all people in Georgia have equitable and inclusive access to quality, resilient and gender-sensitive services delivered in accordance with international human rights standards | UNFPA Maternal Mortality Report 2024 |
|  | National Birth Registry 2022 |
|  | Seeking health and medical care abroad: A Rapid Situational Analysis on the Drivers of Health-related Migration from Georgia Mzia Tabatadze MD. MPH. PhD Tbilisi, Georgia June 20, 2024 |
|  | IOM SERVICE HUBS Achievements, lessons learned and opportunities for further development |
|  | UNPRPD 2nd annual report |
| Outcome 3: By 2025, all people without discrimination benefit from a sustainable, inclusive and resilient economy in Georgia | GEORGIA SOCIAL PROTECTION SYSTEM READINESS ASSESSMENT UNICEF May, 2020 |
|  | March 2024 Social protection of children in Georgia: Challenges and recommendations Analytical report |
|  | Women and Children with Disabilities Report] |
|  | UNICEF Georgia Country Office ¦ UNICEF Europe and Central Asia Region January 2022 CASE STUDY: See every Colour: addressing stigma against children with disabilities and supporting their social inclusion through social and behavior change interventions. |
|  | Report of final evaluation of the joint SDG Programme “Transforming Social Protection for Persons with Disabilities in Georgia” Programme implemented by UNICEF, UNFPA, OHCHR, UN Women, WHO, UNDP Programme funded by Joint SDG fund Consultant: DEPA Consulting August 2022 |
|  | Report ESTIMATING THE IMPACT OF COVID-19 ON CHILD POVERTY IN GEORGIA USING A MICRO-SIMULATION MODEL Prepared for UNICEF by Development Analytics |
| Outcome 4: By 2025, conflict affected communities enjoy human rights, enhanced human security and resilience | Quarterly Progress Report 1 October – 31 December 2022 “USAID Partnering for Resilience Program” Agreement No. 72011422IO00003 Prepared for: USAID/Georgia 29 Georgian-American Friendship Avenue Tbilisi 0131, Georgia |
|  | EU-UN Joint Programme on Improving Vocational Education in Abkhazia, Georgia https://open.undp.org/projects/00113232 Mid-Term Evaluation 31.08.2021 |
|  | Final Evaluation Joint EU-UNDP Civil Society Support Programme Phase II 1 July 2020 – 30 June 2023 April 2023 |
|  | Final Evaluation UNDP/UNICEF Horizons Project Strengthening Community Resilience in Abkhazia funded by USAID Project ID 00100478 Olena Krylova |
|  | Final Evaluation UK Fund for Sustainable Peace (Complementary Initiative to COBERM) 15 October 2020 - 30 September 2023 Elinor Bajraktari and Rusudan Kardava September 2023 |
|  | Evaluation of COBERM for UNDP Georgia Final Report André Kahlmeyer Rusudan Konjaria Conflict Management Consulting (CMC) www.cmc-consulting.org info@cmc-consult.eu |
| Outcome 5: By 2025, all people, without discrimination, enjoy enhanced resilience through improved environmental governance, climate action and sustainable management and use of natural resources in Georgia | Mid-Term Evaluation Final Report UNDP Project “Strengthening the Climate Adaptation Capacities in Georgia” |
|  | Terminal Evaluation GEF Project ID: 4835; PIMS No. 4732 Expansion and Improved Management Effectiveness of the Achara Region’s Protected Areas |
|  | FAO-GEF Project Implementation Report 2021 – Revised Template Period covered: 1 July 2020 to 30 June 2021 |
|  | FAO-GEF Project Implementation Report 2022 – Revised Template Period covered: 1 July 2021 to 30 June 2022 |
|  | FAO-GEF Project Implementation Report 2023 Period covered: 1 July 2022 to 30 June 2023 |

Annex 13: Progress on outputs

| Indicator | Baseline | 2021 Progress | 2022 Progress | 2023 Progress |
| --- | --- | --- | --- | --- |
| 1.1.1: Percentage of the population satisfied with their last experience of public services (by sex) | Ratio of population in 2015 satisfied with services received during the previous 12 months from the following institutions: 112: 91%; Police: 70%; Public Service Hall - 96%; Mayor's office - 57% | · Satisfaction with Local Self-Governments (Mayor’s Office, Sakrebulo): 60.62% (female 61.5%, male 59.6%) · Public Service Hall (2019 data): 58%. · Georgian Police (2019 data): 43%. | No update; next survey planned for 2023. | According to the poll, 54% of respondents feel the government is performing well, reflecting a notable increase in satisfaction compared to prior results. Specifics on public service satisfaction by sex, however, are not available in this survey summary. (https://civil.ge/archives/573751) |
| 1.1.2: For the facilitation of the integration of foreigners, including refugees, returned migrants, humanitarian status holders, immigrants with the right of residence and stateless living in Georgia the existence of: a) institutional and b) legal framework | · Refugees, humanitarian status holders, stateless: a) partially, b) partially. · Immigrants with right of residence: a) No, b) No. · Returned migrants: a) Yes, b) No. | · Refugees: a) not yet achieved, b) not yet achieved. · Immigrants: a) not yet achieved, b) not yet achieved. · ∙ Returned migrants: a) achieved, b) achieved. | Same as 2021. | · Refugees: a) achieved, b) not yet achieved. · Immigrants: a) not yet achieved, b) not yet achieved. · Returned migrants: a) achieved, b) achieved. |
| 1.1.3: Number of policies/procedures adopted by the Government of Georgia that aim at improvement of institutionalization of gender equality and gender mainstreaming | · 1 policy: Gender Equality Law (2010). · National Action Plan for 2018-2020. | 2 policies adopted, 3 submitted for approval. | 6 new policies adopted. | 7 new policies adopted. |
| 1.1.4: The capacity and professionalism of male and female public servants at local and national levels strengthened to better serve their constituency | · a) Data on professional development plans to be established. · b) 15% of public servants attended professional development courses | · a) 47% of agencies fulfill plans. · b) 50% of public servants improve skills (615 public servants trained). | · a) 27% of agencies fulfill plans. · b) 37% of public servants improve skills (various trainings provided). | · a) 35% of agencies fulfill plans. · b) 22% of public servants fulfilled their learning plans (1,109 public servants). |
| 1.1.5: Quality/level of evidence-based and participatory law-making processes and executive oversight | Score of 59/100. | No data (study conducted every 4 years) | No data available. | Not available for 2023, as the next National Integrity System (NIS) assessment will be conducted by the Transparency International – Georgia in 2024 and therefore, results will be available later in 2024 or 2025 the latest. |
| 1.2.1 Number and/or percentage of people, including juveniles, in contact with justice and administrative bodies, including collective labour dispute cases, who are subject to a diversion order or alternative measure for dispute resolution or custodial sentence [related to NSDG 16.3.1.1.] (GT 16.3) Custodian: ILO Contributors: UNICEF, UNDP, UNODC | 1/ Baseline 2013-2020 (as of July 2020): 250 court mediation civil cases referred to 4 mediation courts centers in Tbilisi, Gori, Rustavi and Mtskheta Juveniles – 59% 2/State labour dispute mediation services: 4 mediation cases in 2019 3/ Number of Collective Bargaining Agreements concluded at sectoral and enterprise levels: 4 in 2019 | Nearly 150 referrals to mediation in civil cases through three court mediation centers in 2021; Diverted juveniles in 2021 – 80% (unpublished data, not for public distribution until March 2022); 5 collective dispute mediation agreements signed in 2021. 9 enterprise-level collective bargaining agreements concluded in 2021. | The rate of diversion in 9 months of 2022 - 81% - out of cases meeting diversion criteria (source: General Prosecutor’s Office). 6 collective dispute mediation agreements signed in 2022. | The rate of diversion for 12 months of 2022 stands at 80%. 4 collective dispute mediation agreements were signed in 2023. |
| 1.2.2 Implementation Rate of the National Human Rights Strategy 2021- 2030 NSDG 16.3.1.1. (GT 16.3) Custodian: UNDP Lead reporter: OHCHR Contributors: UNICEF, UN Women, UNFPA | National Human Rights Strategy 2021- 2030 is in the process of elaboration |  |  | In March 2023, the Parliament approved the Strategy followed by the adoption of its Action Plan 2024-2026 in December 2023. |
| 1.2.3 % recommendations accepted in the 3rd cycle of UPR implemented or actions taken; % recommendations by UN Treaty Bodies and Special Rapporteurs implemented or actions taken; % issues of non-conformity raised in comments of the ILO supervisory bodies implemented. Custodian: OHCHR Contributor: ILO, UN Women, UNFPA, UNDP NSDG (Crosscutting) | 2013: Mid-term evaluation of implementation of 2nd cycle compiled by UPR-Info 99/133 assessed accepted recommendations (74.4%) fully or partially implemented 2017: 4 issues assessed by the UN Human Rights Committee as follow-up to the recommendations issued by this Committee in 2013. 1 received a grade of A, 2 received a grade of B, 1 received a grade of C As of November 2019, the Supervisory Bodies of the ILO have raised 13 issues of non-conformity with regard to the application of the 8 Fundamental Human Rights Conventions and 1 of the Governance Convention (C122) of the ILO. | 257 3rd cycle UPR recommendations accepted. The comments of the 2021 session of the ILO CEACR will not be public until February/March 2022. | Georgia was reviewed by the UN Human Rights Committee and CERD in 2022. Georgia will be reviewed by CEDAW and CRPD in 2023. | A number of UPR recommendations reflected in the National Human Rights Strategy and action plan for 2024-2026. CERD published its concluding observations on the combined ninth and tenth periodic reports of Georgia on 13 December 2022. Georgia submitted its follow-up to the concluding observations on 28 December 2023, reflecting progress in several areas, including the implementation of the parliamentary Code of Ethics, raising awareness regarding ethics and general rules of behavior in the civil service, elimination of sexual harassment in the workplace, combating hate speech, promoting equality, and addressing non-discrimination issues. CEDAW issued its concluding observations on the sixth periodic report of Georgia on 2 March 2023. However, data on the implementation rate is not available. CRPD published its concluding observations on Georgia's initial report on 18 April 2023. Similarly, the implementation rate is not available. |
| 1.3.1. Adopted and costed EVAW & DV NAP and its implementation rate NSDG 5.1.1 | Yes (Current EVAW & DV NAP covers 2018-2020) - implementation rate to be determined in 2021. | EVAW & DV National Action Plan (NAP) was developed in 2021. Adoption of NAP is delayed. | EVAW & DV NAPs were adopted in late 2022. | EVAW & DV NAP was adopted in late 2022. The implementation is on track. |
| 1.3.2. Proportion of males and females, subjected to physical, psychological or sexual violence by sex and age in the previous 12 months. NSDG 16.1.1.3. | 2017: Female - 3.2% * Note: Includes only for women: physical, psychological or sexual violence on the part of the partner and sexual violence on the part of the non-partner 69% of children 1-14 experience any type of violent discipline in the last month | 56.2 % of children were subject to any type of violence disciplining method in 2021. Disaggregation by sex: male -57.6%; female – 54.7% Source – Real Time Monitoring Survey (MICS Plus) by GeoStat https://www.geostat.ge/ka/mics-plus N/A on violence against women. | N/A on violence against women. New data to become available in 2023 as GEOSTAT and UN Women will finalize the National Violence against Women Study. | 18.2% of women and girls aged 15-64 have experienced at least one form of violence in the past 12 months. 50.1% of women and girls aged 15-64 have experienced at least one form of violence in their lifetime. 31% of children were subject to any type of disciplining method in 2022. Disaggregation by sex: male – 34.8%; female – 26.3% per Child Welfare Survey in GEORGIA 2023 conducted in cooperation with the National Statistics Office of Georgia available at: https://www.unicef.org/georgia/reports/child-wellbeing-georgia-2023 |
| 1.3.3. Proportion of ever-partnered women and girls aged 15-64 subjected to physical, sexual or psychological, violence by a current or former intimate partners a) previous 12 m. b) lifetime by form NSDG 5.2.1 | a) 3.5 % of women (aged 15-64) experienced physical, sexual and/or psychological intimate partner violence (IPV); 3.2% of women experienced psychological abuse; 2.8% of women experienced economic abuse; and 1% experienced physical and/or sexual violence by a partner within the previous 12 months (2017) b) 13.6 % of women (aged 15-64) experienced physical, sexual and/or psychological intimate partner violence; 13% of women experienced psychological abuse; 9.6% of women experienced economic abuse; and 6% experienced physical and/or sexual violence by a partner in her lifetime (2017) | N/A. New data to become available in 2023 as GEOSTAT and UN Women will conduct the National Violence against Women Study in 2022-2023. | No data available till 2023 | Any type of violence experienced from intimate partner (women aged 15-69)– 22.9% (lifetime), 9% in the last 12 months Source: National Violence against Women Study in 2022. P. 55, table 5.1 a) In previous 12 month Physical –0.6% Sexual – 0.4 % Psychological – 8.7 % Economic – 2.1 %. b) In lifetime Physical – 5.1 % Sexual – 3.0 % Psychological – 20.5 % Economic – 7.2 %. |
| 2.1.1. Coverage with at least eight (8) antenatal care visits (ANC) NSDG: 3.1.1 (GT 3.1) Lead Reporter: UNFPA Contributors: UNICEF, WHO | 42% (2019) Actual in 2020 – 35%; according to NCDC statistical Yearbook (2020). Provision of Antenatal Care services continued despite COVID-19 epidemic-related lockdown & travel restrictions, but utilization deteriorated. Coverage with at least 6 ANC visits, the most critical ones, was almost 70%. | 37,8% (NCDC) Despite the COVID-19-related lockdown & travel restrictions, coverage with 8 ANC visits increased in comparison to 2020, and almost equaled to pre-COVID year of 2019 data, the utilization deteriorated. Based on the ANC regionalization model, a nationwide assessment of over 150 ANC facilities was conducted. | 37% (data was obtained from NCDC in response to a request made by UNFPA, data are not published yet) | 38.5%[3] |
| 2.1.2. Elimination of mother-to-child transmission (EMTCT) of HIV and Syphilis achieved NSDG: 3.3.1 (GT 3.3) Lead Reporter: WHO Contributors: UNFPA, UNICEF | No (2020) |  | EMTCT Assessment conducted; National EMCT Action Plan 2022-2024 developed; The National validation report drafted to be submitted to the WHO Regional Validation Council. | The assessment of EMTCT status for HIV, HBV and syphilis was conducted. The National EMTCT Action Plan for the period of 2022-2024 has been updated with the UN joint support, and expanded to cover the elimination of Hepatitis B. |
| 2.1.3. Number of encounters with the Primary Health Care (PHC) units/outpatients facilities, providing essential health services per capita/per year NSDG 3.8.1 (GT 3.8) Lead Reporter: WHO Contributors: UNICEF, UNFPA | 3.6 visits (2019) | Number of encounters with the PHC units/outpatient facilities, providing essential health services per capita/per year: 12807695 (3.4 visits). The decrease may be attributed to COVID-19. Available data: in 2021 the number of total encounters with outpatient facilities was 4.4 (incl. children under 15, ambulance calls and ambulance calls for under 15) Encounters with physicians: 4. https://test.ncdc.ge/Handlers/GetFile.ashx?ID=b3956fe5-2a48-4fc1-9a5a-37d13c6d397f |  | In 2023 the number of total encounters with outpatient facilities was 4.4 (incl. children under 15, ambulance calls and ambulance calls for under 15) Encounters with physicians. |
| 2.1.4 Share of districts with DTP3 containing vaccine coverage below 80 per cent NSDG 3.8.1 (GT 3.8) Lead Reporter: UNICEF Contributors: WHO Adjusted formulation: District or equivalent administrative unit with at least 80% coverage of measles-containing vaccine for children < 1 year receiving (21-02-L2-05) NSDG 3.8.1 (GT 3.8) | 1.3% (2018) Adjusted: 92.8 (2018) | District or equivalent administrative unit with at least 80% coverage of DTP-containing vaccine for children < 1 year: 60% 63% | 92% | 93.8% |
| 2.1.5 Age-standardized prevalence of current tobacco use among persons aged 15 years and older NSDG 3.a.1 (GT 3.a) Lead Reporter: WHO Contributors: UNICEF, UNFPA | Both – 29.7% Men – 54.2% Women – 5.2% (2018) | Prevalence of current tobacco use among 18–69-year-olds decreased from 31% in 2016 to 27,5% in 2020. No estimation of age-standardized prevalence of current smoking among 15+ aged has been conducted in 2021. | No study available since 2020 on prevalence of tobacco use. | No study available since 2020 on prevalence of tobacco use. Field work for the Global Adult Tobacco Survey (GATS) has been planned for 2024 and results will be available in 2025. Despite short-term achievements in tobacco control, sustainability of this progress is under question due to aggressive marketing of novel tobacco products and intensified interference of tobacco industry in the state policy and legislation in recent years[4]. |
| 2.2.1: Participation of children in organized educational process, by sex, by ethnicity (one year before the official school age) NSDG: 4.2.2 (GT 4.2) | Total: 89.6%; boys: 87.5%; girls: 92.2%; Georgian: 93.5%, Azeri: 48%, Armenian: 76.1%. | No data | RTM/MICS Plus indicates a drop in preschool attendance (66%). | Total 90.9% (Boys: 95.8%, Girls: 86.1%) |
| 2.2.2: # of children with special educational needs (SEN) and/or children with disabilities (CWD) participating into mainstream education, NSDG 4.a.1 (GT 4.a) | 7,371 school-age children with disabilities (CWD) out of 11,500 mainstreamed. | 10,482 students with SEN | 11,461 students with SEN | 12,801 students with SEN |
| 2.2.3: Human Rights, gender equality and/or reproductive health and rights issues are integrated into the teachers’ a) pre- and b) in-service training programmes/ systems NSDG: 4.c.1 (GT 4.c) | · a) No; · b) No | Recommendations developed; cooperation with TPDC, syllabi updated, and educators trained. | Capacity building for universities and teachers, training programs initiated. | Pre- and in-service training programs strengthened; new bachelor programs launched. |
| 2.3.1: Improved inclusive and gender sensitive legislation and policy ensuring the rights of all PwDs, NSDG: 10.3.1 (GT 10.3) | · No gender-sensitive strategy or annual action plans; legislation not aligned with international standards. | Action plans adopted; National Accessibility Plan in progress. | 3 rounds of annual action plans adopted; Accessibility Plan pending. | Additional action plans adopted; draft laws on web accessibility developed. |
| 2.3.2: Capacity of systems and institutions improved to deliver rights-based and integrated social services, including for persons with disabilities and victims of trafficking in human beings (THB), NSDG: 1.3.1 (GT 1.3) | · a) No national guidelines for SRHR and GBV services. · ∙ b) No local action plans for social services in selected municipalities. | SRHR policy and service delivery solutions developed | SOP for GBV response amended; Action Plans adopted in 2 municipalities. | SOPs further refined; Action Plans adopted and funded in 2 municipalities. |
| 2.3.3: Number of shelters and crisis centers for DV victims/survivors functional funded from the State Budget, NSDG 5.2.1 (GT 5.2) | 5 shelters, 5 crisis centers | No major progress; renovation work for a new shelter initiated. | Renovation pending completion. | 6 shelters; a new shelter opened in Tbilisi with 15 additional beds. |
| 3.1.1: Number of new services introduced by providers within business development infrastructure, including innovations, ecosystem and formalizing informal enterprises | Limited number of services. | 2 new services introduced (Labour Safety services and Environmental Self-Scanning for packaging companies). | 3 new services introduced (financial reporting systems for SMEs, EPR implementation, Batumi co-working/networking service). | Not specified for 2023. |
| 3.1.2: % of companies in selected clusters demonstrating at least 20% growth rate in turnover or export | 0%. | 51% of companies showed at least a 15% increase in sales (23 out of 45 PMAG member companies). | Same as baseline. The next data update will be available in 2023, according to the GeoStat. UNDP, 2022 figures will be available in Mar 2023 | Market Development Initiatives: FAO and EU Support: Initiatives generated 250,000 GEL in sales for 55 producers in 2023, suggesting positive growth in turnover within this cluster. Diaspora-Led Market Expansion: Spain Market Entry: With diaspora support, nine Georgian companies introduced 9,000 products in Spain via the "Georgian Corner" in Madrid, increasing market exposure and likely turnover. Sector-Specific Skill Building: Workshops by IOM, UNDP, UNIDO: Focused on packaging and pharmaceuticals, enhancing international market readiness and export potential. Business Capacity Building: Agribusiness Training: 140 agribusinesses trained in 2023, aimed at quality improvements and export positioning.. |
| 3.1.3: Advisory Board on Child Rights and Corporate Social Responsibility established and fully functional and number of private companies that are implementing corporate social responsibility measures | · a) No Advisory Board in place. · b) 76 companies signed the Women’s Economic Empowerment Principles (WEPs). | · a) Draft concept of the Advisory Council on Child Rights developed. · b) 102 companies signed WEPs. | · a) Business Advisory Council for Children (BACC) launched. · b) 170 companies signed WEPs. | · a) Partnerships with businesses strengthened through BACC, new initiatives like Junior Tech program launched. · ∙ b) 204 companies signed WEPs. |
| 3.1.4: Proportion of women in managerial positions | 36%. | 36.1% women in managerial positions. | Same as 2021. | 43% women in managerial positions within rank I and II, but only 9% in top managerial positions (heads of public entities). |
| 3.2.1. Agricultural productivity - Volume of production per labour unit by classes of farming/pastoral/forestry enterprise size) | 30.6 GEL in 2019 |  | • Small holdings - Male: 13.5 (GEL/labour day); Female 12.6 (GEL/labour day) • Medium and large holdings - Male: 41.5 (GEL/labour day) Female: 38.9 (GEL/labour day) (source: 2022 Annual Report Outcome 3) | • Small holdings - Male: 13.5 (GEL/labour day); Female 12.6 (GEL/labour day) • Medium and large holdings - Male: 41.5 (GEL/labour day) Female: 38.9 (GEL/labour day) (source: 2023 RG3 indicators) |
| 3.2.2. Number of new jobs created by enterprises through improved productivity in rural non-farm activities and through application of EE/RE, digital and other innovative technologies | 0 in 2019 | 417 jobs (source: 2022 Annual Report Outcome 3) | 609 jobs (source: “Improving Rural Development in Georgia” Project under ENPARD III Final Evaluation Report, December 2022) | Ongoing, through the creation of digital tools for MSMEs and the promotion of smart villages (source: 2023 RG3 narrative report​) |
| Number of new policy documents and tools on agriculture and food safety | 0 in 2019 |  | 31 policy and legislative documents (source: ENPARD III Final Report) | Two documents adopted - Law on Food Loss and Waste Reduction, and Law on Geographic Indications. Three more policies developed but not yet approved (source: ENPARD IV 3rd progress report) |
| Increase in per capita income in rural areas | 301.6 GEL in 2019 | 319.3 GEL (source: GeoStat) | 391.7 GEL (source: GeoStat) | 442.4 GEL (source: GeoStat) |
| 3.3.1. Proportion of youth (aged 15-24 and 15-29 years) not in education, employment or training (NEET), by sex | 27.9% (2014) TBI based on LFS new survey data in the mid of 2021 | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: total - 26.8, female - 26.8, male - 26.8; Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex: total - 34.6, female - 37.3, male - 32.1; | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: total - 23.4, female - 23.7, male - 23.1 Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex, total - 30.7, female - 34.5, male - 27.2; | Proportion of youth (aged 15-24) not in education, employment or training (NEET), by sex: total - 21.0, female - 21.6, male - 20.4. Proportion of youth (aged 15-29 years) not in education, employment or training (NEET), by sex: total - 26.9, female - 30.9, male - 23.2. |
| 3.3.2 Number of companies visited by labour inspectors per year | 1,575 inspections (first and follow up) conducted at 835 facilities. | 834[2] Based on the main mandate of Labour Inspection Office 1,540 inspections (first and follow up) conducted on 834 facilities. For 2021, for the reopening economic activities and controlling COVID19 recommendations on workplaces, labour Inspectors together with other supervisory institutions covered 12 778 facilities. | 1,933 3,755 inspections (first and follow up) conducted at1,933 facilities. | 3,334 5,847 inspections (first and follow up) conducted at 3334 facilities. |
| 3.3.3. Number of work-related accidents causing injuries or deaths, in total by sex per 100 000 employees | 12,97 work-related injuries and 3,47 work related deaths per 100 000 employees in 2019 | 20,78 work-related injuries 3,04 work-related deaths | 25,71 work-related injuries 2,73 work-related deaths | 26 work-related injuries 2,55 work-related deaths |
| 3.3.4 Number of interventions to enhance day care facilities and re-skilling of women to enhance their Labour Force Participation Rate (LFPR) | 0 | N/A | N/A | N/A |
| 3.3.5. Number of awareness and advocacy campaigns launched to bridge the gender pay gap | 1 | 1 campaign launched (Gender Pay Gap report updated with UN Women and ILO support) | N/A | 4 initiatives (including development of a manual for Equal Pay Review, SES support, and HR training activities) |
| 3.3.6 Proportion of population covered by social protection floors/systems, by sex, distinguishing children, unemployed persons, older persons, persons with disabilities, pregnant women, newborns, work-injury victims and the poor and the vulnerable (SDG indicator 1.3.1) (GT 1.3) Specifically: (a) population below the national absolute poverty line covered by the Targeted Social Assistance program - TSA (UNICEF) (b) children under the national absolute poverty line covered by the Targeted Social Assistance and Child benefits Program (UNICEF) (c) Proportion of women of reproductive age entitled to receive the state maternity benefit | a) 57.8% of population below the national absolute poverty line covered by the TSA program (Explanation: 19,5% of population under the national absolute poverty line, 11% covered by Targeted Social Assistance) (2019 data) b) 65.5% of children under the national absolute poverty line covered by the TSA and Child benefits Program (explanation: 24.4% of children under national absolute poverty line, 16% covered by the Targeted Social Assistance and Child Benefits) (2019 data) 16% coverage by child benefits (TSA) while 25.5% children live in absolute poverty c) 28% (ILO, UN Women report 2020, 2018 data) |  | 229,633 children were covered by the child cash benefits – 7.5% increase from 2021 (source: 2023 RG3 Indicators) | 251,430 children were covered by child cash benefits, representing 28.6% of all children below 16 (source: 2023 RG3 Indicators) |
| 3.3.7 Number of job seekers including returned migrants and VET graduates supported with skills development, job placement and internships in EU through the skills partnership schemes, gainfully employed at the local markets and/or abroad including through circular labour migration schemes | 2020:0 | N/A | 1,231 (source: 2023 RG3 Indicators) | 1,319 (source: 2023 RG3 Indicators)[MP2] |
| 3.3.8 Number of farmers benefiting from skill development trainings and/or extension services supported by projects, disaggregated by sex and age | 0 | 1,390 farmers benefited from skills development trainings, (38% women). 5,200 farmers (30% women) benefitted from UN-supported extension services (source: 2023 RG3 Indicators) | 853 rural women increased their knowledge and skills through UN Women support (source: 2023 RG3 Indicators) | 1,319 women received TA from UN Women. 391 farmers, (including 267 women) received TA from FAO (source: 2023 RG3 Indicators) |
| 4.1.1: Number of cases of legal and psychological assistance / services received by conflict-affected persons (including GBV survivors), by sex | · UNDP: 1,397 persons (85% female). · UN Women: 417 GBV survivors (99% female). · ∙ UNHCR: 1,300 persons (60% female). | · UNDP: 771 persons (81% female). · UN Women: 900 consultations (99.7% female), 275 individuals received services, 403 individuals reached via awareness campaigns. · ∙ UNHCR: 1,036 persons (68.5% female). | · UNDP: 771 persons (81% female). · UN Women: 735 consultations. · UNHCR: 1,002 persons (68% female). | · UNDP: 110 legal consultations (88 female), 282 psychological consultations (127 female). · UN Women: 904 consultations (536 women), 347 calls received. · UNHCR: 1,138 persons (63% female). |
| 4.1.2: Number of conflict-affected youth and teachers (schools, VET colleges and university) with improved access to quality education services | · UNDP: 20,174 student beneficiaries (40% female). · UNDP: 350 teachers trained. · UNICEF: 5,326 student beneficiaries. | · UNDP: 1,204 students (56% female). · UNDP: 378 teachers trained. · UNICEF: 10,858 students (59% female). | · UNDP: 433 students (52% female). · ∙ UNICEF: 59 teachers, 230 youth reached. | · UNDP: 1,388 students (920 female), 40 teachers (32 female). · UNICEF: 63 teachers, 312 youth. |
| 4.1.3: Number of conflict-affected population with improved access to essential healthcare services, including Sexual and reproductive health services | · UNDP: 10,886 persons (60% female). · UNFPA: 18,000 persons (100% female, cumulative 2015-2020). | · UNDP: 16,375 persons (51% female). · UNFPA: 22,380 persons (100% female). | · UNDP: 55,439 persons (57% female). · UNFPA: 25,755 persons (100% female). · UNICEF: 10,500 children and adolescents. | · UNDP: 1,300 persons (764 female). · UNFPA: 28,820 persons (100% female). · UNICEF: 506 children. |
| 4.2.1 Number of initiatives successfully implemented to improve socio-economic conditions and human security in conflict-affected areas | UNDP - 80 UN Women & FAO - 0 | UNDP: 133 FAO: 18 FAO & UN Women: 38 (source: 2023 RG4 report) | UNDP: 68 FAO: 35 FAO & UN Women: 37 (source: 2023 RG4 report) | UNDP: 61 FAO: 98 FAO & UN Women: 54 (source: 2023 RG4 report) |
| 4.2.2 Number of people benefiting directly from improved socio-economic conditions and improved human security | UNDP - 5,362 UN Women & FAO - 0 | UNDP: 953 (47% women) UN Women & FAO: 754 which 34% women (source: 2023 RG4 report) | UNDP: 1,014 (49% women) FAO: 997 (80% women) UN Women & FAO: 771 women (source: 2023 RG4 report) | UNDP: 10,460 (52.4% women) FAO: 1,154 UN Women & FAO: 1,855 women (source: 2023 RG4 report) |
| 4.2.3 Number of people with improved community resilience against climate-induced multi-hazard natural disasters | Baseline not available | 148 (39% female) | 456 people (54% female) | 8,308 (50% female) |
| 4.3.1 Existence of costed National Action Plan on Women, Peace and Security and its implementation rate Lead Reporter: UN Women | Yes (Current EVAW & DV NAP covers 2018-2020) - implementation rate to be determined in 2021. |  | UN Women: 2022-2024 NAP adopted by the Government of Georgia on October 26, 2022. | 2022-2024 NAP implementation report to be produced in 2024 |
| 4.3.2 Number of initiatives to support direct people-to-people contacts, liaison activities (deliveries of medication and/or other essential goods) and to enhance enabling environment for dialogue and trust within and across the divided communities; Custodian/ Reporter: UNDP Contributors: UN Women, UNFPA | UNDP - 121 (COBERM III, Dialogue II) UN Women - 5 UNFPA - 4 UNDP: 121 (2020) UN Women: 5 UNFPA: 4 WHO: 24 (2020) | UNDP: 50 UN Women: None; interventions are planned for 2022 UNFPA: 1 WHO: 16 | UNFPA: 2 UNDP: 88 cumulative (50+38) UN Women:1 | UNFPA: 2 (joint study tour to Istanbul and exchange visit to Tbilisi) UNDP: 24 UN Women: 1 WHO: 12 Cumulative 2021-2023 UNDP: 112 (50.6% of target) UN WOMEN: 2 (20%) UNFPA: 3 (50%) WHO: 28 (28 %) |
| 4.3.3 Number of people who benefit from peacebuilding initiatives that ensure enhanced confidence within and between the conflict divided communities. Custodian/Lead Reporter: UNDP Contributors: UN Women, UNFPA | UNDP: 26,430 of which 49% female (2020) UN Women: 100 (2020; 100% female) UNFPA: 220 (2020; 70% female) | UNDP: 20,703 of which 57% female UN Women: 128 participants (89% female) in GID/IPRM information sessions, and 52 (100% female) in annual Open Day on WPS. UNFPA: None in 2021; the COVID-19 situation prevented face-to- face workshops. | UNFPA: 17 (70% females) participants of joint workshop in Istanbul. UNDP: 8,932 (62% females) UN Women: 88 participants (89% female) in GID/IPRM information sessions; and 68 representatives of the CSOs working on women’ issues, IDP and conflict affected women and youth at grassroots attended the hybrid meeting (out of which 42 represented grassroots community and 16 were from the women’s CSOs) (100% female). | UNFPA: 22 (90% female) women health professionals, participants of: Istanbul study tour, exchange visit in Tbilisi, and joint capacity building initiatives UNDP: 984 (661 female; 67%) UN Women: 91 participants (95% female) in GID/IPRM information sessions, and 60 - grassroots IDP and conflict affected women and CSO representatives (100% women) participated in annual Open Day on WPS. |
| 5.1.1: Proportion of important sites for terrestrial, freshwater and black sea biodiversity that are covered by protected areas, by ecosystem type | 0 ha of Protected Areas. | 313,112 ha of protected areas with improved management. | 313,112 ha of protected areas with improved management; annual funding increased beyond target. | Replaced by 5.1.1a. Area of terrestrial and marine protected areas created of under improved management practices (hectares), supported by the UN “Progress in 2023: 313,112 ha protected areas under improved management. The reported figures include a) total areas of 9 Protected Areas supported by the UN. The target is expected to be achieved by mid-2024.” |
| 5.1.2: Proportion of local governments that adopt and implement local disaster risk reduction strategies in line with national disaster risk reduction strategy | 0 local governments with DRR strategies. | · Methodology for risk-informed, gender-sensitive municipal preparedness developed. · ToT for Emergency Management Service (EMS) conducted. · ∙ Training initiated in 3 municipalities, with 54% women participants. | Disaster risk management plans developed for 6 municipalities: Akhmeta, Lagodekhi, Telavi, Sighnaghi, Gori, Kobuleti. | 4 additional disaster risk management plans finalized in Abasha, Senaki, Samtredia, Khobi. |
| 5.1.3: Number of initiatives aimed at capacity-building efforts for government and other stakeholders in mainstreaming gender in formulating, monitoring and implementing national climate change policies and plans | None. | · Development of gender-sensitive municipal plans initiated. · Methodology developed, and ToT conducted for EMS staff. | · Gender-sensitive socio-economic vulnerability assessment methodology applied for 30 vulnerable communities in 3 river basins. · Gender-sensitive capacity development plans developed. | · Socioeconomic vulnerability assessment applied for 60 vulnerable communities in 4 river basins. · 90 communities across 7 river basins identified. |
| 5.2.1: Adaptation and mitigation capacities are increased through enhanced use of climate information, products and services and well-established multi-hazard early warning systems, including on community level. | a/ Hydrometric monitoring network outdated and inadequate b/ 0 multi-hazard and risk maps c/ MHEWS and Forecasting for climate -induced hazards does not exist d/ 0 risk reduction measures, based on multi-hazard risk maps, in high-risk areas e/ 0 Community-based climate risk management/EWS | a/ Hydro-metric network upgrade for 6 river basins – total 89 units procured; agro-met network (15 stations) upgrade initiated b/ National maps covering all 11 river basins were developed for 3 hazards (windstorm, hailstorm, avalanche). Hazard map for Flood hazard was developed for 3 river basins c/ Redeployment and enhancement of Rioni river flood forecasting platform d/ Design for 5 risk reduction measures developed. Construction works launched e/ Strategy for Community-based climate risk management /EWS elaborated (source: 2023 RG5 report) | a/ All hydrometeorological and agrometeorological equipment except 2 upper air sounding stations is purchased. The equipment was installed at 22 locations. b/ National maps covering all 11 river basins were developed for windstorm, hailstorm, drought and avalanche. c/ Flood maps developed for 7 river basins and Landslide, mudflow maps developed for 6 river basins. D/ Risk reduction measures implemented at 5 project locations, ongoing at 8 locations and planned at 2 locations e/ 15 out of 100 communities were identified (source: 2023 RG5 report) | a/ The equipment was installed at 79 weather stations out of 154. Landslide and groundwater monitoring systems for 11 locations were procured and installed. Trimble 4D Geotechnical Add-on software for integration of these monitoring stations was procured and operationalized. b) Multi-hazard and risk maps were produced for 7 river basins in western Georgia. c/ Flood forecasting platform was developed and piloted in 5 river basins. Forecasting concepts developed for wind, hailstorm and drought. d/ Risk reduction/flood protection measures was finalized at 9 locations, protecting 31,076 people in the regions. e) Risk assessment identified 45 communities that are at high-risk (multi-hazard) out of 100 communities; River basin-level risk management plans were developed in 4 basins in W. Georgia, and community-based Climate Risk Management plan were developed in 15 high-risk communities in 3 River basins in W. Georgia and works commenced. (source: 2023 RG5 report) |
| 5.2.2: Proportion of land that is degraded over total land area | Baseline: 6.1% area - 4071 square km in 2020 | a) Implementation of the land restoration activity was postponed due to COVID-19. b) More than 200 hectares (2 sq. km) of land in Shida Kartli region were cultivated using no-till planting. c) The direct number of beneficiary farmers is 69 farmers where around 15% are women. In total, 240 farmers and their families (as co-beneficiaries) benefit from the improved quality of the land. | N/A | a) Area of land restored – 537 hectares of pastures are restored (5.37 square kilometers) b) Area of landscapes under improved practices – Sustainable pasture management plans are elaborated for 87,610 hectares (876.1 square kilometers) c) Number of beneficiaries disaggregated by gender as co-benefit of restored land: 382 Persons (157 women, 225 men) |
| 5.2.3: Number of hectares of forest and protected areas under sustainable and climate-resilient management benefitting targeted rural population | Baseline (2017): 0 | 390,602 ha | 83,275 ha | 11,628 ha |
| 5.2.4: Adoption of updated regulations for WASH in schools and health facilities, including monitoring frameworks, which is reported annually | Baseline: No | Draft technical regulations on WASH in Schools have been integrated into Schools’ Operations and Maintenance Technical Regulations. | N/A | The construction standards for general education institutions, which incorporate standards for water, sanitation and hygiene (WASH) for schools have been finalized and are currently undergoing adoption by the government of Georgia. b) The WASH assessment of healthcare facilities conducted nationwide in 2021-2022 has not yet been published yet. Recommendations have been used in the process of accreditation of hospitals for their health service-provision activities. |
| 5.2.5. Mortality rate attributed to household and ambient air pollution[13] |  |  |  |  |
| 5.2.6. Existence of blood lead surveillance system at the national-level | Baseline: Does not exist | An environmental health laboratory established which will serve as a backbone to the Environmental Health Surveillance System; Joint efforts have led to the adoption of a technical regulation on prohibiting lead in paints in Georgia. | The Lead Surveillance System is designed | a) The Lead Surveillance System has been launched and piloted in 2 regions of Georgia. Up to 2,000 blood samples have been collected among randomly selected children and environmental and household samples have been collected for investigation in selected households where children have particularly high BLL. b) Continuous country consultations with WHO European Center for Environment and Health conducted in the process of establishing the Lead Surveillance System. c) Awareness-raising campaigns conducted countrywide to mark International Lead Poisoning Prevention Week (ILPPW) in Georgia. |
| 5.3.1: Renewable energy share in the total final energy consumption and number of rural households improving living conditions through increased energy efficiency and/or use of renewable energy | Baseline from NSDG: Renewable energy share in the energy mix is approximately 29.5% | 19.55% | 18.6% | 17.68% |
| 5.3.2: Gender-responsive technological solutions/initiatives/ projects, as per Long Term Low Emission Development Strategy (LEDS) are in place, improved and/ or applied | No | N/A | Lt-LEDS was finalized (source: 2023 RG5 indicators) | Lt-LEDs was adopted by the government of Geogia. Roadmap preparation started for implementation. Two local municipalities developed Sustainable energy and climate plans that include project ideas. (source: 2023 RG5 indicators) |

Annex 14: Profiling the joint work programmes

ONGOING JOINT PROGRAMMES

| No | Title | Agencies | Budget and donor | Start/End dates |
| --- | --- | --- | --- | --- |
| 1 | Joint EU-UN Programme for Rural Development in Abkhazia, Phase III (ENPARD IV) | UNDP (lead), FAO | Total: 1,995,850 USD Funded by: EU | 01/01/2022 – 31/03/2025 |
| 2 | EU4 Gender Equality: Together against gender stereotypes and gender-based violence - phase II | UN Women, UNFPA | Total: 2,812,670 EUR Funded by: EU | 13/12/2023 - 30/06/2026 |
| 3 | Air Quality for Better Citizen’s Health | UNDP (lead), UNECE, WHO | Total: 4,110,000 EUR Funded by: EU:4,000,000 EUR UNDP: 110,000 EUR | 01/11/2023 – 01/10/2027 |
| 4 | Minimizing the impact of the COVID-19 outbreak in Georgia through telemedicine and digital health solutions | WHO (lead), UNOPS, UNICEF, UNFPA | 1,955,000 USD (first tranche) (total budget 4,679,190 EUR) Funded by: EU | 13/08/2021 -12/08/2025 |
| 5 | Fostering economic empowerment of women farmers by supporting homemade dairy production in Samegrelo and Abkhazia through the Farmer Field Schools approach | FAO (lead), UN Women | Total: 3,251,459 USD Funded by: Switzerland (SDC) | 12/2020 – 09/2024 |
| 6 | Gender Equality for Georgia (GE4G) | UN Women (lead), UNFPA | Total: 1,512,000 EUR Funded by: EU | 04/12/2023 -03/12/2026 |
| 7 | USAID Partnering for Resilience Programme | UNDP (lead), FAO, UNICEF, UNFPA, UN Women, WHO | Total:10,000,000 USD Funded by: USAID | 10/03/2022 -09/05/2027 |
| 8 | Border and Migration Management Action for Georgia (BMMAG): Supporting the Government of Georgia in the Further Development of Border and Migration Management Capacities | IOM (lead), UNHCR | Total: 3,266,000 EUR EU: 2,650,000 EUR SEM: 400,000 CHF IOM: 150,000 EUR (to be mobilized) UNHCR: 50,000 EUR Funded by: EU Swiss State Secretariat for Migration (SEM) | 01/01/2022 – 31/12/2024 |
| 9 | UN Joint Programme for Gender Equality, Phase III | UNDP, UNFPA, UN Women | Total: 7,482,199 USD (77,844,000 SEK) Funded by: Sweden (SIDA) | 04/12/2023 - 31/12/2026 |
| 10 | Improved Specialization in Migration Governance and Integrated Border Management in Georgia (SPECS) | IOM (lead), UNHCR | Total: 2,425,000 EUR (USD 2,599,000) EU: 2,425,000 EUR Funded by: EU | 01/10/23-31/05/25 |
| 11 | Georgia: Strengthening the Capacity of the Health Sector to Address Health - Driven Irregular Migration to Switzerland (Georgia Cares project) | IOM (Lead), WHO | Total: 250,000 CHF (USD 282.000) Funded by: Swiss Development Cooperation Agency (SDC) | 01/01/24- 31/10/24 |
| 12 | Support to Georgia’s 2024 Parliamentary Elections | UNDP, UN Women, OHCHR | Total: 1,067,000 USD Funded by: MFA Denmark USD 867,000 (equivalent to DKK 5,832,309) UNDP TRAC3 USD 200,000 | 10/09/24-31/03/25 |
| 13 | Strengthening SDG localization in Georgia | UNDP (lead), UNICEF, FAO | Total: $309,954USD Funded by: Joint SDG Fund 249,954 USD UNDP: 25,000 USD UNICEF: 15,000 USD FAO: 20,000 USD | 07/ 2024 – 07/ 2025 |
| 14 | UNPRPD [Phase II] – Leave no one behind – from policy and principles to practice in disability inclusive development in Georgia | UNDP (Lead), UNFPA, OHCHR | Total: 300,000 USD Funded by: UNPRPD | 01/08/2024-31/01/2026 |

COMPLETED JOINT PROGRAMMES

| NO | Title | Agencies | Budget and Donor | Start /End Dates |
| --- | --- | --- | --- | --- |
| 1 | Assisting the Georgian Government and Local Communities in Mitigating the Impact of COVID-19 | UNDP (co-lead) UNFPA (co-lead) UNICEF (co-lead) UNHCR (contributing) WHO (contributing) OHCHR (contributing) | USD 1,000,000 Funded by: The UN COVID-19 Response and Recovery Multi-Partner Trust Fund (UN COVID-19 MPTF | 1 May – 31 Dec 2020 |
| 2 | Improving Vocational Education and Training in Abkhazia | UNDP (lead) UNICEF FAO | USD 3, 247, 343 (EUR 2,750,000) Funded by: EU | 1 Feb 2019 / 31 Jan 2022 |
| 3 | Transforming Social Protection for Persons with Disabilities in Georgia | UNICEF (lead) UNDP UNFPA UNOHCHR WHO UNWOMEN | USD 2,000,000 (total budget USD 2,200,000 Funded by: UN SDG Fund | 1 Jan 2020 / 30 June 2022 |
| 4 | Improving Vocational Education in Abkhazia | UNDP (lead) UNICEF FAO | USD 3, 247, 343 (EUR 2,750,000) Funded by: EU | 1 Feb 2019 / 31 Jan 2022 |
| 5 | Rural Development, Phase II (ENPARD III Abkhazia Component) | UNDP (lead) FAO | USD 4, 800, 947 (€ 4,052,000) Funded by: EU | 1 Mar 2018 / 30 Apr 2021 |
| 6 | Joint Program for Gender Equality | UNDP (co-lead)/(adm.agent) UNFPA (co-lead) UNWOMEN (co-lead) | USD 8,319,467 (SEK 70,000,000) Funded by: Government of Sweden | 18 Nov 2016 / 17 Nov 2020 |
| 7 | Horizons Project – Strengthening Community Resilience in Abkhazia | UNDP (lead) UNICEF | USD 7, 550, 000 Funded by: USAID | 20 June 2016 / 18 June 2021 |
| 8 | Innovative Action for Private Sector Competitiveness in Georgia | UNDP (lead), FAO, IOM, UNIDO | 5,843,500 USD Funded by: EU | 01/02/19 – 31/12/23 |
| 9 | UNPRPD 4 call: Leave no one behind — from policy and principles to practice in disability inclusive development in Georgia | UNDP [lead], UNFPA, OHCHR, | 400,000 USD (including USD 100,000 for the inception phase) Funded by: UNPRPD | 01/01/22 – 31/12/23 |
| 10 | Strengthening Georgia’s food and energy resilience. | UNDP, FAO, ILO, UNECE | Total: 319,344 USD Funded by: SDG Fund: 249,994 USD ILO: 9,000 USD UNDP: 60,350 USD | 01/07/22 – 31/03/23 |
| 11 | Ending violence against women and girls in Georgia (EVAWGG) | UN Women (lead), UNFPA | 2,044,317 USD (1.5 million EUR) Funded by: EU | 01/11/20 – 31/10/23 |
| 12 | EEU4Gender Equality: Challenging gender stereotypes and gender-based violence in the Eastern Partnership countries. | UN Women (co-lead) UNFPA (co-lead) | Total: 650,643 EUR (722,977 USD) (7,875,000 EUR total for 6 countries Funded by: EU | 01/03/20 – 30/06/23 |
| 13 | Human Rights for All – Phase II | UNDP, OHCHR | Total: 2,988,954 USD Funded by: EU: 2,690,058 USD UNDP: 181,931 USD OHCHR: 116,959 USD | 01/12/2020 – 30/04/2024 |
| 14 | Mainstreaming a disability inclusive humanitarian response to the Ukrainian refugee crisis | WHO, OHCHR, UNFPA, UNICEF, UN Women | Total: 800,000 USD for 2 countries (Moldova and Georgia) Funded by: UNPRPD | 01/01/2023 - 29/02/24 |

ANNEX 15: RESULTS MANAGEMENT FRAMEWORK FOR THE RECOMMENDATIONS

| Recommendation | Key Actions | Responsibilities | Timeline | Performance Metrics |
| --- | --- | --- | --- | --- |
| Refresh the UN’s Positioning | Develop a new positioning statement; Enhance reputation through knowledge products (policy briefs, podcasts, blogs, op-eds); Establish strategic partnerships with academia, think tanks, and the private sector. | UN RCO, UNCT, Government of Georgia, Development Partners | Q1-Q2 2026 | Positioning statement endorsed; 10 knowledge products published; 5 strategic partnerships established. |
| Aim for Impact | Assess feasibility of streamlining UNSDCF scope; Strengthen technical assistance to maximize policy impact; Prioritize investment in high-impact areas. | UN RCO, UNCT, Ministry of Finance, Ministry of Economy | Q3 2025 | UNSDCF restructuring proposal developed; Government satisfaction with UN TA (80% approval); 10% increase in budget allocation to high-impact programs. |
| Strengthen Private Sector Engagement | Develop a roadmap for private sector engagement; Enhance financing mechanisms for SMEs and start-ups; Promote gender equality in workforce participation. | UNCT, Ministry of Economy, Private Sector Associations | Q3-Q4 2025 | Private sector engagement framework adopted; 5 new private sector partnerships; Female workforce participation increased from 43.1% to 50% by 2026. |
| Embrace Innovation | Establish a UNSDCF Parliamentary Retreat; Launch a UNSDCF Observatory for transparency; Integrate AI-driven data analysis in governance programs. | UN RCO, Parliament of Georgia, Civil Society Organizations | Q2-Q4 2025 | 2 Parliamentary Retreats held per year; 10,000 website visits for UNSDCF Observatory; 3 AI-driven governance initiatives launched. |
| Expand Financing for Results | Establish an Impact Investment Facility; Mobilize additional funding from philanthropic organizations and MDBs; Develop blended finance models. | UNCT, UN RCO, Ministry of Finance, Development Banks | Q3 2025 | Impact Investment Facility launched; $10 million mobilized from new sources; 10 co-financed projects by Q4 2027. |

UNEG’s Norms and Standards for Evaluation (2016), UNEG Guidance on Integrating Human Rights and Gender Equality in Evaluations (2014); UN Women Evaluation Handbook on how to Manage Gender-Responsive Evaluation (2015); UN SWAP EPI Technical Note and Scorecard (2018); UNEG Good Practices for Integrating Gender Equality and Human Rights in Evaluation (2017); and UNEG Guidelines for the Evaluation of the UNSDCF (2021).

Georgia: Asian Development Bank Member Fact Sheet, ADB 2024

https://www.worldbank.org/en/country/georgia/overview

Indicator of Poverty and Gini Co-efficient, National Statistics Office of Georgia 2023

https://www.geostat.ge/en/modules/categories/23/gross-domestic-product-gdp

https://www.scoperatings.com/ratings-and-research/research/EN/173382

https://www.geostat.ge/en/modules/categories/683/Employment-Unemployment

Women and Men in Georgia 2024, GeoStat 2024

Ibid

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

Ibid

Georgia 2023 Report, Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the Regions 2023 Communication on EU Enlargement policy, European Commission 2023

https://www.internal-displacement.org/countries/georgia/

Georgia 2023 Report, Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the Regions 2023 Communication on EU Enlargement policy, European Commission 2023

The Economic Impact of the Russian Invasion of Ukraine on the Caucasus and Central Asia: Short-Term Benefits and Long-Term Challenges, ADB 2022

Creating Markets in Georgia: Unlocking Private Sector Opportunities to Achieve Georgia’s Full Potential, IFC 2023

Indicators of the Labour Force III Quarter 2023, National Statistics Office of Georgia 2023

https://www.geostat.ge/media/57459/Adjusted-gender-pay-gap---2022.pdf

Voluntary National Review 2024, Secretariat of the Inter-Agency SDGs Council of Georgia

https://www.geostat.ge/en/modules/categories/22/national-accounts

https://www.statista.com/statistics/441669/export-of-goods-to-georgia/

https://www.worldbank.org/en/country/georgia/overview#3

Andreas Klaasen et al, Policy Approaches to Stimulate Georgian Exports, ADB 2024

Givi Aideishvili and Bazlu Khonder, Ending Poverty in Georgia: New Economic Modeling, UNDP 2023

https://www.unicef.org/georgia/general-education#:~:text=Georgia's%20expenditure%20on%20education%20is,underperform%20in%20International%20Student%20Assessments.

National Statistics Office of Georgia: Regional Development (2023), https://www.geostat.ge/en

Indicators of Using Information and Communication Technologies (ICT) in Households, GeoStat, 2023

Financing SMEs and Entrepreneurs, OECD 2024

Factsheet: Georgia Women Entrepreneurs, UN Women 2021

https://www.imf.org/en/News/Articles/2023/02/17/pr2345-georgia-imf-staff-concludes-visit

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

OECD (2024), Financing SMEs and Entrepreneurs 2024: An OECD Scoreboard, OECD Publishing, Paris

Ibid

Creating Markets in Georgia: Unlocking Private Sector Opportunities to Achieve Georgia’s Full Potential, IFC 2023

Ibid.

https://www.worldbank.org/en/news/press-release/2018/05/22/world-bank-group-supports-georgia-with-new-country-partnership-framework

Georgia Good Governance Index 2024, Georgia Institute of Politics 2024

Public Administration Reform in Georgia, UNDP 2023

Georgia 2023 Report, Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the Regions 2023 Communication on EU Enlargement policy, European Commission 2023

https://justice.gov.ge/?m=articles&id=kpVk6xQ9OO&lang=2

https://ogpgeorgia.gov.ge/en/action-plan/

https://idfi.ge/en/joint-statement-by-civil-society-organizations-on-withdrawal-from-the-open-government-partnership-(ogp)-council-of-georgia

https://internationalbudget.org/open-budget-survey/rankings

Georgia Public Expenditure and Financial Accountability (PEFA) Assessment 2022, PEFA 2022

Georgia Fiscal Transparency Evaluation, IMF 2024

Georgia Public Expenditure and Financial Accountability (PEFA) Assessment 2022, PEFA 2022

Tamila Nutsubidze and Khatuna Nutsubidze, Voluntary Private Pension Reform in Georgia, Center for Retirement Research, 2024

https://idfi.ge/en/future_of_the_georgian_pension_reform

Tamila Nutsubidze and Khatuna Nutsubidze, Voluntary Private Pension Reform in Georgia, Center for Retirement Research, 2024

https://idfi.ge/en/future_of_the_georgian_pension_reform

Georgia 2023 Report, Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the Regions 2023 Communication on EU Enlargement policy, European Commission 2023

Concluding Observations on the Initial Report of Georgia, Committee on Rights of People with Disabilities April 2023

https://documents.un.org/doc/undoc/gen/g23/264/54/pdf/g2326454.pdf

https://georgia.un.org/en/249802-georgia-prison-system-needs-modernisation-says-un-torture-prevention-body

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

Concluding observations on the sixth periodic report of Georgia, March 2023

Ibid.

https://jam-news.net/abolition-of-gender-quotas-in-georgia/

UN Women, Country Gender Equality Profile: Georgia, 2023, https://georgia.unwomen.org/sites/default/files/2024-04/cgep_eng_web_1.pdf

GEOSTAT, Labour Force Survey, 2022.

Ibid.

Ibid.

Friedrich-Ebert-Stiftung South Caucasus; Youth Study Generation of Independent in Georgia: In Between Hopes and Uncertainties, 2023

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

Ibid

https://georgia.un.org/en/258633-telemedicine-bridging-healthcare-gap-georgia

Ibid

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

Creating Markets in Georgia: Unlocking Private Sector Opportunities to Achieve Georgia’s Full Potential, IFC 2023

Analysis of Legal and Regulatory Framework for Disaster Risk Knowledge Component of Multi-Hazard Early Warning System in Georgia, UNDP 2022

Georgia’s 2030 Climate Change Strategy, 2021: https://mepa.gov.ge/En/Files/ViewFile/50123

Georgia’s Updated Nationally Determined Contribution: https://mepa.gov.ge/En/Files/ViewFile/50124

Ibid

Georgia 2023 Report, Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the Regions 2023 Communication on EU Enlargement policy, European Commission 2023

Voluntary National Review Georgia 2020, Secretariat of the Inter-Agency SDGs Council of Georgia

Final Evaluation of the project “Good Governance for Gender Equality in Georgia (GG4GEG)”, May 2023

Child Well-Being in Georgia 2023, GeoStat and UNICEF

Focus Group for CSOs

The full name is Ministry of Internally Displaced Persons from the Occupied Territories, Health, Labour, and Social Affairs.

Decree of the Government of Georgia No. 523 dated 01.12.22 ”Regarding determining the amount of compensation to be given to victims of violence against women and/or domestic violence and approving the manner of giving it”

https://georgia.unwomen.org/en/digital-library/publications/2023/12/national-study-on-violence-against-women-in-georgia-2022.

https://georgia.un.org/en/263572-statement-united-nations-georgia-regarding-draft-law-amendments-tax-code-georgia-tobacco#:~:text=Tobacco%20control%20is%20not%20a,but%20also%20weaken%20the%20economy.

ENPARD III Final Evaluation Report, January 2023.

Ibid.

“Improving Rural Development in Georgia” Project under ENPARD III Final Evaluation Report, December 2022.

2021 RG3 Report.

ENPARD III Final Evaluation Report, January 2023.

Ibid.

“Improving Rural Development in Georgia” Project under ENPARD III Final Evaluation Report, December 2022.

EU Innovative Action for Private Sector Competitiveness in Georgia, Final Evaluation Report, May 2024.

ENPARD III Final Evaluation Report, January 2023.

Interviews conducted during the UNSDCF evaluation.

EU Innovative Action for Private Sector Competitiveness in Georgia, Final Evaluation Report, May 2024.

Transforming Social Protection for Persons with Disabilities in Georgia, Final Evaluation Report, 2022 https://erc.undp.org/evaluation/documents/download/21482

Assessment of the Social Protection System in Georgia, 2020 https://www.ilo.org/sites/default/files/wcmsp5/groups/public/@europe/@ro-geneva/@sro-moscow/documents/publication/wcms_767261.pdf

Loneliness among older people - research analyses, Georgia, UNFPA, 2021 https://georgia.unfpa.org/en/publications/loneliness-among-older-people-research-analyses-georgia-2021

Study of Reintegration Outcomes Among Returned Migrants in Georgia, April 2024.

Information in Georgian is available at: https://lio.moh.gov.ge/editor/upload/20240618051616-2021-2023-%E1%83%A8%E1%83%94%E1%83%9B%E1%83%9D%E1%83%AC%E1%83%9B%E1%83%94%E1%83%91%E1%83%A3%E1%83%9A%E1%83%98%20%E1%83%A1%E1%83%90%E1%83%9B%E1%83%A3%E1%83%A8%E1%83%90%E1%83%9D%20%E1%83%90%E1%83%93%E1%83%92%E1%83%98%E1%83%9A%E1%83%94%E1%83%91%E1%83%98.xlsx

ILO contribution to UNSDCF.

See every Colour: addressing stigma against children with disabilities and supporting their social inclusion through social and behaviour change interventions, January 2022.

EU Innovative Action for Private Sector Competitiveness in Georgia, Final Evaluation Report, May 2024.

See every Colour: addressing stigma against children with disabilities and supporting their social inclusion through social and behaviour change interventions, January 2022.

ENPARD III Final Evaluation Report, January 2023.

Assessment of the Rural Development Agency`s Programme of Pilot Programme for Women, UN Women 2023

Ibid.

ENPARD III Final Evaluation Report, January 2023.

Ibid.

“Women’s Economic Empowerment in the South Caucasus” Regional Project, Final Evaluation Report, May 2021.

UNCT Annual Report 2023.

Transforming Social Protection for Persons with Disabilities in Georgia, Final Evaluation Report, July 2022.

USAID Partnering for Resilience Program, Quarterly Progress Report, 1 October – 31 December 2023.

EU-UN Joint Programme on Improving Vocational Education in Abkhazia, Mid-term Evaluation Report, 2021.

Mid-Term Evaluation of the Swiss-funded project “Fostering economic empowerment of women farmers by supporting homemade dairy production through the Farmer Field Schools (FFS) approach, Evaluation Report, December 2022.

Joint EU-UNDP Civil Society Support Programme, Final Evaluation Report, April 2023.

USAID Partnering for Resilience Program, Quarterly Progress Report, 1 October – 31 December 2023.

Mid-Term Evaluation of the Swiss-funded project “Fostering economic empowerment of women farmers by supporting homemade dairy production through the Farmer Field Schools (FFS) approach, Evaluation Report, December 2022..

Confidence Building Early Response Mechanism Project, Final Evaluation Report, November 2022.

UNCT Annual Report, 2023.

USAID Partnering for Resilience Program, Quarterly Progress Report, 1 October – 31 December 2023.

Mid-Term Evaluation of the Swiss-funded project “Fostering economic empowerment of women farmers by supporting homemade dairy production through the Farmer Field Schools (FFS) approach, Evaluation Report, December 2022.

E.g. Partnering for Resilience Program (USAID), EU-UN Joint Programme on Improving Vocational Education in Abkhazia, EU-UNDP Civil Society Support Programmer, COBERM, UNDP/UNICEF Horizons Project Strengthening Community Resilience in Abkhazia (USAID)

Interviews with healthcare staff in villages Tkviavi and Kvemo Nikozi.

Strengthening the Climate Adaptation Capacities in Georgia, Mid-term Evaluation Report, December 2021.

https://www.energy-community.org/dam/jcr:4dfd3e00-78c0-47a8-a2d9-01ec62459010/National__Energy_and_Climate_Plan_of_Georgia_(DRAFT)%20(2).pdf

https://mepa.gov.ge/En/PublicInformation/34075

Report on Ending Childhood Lead Poisoning in Georgia Progress and lessons learned between 2017 and 2023.

2023 RG5 report.

Strengthening the Climate Adaptation Capacities in Georgia, Mid-term Evaluation Report, December 2021.

Interview with NEA.

FAO-GEF Project Implementation Report 2023.

Strengthening the Climate Adaptation Capacities in Georgia, Mid-term Evaluation Report, December 2021.

National Pastureland Management Policy Document, 2022.

Readiness and Preparation Support, Annual Performance Report, 2024.

Interview with farmer in Village Dzevera, Kvemo Kartli region.

https://mepa.gov.ge/En/PublicInformation/34075

2023 RG5 indicators.

https://sdg.gov.ge/sdg-tracker

Renewable Energy for Sustainable Forest Management and Community Resilience, https://www.undp.org/sites/g/files/zskgke326/files/2023-05/undp-georgia-jsb-machakhela-renewable-energy-practices-prodoc.pdf

Roadmap to Implementation of Georgia’s Long-Term Low Emission Development Strategy, 2024.

Interview with NEA.

Ibid.

Georgia’s Long-Term Low Emission Development Strategy, 2023.

Report on Ending Childhood Lead Poisoning in Georgia Progress and lessons learned between 2017 and 2023.

Sizing the Impact Investing Market, GIIN 2024

Other than YouTube, Facebook is the most popular social media platform in Georgia with a 32.1% market share in July 2024, as reported by StatsCounter Global Stats https://gs.statcounter.com/social-media-stats/all/georgia