| UNCT-SWAP GENDER EQUALITY SCORECARD |  |
| --- | --- |
| United Nations Country Team NIGERIA |  |
| January-February 2021 |  |
| Consultant: Susana María Fernandez Alonso |  |

TABLE OF CONTENT:

List of acronyms and abbreviations	3

1.	BACKGROUND	4

2.    METHODOLOGY	4

3.	COUNTRY CONTEXT	6

4.   FINDINGS	7

4.1 Findings overview	7

4.2 Findings overview by dimension area	8

4.2.1 Planning	8

4.2.2 Programming and M&E	9

4.2.3 Partnerships	10

4.2.4 Leadership and organizational culture	10

4.2.5 Gender architecture and capacities	11

4.2.6 Resources	12

4.2.7 Results	12

5.	CONCLUSION	12

5.	ACTION PLAN	13

6.	ANNEXES	14

Annex A: Organizational culture staff survey results in Nigeria	14

UNCT Nigeria - SWAP scorecard findings by indicator	17

Action plan for UNCT Nigeria performance improvement on GEEW	35

# List of acronyms and abbreviations

ARC		Assessment of Results and Competencies

AWP		Annual Work Plan

BOS		Business Operations Strategy

CEB		Chief Executives Board

CEDAW		Convention on the Elimination of all forms of Discrimination Against Women

CCA		Common Country Analysis

CSO		Civil Society Organizations

FAO		Food and Agriculture Organization of the United Nations

GBV		Gender-based Violence

GEEW		Gender Equality and the Empowerment of Women

GTG		Gender Thematic Group

HOA		Heads of Agencies

IAT		Inter-Agency Team

ILO		International Labor Office

IOM		International Organization for Migration

JP		Joint Programmes

M&E		Monitoring and Evaluation

OMT		Operations Management Team

RC		Resident Coordinator

RCO		Resident Coordinator Office

SDG		Sustainable Development Goals

TOR		Terms of Reference

UN		United Nations

UNCT		United Nations Country Team

UNAIDS		Joint United Nations Programme on HIV/AIDS

UNDAF		United Nations Development Assistance Framework

UNDSS		United Nations Department of Safety and Security

UNDP		United Nations Development Programme

UNESCO	United Nations Educational, Scientific and Cultural Organization

UNFPA		United Nations Population Fund

UNHCR		United Nations Refugee Agency

UNIC		United Nations Information Centers

UNICEF		United Nations Children’s Fund

UNIDO		United Nation Industrial Development Organization

UNITAR		United Nations Entity for Training and Research

UNOCHA	United Nations Office for the Coordination of Humanitarian Affairs

UNODC		United Nations Office on Drugs and Crime

UNSDPF	United Nations Sustainable Development Partnership Framework

UNSDG		United Nations Sustainable Development Group

UN-SWAP	UN System-Wide Action Plan for Gender Equality and Women’s Empowerment

UN WOMEN	United Nations Entity for Gender Equality and the Empowerment of Women

WIPO		World Intellectual Property Organization

WFP		World Food Programme

WHO		World Health Organization

WMO		The World Meteorological Organization

# BACKGROUND

The United Nations (UN) gender scorecard is a globally standardized assessment of the effectiveness of UN country level gender mainstreaming processes. The gender scorecard sets the United Nations Country Team (UNCT) performance indicators for gender equality that establish an accountability framework to assess UNCT gender equality performance. The tool lays down the minimum standards for gender equality that UNCT should achieve for a proper gender mainstreaming performance.

The development of the gender scorecard was proposed by the United Nations Sustainable Development Group (UNSDG) in July 2006 and endorsed by the Principals in April 2008. The framework was further developed by the UN in response to the UN Chief Executives Board for Coordination (CEB) system-wide Policy on Gender Equality and the Empowerment of Women (CEB/2006/2) and was endorsed by the CEB in 2012.

In 2018, the gender scorecard methodology was revised in tandem with the UN-SWAP. The System-Wide Action Plan for Gender Equality and the Empowerment of Women (UN-SWAP), launched in 2012, is a UN system-wide accountability framework designed to measure, monitor and drive progress towards a common set of standards, applying to all entities, departments and offices of the UN system. This methodological revision of the gender scorecard, now UNCT SWAP gender equality scorecard, has ensured closer alignment with the UN-SWAP and with the Sustainable Development Goals (SDGs), recognizing the importance of gender equality and the empowerment of women to SDG achievement.

The UNCT Nigeria implemented for the first time the UNCT-SWAP gender equality scorecard in January 2021.

# 2.    METHODOLOGY

The UNCT-SWAP gender equality scorecard is focused on specific UNCT performance, rather than single agency performance, providing an assessment of how UNCT is mainstreaming gender and what the UN system as a whole is contributing to gender equality and the empowerment of women (GEEW) in the country. The scorecard set 7-dimension areas across 15 indicators, addressing key components, as follows:

1. Planning;

2. Programming and monitoring and evaluation;

3. Partnerships;

4. Leadership and organizational culture;

5. Gender architecture and capacities;

6. Resources;

7. Results.

Each dimension area includes performance indicators that establish the minimum criteria that UNCT must meet or exceed to fulfil its mandate on GEEW.

The overall scorecard process, led by the GTG, was coordinated by UN Women and the RCO. An inter-agency team (IAT) was formed in December 2020 to implement the exercise, comprised of representatives of key agencies and different sectors covered by the scorecard, such as communication, monitoring and evaluation (M&E), Human Resources/OMT, the Gender Theme Group (GTG) and the Resident Coordinator Office (RCO). 31 members were nominated by HOAs although only 17 participated directly in the self-assessment, forming the inter-agency core assessment team, a smaller and functional group that enabled interagency stakeholders to work collaboratively to measure UNCT’s performance against minimum requirements. The exercise was carried out in a highly participatory manner, promoting internal dialogue and fostering deeper understanding and ownership of results by UNCT.

An international consultant was hired to guide the exercise, provide support and assistance to the assessment team and facilitate the working sessions. As a result of the current COVID-19 pandemic, the scorecard methodology was adapted to online modalities.

Prior to hiring the international consultant, an online survey of personnel perception of organizational environment for the promotion of gender equality was conducted. The survey was open for 2 weeks. In total, the survey reached 436 responses, exceeding the minimum number of responses required to ensure the validity of results. The results of the survey were used for the assessment of indicator 4.2 “Organizational culture fully supports promotion of gender equality and the empowerment of women”. A breakdown of survey responses can be found in annex A.

The scorecard coordinators distributed a gender parity table template to the human resources departments of UN agencies. The table requested quantitative data on the number of women and men in the all UN professional categories in Nigeria, both national and expatriate. All agencies completed and filled out the table template. An excel sheet was then created for the consolidation of all sex-disaggregated UN staffing data. These data were used for the assessment of indicator 4.3 “Gender parity in staffing is achieved”.

All documentation, evidence and means of verification against indicators were uploaded by the scorecard coordinators on a google drive for quick and easy access to information by members involved in the assessment.

The process conducted by the consultant was as follows:

- Background document review: The consultant reviewed the most relevant documents to get an understanding of UNCT processes and procedures, such as UNCT-SWAP technical guidance and framework; UNCT gender scorecard reports from the countries in the region and from other countries; Common Country Analysis (CCA) report 2016; United Nations Sustainable Development Partnership Framework (UNSDPF) 2018-2022; New UNSDG Sustainable Development Cooperation Framework Guidance; UNCT planning, programming and budgeting documents; GTG documentation, such as TOR, Annual Work Plan (AWP) and reports of trainings; CCA diagnosis papers for SDGs, December 2020; Capacity Development Assessment by GTG, December 2020, and CEDAW reports and other national assessments/national gender plans and legislation.

- Briefing meeting: A briefing session with the larger assessment team took place on December 22, 2020 via Zoom. During the meeting, the expectations on the team were clarified and the basis for work coordination provided. The availability of the members was ascertained in order to form a smaller and more operational group to be directly involved in the self-assessment, leaving the larger group for consultative purposes. A core assessment team was then formed and assigned across indicators. In total, 17 members were part of the core team and distributed into 6 evaluation groups. They were demanded to familiarize themselves with the scorecard guidebook; in particular, with the guidance regarding the indicators of their responsibility and to provide preliminary assessments.

- In-country self-assessment: Evaluation groups worked to agree on evidence, revise data and means of verification, get a common understanding on the findings against the indicators of their responsibility, elaborate rationale and explanations and reach consensus on tentative scoring against indicators. Online thematic meetings were held during January 2021 and first week of February between the evaluation groups and the consultant to revise evidence data, discuss findings, update rationale and explanation against indicators, identify concerns and improve the assessment against indicators.

- Action planning workshop: A session via Zoom was held on February 15, 2021 to present findings, results and final scores against indicators to the core team, allowing space for feedback and consensus building. During the workshop, a proposal for an action plan was presented by the consultant. This proposal had been elaborated based on findings. This was followed by a discussion, dimension area by dimension area, about the action plan where new measures to improve UNCT performance on gender mainstreaming were proposed and other measures were updated and improved. A final action plan for UNCT performance improvement on GEEW was eventually developed and agreed upon.

- Results sharing: The findings on the indicators and the draft action plan was shared with the larger inter-agency team, for feedback and comments.

- UNCT debriefing session: A debriefing session with HOAs was held via Zoom at the beginning of March to present the findings of the scorecard exercise, the scorings against indicators, the UNCT strengths and weaknesses as far as GEEW is concerned and the main recommendations for performance improvement. Discussions took place among HOA and further feedback was collected by the consultant.

The members of the core assessment team devoted a great deal of time to the scorecard exercise and actively participated in virtual meetings, making significant contributions to the evaluation of indicators and to the action plan.

This report has been produced by the international consultant based on findings and feedback.

# COUNTRY CONTEXT

The UN system’s strategic response in Nigeria is currently being provided under the UNSDPF 2018-2022, signed with the Federal Government of Nigeria. The current UNSDPF is the fourth in the series of Common Country Programme Document produced by the UN system in Nigeria. The document has applied Standard Operating Procedure for UN coherence, lays on partnerships and focuses on SDGs as the foundation for development. The Federal Republic of Nigeria and the UN system are, therefore, committed to working together in partnership under a fully-fledged 'Delivering as One' modality to implement the UNSDPF.

The UNSDPF 2018-2022, built on inclusive development, gender equality and the empowerment of women, sustainable development, resilience, and accountability, supports the universal agenda which leaves nobody behind and provides focused and coordinated efforts to render people more resilient and engaged toward inclusive and sustainable development.

Three strategic priority result areas are elaborated upon as the mainstay of this framework:

- Governance, Human Rights, Peace, and Security;

- Equitable Quality Basic Services;

- Sustainable and Inclusive Economic Growth and Development.

All these were selected together with nine outcomes with specific baselines, targets and indicators.

The UNCT Nigeria embarked in the last quarter of 2020 on the process of updating the current CCA, a collective analysis of the situation of Nigeria by the UN system, which is dated 2016. The CCA will serve as basis for the subsequent development of the upcoming UNSDPF.

The process of development of the new CCA generation is being led by the GTG. Gender focal points were strategically embedded in the thematic groups for the development of diagnostic papers for each of 17 SDGs and other thematic areas in order to ensure that gender equality is properly integrated across the document. At the time of this scorecard, UNCT had developed 20 SDG diagnosis papers in December 2020, out of 25.

Given gender equality is a non-negotiable agenda for UNCT Nigeria as the GTG is represented in the overall implementation arrangement structure for the UNSDPF 2018-2022, this scorecard is being undertaking during the planning stage of the upcoming UNSDPF to enable findings to feed directly into the new program cycle. It will strengthen gender-responsive planning in line with UN minimum standards on GEEW, ensure greater accountability by UNCT towards gender equality, aligned with UN corporative Policy on GEEW, and enhance gender results in the current as well as the upcoming program cycle.

The final aim of the scorecard exercise is then to identify gaps and corrective actions for an adequate UNCT performance on gender mainstreaming during the next programming cycle.

# 4.   FINDINGS

The scorecard methodology does not provide for quantitative scores. The UNCT SWAP-scorecard incudes 3 level of ratings and a missing option:

  - Exceeds minimum requirements;

  - Meets minimum requirements;

  - Approaches minimum requirements;

  - Missing.

The criteria to exceed, meet or approach minimum requirements is provided by UNSDG for each indicator. If UNCT fails to approach minimum requirements, the indicator is then scored as missing.

If UNCT is considered approaching minimum requirements, greater efforts should be done over the next year, so that UNCT can meet minimum requirements in the next reporting.

The UNCT should aim at meeting minimum requirements as an adequate performance on gender mainstreaming. However, meeting minimum standards should be contemplated as a starting point from which UNCT should strengthen current work and reinforce existing country efforts to address GEEW. The objective should be to exceed minimum requirements, so that best practices are shared with other UNCTs.

It is important to look not only at the scorings across indicators but also at the explanations and rationales provided by indicator to justify the assessments.

## 4.1 Findings overview

A summary of the scorings against all indicators across the 7-dimension areas is outlined in the following table.

UNCT-SWAP Gender Equality Scorecard - Scorings

| Country: Nigeria Assessment year: 2021 (January) Coordinators: Ms. Elise Dietrichson (UN Women) and Ms. Ayodeji Olugbemi (RCO) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Missing | Approaches minimum requirements | Meets minimum requirements | Exceeds minimum requirements |
| - Planning |  |  |  |  |
| 1.1. Common Country Analysis integrates Gender Analysis |  |  |  |  |
| 1.2. Gender Equality mainstreamed in UNDAF outcomes |  |  |  |  |
| 1.3. UNDAF indicators measure changes on Gender Equality |  |  |  |  |
| - Programming and M&E |  |  |  |  |
| 2.1. Joint Programs contribute to reducing Gender Inequalities |  |  |  |  |
| 2.2. Communication and Advocacy address areas of Gender Inequality |  |  |  |  |
| 2.3. UNDAF Monitoring and Evaluation measures Progress against planned Gender Equality Results |  |  |  |  |
| - Partnerships |  |  |  |  |
| 3.1. UNCT collaborates and engages with Government on Gender Equality and the Empowerment of Women |  |  |  |  |
| 3.2. UNCT collaborates and engages with Women’s/Gender Equality CSO |  |  |  |  |
| - Leadership |  |  |  |  |
| 4.1. UNCT Leadership is committed to championing Gender Equality |  |  |  |  |
| 4.2. Organizational Culture fully supports promotion of Gender Equality and the Empowerment of Women |  |  |  |  |
| 4.3. Gender Parity in staffing is achieved |  |  |  |  |
| - Gender Architecture and Capacities |  |  |  |  |
| 5.1 Gender Coordination Mechanism is empowered to influence the UNCT for Gender Equality and the Empowerment of Women |  |  |  |  |
| 5.2 UNCT has adequate Capacities developed for Gender Mainstreaming |  |  |  |  |
| - Resources |  |  |  |  |
| 6.1. Adequate resources for Gender Mainstreaming are allocated and tracked |  |  |  |  |
| - Results |  |  |  |  |
| 7.1. UN Programmes make a significant contribution to Gender Equality in the Country |  |  |  |  |

The completed scorecard findings by indicator can be found in annex B. A summary of key findings by dimension area is provided hereunder.

## 4.2 Findings overview by dimension area

### 4.2.1 Planning

UNCT Nigeria is not adequately performing in this dimension area, since it does not meet minimum requirements for any of the 3 indicators.

Indicator 1.1. UNCT approaches minimum requirements for the 2016 CCA since gender analysis is not visibly integrated across all sectors and only some sex-disaggregated data are provided. In particular, gender analysis is not included across the Nigerian development context and the analysis of the following sectors: (i) inclusive economic growth and prosperity, (ii) youth unemployment, (iii) comparative advantage and (iv) planet environment protection, resilience, and sustainable development. Gender analysis and consistent data disaggregated by sex must be included across all sections in the CCA, including underlying causes of gender inequality and discrimination in line with SDG priorities including SDG 5. Furthermore, for this indicator, the assessment team carried out an analysis of the SDG diagnosis papers submitted last December as part of the ongoing process of CCA formulation. The conclusion was that UNCT would still not meet minimum requirements due to the fact that gender analysis is not included in all diagnostic papers and only some analyses of sectors include sex-disaggregated and gender-sensitive data.

Indicator 1.2. UNCT approaches minimum requirements for the mainstreaming of gender equality across UNSDPF outcome areas because GEEW is not visibly mainstreamed across all outcomes of the UNSDPF 2018-2022. In particular, gender equality is visibly mainstreamed across outcomes 1 (Good Governance and Rule of Law), 2 (Humanitarian Response, Peacebuilding, and Security), 4 (Learning and Skills Development), 5 (Water, Sanitation and Hygiene), 6 (Protection) and 7 (Diversified Economic Growth) but is not visibly mainstreamed across outcomes 3 (Health, Nutrition, and HIV&AIDS), 8 (Population Dynamics) and 9 (Environmental Sustainability and Food Security). In addition, no UNSDPF outcome specifically targets gender equality. GEEW must be visibly mainstreamed across all outcome areas in line with SDG priorities including SDG 5 and furthermore, one UNSDPF outcome should specifically be related to GEEW, addressing gender inequalities.

Indicator 1.3. UNCT approaches minimum requirements for UNSDPF outcome indicators due to the fact that only 27.66% of indicators formulated in the UNSDPF 2018-2022 track progress towards gender equality. In particular, no indicator can measure changes in gender equality for outcomes 2, 5, 7, 8 and 9. The indicators that appear most sensitive to gender are those in outcomes 4 and 6. As a result, a stronger effort needs to be done by UNCT in regards with the disaggregation of indicators by sex whenever possible in the upcoming UNSDPF.

The UNCT planning should be strengthened in the short term by an effective integration of GEEW in the upcoming UNSDPF, across the CCA, outcomes and indicators.

### 4.2.2 Programming and M&E

UNCT Nigeria is not adequately performing in this dimension area concerning joint programs (JPs) and communication and advocacy since it does not meet minimum requirements for these 2 indicators. Nevertheless, UNCT exceeds minimum requirements for the M&E related indicator.

Indicator 2.1. Concerning JPs, UNCT approaches minimum requirements since gender equality is not visibly mainstreamed into all JPs (in fact, only one JP does not visibly mainstream gender but this in itself causes the criterion not to be met). Gender equality must be visibly mainstreamed into all JPs to meet the minimum requirements for this indicator. However, at the time of the assessment there were 2 joint programmes on promoting gender equality and the empowerment of women, which is very good. A system to ensure gender mainstreaming in JPs still need to be in place, be it through the GTG or the use of external expertise.

Indicator 2.2. Concerning communication and advocacy, UNCT approaches minimum requirements because the joint communication strategy does not visibly include GEEW communication and advocacy. On the other hand, the UNCT has contributed collaboratively to GEEW communication and advocacy in traditional thematic areas, such as gender-based violence (GBV). To improve UNCT performance in this regard, it is necessary to include communication and advocacy activities on GEEW in the annual work plan of the joint communication group (should it ever be developed) and in the joint communication strategy. For best improvement, joint communication and advocacy on GEEW must target at least one non-traditional thematic area.

Indicator 2.3. This is the area where the UNCT Nigeria performs excellency. UNSDPF results matrix data for gender-sensitive indicators is gathered as planned. The Nigeria 2019 One UN report includes comprehensive component on GEEW within outcomes 1, 2, 4 and 6. An analysis of the gender marker was presented in the report, reflecting the percentage of gender-focused activities and the amount of resources spent per marker for gender equality and the empowerment of women. In addition, the joint M&E group received technical training on the gender marker last year. To keep this indicator exceeding minimum requirements, it is necessary to strengthen the capacities of the joint M&E group in gender-sensitive M&E.

### 4.2.3 Partnerships

UNCT Nigeria is performing sufficiently in this dimension area but it does not meet minimum requirements for 1 of the 2 indicators.

Indicator 3.1. Concerning partnership with Government, for which UNCT approaches minimum standards, the UN system has collaborated with the Federal Ministry of Women Affairs on a large number of joint initiatives to promote gender equality. However, this institution was not fully involved in the consultations of the current UNSDPF 2018-2022, although its participation is expected for the meetings and validation workshops of the upcoming CCA. On the other hand, the UNCT has not still made contribution to substantively strengthen Government participation and engagement in gender-related SDGs localization and/or implementation within the current UNSDPF cycle. To enhance performance in this area, it is necessary to collaborate with other government institutions (other than the Federal Ministry of Women) on joint initiatives fostering GEEW and to contribute jointly to Government engagement in gender-related SDGs.

Indicator 3.2. Concerning partnership with civil society organizations (CSO), for which UNCT meets minimum standards, the UNCT has collaborated with GEEW CSOs and/or women’s rights advocates on joint initiatives that foster gender equality and empowerment of women within the current UNSDPF cycle. However, GEEW CSOs have not participated in the consultations of the current UNSDPF 2018-2022, although their participation is expected for the meetings and validation workshops with different stakeholders that will take place for the upcoming CCA once all SDG papers are submitted. To enhance performance in this area, it is necessary to make significant contributions to substantively strengthen GEEW CSO participation and engagement in gender-related SDGs localization and/or implementation and ensure GEEW CSO participation in the consultations of the upcoming UNSDPF, including CCA and strategic prioritization.

### 4.2.4 Leadership and organizational culture

The performance of UNCT Nigeria in this dimension area is acceptable. UNCT meets minimum requirements for 2 indicators. However, UNCT is not adequately performing for indicator 4.3 (related to gender parity in staffing) for which the country team does not even approach minimum requirements.

Indicator 4.1. Concerning UNCT commitment to championing gender equality, senior managers play a critical role within UNCT for the promotion of GEEW and at least 60% of HOAs meetings should address GEEW, and there should be evidence of decision-making and follow through, rather than general information sharing. In this regard, gender equality was discussed in all (4) standard HOA meetings during the last 12 months. However, 15 COVID-19 specific meetings were also held last year, the agenda of which was particularly tailored to addressing the pandemic, mainly targeted towards staff Duty of Care and Social Economic Response and Basket Fund to support the government’s response to COVID-19, where substantial discussions on gender equality did not always take place. Another criterion under this indicator concerns the RC, who must demonstrate leadership and public championing on gender equality. At least one third of RC speeches over the last 12 months should include references to GEEW and/or as to how the UNCT is promoting GEEW. The evaluation has shown that RC in Nigeria publicly defended gender equality in 13 speeches, although the total number of RC speeches made last year could not be traced. Finally, 76% of staff think that HOAs are committed to gender equality in the workplace.

Indicator 4.2. The results of the survey of staff perception of organizational environment for gender equality revealed a positive rating of 74%, which means that UNCT Nigeria meets minimum requirements. The survey dealt with perceptions of gender equality in the UN system, equal treatment in the workplace and work-life balance. However, the results in the male population show an average positive score of 80%, while the average positive score for women is only 64%. The questions related to the measures in place to ensure work-life balance of staff were those that received the most negative opinions. 17% of female staff members and 11% of male staff members think that the package of flexible work arrangements does not support staff to achieve adequate work-life balance. In particular, 14% of respondents think that HOAs are not supportive of staff to establish an adequate relationship between work life and home life. This is also the question that received the most negative opinions from women (20%), compared to only 9% negative responses from men.

Indicator 4.3. Concerning gender parity in staffing, this area is underperformed as the scorecard exercise assessed this indicator as missing. This is mainly due to the fact that UNCT has not in place a mechanism for monitoring gender parity in staffing. An analysis of the consolidated gender-disaggregated data on UNCT staffing showed that women are under-represented, with an overall representation rate of 34%, compared to 66% for men in most staff categories. In relation to the highest levels of responsibility: (i) there are only 2 women (14%) compared to 12 men (86%) at the D1-D2 levels for international staff and (ii) interestingly, concerning national staff and service contracts, the only professional category that has more representation of women than men is the NOD level, with 4 women compared to 1 man. There is a wide disparity at the G2 to G3 level, with only 8% of women, especially at the G2 level, with only 2 women (4%) compared to 250 men (96%).

### 4.2.5 Gender architecture and capacities

The performance of UNCT Nigeria in this dimension area can be improved. UNCT meets minimum requirements for one indicator but approaches minimum standards for the other indicator.

Indicator 5.1. Concerning the GTG, the UNCT approaches minimum requirements. The GTG is chaired by the UN Women Deputy Country Representative. The group has a TOR and an approved annual work plan, and it meets regularly (25 meetings held during the past year). Members include at least 50% senior staff (P4 and above; NOC and above). Nevertheless, the GTG has not provided substantive input into the development of the UNSDPF 2018-2022, although the group is currently leading the process of updating the CCA and thematic groups include one gender focal point in their composition. To enhance performance in this regard, the GTG must provide substantive input into the development of the next UNSDPF including CCA, strategic prioritization, and results framework.

Indicator 5.2. Concerning UNCT’s capacities for gender mainstreaming, the performance of UNCT is adequate. A substantive inter-agency gender capacity development activity for UN staff was carried out in July 2020 (training on the Enabling Environment Guidelines) led by GTG, HR network, the Gender Parity Team at UN Women HQ and RCO. In addition, a presentation on the Enabling Environment Guidelines for UNCT was undertaken by GTG in August 2020. On the other hand, a capacity needs assessment was conducted during the GTG retreat in 2020 and then a capacity development plan is established. Nevertheless, induction materials do not include GEEW commitments and gender development challenges of the country. To enhance performance in this regard, the UN gender equality briefing kit must be updated and utilized for orientation of new staff members and consultants.

### 4.2.6 Resources

This is one of the dimension areas best performed by UNCT, with the only indicator meeting minimum requirements.

Indicator 6.1. The UNCT has carried out one training on the gender marker last year, addressed at the joint M&E group. On the other hand, gender equality and the empowerment of women is mainstreamed into most of the activities being implemented by the UN system in Nigeria. The 2019 Nigeria One UN report presents an analysis of the gender marker, showing that over 83% of the activities/services delivered contributed to or has GEEW as primary objective of the interventions. To exceed minimum requirements for this indicator, it is needed to establish (and exceed) a financial target for program allocation for GEEW.

### 4.2.7 Results

This is the other dimension area best performed by UNCT, with the only indicator meeting minimum requirements.

Indicator 7.1. The UNCT is on track to achieve all gender equality and the empowerment of women results planned in the UNSDPF 20108-2022 result matrix in line with SDG priorities including SDG 5, as showed in the UN INFO Indicators report. To exceed minimum requirements for this indicator, at least one outcome level UNSDPF result must contribute to transformative change in relation to gender equality and the empowerment of women. Therefore, UNCT should be able to determine whether any outcome level UNSDPF result has contributed to substantial GEEW change in the country by the end of the current planning cycle.

# CONCLUSION

This scorecard exercise found 1 indicator to be missing, where UNCT should urgently enhance performance:

- Gender parity in staffing is achieved (indicator 4.3).

It further revealed 7 indicators approaching minimum requirements, where UNCT should concentrate efforts to upgrade the scorings in the next reporting:

- Common country assessment integrates gender analysis (indicator 1.1);

- Gender equality mainstreamed in UNDAF outcomes (indicator 1.2);

- UNDAF indicators measure changes on gender equality (indicator 1.3);

- Joint Programs contribute to reducing gender inequalities (indicator 2.1);

- Communication and advocacy address areas of gender inequality (indicator 2.2);

- UNCT collaborates and engages with Government on gender equality and the empowerment of women (indicator 3.1);

- Gender Coordination Mechanism is empowered to influence the UNCT for gender equality and the empowerment of women (indicator 5.1).

The assessment found UNCT adequate performance for 6 indicators that are meeting minimum standards. UNCT could strengthen efforts to move these indicators from meeting to exceeding minimum standards in the next reporting, serving as global leader for other UNCTs:

- UNCT collaborates and engages with women’s/gender equality CSO (indicator 3.2);

- UNCT leadership is committed to championing gender equality (indicator 4.1);

- Organizational culture fully supports promotion of gender equality and the empowerment of women (indicator 4.2);

- UNCT has adequate capacities developed for gender mainstreaming (5.2);

- Adequate resources for gender mainstreaming are allocated and tracked (indicator 6.1);

- UN programmes make a significant contribution to gender equality in the country (indicator 7.1).

The exercise revealed exceptional performance for 1 indicator:

- UNDAF monitoring and evaluation measures progress against planned gender equality results (indicator 2.3).

As a result of the assessment, strengths of UNCT Nigeria related to GEEW are: (i) M&E, (ii) leadership, (iii) organizational culture, (iv) UNCT capacities for gender mainstreaming, (v) resources and (vi) results.

Areas requiring improvement are: (i) CCA, (ii) UNSDPF outcomes, (iii) UNSDPF indicators, (iv) joint programmes, (v) communication & advocacy, (vi) partnerships and (vii) the GTG. These areas might become potential strengths of UNCT if the right action is taken in the short-term.

The weakness/area requiring major improvement is: (i) gender parity in staffing.

# ACTION PLAN

The members of the assessment team, together with the consultant, worked on an action plan during the workshop held in February. Scorecard findings fed into a structured UNCT SWAP-scorecard action plan designed for UNCT performance improvement on GEEW, which can be found in annex C.

The action plan further underlines the gaps between UN minimum requirements and UNCT practices identified in the findings by indicator (annex B). It includes steps to be taken, time-frame, allocation of responsibility, resources required and means of verification. It also points out the linkages to the SWAP-scorecard indicators for tracking purposes.

With the aim to ensure a comprehensive response to many of the issues highlighted in the action plan, a good understanding and appropriation of the recommendations by UNCT is needed.

The action plan requires endorsement and a management response at the UNCT senior management level. As set out in the scorecard guidelines, the action plan must be on the agenda of UNCT HOA meetings to ensure follow up, at least every six months until all actions are completed.

The action plan should further be part of the GTG annual work plan. However, the responsibility for follow-up needs to be shared among UNCT agencies and sectors to encourage decentralization of responsibility and accountability for GEEW. For that reason, inter-agency teams other than GTG are assigned responsibilities in the action plan. At the core of the process, UNCT HOA must coordinate efforts for better delivering on GEEW.

To conclude, the UN Women Coordination Division and the UNCT-SWAP Gender Equality Scorecard helpdesk are currently working to launch an online reporting platform for comprehensive and annual scorecard reporting by end of 2021. In this way, annual progress on scorecard indicators must be reported every year in the platform.

# ANNEXES

## Annex A: Organizational culture staff survey results in Nigeria

BREAKDOWN OF SURVEY RESPONSES BY SET OF QUESTIONS

Set 1: Staff perception of gender equality in UN system

Set 2: Equal treatment in the work-place

Set 3: Work-life balance

The charts display the positive responses (strongly agree and agree).

Survey opened December 2020.

436 responses.

Confidence interval of 7.5.

SURVEY RESULTS BY GENDER

## UNCT Nigeria - SWAP scorecard findings by indicator

- PLANNING

| INDICATOR 1.1: COMMON COUNTRY ANALYSIS INTEGRATES GENDER ANALYSIS |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| CCA or equivalent includes: a) Gender analysis across the majority of sectors including underlying causes of gender inequality and discrimination in line with SDG priorities including SDG 5; and b) Some sex-disaggregated and gender-sensitive data. | CCA or equivalent includes: a) Gender analysis across all sectors including underlying causes of gender inequality and discrimination in line with SDG priorities including SDG 5; and b) Consistent sex-disaggregated and gender-sensitive data. | CCA or equivalent meets minimum requirements and includes: c) Targeted gender analysis of those furthest behind. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) Gender analysis is integrated across the majority of sectors in the current CCA, dated 2016, including underlying causes of gender inequality and discrimination, in line with SDG priorities including SDG 5. In the CCA report, gender equality is extensively discussed across 3 main areas: i) gender mainstreaming, women’s empowerment, ii) violence against women and girls, and iii) child abuse and protection from early marriage and harmful practices. Gender equality is also discussed in other analyses of sectors although some of them do not include an in-depth discussion on underlying causes of gender inequality and discrimination. In total, 61% of the sectors/areas covered by the CCA, including the recommendation and indicator sections, are addressing gender equality. In summary, gender analysis is included across the analysis of the following sectors: (i) health, (ii) education, (iii) gender, (iv) justice, governance, peace, and security and further across (v) the recommendation and (vi) indicator for SDG sections. It is noted that the health, education and justice, governance, peace and security sectors would need improvement as far as GEEW is concerned. On the contrary, gender analysis is not included across the Nigerian development context and the analysis of the following sectors: (i) inclusive economic growth and prosperity, (ii) youth unemployment, (iii) comparative advantage and (iv) planet environment protection, resilience, and sustainable development. In 2020, the UN in Nigeria embarked on the process of developing the 2021 CCA document. To ensure that GEEW is properly articulated in the document, gender focal points were embedded in the thematic groups for the development of diagnostic papers for each of 17 SDGs and other thematic areas. At the time of this assessment, 20 out of the 25 expected diagnostic papers have been produced. The analysis of the submitted draft diagnostic papers is as follows: - SDG 1 (No poverty) and SDG 2 (Zero Hunger) diagnostic papers mention issues of gender equality, but no detailed analysis is provided for any of the drafts; - SDG 5 (Gender Equality) and SDG 10 (Reduced Inequalities) diagnostic papers provide detailed gender analysis given the fact that these SDGs are gender-focused; - SDG 4 (Quality Education) diagnostic paper provides information about some aspects of gender analysis; - SDG 16 (Peace, Justice and Strong institutions) paper includes gender analysis and addresses specific killings, sexual gender-based violence and other forms of violence affecting women and girls as well as gender barriers to access to justice; - All the other diagnostic papers - except for SDG 3 (Health), SDG 11 (Sustainable Cities and Communities), SDG 13 (Climate change), and for thematic areas on human rights and risk profile which are yet to be submitted - do not include analysis on gender equality. Since the process is ongoing there is an opportunity for UN Nigeria to ensure that GEEW is incorporated in diagnostic papers and the final CCA document to be produced. b) In the 2016 CCA report, some sectors include sex-disaggregated and gender-sensitive data where available. Data disaggregated by sex are provided under Education, Gender and Justice, Governance, Peace and Security, giving a total score of 38% of sectors providing sex-disaggregated data. It is surprising to find out that the health sector does not provide data disaggregated by sex. The analysis of the draft diagnostic papers for the upcoming CCA, which are currently under review, revealed that: - Sex-disaggregated data are provided in SDG 1 (No Poverty) only for children; - Sex-disaggregated data are partly provided in SDG 2 (Zero Hunger) where “the proportion of arable land to men and women” is mentioned; - Under SDG 4 (Quality Education), detailed sex-disaggregated data are provided; - The analysis of SDG 5 (Gender Equality) and SDG 10 (Reduced Inequalities) are dedicated to gender hence sex disaggregation data are provided based on availability; - A review of other SDGs drafts CCA diagnostic papers revealed that data could have been disaggregated by sex for many of the elements. In conclusion, efforts need to be made by the UNCT to disaggregate data by sex for most CCA diagnostic papers and the final document. c) The current CCA (2016) does not include a targeted gender analysis of those furthest behind. Efforts need to be made to include this analysis in the upcoming final CCA document. |  |  |
| Evidence or means of verification: - Nigeria Common Country Analysis (CCA) Report 2016, UNCT Nigeria, October 31, 2016; - List of thematic group members for the development of the upcoming CCA report, with gender focal members embedded; - CCA Diagnostic Papers submitted as of January 15, 2021. |  |  |

| INDICATOR 1.2: GENDER EQUALITY MAINSTREAMED IN UNDAF OUTCOMES |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) Gender equality and the empowerment of women is visibly mainstreamed across some outcome areas in line with SDG priorities including SDG 5. | a) Gender equality and the empowerment of women is visibly mainstreamed across all outcome areas in line with SDG priorities including SDG 5. or b) One UNDAF outcome specifically targets gender equality in line with UNDAF Theory of Change and SDG priorities including SDG 5. | a) Gender equality and the empowerment of women is visibly mainstreamed across all outcome areas in line with SDG priorities including SDG 5. and b) One UNDAF outcome specifically targets gender equality in line with UNDAF Theory of Change and SDG priorities including SDG 5. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) The UNSDPF-2018-2022 was developed under several pillars; one of the major pillars of engagement being gender equality and the empowerment of women. The UNSDPF-2018-2022 problem analysis considers the intersection of gender equality with poverty and in turn, prescribes promoting gender equality as central to addressing development and humanitarian challenges. All three result areas under the UNSDPF refer to gender equality, including safeguarding the civil and socio-economic well-being of women, girls, boys and men, as being central to the development process. However, a more in-depth analysis of the document revealed the following: - UNSDPF Result Area 1 (Governance, human rights, peace, and security) visibly mainstreams GEEW since GEEW is mainstreamed across outcomes 1 and 2; - UNSDPF Result Area 2 (Equitable quality basic services) partially mainstreams GEEW since GEEW is mainstreamed across outcomes 5 and 6 but not across outcomes 3 and 4; - UNSDPF Result Area 3 (Sustainable and inclusive economic growth & development SDG) does not properly mainstreaming GEEW since GEEW is only mainstreamed across outcome 7 but not at all across outcomes 8 and 9. In conclusion, the Result Area that does a good job of mainstreaming GEEW is Result Area 1 (Governance, human rights, peace, and security sectors). In summary, GEEW is visibly mainstreamed across outcomes 1 (Good Governance and Rule of Law), 2 (Humanitarian Response, Peacebuilding, and Security), 4 (Learning and Skills Development), 5 (Water, Sanitation and Hygiene), 6 (Protection) and 7 (Diversified Economic Growth) through the formulation of specific outputs that include gender equality and the inclusion of gender references in the narrative of the outcomes. GEEW is not at all mainstreamed across outcomes 3 (Health, Nutrition, and HIV&AIDS), 8 (Population Dynamics), and 9 (Environmental Sustainability and Food Security). Along the same lines as the conclusions drawn for indicator 1.1, it is surprising to note that GEEW is not mainstreamed across health & HIV/AIDS, being it considered a traditional sector. b) No UNSDPF outcome is specifically targeting gender equality and the empowerment of women in line with UNDAF Theory of Change and SDG priorities including SDG 5. In spite that outcome 6 is addressing the prevention and response to violence, abuse, exploitation (including trafficking), and harmful social norms, with a focus on the most disadvantaged, it does not specifically mention gender-based violence. |  |  |
| Evidence or means of verification: - United Nations Sustainable Development Partnership Framework (UNSDPF) 2018-2022, United Nations System in Nigeria. |  |  |

| INDICATOR 1.3: UNDAF INDICATORS MEASURE CHANGES ON GENDER EQUALITY |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| Between one-fifth and one-third (20-33 percent) of UNDAF outcome (and output) indicators measure changes in gender equality and the empowerment of women in line with SDG targets including SDG 5. | Between one-third and one-half (33-50 percent) of UNDAF outcome (and output) indicators measure changes in gender equality and the empowerment of women in line with SDG targets including SDG 5. | More than one-half of UNDAF outcome (and output) indicators measure changes in gender equality and the empowerment of women in line with SDG targets including SDG 5. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: The UNSDPF 2018-2022 has 47 outcome indicators. Out of 47 outcome indicators, 13 measure changes in gender equality and the empowerment of women (27.66%). A particular analysis by outcomes revealed significantly higher levels of gender sensitivity in indicators of outcomes 3, 4 and 6. Nevertheless, indicators of outcomes 2, 5, 7, 8, and 9 are not gender-sensitive at all, as follows: - 2 out 7 under Outcome 1 (Good Governance and Rule of Law); - 0 out of 7 under Outcome 2 (Humanitarian Response, Peacebuilding, and Security); - 3 out of 9 under Outcome 3 (Health, Nutrition, and HIV&AIDS); - 4 out of 6 under Outcome 4 (Learning and Skills Development); - 0 out of 3 under Outcome 5 (Water, Sanitation and Hygiene); - 4 out of 6 under Outcome 6 (Protection); - 0 out of 2 under Outcome 7 (Diversified Economic Growth); - 0 out of 2 under Outcome 8 (Population Dynamics); - 0 out of 5 under Outcome 9 (Environmental Sustainability and Food Security). It is noted that outcome 3 includes indicators that measure changes in GEEW but gender equality is not mainstreamed across the formulation of this outcome. On the contrary, outcomes 2, 5, and 7 do not include any indicator measuring changes in GEEW but gender equality is mainstreamed across the formulation of these outcomes. Output indicators are formulated in UNCT joint work-plan. The assessment qualifies an indicator based on either a definition that includes disaggregation by sex or a gender-specific definition. To conclude, the UNSDPF document notes the major gap on gender disaggregated data on various social and economic sectors and addresses this gap as follows: “It will help generate adequate demographic data disaggregated by gender, age, location (rural or urban) and integrated into the national economic growth and development process with due cognizance given to environmental protection and factors in all circumstances and activities as this will help Nigeria attain sustainable and inclusive economic growth and development .” |  |  |
| Evidence or means of verification: - United Nations Sustainable Development Partnership Framework (UNSDPF) 2018-2022, United Nations System in Nigeria. |  |  |

- PROGRAMMING AND M&E

| INDICATOR 2.1: JOINT PROGRAMS CONTRIBUTE TO REDUCING GENDER INEQUALITIES |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) Gender equality is visibly mainstreamed into at least 50 percent of JPs operational at the time of assessment. or b) A Joint Program on promoting gender equality and the empowerment of women is operational over current UNDAF period in line with SDG priorities including SDG 5. | a) Gender equality is visibly mainstreamed into all JPs operational at the time of assessment. and b) A Joint Program on promoting gender equality and the empowerment of women is operational over current UNDAF period in line with SDG priorities including SDG 5. | Meets minimum requirements and c) A system is in place to ensure gender mainstreaming in JPs. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) There are 7 joint programmes (JPs) operational in Nigeria at the time of assessment. The analysis of how they contribute to reducing gender inequalities is presented below: 1. Title: Transitioning from Humanitarian relief to Long Term Development: Addressing the Herdsmen- Farmers Conflict in Nigeria. Implementing agencies: UNDP, UNHCR and FAO. The project is primarily focused on SDGs 1,2,8,15 and 16 and does not include any gender-focused SDG (i.e. 5 and 10). The contextual analysis does not consider the gender dimension of the conflict. However, 2 of the activities proposed, such as a) community-based protection and b) livelihood and empowerment mention “the response to violations of rights including SGBV” and set out that “women and youths will be part of the livelihood and empowerment project”. In any case, these 2 references to GEEW are not sufficient for proper integration of gender and therefore the team concluded that gender is not visibly mainstreamed into this JP. 2. Title: Spotlight Initiative to eliminate violence against women and girls in Nigeria. Implementing agencies: UNDP, UNICEF, Un Women, UNESCO and UNFPA. The project is primarily focused on promoting gender equality and empowerment of women through designing and implementing programmes that prevent and respond to violence against women and girls. The aim is to support a Nigeria where all women and girls, particularly the most vulnerable, live a life free from violence and harmful practices. The analysis of the country situation, the expected results and the activities are all gender-focused. This JP directly addresses issues of gender-based violence, harmful traditional practices, access to basic services, availability of appropriate laws and capacity building for women’s group. 3. Title: Peace-Building Fund Project: Integrated Approach to building Peace in Nigeria’s Farmer-header Crisis. Implementing agencies: UNDP, UN women, FAO and OHCHR. This JP has a gender marker score of 2 which means that gender equality is a significant objective. Over 32.9% (USD 928.5 thousand) of the total budget (USD 3 million) will be allocated to activities pursuing gender equality and the empowerment of women, with UN Women as one of the key implementing agencies. The project recognizes that even though more men than women may have been killed on both sides of the clashes in the affected states because of their direct involvement in the fighting, women and girls are the population worst affected by the physical and psychological effects during and in the aftermath of these violent clashes. Based on this analysis, the team concluded that gender equality is visibly mainstreamed into this JP. 4. Title: Joint SDG funds: Institutionalizing Social Protection for Accelerated SDG Implementation in Nigeria. Implementing agencies: UNICEF, ILO, UNDP, WFP, WHO and Government. This JP has a gender marker score of 2 which means that gender equality remains a significant objective. The project contributes to Nigeria UNSDPF outcome 6 which states that by 2022, the National and State Social Protection Policies are implemented and adequately financed with protection systems and services strengthened to effectively prevent and respond to violence, abuse, exploitation (including trafficking) and harmful social norms, with a focus on the most disadvantaged, the majority of which are women and girls. The project is primarily focused on SDGs 1 (No poverty), 2 (Zero hunger) ,3 (Good health and wellbeing), 4 (Education) and 10 (Reduced inequalities), including gender-focused elements aimed at instituting social protection. Nigeria has adopted the National Social Protection Policy which has the overarching goal of establishing a gender-sensitive and age-appropriate framework to ensure a minimum social floor for all Nigerian citizens for a life of dignity which is gender-focused. Additionally, the communal engagement of women and adolescent girls in social behavior change communication activities will improve their participation in the decision-making process, creating conditions to advance GEEW (SDG 5). Based on this analysis, the team concluded that this JP significantly addresses the promotion of gender equality and the empowerment of women. 5. Title: Elimination of Female Genital Mutilation: Accelerating Change. Implementing agencies: UNFPA and UNICEF. Nigeria joined the second phase of the Global UNFPA-UNICEF Joint Program-Accelerating Change in 2013, which is implemented in partnership with the government of Nigeria, through the Federal Ministries of Health and Women Affairs and Social Development. This JP is currently being implemented in 16 countries, links community-level transformation of social/gender norms that often drive FGM with laws banning the practice and access to quality sexual and reproductive health (SRH) and child protection services for girls and women at risk of and affected by FGM. The Nigeria programme is currently deploring various strategies such as health systems capacity enhancement, social norms change, policy advocacy, coordination, data, and research as well as documentation to mobilize accelerated actions towards the abandonment of the harmful practice nationally and in 5 high burdened states of Ebonyi, Ekiti, Imo, Osun, and Oyo. In the last ten year, the joint program has recorded significant milestones in Nigeria. 6. Title: Nigeria UN Plus Offer for Socio-Economic Recovery 2020-2022. Implementing partners: all UN agencies. This is the UN Nigeria socio-economic recovery response plan to COVID-19. The plan has 4 pillars, strengthening health systems and response, protection, macroeconomic stability & economic recovery, and social cohesion & community resilience: - Under pillar 1, Health: one indicator is gender-sensitive. The need to address gender-based violence is mentioned and output 7 is focused on gender-based violence; - Under pillar 2, Protection: all 4 population-based indicators are disaggregated by sex and outputs are gender-focused; - Under pillar 3, Macroeconomic: indicators are not disaggregated by sex and there is not any gender-focused output. - Under pillar 4, Social cohesion: one of the activities is to enhance advocacy and sensitization efforts to prevent and respond to GBV. Based on this analysis, since one of the pillars is on protection and is gender-focused while 2 of the pillars either have at least 1 output or activity that are looking at the issue of gender equality, the group concluded that gender equality is properly integrated into this JP. 7. Title: Risk Communication and Community Engagement (RCCE) under the UN Support to the National COVID-19 Multi-Sectoral Pandemic Response. Implementing agencies: UNICEF, UNAIDS, UNFPA, UN Women and WHO. The project has the overall objective of influencing individual behavior change with messages on effective handwashing and hygiene practices; social distancing; combating stigmatization and using risk communication and community engagement to mitigate socio-economic consequences of the Covid-19 pandemic and associated measures. Concerning the intended outcomes areas of the programme, 3 outcomes out of 8 are targeting GEEW. These outcomes are the following: (i) Risks and impact of GBV, including the intersecting SRH consequences, are mitigated and minimized; (ii) Social safety net support, including health and social essential services, have mitigated the risks and impacts of COVID 19 on the most vulnerable women, girls, and young people and (iii) Affected women, girls, and young people lead and participate in COVID-19 response planning and monitoring. Based on this analysis, the team concluded that gender equality is visibly mainstreamed into this JP. 8. Restoring and promoting sustainable agriculture-based livelihoods for food security, employment, and nutrition improvement in Borno State. Implementing agencies: WFP/FAO/UN Women. The objective of this programme is to enhance social protection, through the creation of employment and the promotion of environment and climate-friendly livelihood opportunities, with a special focus on women, youth and vulnerable households. One result, out of 3, is addressed at small holder farmers (men, women and youth) for enhancing skills and knowledge to implement good agricultural, nutrition, and gender practices. There are some gender-specific activities in the JP work plan. Based on this analysis, it is concluded that gender equality is mainstreamed into this JP. From the analysis above, gender is visibly mainstreamed in 7 out of 8 JPs currently operational in Nigeria. b) Two (2) joint programs on promoting gender equality and the empowerment of women are operational at the time of the assessment, in line with SDG priorities including SDG 5. They are the following programmes: “Spotlight Initiative to eliminate violence against women and girls in Nigeria” and “Elimination of Female Genital Mutilation: Accelerating Change”. c) There is not a system in place to ensure gender mainstreaming in joint programmes. A discussion on this topic has yet to be initiated at the GTG meetings. |  |  |
| Evidence or means of verification: - JP ProDoc “Transitioning from Humanitarian relief to Long Term Development: Addressing the Herdsmen- Farmers Conflict in Nigeria” (36 months), July 2018; - JP ProDoc “Spotlight Initiative to eliminate violence against women and girls in Nigeria”, Jan 2019 - December 2022; - JP ProDoc “Integrated Approach to building Peace in Nigeria’s Farmer-header Crisis” (24 months), January 2019; - JP ProDoc “Institutionalizing Social Protection for accelerated SDG implementation in Nigeria”, Jan 2020-Jan 2022; - JP ProDoc “Elimination of Female Genital Mutilation: Accelerating Change”, January 2018-December 2021, (https://www.unfpa.org/unfpa-unicef-joint-programme-female-genital-mutilations); - JP ProDoc “Nigeria UN Plus Offer for Socio-Economic Recovery 2020-2022”; - JP ProDoc “Risk Communication and Community Engagement (RCCE) under the UN Support to the National COVID-19 Multi-Sectoral Pandemic Response”, May 2020 - April 2021; - JP ProDoc “Restoring and promoting sustainable agriculture-based livelihoods for food security, employment, and nutrition improvement in Borno State”, February 2018-January 2021. |  |  |

| INDICATOR 2.2: COMMUNICATION AND ADVOCACY ADDRESS AREAS OF GENDER INEQUALITY |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) The UNCT has contributed collaboratively to at least one joint communication activity on GEEW during the past year. | a) The UNCT has contributed collaboratively to at least one joint advocacy campaign on GEEW during the past year. and b) Interagency Communication Group Annual Work Plan or equivalent visibly includes GEEW communication and advocacy. | Meets minimum requirements and c) The UNCT has contributed collaboratively to communication or advocacy in at least one non-traditional thematic area during the past year. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) The UNCT has contributed collaboratively to joint communication activities on GEEW during the past year, as follows: - In the context of eliminating violence against women and girls, UN Nigeria in collaboration with the Federal Ministry of Women Affairs and supported by EU-UN Spotlight mobilized and engaged with Traditional and Religious Leaders for Community Action to End all forms of VAWG. The conference was held on August 6, 2020. A video message of the Deputy Secretary-General (DSG) was screened at the Webinar. - With the spike in domestic violence as a result of the COVID-19 lockdown, UN Nigeria in collaboration with the Federal Ministry of Women Affairs, EU-UN Spotlight Initiative and Nigeria’s Governors Forum held a High-Level Town Hall Meeting on Sexual and Gender-Based Violence on 25 August, 2020 to declare a state of emergency on the status of GBV in the country. The Town Hall meeting brought together survivors, civil society representatives, government, police and representatives from the EU and UN in Nigeria. It was broadcast live on Channels TV and focused on improving access to justice and the adoption of legal frameworks that protect women and girls. There was a special message from the President of the Federal Republic of Nigeria. - To celebrate the 16 Days of Activism to End Violence against Women and Girls, the UN system in Nigeria, UN Women, Generation Equality, and Spotlight Initiative launched #IDeyWithHer campaign tailored after the #WithHer campaign, seeking to raise awareness of gender norms and harmful stereotypes that perpetuate violence against women and girls. - Against the backdrop of the high incident of rape in Nigeria during the COVID19 lockdown, social media promotion of Ending Rape, EVAWG & Harmful Practices were hugely disseminated during March - June on the social media platforms of all UN agencies. Messages, cards, and graphics created by UN Women, GTG, UNIC, UNFPA and UNICEF were disseminated. - The National Situation and Data Dashboard for ending VAWG in Nigeria was launched on November 2020, 17 by the UN DSG. The aim was to improve and strengthen measurement and methodologies for VAWG data collection and harmonization in Nigeria. b) The interagency communication group does not have an annual joint action plan. There is a communication strategy for UN Nigeria but it does not visibly include GEEW communication and advocacy. c) The UNCT has not contributed collaboratively to communication or advocacy in any non-traditional thematic area during the past year. |  |  |
| Evidence or means of verification: - https://nigeria.un.org/en/86873-traditional-and-religious-leaders-urged-mobilise-community-action-end-violence-against-women; - Minutes of the High-Level Town Hall Meeting on Sexual and Gender Based Violence, August 25 2020; - https://www.vanguardngr.com/2020/11/un-charges-nigerian-govt-stakeholders-to-end-shadow-pandemic-gender-based-violence/; - 16 Days of Activism Report, 2020, UN Women; - #IDeyWithHer hashtag on Twitter; - https://opinion.premiumtimesng.com/2020/11/25/turning-the-tide-on-gender-based-violence-in-nigeria-in-the-midst-of-covid-19-by-edward-kallon/; - https://www.spotlightinitiative.org/fr/node/44676; - UNCT communication strategy. |  |  |

| INDICATOR 2.3: UNDAF MONITORING AND EVALUATION MEASURES PROGRESS AGAINST PLANNED GENDER EQUALITY RESULTS |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| Meets one of the following: a) UNDAF Results Matrix data for gender-sensitive indicators gathered as planned. b) UNDAF reviews/ evaluations assess progress against gender-specific results. | Meets two of the following: a) UNDAF Results Matrix data for gender-sensitive indicators gathered as planned. b) UNDAF reviews/ evaluations assess progress against gender-specific results. c) The M&E Group or equivalent has received technical training on gender-sensitive M&E at least once during the current UNDAF cycle. | Meets all of the following: a) UNDAF Results Matrix data for gender-sensitive indicators gathered as planned. b) UNDAF reviews/ evaluations assess progress against gender-specific results. c) The M&E Group or equivalent has received technical training on gender-sensitive M&E at least once during the current UNDAF cycle. |
| Score: Exceed minimum requirements |  |  |
| Findings and explanation: a) UNSDPF Results Matrix data for gender-sensitive indicators are being gathered as planned. The Nigeria UNSDPF Result and Resource Matrix have 3 results areas, as follows: - Result Area 1: Governance, Human rights, Peace and Security; - Result Area 2: Equitable Quality Basic Services; - Result Area 3: Sustainable and Inclusive Economic Growth and Development. There are 9 outcomes distributed among these 3 Result Areas, with 2 outcomes in Result Area 1, 4 outcomes in Result Area 2, and 3 outcomes in Result Area 3, and 28 outputs in total. 117 indicators are tracked under the UNSDPF with 47 tracked at the outcome and 70 at the output level. 26 (22%) of the indicators are gender-focused and data for 20 (77%) of the indicators have been reported on the UNINFO although there are still gaps to be filled, which the M&E group is addressing. Further analysis of the indicators revealed that there are about 33 indicators that could have sex disaggregation but currently are not disaggregated by sex even when the indicator statement includes it, as shown in the table below. This is an area that the M&E group will also focus on to ensure that data are properly disaggregated. Summary of UNSDPF to know how many are gender-focused and availability of gender Maker. Variables; Result Area 1; Result Area 2; Result Area 3; Grand Total. Outcome Indicators; Output Indicators; Total; Outcome Indicators; Output Indicators; Total; Outcome Indicators; Output Indicators; Total. Total Number of Indicators; 14; 15; 29; 24; 37; 61; 9; 18; 27; 117. Number Gender-focused; 2; 7; 9; 9; 7; 16; 0; 1; 1; 26. Number with gender data reported; 2; 5; 7; 7; 6; 13; 0; 0; 0; 20. Number with capacity to have gender data disaggregation but don’t have; 3; 4; 7; 9; 16; 25; 1; 0; 1; 33. b) The Nigeria 2019 One UN Report included a comprehensive component on GEEW (within outcomes 1, 2, 4, and 6). Also, an analysis of gender marker was presented in the report which shows the percentage of gender-related activities and the amount of resources spent per marker for gender equality and women/girl’s empowerment. The midterm review of the Nigeria UNSDPF 2018-2022 is slated for 2021 hence no evaluation report for review. c) During the M&E group meeting on 23rd September 2020, a member of the group from UN Women made a presentation on “The Gender Marker” to the rest of the members. It was through a Zoom meeting but the attendance was not taken on the day of the meeting. The PowerPoint presentation is in the shared drive. |
| Evidence or means of verification: - Nigeria UNSDPF 2018-2022; - Tables of indicators of outcomes and outputs for Result Areas 1, 2 and 3 and UNCT joint work plan 2020; - UN INFO indicators report; - Draft 2019 One UN report; - Presentation on the Gender Marker for the joint M&E Group, 19 August 2020; - Minutes of the M&E group meeting, September 23, 2020. |  |  |

- PARTNERSHIPS

| INDICATOR 3.1: UNCT COLLABORATES AND ENGAGES WITH GOVERNMENT ON GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) The UNCT has collaborated with at least one government agency on a joint initiative that fosters gender equality within the current UNDAF cycle. | Meets two of the following: a) The UNCT has collaborated with at least two government agencies on a joint initiative that fosters gender equality within the current UNDAF cycle. b) The National Women’s Machinery participates in UNDAF consultations: country analysis, strategic prioritization, implementation, M&E. c) The UNCT has made at least one contribution to substantively strengthen Government participation and engagement in gender-related SDGs localization and/or implementation. | Meets all of the following: a) The UNCT has collaborated with at least two government agencies on a joint initiative that fosters gender equality within the current UNDAF cycle. b) The National Women’s Machinery participates in UNDAF consultations: country analysis, strategic prioritization, implementation, M&E. c) The UNCT has made at least one contribution to substantively strengthen Government participation and engagement in gender-related SDGs localization and/or implementation. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) The UNCT has collaborated with a number of government agencies on joint initiative that fosters gender equality within the current UNDAF cycle: - UNWOMEN, UNFPA, UNHCR, UNOCHA, FAO and WFP, through the GTG, collaborated with the Federal Ministry of Women Affairs for specific sensitization and advocacy activities for the 2020 16 Days of Activism against Gender-Based Violence. - UNICEF, UN Women and UNFPA conducted a training of 37 members of the Gender-Based Violence and Child Protection Response Team in Sokoto State in Jun 2020, in collaboration with the State of Ministry of Women Affairs, as part of a joint Spotlight Initiative and adaptations of programmes in light of COVID-19. The training focused on basic principles of child protection, case management and child protection information management system (CPIMS) to strengthen their capacity to provide prevention and response services for children and women. - UNICEF, together with UNFPA and UN Women, supported the Federal Ministry of Women Affairs and other stakeholders to develop a 5-year Plan of Action on Child Protection, ensuring that child marriage and gender-based violence are identified as priority areas in the plan (UNICEF-Government of Nigeria Programme of Cooperation, 2018-2022 Programme Strategy Note: Child Protection). - UNFPA as lead, alongside with UNHCR, supported strengthening coordination and programming for GBV in the North East humanitarian response (2018-2019). UNFPA, working with other UN agencies (UNHCR, FAO, WFP, UNOCHA) co-led the Call to Action on GBV in humanitarian context with the Federal Ministry of Women. b) The Federal Ministry of Women has not participated in the consultations of the current UNSDPF 2018-2022. Concerning the current process of development of the upcoming CCA, a guidance is provided to CCA thematic groups in the preparation of the diagnostic papers for them to liaise with all relevant stakeholders. To date, no group has reported that they consulted stakeholders. However, meetings and validation workshops with different stakeholders are expected to be carried out once all SDG papers are submitted. c) The UNCT has not made any contribution to substantively strengthen Government participation and engagement in gender-related SDGs localization and/or implementation. |  |  |
| Evidence or means of verification: - 16 Days of Activism Report, 2020, UN Women; - Spotlight Initiative Country Programme Document, 2019; - 5-year National Plan of Action on Child Protection (2018-2022); - UNICEF - Government of Nigeria Programme of Cooperation, 2018-2022 Programme Strategy Note: Child Protection; - Call to Action on Protection from Gender-based Violence in Emergencies: Northeast Nigeria Road Map 2018-2019. |  |  |

| INDICATOR 3.2: UNCT COLLABORATES AND ENGAGES WITH WOMEN’S/GENDER EQUALITY CSO |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| The UNCT has collaborated with GEEW CSO and women’s rights advocates on at least one joint initiative that fosters gender equality and empowerment of women within the current UNDAF cycle. | Meets two of the following: a) The UNCT has collaborated with GEEW CSO and women’s rights advocates on at least two joint initiatives that foster gender equality and empowerment of women within the current UNDAF cycle. b) GEEW CSO participates in UNDAF consultations: country analysis, strategic prioritization, implementation, M&E. c) The UNCT has made at least one contribution to substantively strengthen GEEW CSO participation and engagement in gender-related SDGs localization or implementation. | Meets all of the following: a) The UNCT has collaborated with GEEW CSO and women’s rights advocates on at least two joint initiatives that foster gender equality and empowerment of women within the current UNDAF cycle. b) GEEW CSO participates in UNDAF consultations: country analysis, strategic prioritization, implementation, M&E. c) The UNCT has made at least one contribution to substantively strengthen GEEW CSO participation and engagement in gender-related SDGs localization and/or implementation. |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: a) The UNCT has collaborated with GEEW CSO and/or women’s rights advocates on joint initiatives that fosters gender equality and empowerment of women within the current UNSDPF cycle: - OCHA, in collaboration with UN Women, IOM, WFP FAO, UNICEF, UNFPA and UNHCR supported an Inter-Agency Humanitarian Evaluation (IAHE) Mission on Gender Equality and the Empowerment of Women and Girls in February 2020. The GEEW CSO who further collaborated with UN agencies and other international NGOs was Borno Women Development Organization. The Inter-Agency Humanitarian Evaluation (IAHE) on Gender Equality and the Empowerment of Women and Girls (GEEWG) assessed the progress on the operationalization of the Inter-Agency Standing Committee (IASC) GEEWG agenda since 2017. The IAHE also captured best practices and provided recommendations to further mainstream GEEWG into humanitarian action. - With support from UN Women, UN OCHA and UNHCR, the Borno State Network of Women CSOs held an event to commemorate the 16 days of activism and to formally launched the network that was established in March 2020. During the formal launch event, series of discussion sessions were held to look at the state of women and girls in the states and come up with recommendations to strengthen their engagements. Over 30 women-led organizations were in attendance including representatives of Nigerian Government Ministries, Departments and Agencies (MDAs) and the academia. The event also raised awareness and knowledge about the impact of the northeast conflict on the population, especially women as well as their relentless support for the most vulnerable since the very early days of the crisis. - UNDP supported by other UN agencies under the EU-UN Joint Spotlight Initiative with the National Human Rights Commission organized a high-level Human Rights Defenders Workshop addressed at human rights partners who support Interventions for women and girls in Nigeria. The workshop provided a space for practice for human rights defenders and a launch of the community of practice and their guidelines for engagement. b) GEEW CSOs have not participated in the consultations of the current UNSDPF 2018-2022. Concerning the current process of development of the upcoming CCA, meetings and validation workshops with different stakeholders are expected to be carried out once all SDG papers are submitted. c) UNCT, through WFP, FAO, UNMAS, UN Women, UNICEF, IOM, UNFPA and UNDP, collaborated with FAME Foundation, using sport to raise awareness of gender equality and ending GBV in March 2020. The UNCT had a joint football team and branding centered around the SDGs with emphasis on SDG 5. This activity makes it possible for UNCT to meet criterion c, although it is necessary in the near future to strengthen the UN joint contribution in order to reinforce NGO engagement in this aspect. |  |  |
| Evidence or means of verification: - Programme of Gender Evaluation, OCHA, 2020; - Inter-Agency Humanitarian Evaluation on Gender Equality and the Empowerment of Women and Girls (GEEWG), ReliefWeb, 2020; - 16 Days of Activism Report, 2020, UN Women; - News article: Highlights of NHRC/UN-spotlight Initiative 2 Days Workshop on SGBV; - https://regentafricamedia.org/highlights-of-nhrc-un-spotlight-initiative-2-days-workshop-on-sgbv/; - Project report on the Women’s Day Event 2020 -Women and Sports Dialogue-, March 4, 2020; - Project report on the Women’s Day Event 2020 - Generation Equality Football Tournament-, March 5, 2020. |  |  |

- LEADERSHIP AND ORGANIZATIONAL CULTURE

| INDICATOR 4.1: UNCT LEADERSHIP IS COMMITTED TO CHAMPIONING GENDER EQUALITY |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| Meets 2 of the following: a) Gender equality is a regular topic of discussion in HOA meetings during the last 12 months; b) RC demonstrates public championing of gender equality during the last 12 months; c) HOAs are seen by personnel as committed to gender equality in the workplace during the last 12 months; d) Gender equality is reflected in the Assessment of Results and Competencies (ARC) of UNCTs during the last 12 months. | Meets 3 of the following: a) Gender equality is a regular topic of discussion in HOA meetings during the last 12 months; b) RC demonstrates public championing of gender equality during the last 12 months; c) HOAs are seen by personnel as committed to gender equality in the workplace during the last 12 months; d) Gender equality is reflected in the Assessment of Results and Competencies (ARC) of UNCTs during the last 12 months. | Meets all 4 of the following: a) Gender equality is a regular topic of discussion in HOA meetings during the last 12 months; b) RC demonstrates public championing of gender equality during the last 12 months; c) HOAs are seen by personnel as committed to gender equality in the workplace during the last 12 months; d) Gender equality is reflected in the Assessment of Results and Competencies (ARC) |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: a) Over the last 12 months, only 4 standard UNCT meetings were held. Due to the ongoing pandemic, 15 COVID-19 specific meetings were organized, the agenda of which was particularly tailored to addressing the COVID-19 pandemic, mainly targeted towards staff Duty of Care and Social Economic Response and Basket Fund to support the government’s response to COVID-19. - At the January UNCT meeting, in analyzing the prospects of achieving the SDGs, the UNCT noted that progress in gender equality is stagnant based on results of an assessment carried out (iSDG Model) and would not likely be achieved in 2030 even if there are no budgetary ceilings in this area. - At the March meeting, the UNCT met with the Office of the Special Assistant to the President on SDGs (OSSAP-SDGs) as part of the preparatory phase for the 2020 Voluntary National Review (VNR). The VNR is an in-depth review and evidenced reporting on the progress made towards attaining the SDGs. During the meeting, some UN agencies, particularly UNESCO and UNFPA, committed to supporting the gender lens of the process through programmatic investments and inclusion of gender equality respectively. HOA deliberated on the Call to Action on Human Rights by the Secretary-General with seven domains, including gender equality - At the October meeting, the UNCT deliberated and agreed to undertake the Gender Score Card exercise which is aimed at ensuring accountability by senior managers and improving UN accountability of gender indicators. The exercise was further deemed necessary as it is integral to the CCA development that would inform the next cooperation framework. - At the December meeting which took place in the aftermath of the high-level visit by the UN Deputy Secretary-General to Nigeria, key follow-up actions by the UNCT included coordinated UNCT support to the Gender Equality Bill at the National Legislature which UNWOMEN & UNFPA were tasked to lead joint UN policy support to the proposed bill. Nevertheless, this criterion is not considered met by UNCT since at least 60% of HOA meetings (standard + COVID-19 specific meetings) held last year did not address GEEW in substance. b) Over the year 2020, the RC demonstrated his commitment to gender equality through his public championing at events and programmes. 13 speeches made by the RC over the past 12 months included references to GEEW and/or as to how the UNCT is promoting GEEW. Some of his speeches included: (i) remarks at the Nigerian Governors’ Form at the GBV townhall meeting aimed at enhancing gender equality related issues in the States; (ii) RC’s remarks at the Spotlight Initiative Steering Committee meeting on 5 June 2020; (iii) RC’s remarks at the launch of the GBV data situation room; (iv) statement on the launch of the first GBV tracking tool (barometer) on sexual and GBV response in Nigeria; (v) RC’s statement at the virtual townhall meeting on SGBV; (vi) RC’s remarks to mark the 2020 International Women’s Month under the theme “I am Generation Equality: Realizing Women’s Rights for an Equal Future”; (vii) RC speech at the graduation ceremony of beneficiaries of the female artisanship program under the federal government intervention programme on 16 Dec 2020; (viii) RC speech support the development of gender policy during address to Adamawa State Government 14-16 Sept. 2020; (ix) RC's speech commending the government of Nigeria for promoting development and equal rights of women through the Ministry of Women at the commission of the Ministry's new office complex on 16 Jan 2020; (x) RC's speech to the Bauchi State government highlighting empowerment of women as a priority area of investment during an advocacy visit on 8-9 Sep 2020; (xi) RC's speech to the Taraba State government highlighting empowerment of women as a priority area of investment during an advocacy visit on 12-14 Oct 2020; (xii) RC's speech to the Plateau State government highlighting empowerment of women as a priority area of investment during an advocacy visit on 14-16 Oct 2020, and (xiii) RC's speech to the Adamawa State government highlighting empowerment of women as a priority area of investment during an advocacy visit on 14-16 Sep 2020. However, the total number of RC speeches made last year could not be traced. c) As part of the scorecard exercise, a survey was launched for UN staff on organizational culture with a sub-set of the survey focusing on staff perceptions on gender equality in the work place on areas such as the equal representation of women and men at all levels, UNCT commitment to gender equality, etc. This survey, completed by over 400 staff members, revealed a positive and encouraging perception by staff members that HOAs are at the fore of gender equality in the workplace. According to the results of the survey, 76% of staff, either strongly agree or agree with the second question on the organizational culture survey: “Heads of Agencies in this UNCT demonstrate leadership and commitment to gender equality in the workplace”. d) On December 24, 2020, the DCO Director and R-UNSDG Chair jointly rated the 2019 UNCT performance appraisal as ‘Exceeds performance expectations.’ This assessment is based on the implementation of the partnership framework focused around the five key areas of SDGs Implementation, Operationalizing the SDGs Prevention Vision, Strategic Financing and Partnerships, LNOB, and Human Rights in the 2030 Agenda and Business Innovations. In all these five key areas, Gender Equality was a key cross-cutting theme deeply mainstreamed therein. Particularly, the executive summary of the report highlights the fact that ‘over 98% of services/activities delivered had a human rights and/or gender dimension’ with gender equality investments alone grossing $17M. |  |  |
| Evidence or means of verification: - The minutes of all (4) UNCT regular meetings held between January and December 2020; - 13 gender-related public speeches made by the RC over the last 12 months; - Survey of UN staff on the perception of the organizational environment concerning the promotion of gender equality; - 2019 UNCT performance appraisal/assessment report. |  |  |

| INDICATOR 4.2: ORGANIZATIONAL CULTURE FULLY SUPPORTS PROMOTION OF GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| Survey results of personnel perception of organizational environment for the promotion of gender equality scored a positive rating of 50-64 percent. | Survey results of personnel perception of organizational environment for promotion of gender equality scored a positive rating of 65-80 percent. | Survey results of personnel perception of organizational environment for promotion of gender equality scored a positive rating of over 80 percent. |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: The survey results of personnel perception of the organizational culture for promotion of gender equality was completed by 436 staff members, 79.36% of respondents being national personnel and 20.64% international personnel. In particular, 68.13% of respondents had SB1-SB5, G1-G7, or NOA-D contract; 17.09% P1-D2 contract, and 14.78 had other contract modalities, such as UNV or SSA/IC. The job of 50.23% of respondents included personnel supervisory functions. In total, 43.81% of respondents were women, 55.96% men, and 0.23% other gender. This finding is important, concluding that women have participated in the survey to a greater extent than men, given the fact that male staff is twice female staff in UN Nigeria (the number of male staff members is double the number of female staff members). The results of the survey indicate a positive response of 74%, meeting the minimum requirements. The analysis of female responses shows an average positive score of 64% across the 10 questions addressing issues of work- life balance, discrimination, and gender equality compared to the 80% positive score from the male counterparts. Thus, if only positive responses from male staff were considered, the UNCT would exceed minimum standards, whereas if only female staff were considered, the UNCT would only approach minimum standards. There were positive responses among male and female respondents on equal participation and efforts by the head of agencies and UN personnel to promote gender equality in the workplace with 76% considering the participation of female staff is paramount at the leadership level. The question concerning the procedures in place by the UN system in Nigeria to protect personal safety and security of staff was the one that received the highest number of positive responses (79%), being the one that also received the highest number of positive responses from women (76%). The set of questions related to the work-life balance is the one that received fewer positive responses than those observed for the other dimensions, which means that UNCT’s efforts need to be reinforced in this regard. In particular, 72% of male staff think that the package of flexible work arrangements (e.g. telecommuting, staggered hours, compressed work schedule) support staff to achieve adequate work-life balance, while only 65% of female staff think so. This question received 17% negative responses from women compared to 11% negative responses from men. The question that received the lowest number of positive responses was the one related to the support from heads of agencies to establish an adequate relationship between work life and home life, with 64% positive responses (72% male, 53% female), 22.27% neutral (19% male, 27% female), and 14% negative responses (9% male, 20% female). As observed, this question is the one that received the highest number of negative responses from female staff (20%). |  |  |
| Evidence or means of verification: - Survey results of personnel perception of organizational environment for the promotion of gender equality. 436 responses (191 female, 244 male and 1 others) out of a total of 2.792 staff; confidence interval of 7.5). |  |  |

| INDICATOR 4.3: GENDER PARITY IN STAFFING IS ACHIEVED |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) The UNCT has in place a mechanism for monitoring gender parity in staffing that is regularly used to monitor parity levels for General Service staff and all professional levels. | Approaches minimum requirements and b) The UNCT can demonstrate positive trends towards achieving parity commitments. | Meets minimum requirements and c) The Business Operations Strategy (BOS) includes gender-specific actions and indicators in at least one Business Operation Area to foster gender equality and women’s empowerment. |
| Score: Missing |  |  |
| Findings and explanation: a) The UNCT is implementing several measures from HQ to country offices aimed at achieving equal representation of women and men at various recruitment levels, such as initiatives for recruiting more women, an equal number of male and female representation at interview panels, etc. However, UNCT does not have a joint mechanism for monitoring gender parity in staffing. This monitoring is done at the agency level. The consolidated data collected as part of this exercise can serve as a baseline for future monitoring. At the agency level, the management of monitoring the gender parity is undertaken by the human resources team on quarterly basis, as specified by some agencies, and the review of some related cases by OMT. b) The UNCT consolidated sex-disaggregated staffing data analysis showed that the representation of women is low, with an overall representation rate of 34% for women, compared to 66% for men. The number of male staff is double the number of female staff. - Concerning international staff, women have a representation rate of 36%, compared to 64% for men. It is highlighted that there are only 2 women (14%) compared to 12 men (86%) at the highest levels of responsibility (D1 and D2). - Concerning national staff and service contracts, women have a representation rate of 34%, compared to 67% for men. SB level is 43% female and 57%, male. G and NO levels are both 33% female and 67%, male. Interestingly, the only professional category that has more representation of women than men is NOD (the highest level of responsibility), with 4 women compared to 1 man. There is a wide disparity at the G2 to G3 level, with only 8% of women. The highest disparity is found at the G2 level, with only 2 women (4%) compared to 250 men (96%). This is because jobs at this level are traditionally perceived as reserved for men, such as driver, clerk and messenger. - Concerning other UNCT staff (UNV, SSA/IC, etc.), the trend is the same as for national and international staff. The representation of women is only 34% compared to 66% for men. c) The Nigeria Business Operation Strategy 2018-2022 was developed with the seven (7) Common BOS Outcome Areas of Procurement, Harmonized Approach to Cash Transfer, Human Resources, ICT, Travel/DSA Harmonization, Common Services, and Finance, with the main aim of reducing transactional costs, harnessing economies of scale and enhancing the quality of service. Gender-specific actions and indicators are not specifically visible in the BOS document but they are nuanced under the Human Resource outcome area of the BOS, where there is a commitment to enhancing quality and performance for the UN human resource by utilizing several parameters including gender inclusion. In particular, BOS output 1.2, which outlines the establishment of a platform for spouses of UN staff, was specifically targeted at engaging qualified female partners of international staff members with suitable consultancy roles. |  |  |
| Evidence or means of verification: - Consolidated and sex-disaggregated staffing data from (WFP, FAO, UN Women, UNIDO, WHO, ILO, UNAIDS, RCO, UNDP, UNODC, VMO, IOM, UNESCO, UNHCR, UNIC, UNICEF, UNOCHA). - Business Operation Strategy 2018-2022, UN Nigeria. |  |  |

- GENDER ARCHITECTURE AND CAPACITIES

| INDICATOR 5.1: GENDER COORDINATION MECHANISM IS EMPOWERED TO INFLUENCE THE UNCT FOR GEEW |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| Meets 2 of the following: a) A coordination mechanism for gender equality is chaired by a HOA; b) The group has a TOR and an approved annual work plan; c) Members include at least 50% senior staff (P4 and above; NOC and above); d) The group has made substantive input into the UNDAF including the country analysis, strategic prioritization, results framework and M&E. | Meets 3 of the following: a) A coordination mechanism for gender equality is chaired by a HOA; b) The group has a TOR and an approved annual work plan; c) Members include at least 50% senior staff (P4 and above; NOC and above); d) The group has made substantive input into the UNDAF including the country analysis, strategic prioritization, results framework and M&E. | Meets all 4 of the following: a) A coordination mechanism for gender equality is chaired by a HOA; b) The group has a TOR and an approved annual work plan; c) Members include at least 50% senior staff (P4 and above; NOC and above); d) The group has made substantive input into the UNDAF including the country analysis, strategic prioritization, results framework and M&E. |
| Score: Approaches minimum requirements |  |  |
| Findings and explanation: a) The gender coordination mechanism for the country team is the Gender Theme Group (GTG), which is not chaired by a HOA but by the UN Women Deputy Country Representative. The group meets regularly. In total, the GTG held 25 meetings during the past year. It has met between 1-3 times a month since April 2020 due to the COVID-19 crisis. In addition, a GTG retreat was carried out on December 14 and 15, 2020. b) The GTG has a TOR and an approved work plan for 2020, both endorsed by UNCT. The 2021 work-plan was prepared in the retreat held last December and UNCT endorsement is pending. c) There is 1 senior international staff at the P4 level. However, the majority of members are senior national staff at the NOC level and above. d) The GTG did not make any substantive input into the UNSDPF 2018-2022, including the current country analysis dated 2016. The support for the development of the UNSDPF was at the agency level at that time. Nevertheless, the upcoming CCA is currently in process of development and it is worth noting that the GTG is leading the consultations on the new CCA generation. The GTG nominated focal points significantly contributed during the third quarter of 2020 to the gender analysis across all SDGs and sectors in the ongoing CCA process for Nigeria. The GTG developed a brief on the United Nations Response to the Upsurge in Sexual and Gender-based Violence in Nigeria (Brief, 2 July 2020). A guidance brief was also developed to provide key recommendations on gender equality issues and how they should be mainstreamed in the response to the COVID-19 pandemic and its impacts in Nigeria (Brief, 8 July 2020). This brief was prepared by the GTG and the UN Communications Group, representing all resident UN entities in Nigeria. |  |  |
| Evidence or means of verification: - Approved list of GTG members; - GTG Annual Work Plan 2020; - Final TOR of GTG; - Report of the GTG retreat, 14-15 December 2020; - CCA diagnosis papers for SDGs, December 2020; - COVID-19 in Nigeria: UN Key Recommendations on Gender (Brief, 8 July 2020); - The United Nations Response to the Upsurge in Sexual and Gender-based Violence in Nigeria (Brief, 2 July 2020). |  |  |

| INDICATOR 5.2: UNCT HAS ADEQUATE CAPACITIES DEVELOPED FOR GENDER MAINSTREAMING |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) At least one substantive inter-agency gender capacity development activity for UN personnel has been carried out during the past year. | Meets 2 of the following 3: a) At least one substantive inter-agency gender capacity development activity for UN personnel has been carried out during the past year. b) A capacity development plan based on an inter-agency capacity assessment is established or updated at least once per UNDAF cycle and targets are on track. c) UNCT induction material includes gender equality and the empowerment of women commitments and related development challenges of the country. | Meets all of the following: a) At least one substantive inter agency gender capacity development activity for UN personnel has been carried out during the past year. b) A capacity development plan based on an inter-agency capacity assessment is established or updated at least once per UNDAF cycle and targets are on track. c) UNCT induction material includes gender equality and the empowerment of women commitments and related development challenges of the country. |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: a) A training (virtual webinar) on the Enabling Environment Guidelines (EEG) during COVID-19, led by GTG contributing agencies, HR network, the Gender Parity Team at UN Women HQ and RCO, was conducted on July 21, 2020 for all UN staff in Nigeria. The event was a great success and presented critical insight into the challenges faced by the UN staff in their working environment. The EEG was launched by the Secretary-General in 2019, as part of the UN Reform, and in support of the SG’s System-wide Strategy on Gender Parity. It was, therefore, extremely apt to hear the recommendations of the GTG and Gender Parity Team in implementing these guidelines in Nigeria. Prior to the webinar, the GTG circulated the Enabling Environments Survey to all staff to ascertain views on themes such as discrimination, harassment, flexible working arrangements and career development. Following the seminar, the RC requested an EEG roll-out strategy for Nigeria and requested HOA to report on gender parity data. A presentation on the EEG guidelines for UNCT was undertaken by GTG in August 2020. b) A capacity needs assessment was conducted during the GTG retreat in 2020. It was a GTG gender equality capacity assessment carried out through a survey and based on the UN Women format for gender equality assessments. The survey had 18 responses in total. As a result, a capacity development plan was included as part of the AWP 2021. This plan includes actions such as gender training for GTG and gender focal points based on training needs assessment, training based on specific topics for all UN colleagues, training on gender mainstreaming in design and implementation of programmes for programme staff, and training on gender audit/ILO for GTG members. c) The GTG annual work plan 2020 included an action (not finally undertaken that year) to update the UN gender equality briefing kit -with a review from GTG members-, for orientation of new staff members and consultants and as a reference resource material for UN staff. The development of the kit was co-led by UN Women and UNFPA in 2013. The draft dated 2013 is uploaded on the drive but the final version of this document could not be traced. In any case, the UN gender briefing kit is not yet used in UNCT. On the other hand, UNDSS provided specific training in 2019 to new female staff but was more focused on their safety as females in Nigeria. The objective of this training was to increase awareness of security risks that may affect female personnel and the topics covered were safe travel/commuting, all forms of violence against women (including sexual harassment, assault and rape), cultural awareness, operations in field locations (including road movements, radio use, women’s specific field issues, basic vehicle maintenance and car safety), surviving as a female hostage, residential security and office security, stress management and self-defense techniques/tips. A training was held on October 2 and 3, 2019 in Abuja, and trainings were also scheduled in Lagos, Port Harcourt, and Kaduna duty stations. However, the UNDSS trainings were not organized during 2020. |  |  |
| Evidence or means of verification: - Power-Point Presentation “Creating an enabling environment. Country-specific challenges and recommendations for creating an enabling environment in the UN in Nigeria”, utilized in the webinar on EEG, 21 July 2020; - Power-Point Presentation “How to Build an Enabling Environment and Why it Matters? By the UN System in Nigeria”, utilized in the webinar on EEG, 21 July 2020; - Training documents utilized and shared with UN staff during the webinar on EEG, 21 July 2020 (1. Vacancy announcements: Examples of good practice; 2. Benefits of flexible working, 3. Flexible working arrangements for the UN: Why it makes sense; 4. The Enabling Environment in focus, and 5. Gender parity is a commitment, not only an aspiration - Gender parity benefits all); - Report of the GTG retreat, 14-15 December 2020; - GTG gender equality capacity assessment’s summary of responses, 15 December 2020; - GTG annual work plan 2020 and GTG annual work plan 2021 (not yet endorsed by UNCT); - Gender Equality Briefing Kit, the United Nations System in Nigeria, draft dated February 28, 2013; - UNDSS training paper, 2019. |  |  |

- RESOURCES

| INDICATOR 6.1: ADEQUATE RESOURCES FOR GENDER MAINSTREAMING ARE ALLOCATED AND TRACKED |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) The UNCT has carried out at least one capacity building event on the gender marker over the current UNDAF cycle. | Approaches minimum requirements and b) The UNCT has established and met a financial target for program allocation for Gender Equality and the Empowerment of Women. | Meets minimum requirements and c) The UNCT has established and exceeded a financial target for program allocation for Gender Equality and the Empowerment of Women. |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: a) During a meeting of the joint M&E group, held on September 23, 2020, a presentation on the Gender Marker was made by a member of the group from UN Women. The objectives of the presentation were to enhance understanding of how to use the Gender Marker methodology, improve skills to make better use of the Gender Marker, and promote greater accuracy and consistency in the use of the Gender Marker, especially when reporting in the UN INFO and UNSDPF. The attendance was not taken on the day of the meeting since the presentation was carried out online via Zoom. b and c) Gender equality and the empowerment of women are mainstreamed into most of the activities being implemented by the UN system in Nigeria. Analysis of the gender marker from the 2019 Nigeria One UN report of the implementation of UNSPDF activities showed that over 83% of the activities/services delivered contributed to or has GEEW as the primary objective of the interventions. From the expenditure analysis, the majority of funds (82% - USD 373.1 million) were spent on activities that made a principal (42% - USD 192.7 million) or significant (40% - USD 180.4 million) contribution towards the realization of gender equality and the empowerment of women in Nigeria. Figure 1: Gender marker by expenditure. Source: 2019 Nigeria One UN report |  |  |
| Evidence or means of verification: - Presentation on the Gender Marker for the joint M&E Group, 19 August 2020; - Minutes of the M&E group meeting, September 23, 2020; - 2019 Nigeria One UN Report; - Gender Equality Marker Table & Graphs, October 20, 2020. |  |  |

- RESULTS

| INDICATOR 7.1: UN PROGRAMMES MAKE A SIGNIFICANT CONTRIBUTION TO GENDER EQUALITY IN THE COUNTRY |  |  |
| --- | --- | --- |
| Approaches Minimum Requirements | Meets Minimum Requirements | Exceeds Minimum Requirements |
| a) The UNCT has achieved or is on track to achieve some gender equality and the empowerment of women results as planned in the UNDAF outcomes in line with SDG priorities including SDG 5. | a) The UNCT has achieved or is on track to achieve all gender equality and the empowerment of women results as planned in the UNDAF outcomes in line with SDG priorities including SDG 5. | Meets Minimum Requirements and b) At least one outcome level UNDAF result has contributed to transformative change in relation to gender equality and the empowerment of women. |
| Score: Meets minimum requirements |  |  |
| Findings and explanation: The UN INFO Indicators report showed that UNCT is on track of achieving the gender equality and the empowerment of women results planned in the UNSDPF 2018-2022: - Under the Governance, Human Rights, Peace and Security Pillar: Governance institutions at Federal/Focused States/LGAs strengthened to effectively plan, mobilize, manage resources, monitor & evaluate projects to ensure evidence-based quality gender-sensitive service delivery; Evidence-based and gender-sensitive policies and institutional mechanisms (including anti-corruption, electoral support, rule of law, and access to justice and preventing human trafficking) enabled at the national/sub-national level for good governance; Institutions of peace-building and social cohesion promoted and strengthened from a human rights and gender; Gender and human rights sensitive policy/plans and regulatory frameworks enabled at the national and sub-national levels for peace and a coordinated resilience based approach to humanitarian action; Strengthened resilience, diversification of livelihoods, and local economies of crisis-affected communities, particularly for youths, women, IDP,s returnees, host communities and other vulnerable communities to meet their basic food and nutrition needs and through the restoration of basic. - Under Equitable Quality Basic Services Pillar: Strengthened resilience of families & communities to disasters and enhanced support to national and sub-national institutions to deliver gender-sensitive basic WASH services in humanitarian situations.; Protection systems and services are strengthened to more effectively prevent and respond to violence, abuse, exploitation (including and harmful social norms in target states. trafficking) and harmful social norms in target states. - Under Sustainable and Inclusive Economic Growth and Development Pillar: Entrepreneurship and vocational skills programmes and decent job initiatives developed to create economic opportunities for youths and women as well as increase sectoral labor productivity growth. b) At this stage of UNSDPF 2018-2022 implementation, no transformative change on gender equality is recorded at the outcome level. |  |  |
| Evidence or means of verification: - UN INFO Indicators report, 2020; - 2019 Nigeria One UN Report. |  |  |

## Action plan for UNCT Nigeria performance improvement on GEEW

| Action | Responsibility | Key focal point for implement. |  | Required Resources | Timing | Results Explanation and links to SWAP-scorecard assessment | Evidence/ means of verification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Planning |  |  |  |  |  |  |  |
| Indicator 1.1. COMMON COUNTRY ANALYSIS INTEGRATES GENDER ANALYSIS |  |  |  |  |  |  |  |
| 1.1. Integrate gender analysis and consistentsex disaggregated data across all sections of the upcoming CCA (2021), including in the analysis of infrastructure, environment and climate change and other non-traditional sectors, referring to underlying causes of gender inequality and discrimination | PMT/ CCA thematic groups with the support of GTG and RCO | CCA thematic groups |  | No financial resources required | By Jun 2021 | These measures would ensure adequate integration of gender equality and the empowerment of women across the upcoming CCA. Gender analysis must be included across the analysis of all SDGs related sectors, including SDGs 7, 9, 11, 12, 13, 14 and 15 (non-traditional sectors). Action 1.1 would move indicator 1.1 from approaching to meeting minimum requirements. Action 1.2 would move indicator 1.1 to exceeding minimum requirements. Gender focal points embedded in CCA thematic groups must highlight the areas that need further analysis in terms of gender equality and disaggregation of data by sex, so that thematic groups can update the diagnosis papers based on the review. | CCA |
| 1.2. Include a targeted gender analysis of those furthest behind in the upcoming CCA | PMT/CCA thematic groups with the support of GTG and RCO | CCA thematic groups |  | No financial resources required | By Jun 2021 |  | CCA |
| Indicator 1.2. GENDER EQUALITY MAINSTREAMED IN UNDAF OUTCOMES |  |  |  |  |  |  |  |
| 1.3. Formulate at least one outcome specifically targeting GEEW and visibly mainstream gender equality across all outcome areas, formulating gender equality outputs for each outcome in the upcoming UNSDPF | PMT/GTG with the support of M&E group | PMT |  | No financial resources required | By December 2022 | This measure would allow for adequate mainstreaming of gender equality and the empowerment of women across the results framework of the upcoming UNSDPF. Special attention should be given to non-traditional outcomes. This action would move indicator 1.2 from approaching to exceeding minimum requirements. | Nigeria UNSDPF |
| Indicator 1.3. UNDAF INDICATORS MEASURE CHANGES ON GENDER EQUALITY |  |  |  |  |  |  |  |
| 1.4. Provide capacity building training for GTG members and M&E coordination group on gender analysis and gender data | GTG Chair and M&E Chair | GTG |  | 3.000 USD (1 local consultant or regional expertise and coffee break) | By April 2021 | Capacity building on gender analysis and gender statistics will enable GTG and M&E representatives’ skills to ensure compliance with gender analysis in the CCA. Training on gender data will ensure formulation of gender-sensitive indicators by M&E group. | Reports of capacity building trainings |
| 1.5. Disaggregate by sex the indicators (as far as possible) and indicate it in the definition (baseline and target) of indicators in UN joint work plans 2021 and 2022 | PMT/M&E group with the support of GTG and RCO | M&E group |  | No financial resources required | By March 2021 By March 2022 | These measures would enable at least 33-50% of UNSDPF indicators to measure changes in gender equality and the empowerment of women. Actions 1.5 and 1.7 would enable tracking of progress on GEEW in output indicators and measure performance of UNCT on GEEW in the planning dimension area. In particular, action 1.6 would move indicator 1.3 from approaching to meeting minimum standards. | UN joint workplans |
| 1.6. Formulate more than 33% of indicators that can measure changes in GEEW in the results framework of the upcoming UNSDPF | PMT/M&E group with the support of RCO and GTG | M&E group |  | No financial resources required | By December 2022 |  | Next UNSDPF |
| 1.7. Disaggregate by sex the indicators (as far as possible) and indicate it in the definition (baseline and target) of indicators in the joint work plan 2023 | PMT/M&E group with the support of GTG and RCO | M&E group |  | No financial resources required | By March 2023 |  | UN joint work-plans |
| - Programming and monitoring and evaluation |  |  |  |  |  |  |  |
| Indicator 2.1. JOINT PROGRAMS CONTRIBUTE TO REDUCING GENDER INEQUALITIES |  |  |  |  |  |  |  |
| 2.1. Put in place a system to ensure gender mainstreaming in the formulation of joint programs | UNCT/RCO/ GTG | RCO |  | Will be determined according to mechanism put in place | By Jun 2021 | This measure would ensure the contribution of joint programmes to the improvement of gender equality in the country, in line with SDG 5. The action would move indicator 2.1 from approaching to exceeding minimum requirements. | JP pro-docs; IMS, RCAR, screening tool or other documents of internal JPs review process |
| INDICATOR 2.2 COMMUNICATION AND ADVOCACY ADDRESS AREAS OF GENDER INEQUALITY |  |  |  |  |  |  |  |
| 2.2. Visibly include GEEW communication and advocacy in the joint communication annual work-plans of the inter-agency communication group (if work-plans are developed) and in the UNCT communication strategy | UNCG and GTG | UNCG |  | No financial resources required | By Jun 2021 | Joint communication and advocacy on gender issues is an essential aspect of the work of the UNCT. One of the key guiding principles of the "communication as one" initiative is to use joint UN communication to promote the realization of human rights, gender equality and other standards. Action 2.2 would move indicator 2.2 from approaching to meeting minimum requirements. Actions 2.3 and 2.4 would have a positive impact on indicator 2.2. Action 2.5 would move indicator 2.2 to exceeding minimum requirements. | UNCG and GTG AWP |
| 2.3. Include bi-annual news articles from GTG in the UN Newsletter | GTG and UNCG | GTG |  | No financial resources | Bi-annual |  | UN Newsletter |
| 2.4. Increase the interaction/ concertation between the GTG and the UNCG group through 2 meetings per year | UNCG and GTG | GTG |  | No financial resources required | Bi-annual |  | Meeting minutes |
| 2.5. Organize at least one joint communication and/or advocacy activity in non-traditional thematic areas every year | UNCG and GTG | UNCG |  | Will be determined on the basis of the activity | Annually |  | Event reports |
| Indicator 2.3. UNDAF MONITORING AND EVALUATION MEASURES PROGRESS AGAINST PLANNED GENDER EQUALITY RESULTS |  |  |  |  |  |  |  |
| 2.6. Build the capacity of the UN M&E group on gender-sensitive M&E and/or the gender marker (GEM) at least once during the next programming cycle | M&E group with the support of GTG | M&E group |  | 3.000 USD (1 local consultant or regional expertise and coffee break) | By December 2022 | Gender-sensitive M&E is an essential means by which the UN system ensures that it meets its commitment to leave no one behind. The criteria to exceed minimum requirements for indicator 2.3 needs that the inter-agency M&E group receives technical training on gender-sensitive M&E at least once every UNSDPF cycle. Action 2.7 would need UNCT/HOA to avail funding and have a dialogue with different sectors. Action 2.8 would need M&E Group and GTG to prepare and support the implementation of a work-plan for data collection by sectors and UNCT to avail financial and human resources. These four actions would keep indicator 2.3 exceeding minimum requirements. | Training reports |
| 2.7. Build the capacity/awareness of government partners in the collection of sex-disaggregated/ gender-sensitive statistical data | PMT and M&E group with the support of GTG | M&E group |  | Will be determined according to funding availed by UNCT | By Jun 2021 |  | Training reports |
| 2.8. Provide technical support/ accompany government partners in the collection of sex-disaggregated/gender-sensitive statistical data | M&E group with the support of GTG | M&E group |  | Will be determined according to funding availed by UNCT | Throughout programming cycle |  | Minutes of the meetings |
| 2.9. Integrate sex disaggregated data in UN sectors & programmes/plans | PMT/ M&E group with the support of GTG | M&E group |  | No financial resources required | Throughout programming cycle |  | Programmes and plans indicator matrix |
| - Partnerships |  |  |  |  |  |  |  |
| Indicator 3.1. UNCT COLLABORATES AND ENGAGES WITH GOVERNMENT ON GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN |  |  |  |  |  |  |  |
| 3.1. Ensure full involvement and participation of Federal Ministry of Women in the upcoming UNSDPF consultations, including CCA consultations | RCO/CCA thematic groups/GTG | RCO | No financial resources required |  | By December 2021 (CCA) December 2022 (UNSDPF) | The UN has played an important role historically supporting the creation and development of women’s machineries, and their national knowledge and expertise should inform UNDAF processes. The participation of the National Women’s Machinery in the upcoming UNSDPF processes will move indicator 3.1 from approaching to meeting minimum requirements. It is important to ensure participation of this machinery in the upcoming CCA consultations to be held in 2021. Action 3.2 will move indicator 3.2 to exceeding minimum requirements. | List of attendance of consultations |
| 3.2. Carry out at least one joint activity to substantively strengthen Government participation and engagement in gender-related SDGs localization and/or implementation | RCO/GTG | GTG | Will be determined according to joint activity |  | By December 2022 |  | Report of the activity |
| Indicator 3.2. UNCT COLLABORATES AND ENGAGES WITH WOMEN’S/GENDER EQUALITY CSO |  |  |  |  |  |  |  |
| 3.3. Ensure participation of GEEW CSO in the upcoming UNSDPF consultations, including CCA consultations | RCO/CCA thematic groups/GTG | RCO | No financial resources required |  | By December 2021 (CCA) December 2022 (UNSDPF) | Partnerships with non-governmental actors are essential to an efficient and effective UN response, based on the principles of equality, transparency, results-oriented approach, responsibility and complementarity. GEEW CSOs include local non-governmental and civil society actors focused on GEEW. Groups may represent women and girls as well as those that are marginalized on the basis of their sexuality or gender identity. Action 3.3 will move indicator 3.2 from approaching to meeting minimum requirements. Action 3.4 will move indicator 3.2 to exceeding minimum requirements. | List of attendance of consultations |
| 3.4. Carry out at least one joint activity to substantively strengthen GEEW CSO participation and engagement in gender-related SDGs localization and/or implementation | RCO/GTG | GTG | Will be determined according to joint activity |  | By December 2022 |  | Report of the activity |
| - Leadership |  |  |  |  |  |  |  |
| Indicator 4.1. UNCT LEADERSHIP IS COMMITTED TO CHAMPIONING GENDER EQUALITY |  |  |  |  |  |  |  |
| 4.1. Include the follow-up of the scorecard action plan as a substantive agenda item for discussion at least every 6 months at HOA meetings | RC/UNCT/RCO | RCO |  | No financial resources required | By April 2021 | Senior managers play a critical role in UNCT for the promotion of gender equality, as outlined in the UN Leadership Model approved by the Chief Executives Board. At least 60% of HOA meetings should focus on gender equality, and there should be evidence of decision-making and follow-up, rather than general information sharing. In addition, at least 33% of the RC speeches over the year must address GEEW. These measures will move indicator 4.1 from meeting to exceeding minimum requirements. | UNCT minutes |
| 4.2. Include references to GEEW or to how UNCT is promoting GEEW in at least one third of the RC speeches over the year | RCO with the support of GTG | RCO |  | No financial resources required | Every year |  | RC Speeches |
| Indicator 4.2. ORGANIZATIONAL CULTURE FULLY SUPPORTS PROMOTION OF GENDER EQUALITY AND THE EMPOWERMENT OF WOMEN |  |  |  |  |  |  |  |
| 4.3. Organize brown bag lunches or equivalent on the package of entitlements (e.g. maternity, paternity, breastfeeding) and the package of flexible work arrangements (e.g. compressed work schedule, telecommuting, staggered hours) to support staff to achieve adequate work-life balance, aligned with the implementation of the UN Enabling Environment Guidelines, with the participation of HOAs | OMT/UNCT/ HR network | HR network |  | No financial resources required | By December 2021 | The set of questions related to adequate work-life balance was the one that received the most negative opinions from staff. In particular, 14% of staff think that UNCT Nigeria do not allow for adequate work-life balance in the survey of personnel perception of organizational environment for promotion of gender equality. It was also the issue that received the most negative opinions from women (20%), compared to 9% negative responses from men. These measures would have a positive impact on indicator 4.2. | Event reports and statements from HOA on commitment to EEG implementation |
| Indicator 4.3. GENDER PARITY IN STAFFING IS ACHIEVED |  |  |  |  |  |  |  |
| 4.4. Establish a mechanism for monitoring gender parity in staffing to monitor parity levels for general service staff and all professional levels | OMT/UNCT/ HR network with the support of RCO | OMT |  | No financial resources required | By September 2021 | The UNCT does not have a joint monitoring mechanism for gender parity. For the scorecard, this is the first time that gender-disaggregated staffing data are collected from UN agencies. This measure would move indicator 4.3 from missing to approaching minimum standards. | Mechanism established |
| 4.5. Redesign job descriptions, application forms and processes to maximize candidate pools, including the development of standard inclusion statements in job advertisements and in the careers section of the organization’s website such as mention of women, persons with disabilities, trans and gender non-confirming individuals, and further strengthen messaging that the organization welcomes diversity in all its forms. | OMT/HR network with the support of RCO | HR network |  | No financial resources required | By December 2021 | The UNCT consolidated sex-disaggregated staffing data analysis showed that the representation of women is very low, with an overall representation rate of 34% for women, compared to 66% for men. The number of male staff is double the number of female staff. It is therefore necessary to increase the representation of women in UNCT Nigeria for achieving gender parity in staffing. On the other hand, UNCT recruitment process must be aligned with the Enabling Environment Guidelines (EGG). These measures will allow UNCT to implement the global UN set of recommendations on the EEG for recruitment and will feed into the recruitment of more female staff. All actions will have a positive impact on indicator 4.3. | Job descriptions Application forms Processes |
| 4.6. Develop guidelines for gender-sensitive recruitment | OMT/HR network with the support of RCO | HR network |  | No financial resources required | By December 2021 | Gender-sensitive recruitment will facilitate hiring a higher number of women through interview panels that systematically consider gender sensitivity as a criterion in selection, as set up in the Supplementary Guidance on the Enabling Environment Guidelines, UN Women 2019 (page 42). For instance, Central Review Bodies and the Executive Director receive a table of gender parity statistics at each step of the selection process, with the final unranked list of recommended candidates normally including at least one woman. These actions will move indicator 4.3 to exceeding minimum requirements. | Guidelines for gender-sensitive recruitment |
| 4.7. Introduce gender responsive procurement aligned with the UN 2.0 Business Operations Strategy (BOS) | OMT | OMT |  |  | By March 2022 |  | Procure-ment |
| - Gender architecture and capacities |  |  |  |  |  |  |  |
| Indicator 5.1. GENDER COORDINATION MECHANISM IS EMPOWERED TO INFLUENCE THE UNCT FOR GEEW |  |  |  |  |  |  |  |
| 5.1. GTG to make a substantive input into the development of the next UNSDPF including strategic prioritization and results framework | PMT/GTG | GTG |  | No financial resources required | By December 2022 | The GTG is a key mechanism for joint UN action and coordination at the country level. The empowerment of the GTG is therefore essential to enable it to influence UNCT for GEEW. These actions would move indicator 5.1 from approaching to meeting minimum requirements. | Input document from GTG |
| 5.2. Carry out retreat of the GTG on an annual basis | GTG with the support of RCO and RC | GTG |  | Will be determined on the basis of the days of duration and activities to be carried out | Every year |  | GTG annual retreats |
| 5.3. Update TOR for GTG Representatives to include minimum 15% staff time and deliverables to implement GTG AWP and participate and prepare for GTG bi-weekly meetings | UNCT with the support of GTG representa-tives | UNCT |  | No financial resources required | By April 2021 | Lack of staff time and capacity of GTG members is a key challenge for UNCT to reach minimum standards for the scorecard. This action will have a positive impact on indicator 5.1. | TOR of GTG focal points |
| 5.4. UNCT to approve budget for a costed GTG AWP and provide funds for implementation | UNCT/PMT supported by GTG | UNCT |  | Will be determined by GTG AWP in consultation with PMT | By April 2021 | With a funded AWP the GTG will be enabled to lead and implement activities to respond to the requirements of the UNCT SWAP and GTG TOR. This action will have a positive impact on indicator 5.1. | Budget approved |
| 5.5. Organize an all staff virtual session to present the UNCT SWAP gender equality scorecard action plan to UN staff members | GTG/RCO | Hosted by RCO |  | No financial resources required | By April 2021 | This measure will have a positive impact on all scorecard indicators since it will contribute to increase awareness and strengthen capacity of staff to improve performance of UNCT in gender mainstreaming. | Report of the session |
| Indicator 5.2. UNCT HAS ADEQUATE CAPACITIES DEVELOPED FOR GENDER MAINSTREAMING |  |  |  |  |  |  |  |
| 5.6. Implement the capacity development actions for GTG and UN personnel before the end of the current UNSDPF 2018-2022, based on the capacity assessment carried out during the GTG retreat last December 2020 | UNCT/GTG with the support of RCO | GTG |  | Will be determined on the basis of duration of trainings and number participants | By December 2022 | Lack of capacity for gender equality and the empowerment of women is identified as one of the main obstacles to improving UNCT performance on GEEW. UN system’s staff must have the capacity to fulfill the UN mandate on gender equality. Actions 5.6 and 5.7 would keep indicator 5.2 in meeting minimum requirements. Actions 5.8 and 5.9 would move indicator 5.2 from meeting to exceeding minimum requirements. | Report of the trainings |
| 5.7. Update the UNCT capacity development plan at least once during the next UNSDPF cycle and track targets | GTG | GTG |  | No financial resources required | By December 2023 |  | GTG AWPs and/or capacity development plan |
| 5.8. Update the UN gender equality briefing kit for orientation of new staff members and consultants | GTG | GTG |  | No financial resources required | By November 2021 |  | UN gender equality briefing kit |
| 5.9. Distribute the updated UN gender quality briefing kit to all UN Staff | RCO with the support of GTG | RCO |  | No financial resources required | By December 2021 |  | Distribution emails of the gender briefing kit |
| - Resources |  |  |  |  |  |  |  |
| Indicator 6.1. ADEQUATE RESOURCES FOR GENDER MAINSTREAMING ARE ALLOCATED AND TRACKED |  |  |  |  |  |  |  |
| 6.1. Organize at least one capacity building event on the gender marker targeting UN staff during each UNSDPF programming cycle | UNCT/M&E group with the support of RCO and GTG | M&E group |  | US 2.000$ (regional expertise x 1.5 days and coffee break) | Before the end of each programming cycle | Gender-sensitive targeting and financial tracking is an important means of monitoring UN investments against commitments to gender equality. Measure 6.1 would keep indicator 6.1 meeting minimum requirements by organizing training on the gender marker at least once for each UNSDPF programming cycle. Measure 6.2 would move indicator 6.1 to exceeding minimum requirements. | Report of the trainings |
| 6.2. Establish and track a financial target for program allocation for Gender Equality and the Empowerment of Women | UNCT/PMT with the support of M&E group and GTG | UNCT |  | No financial resources required | By November 2021 |  | Financial target established |
| - Results |  |  |  |  |  |  |  |
| Indicator 7.1. UN PROGRAMMES MAKE A SIGNIFICANT CONTRIBUTION TO GENDER EQUALITY IN THE COUNTRY |  |  |  |  |  |  |  |
| 7.1. Include in TOR of experts in charge of UNSDPF reviews the responsibility to thoroughly assess progress towards gender equality and the empowerment of women | UNCT/PMT/ RCO | RCO |  | No financial resources required | By 2022 (mid-term review and final evaluation of UNSDPF) | The UNCT must be able to provide evidence to demonstrate progress on GEEW by assessing the extent to which the UNCT has contributed to gender equality in Nigeria, with some form of measurable change. On the other hand, PMT must actively instruct and utilize the GTG as a support mechanism for gender mainstreaming. More regular coordination between PMT and GTG can strengthen the integration of GEEW in programming. To exceed the requirements of this SWAP scorecard dimension, the UNCT should demonstrate that at least one outcome level UNSDPF result has contributed to transformative change in relation to gender equality and the empowerment of women. These actions would have a positive impact on indicator 7.1. | TOR of experts |
| 7.2. Include responsibility for gender mainstreaming and the promotion of GEEW visibly in the mandate/TOR of the result groups and UN coordination mechanisms | UNCT/PMT/M&E/RCO with the support of GTG | RCO |  | No financial resources required | By Jun 2021 |  | TOR of UN coordination mechanisms |
| 7.3. Establish a link between the GTG and the result groups and between GTG and the Project Management Team (PMT) (i.e. annual coordination meetings, etc.) | Result groups/ PMT/GTG/ RCO | RCO |  | No financial resources required | By Jun 2021 |  | Reports of coordination meetings |

For UNCT Nigeria, this minimum number was 338, given that UN staff number was 2.792 at the time of the assessment.

Agencies participating in the larger inter-agency groups were FAO, ILO, IOM, RCO, UNAIDS, UNDP, UNESCO, UNFPA, UNHCR, UNIC, UNICEF, UNIDO, UNITAR, UNOCHA, UNODC, UN Women, WFP, WHO and WMO.

Agencies participating in the assessment core team were FAO, RCO, UNAIDS, UNFPA, UNIC, UNICEF, UNOCHA, UNODC, UN WOMEN, WFP and WHO.

Non-traditional thematic areas are those areas in which women are not traditionally involved and are under-represented, such as environment, infrastructure, climate change, technological innovation, transportation, urban planning, etc.

Consistent means that all CCA key population-based data should be disaggregated by sex, especially population-based data in relation to the main development challenges highlighted by the CCA (e.g. poverty, hunger, education, health, infrastructure, housing, control of resources, and/or economic development). If gender-sensitive and/or sex disaggregated data is not available, this should be noted in the CCA along with any initiatives to facilitate use of GEEW-related data in the future. The onus is on the UNCT to either include sex disaggregated and gender-sensitive data, or explain why this has not been included.

Joint work-plans are elaborated on an annual basis for the implementation of the UNSDPF 2018-2022.

Non-traditional thematic areas are those areas in which women are under-represented, such as environment, climate change, industry, transport, technological innovation, infrastructure, etc.

UN Enabling Environment Guidelines: https://www.unwomen.org/-/media/headquarters/attachments/sections/library/publications/2019/gender-parity-enabling-environment-guidelines-en.pdf?la=en&vs=1535.

Reference: pages 10 and page 25 of the Supplementary Guidance on the Enabling Environment Guidelines, UN Women 2019.

https://www.unwomen.org/-/media/headquarters/attachments/sections/library/publications/2019/gender-parity-enabling-environment-guidelines-supplementary-guidance-en.pdf?la=en&vs=1535

The UN 2.0 Business Operations Strategy (BOS): https://unsdg.un.org/resources/business-operations-strategy-bos-20-guidance.

Trainings based on specific topics/sectors for UN colleagues, gender mainstreaming in design and implementation of programme for programme staff, training on gender audit/ILO Training for GTG, etc.