UNSDCF 2021-2025 Final Evaluation

Management Response

Turkmenistan, 19 December 2024

| Recommendation 1: Strengthen planning and implementation structures and mechanisms |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| --- | --- | --- | --- | --- |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - Update ToRs of RGs and Steering Committee to reinforce the roles of Results Groups and the Steering Committee in driving strategic discussions, joint planning, and cross-sectoral synergies. | Dec 2025 | RCO and UNCT | Not initiated |  |
| - UNCT to initiate joint planning and programming to be translated into the joint initiatives/programs (at least one per Outcome) | Dec 2026 | UNCT | Initiated |  |
| Recommendation 2: Improve results framework, including monitoring, evaluation, and data collection systems |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT to ensure alignment of their programming results to the specific Outputs and Outcomes within the UNSDCF results matrix | Dec 2025 | UNCT | Initiated |  |
| - Update ToR of MEL Group to support tracking and monitoring of planned activities by using UNINFO platform with standardized monitoring and evaluation systems that facilitate data comparability | Dec 2025 | MEL Group | Not initiated |  |
| - UNSDCF MEL plan for the full duration of the UNSDCF 2026-2030 developed | June 2025 | UNCT, MEL Group | Not initiated |  |
| - MEL Group with the State Statistics Committee to co-lead implementation of the Roadmap on SDGs indicators once endorsed by the government. | Dec 2026 | UNCT, MEL Group | Not initiated |  |
| Recommendation 3: Explore opportunities to diversify funding, enhance resource mobilization and financial sustainability |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT to develop a comprehensive Resource Mobilization and Partnerships Strategy that diversifies funding sources beyond the GoT and traditional donors | Dec 2025 | UNCT | Not initiated |  |
| Recommendation 4: Promote LNOB - gender equality and disability inclusion across all outcomes |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT while working on a new Theory of Change of the UNSDCF 2026-2030, to - establish a highly participatory process to consider and reflect the voices and needs of marginalized groups and prioritize LNOB integration, particularly gender equality and disability inclusion, youth and HRBA across all Outcomes - address barriers to inclusion tailoring activities to meet the needs of vulnerable populations - in addition to general indicators, to establish specific LNOB-focused targets and disaggregated indicators based on the data availability | Dec 2025 | UNCT | Initiated |  |
| - UNCT with support of the Regional IBC on Gender Equality to conduct capacity-building initiatives to enhance UN staff understanding and the implementation of gender and disability mainstreaming practices | Dec 2026 | RCO, UNCT | Not initiated |  |
| Recommendation 5: Strengthen support for institutional development and systemic (governance) reforms |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT to intensify its support for institutional and systemic reforms within the upcoming UNSDCF 2026–2030 through aligning the efforts with the national development frameworks including NPSEDT 2022-2052 | Dec 2025 | UNCT | Not initiated |  |
| Recommendation 6: Increase stakeholder engagement and foster inclusive development |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT to establish a Partnerships platform for CSOs to increase its engagement with a broader range of stakeholders, including civil society organizations and marginalized communities. | Dec 2025 | UNCT | Initiated | The concept note of the platform was drafted by RCO. |
| - UNCT to increase its engagement with a broader range of stakeholders and reinforce their roles in Results Groups by including them as the members of the RGs when updating the respective ToR (envisaged in Action 1.1 above) | Dec 2025 | UNCT | Not initiated |  |
| Recommendation 7: Improve the focus on impact and long-term sustainability |  |  | Accepted / Partially accepted / Rejected (Please select one as appropriate) |  |
| Explanation (of rejection or partial acceptance) |  |  |  |  |
| Actions to be taken | Timeframe | Responsible entity/ies | Tracking (or monitoring) |  |
|  |  |  | Status (Initiated/Not initiated/ Completed/No longer applicable) | Comments (or action taken) |
| - UNCT to improve the sustainability of UNSDCF results and concentrate on progress towards impact by developing clear exit strategies for all major interventions and discussing successfully piloted initiatives at the Results Groups | Dec 2026 | UNCT | Not initiated |  |

The National Program for the Socio-Economic Development of Turkmenistan 2022-2052