## Sheet1
Country ERITREA ; UNSDCF 2022-2026 EVALUATION MANAGEMENT RESPONSE
Evaluation Title: UNSDCF Evaluation — Management Response Eritrea United Nations Sustainable Development Cooperation Framework 2022–2026 Evaluation year: April 2026 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: UN Resident Coordinator's Office (RCO) • Frequency of monitoring and updating: Semi-Annual The United Nations Country Team (UNCT) in Eritrea welcomes the independent evaluation of the UNSDCF 2022–2026 and expresses its appreciation to the Evaluation Team for a rigorous, evidence-based, and participatory assessment. The evaluation was conducted in accordance with UNEG Norms and Standards and the DCO UNSDCF Evaluation Guidelines (2024), and the UNCT recognizes the quality and depth of analysis presented. The UNCT is encouraged by the evaluation's overall findings, which confirm that the Cooperation Framework was highly relevant, well aligned with Eritrea's national development priorities and the SDGs, and effective in delivering significant results in maternal and child health, education, gender equality, WASH, and climate resilience. The evaluation affirms the strength of the government–UN partnership, the effectiveness of joint programming approaches such as the UNFPA–UNICEF FGM elimination programme, and the operational efficiency gains achieved through the Business Operations Strategy 2.0. The UNCT acknowledges the evaluation's identification of important gaps: insufficient funding (only USD 228.61 million mobilized against a requirement of USD 475.58 million); limited coverage of persons with disabilities; underdeveloped private sector and livelihoods programming; and weak disability-disaggregated data systems. These findings are consistent with the UNCT's own assessments and will be central to the design of the next Cooperation Framework (2027–2031). The UNCT accepts all seven recommendations put forward by the Evaluation Team and commits to translating them into concrete, time-bound actions. The management responses below detail the actions, responsible entities, and timeframes for each recommendation. The Resident Coordinator's Office will lead semi-annual monitoring of implementation progress, reporting to the Joint Steering Committee. The management response will be publicly disseminated alongside the final evaluation report in accordance with DCO requirements.
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Deepen National Ownership and Institutionalization of Cooperation Framework Priorities.
Management response - Accepted/Partially Accepted/rejected : The UNCT fully accepts this recommendation. The evaluation confirms that strong government ownership was the single most important enabler of results in the 2022–2026 cycle. In the next CF, the UNCT will ensure that CF priorities are directly derived from and aligned with Eritrea's National Development Plan and sector strategies, and that Joint Work Plans serve as the primary operational instruments for translating those priorities into action. Government institutions will progressively take the lead in coordination, monitoring, and reporting throughout the 2027–2031 cycle. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Integrate national development priorities, including the National Development Plan, into the CF 2027–2031, ensuring UNSDCF outcomes are fully aligned with and derived from national priorities. | Next CF | RCO,PMT, MoFND |  |  | December | 2026
1.2 | Strengthen Joint Work Plans (JWPs) as the primary operational instrument of the CF, ensuring they are co-developed with government counterparts, aligned with national planning cycles, and used consistently to operationalize UNSDCF priorities | Next CF | RCO,PMT, MoFND |  |  | December | 2026
…
Recommendation 2: Strengthen the Leave No One Behind (LNOB) Agenda with Dedicated, Resourced Programmes
Management response - The UNCT fully accepts this recommendation. The evaluation correctly identifies that LNOB commitments were not consistently translated into dedicated, resourced interventions — particularly for persons with disabilities, remote rural communities, and climate-affected households. In the 2027–2031 CF, the UNCT will move LNOB from a cross-cutting principle to a set of targeted, budgeted programme actions, anchored in disaggregated data from the EPHS-2025 and supported by expanded social protection. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Design targeted programme outputs for women, youth, persons with disabilities, and climate-affected communities in the 2027–2031 CF results framework, with dedicated budget lines in JWPs — treating LNOB as a programming priority rather than only a cross-cutting principle | 2027-2031 | RCO,PMT, MoFND |  |  | December | 2027
2.2 | Invest in disaggregated data systems (by sex, age, disability, and location) using EPHS-2025 as the baseline, and expand social protection measures to cushion vulnerable groups from climate and economic shocks | 2027-2031 | RCO,PMT, MoFND |  |  | December | 2027
Recommendation 3: Scale Up Integrated and Multi-Sectoral Approaches
Management response -The UNCT fully accepts this recommendation. The evaluation shows that the highest-impact results — FGM elimination, ODF villages, climate-resilient agriculture — were achieved through integrated, multi-agency approaches. In the 2027–2031 CF, the UNCT will build on this evidence by expanding joint programmes and strengthening JWPs and One-UN delivery platforms as the standard operating model. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Expand joint, multi-sectoral programmes in food systems, health, WASH, education, and climate resilience — building on the UNFPA–UNICEF FGM model — with shared results frameworks, co-financing, and joint monitoring, as the preferred delivery modality for complex cross-sectoral priorities in the next CF | Q1–Q2 2027 | All UNCT Agencies, RCO |  |  | June | 2027
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: Embed Resilience and Climate Adaptation Across All Outcomes
Management response - The UNCT fully accepts this recommendation. Eritrea's vulnerability to climate shocks — droughts, desertification, erratic rainfall, and regional instability — makes climate resilience a non-negotiable programming principle. The evaluation confirms that resilience-focused interventions (solar-powered water systems, climate-smart agriculture, dam construction) proved most durable. The next CF will require every outcome area to include an explicit climate and disaster risk component, with crisis-sensitive programming standards applied system-wide. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Embed resilience and climate adaptation across the UNSDCF by integrating climate risk screening into outcomes, JWPs, and development–emergency preparedness linkages. | 2027–2031 | UNCT, PMT |  |  | December | 2028
4.2
Recommendation 5: Expand Partnerships and Diversify Resource Mobilization
Management response - The UNCT fully accepts this recommendation. The evaluation identifies the financing gap — only 48% of the required USD 475.58 million mobilized — as the single most significant constraint on UNSDCF impact. Eritrea's unique operating context, including limited donor presence and UCM-related restrictions, requires a diversified and creative approach to resource mobilization. The UNCT will develop a joint resource mobilization strategy with GoSE that targets private sector actors, diaspora networks, regional institutions, and South-South partners alongside traditional donors. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | 5.1 Develop a joint GoSE–UNCT resource mobilization strategy for the 2027–2031 CF that diversifies financing by engaging private sector actors, diaspora networks, AfDB, and South-South partners — with specific financing targets for underfunded areas including youth employment and disability inclusion | 2027 | UNCT,MoFND |  |  | December | 2027
5.2 | Promote innovative financing mechanisms — including blended finance, climate funds (GCF, GEF, Adaptation Fund), and pooled UNCT resources — in the face of shifting global financing landscape and declining and unpredicatable ODA.UNCT will explore innovative financing instruments to increase the scale and sustainability of CF interventions | 2027 | UNCT,MoFND |  |  | December | 2027
…
Recommendation 6: Invest in Data, Monitoring, and Accountability Systems
Management response - The UNCT fully accepts this recommendation. The evaluation identifies weak M&E systems and data gaps as a foundational constraint that limited the UNCT's ability to track equity outcomes, demonstrate attribution, and course-correct during implementation. The absence of disability-disaggregated data and the incomplete operationalization of results-based management are particularly noted. The UNCT commits to treating data and accountability systems as a core investment — not an afterthought — in the 2027–2031 cycle, with a clear pathway toward nationally-led M&E by the end of the cycle. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Strengthen UNSDCF Results & Resources Framework with clearer outcome-level indicators | 2027 | PMT, MoFND |  |  | December | 2027
6.2 | Strengthen data‑driven decision‑making by operationalizing EPHS 2025 data and embedding evidence‑based reviews in Joint Performance Review Meetings. | 2027 | PMT, MoFND |  |  | December | 2027
…
Recommendation 7: Advance Gender Equality and Human Capital Development
Management response - The UNCT fully accepts this recommendation. The evaluation documents transformative gains in gender equality — FGM abandonment in 17 sub-zobas, girls' school retention surpassing boys, and facility-based births reaching 85% — and identifies gender equality as a cross-cutting driver of compounding results across all sectors. The next CF will consolidate these gains through legal and institutional embedding, while expanding the scope of gender programming to include women's economic rights, youth employment pathways, and digital skills. Human capital development — linking education, health, and livelihood outcomes — will be treated as a strategic priority for Eritrea's demographic dividend. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Consolidate gains in FGM reduction, maternal health, and girls' education by embedding progress in legal and institutional frameworks — including strengthening national policies on harmful practices and integrating SRH into the Essential Health Package — and mainstream gender equality across all UNSDCF pillars using the UNCT Gender Equality Marker | 2027 | UNCT |  |  | December | 2027
7.2 | Expand youth-focused, market-linked skills programmes to translate human capital gains into employment and economic participation, with dedicated outputs in the 2027–2031 CF results framework | 2027 | UNCT |  |  | December | 2027
…

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030