| Bosnia and Herzegovina Cooperation Framework 2021 - 2025 EVALUATION MANAGEMENT RESPONSE |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation Title/Year: Final Evaluation of the United Nations Sustainable Development Cooperation Framework (UNSDCF) in Bosnia and Herzegovina 2021-2025 / 2025 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee (TBD) • Follow-up monitoring and updating of the management response’s implementation: 2025 • Frequency of monitoring and updating: Quarterly monitoring and annual reporting |  |  |  |  |  |  |  |  |
| Recommendation 1: Align the formulation of the 2026-2030 UNSDCF priorities to those of the 2030 SDG Development Framework for BiH and EU accession agenda. The next UNSDCF Priorities should align with the EU accession roadmap and the 2030 SDG framework priorities so there is coherence between these key frameworks. This would create synergy and boost reforms in line with EU accession and SDGs at the same time, creating coherence between these development agendas and ensuring more efficient use of resources for multiplied effects. It is needed also to further operationalize the on-going strategic dialogue into a strategic partnership, that will define the roles of the UN, the EU and BiH institutions, as well as the rules for funding UN interventions. This recommendation and the recommendation for the UN to redefine its role and strategic objective, based on the UN Agency (human-rights based, LNOB) mandates, its expertise, unique know-how (convening, facilitating power) are mutually supportive. Operationalizing rules for the UN to seek EU funding in a unified manner would reinforce the UNRCO role in coordinating the process of jointly developing projects. The key bilateral donors and the EU are focusing on the same priorities: support BiH’s EU accession, supporting institutions in implementing necessary reforms, while assisting the country to rich its 2030 domesticated SDG targets through strategic partnership with the UN. More than encouraging the UN to commit and deliver as UN, donors are expecting the UN to fully become a strategic partner. The evaluation recommends reflecting on the positioning of donors in the next UNSDCF by including the recommendation suggested above as part of the next UNSDCF resource mobilization strategy. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | n/a |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by: RC |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 1.1 | Prioritize alignment of the 2026-2030 UNSDCF with the EU accession roadmap and the 2030 SDG framework during the Prioritisation Retreat with the SDG Council BiH. |  | Q4 2024 | RCO/CF design team/UNCT |  | Completed | Completed | 2025 |
| 1.2 | Develop the draft results framework for the 2026-2030 UNSDCF, ensuring it includes strong alignment with SDG priorities and the EU accession agenda. |  | Q4 2024 – Q1 2025 | RCO/CF design team/PMT |  | Ongoing as expected | April | 2025 |
| 1.3 | Conduct extensive consultations with key stakeholders, including the EU, government authorities, and other development partners, to finalize the UNSDCF and ensure it is fully aligned with the 2030 SDG framework and the EU accession process. |  | Q1 2025 | RCO/CF design team/UNCT |  | Ongoing as expected | May | 2025 |
| Recommendation 2: Increased Focus on Human Rights, combining universal or broad changes for all citizens, together with a more structured approach to vulnerable groups based on LNOB principle. The UN must focus more on human rights in all strategic priority areas. Particularly in the areas that are more focused on infrastructure, climate change, green transition, economic growth, where often the focus is more on technology, processes, and material aspects than on human rights perspective. The UN's role remains crucial in ensuring that reforms prioritize the protection of human rights, social inclusion, and the protection of marginalized groups. Therefore, the UNSDCF interventions should be designed in the way that fundamental reforms and key transitions aim at impacting whole BiH population, all citizens, but at the same time, it should carefully pay attention to the most vulnerable. This means that more structured approach is needed to identify more precisely groups under the risks to be omitted from changes. Instead on focusing on broad potentially vulnerable groups unselectively, such as children, youth, women, the structured approach should more precisely identify which sub-groups are under specific risks related to specific interventions. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  |  |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by: OHCHR |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 2.1 | Prepare a Country Analysis that includes an LNOB analysis, ensuring that the most vulnerable populations are accurately identified, particularly those at risk of being left behind |  | Q4 2024 – Q1 2025 | RCO/ PMT/ OHCHR |  | Ongoing as expected | March | 2025 |
| 2.2 | Integrate human rights standards in the design of UNSDCF, ensuring the LNOB principle is embedded across all outcomes and indicators. |  | Q1 2025 | OHCHR/RCO CF Design Team/ UNCT |  | Ongoing as expected | April | 2025 |
| Recommendation 3: Consistently mainstream gender equality in the next UNSDCF, investing efforts in halting and reversing gender equality backsliding. Having in mind the deteriorating situation regarding gender equality and women’s rights, the next UNSDCF has to pay particular attention to GEWE and use its collective authority to counter the gender backsliding instigated by raising anti-gender movements, which in certain cases became institutional. With this aim, the next UNSDCF can take different approaches. One is to have twin track approach, designing stand-alone outcome that would focus mainly on countering backlash, raising awareness, advocacy, protection and strengthening human rights defenders and women’s rights activists, while at the same time, mainstreaming gender in other outcome areas such as green transition, digitalization, economic development, good governance, etc. In case there is no readiness to include stand-alone GEWE in the next UNSDCF, the gender should be more mainstreamed in the outcome areas dedicated to combating hate speech, improving social cohesion and it should involve more UNCT – wide interventions than to rely on one or couple of agencies. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  |  |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by: UN Women |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 3.1 | Ensure gender equality and the empowerment of women are visibly mainstreamed across all outcome areas of the UNSDCF, with a focus on SDG priorities, including SDG 5. |  | Q1 2025 | UNCT/ PMT |  | Ongoing as expected | March | 2025 |
| 3.2 | Ensure that more than half of the UNSDCF outcome and output indicators measure progress on gender equality and the empowerment of women, in line with SDG targets, including SDG 5. |  | Q2 2025 | UNCT/ PMT |  | Ongoing as expected | June | 2025 |
| 3.3 | Conduct an internal survey to assess personnel perception of the organizational environment for promoting gender equality, aiming for a positive rating of over 80% to ensure the organizational culture supports gender equality. |  | Annually | UN Women |  | Ongoing as expected | December |  |
| Recommendation 4: Strengthening Inter-Agency Collaboration and the Role of the RC To address the challenges of agency competition within the UN system in Bosnia and Herzegovina, implementing formal incentives that promote inter-agency collaboration is crucial. This could involve shared funding mechanisms, joint accountability measures, and recognition programs for successful collaborative efforts. Enhancing the authority of the Resident Coordinator can also ensure more cohesive efforts across agencies, reducing competition and fostering joint programming. In that respect the experiences and lessons learned from Gender Equality Accelerator should be considered. Strengthening the RC’s role and formalizing collaboration mechanisms will help increase the UN's collective impact. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | n/a |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RC |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 4.1 | Reform inter-agency coordination mechanisms to reduce competition and fragmentation by creating shared funding mechanisms, joint accountability measures, and recognition programs for successful collaborative efforts. |  | Q2 2025 | UNCT/ RCO |  | Ongoing as expected | June | 2025 |
| 4.2 | Enhance joint programming by establishing clear, inclusive guidance from the outset of program design to ensure that all relevant agencies participate in the design of interventions and that they are aligned with the CF priorities. |  | Q2 2025 | UNCT/ RCO |  | Ongoing as expected | June | 2025 |
| 4.3 | Develop and implement a streamlined decision-making framework to enable the RC to prioritize and support the UNCT effectively, ensuring quick and efficient strategic decisions while fostering an environment of trust and accountability across the UN system. |  | Q3 2025 | UNCT/ RCO |  | Ongoing as expected | September | 2025 |
| Recommendation 5: Increase the inclusiveness of the UNSDCF development process Increase the inclusiveness of the UNSDCF development process (by sharing and seeking feedback/inputs from all stakeholder categories, making adequate space for the voice of the civil society and the private sector) in order to strengthen the relevance and ownership of the CF. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | n/a |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RC |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 5.1 | Conduct broad and inclusive consultations with all relevant stakeholders, including government authorities, CSOs, academia, the private sector, and youth, with a particular focus on engaging marginalized groups and fostering ownership among stakeholders to ensure their active participation in the UNSDCF development process. |  | Q1 2025 | RCO/PMT |  | Ongoing as expected | April | 2025 |
| Recommendation 6: Build a unified, uniform reporting format, using an upgraded version of UNINFO On the basis of the conclusion that different reporting formats between UN agencies and the RCO are creating an additional burden to agencies, it is recommended for UNINFO to establish a unified reporting format, aligned to the extent possible to internal agency format(s). Upgrade UNINFO so that the data inform progress towards UNSDCF output-level target indicators as well as revised outcome-level indicators. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Rejected |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | The UNINFO system is built and administered at the global level by DCO. While the UNCT fully agrees that alignment with individual agency formats/systems is needed and was initially planned in the development of UNINFO, this has not yet been implemented due to technical challenges, as explained by DCO. Although the RCO actively works with the DCO to improve the system and provides feedback from the UNCT, the recommendation to create a unified reporting format within UNINFO is not within the responsibility of the UNCT or RCO. This is a matter that needs to be addressed by DCO at the global level, as UNINFO is managed centrally and requires significant technical adjustments beyond the scope of the country team’s responsibilities. |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 6.1 | N/A |  |  |  |  |  |  |  |
| Recommendation 7: Focus efforts to speed up implementation and increase effectiveness in the UNSDCF areas with moderate achievements To effectively accelerate the achievement of current UNSDCF in areas with moderate progress, identify factors hindering progress and invest efforts, including in advocacy work, to enable achievement of results by the end of the CF cycle. Despite substantial investments and activities by UN agencies, some areas still face setbacks due to inadequate normative, policy, or institutional frameworks, lack of institutional capacities for implementation of laws and policies. To overcome these obstacles, the UN should amplify its advocacy efforts. A decisive 'last mile' push is needed to refine and enhance the frameworks that hinders progress, thus unlocking the full potential for impactful changes and ensuring that all planned reforms are not only initiated but brought to fruition for maximum impact. Use resources of relevant Result Groups and Theme Groups to address the hindering issues in more effective ways. This focused action is particularly crucial in sectors demonstrating slower progress, such as economic and employment opportunities, universal and inclusive access to quality health and social protection services, rule of law, gender equality and social cohesion. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | n/a |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RC |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 7.1 | Conduct a comprehensive review to identify barriers in sectors with moderate progress, such as economic opportunities, health, social protection, rule of law, gender equality, and social cohesion. |  | Q4 2025 | PMT |  | Ongoing as expected | January | 2026 |
| 7.2 | Develop and amplify advocacy efforts to address policy gaps, institutional capacity, and implementation challenges in sectors facing setbacks, engaging government stakeholders, donors, and civil society to ensure the necessary reforms are implemented and institutionalized. |  | Q2 2026 | PMT/ UNCG |  | Ongoing as expected | June | 2026 |
| 7.3 | Develop a resource mobilization strategy focused on ensuring adequate funding and support for sectors with slower progress, particularly those related to health, social protection, gender equality, and economic opportunities, by engaging donors, leveraging partnerships, and aligning resources with identified needs and priorities. |  | Q4 2025 | PMT |  | Ongoing as expected | January | 2026 |
| Recommendation 8: Elevate the UNSDCF’s communication strategy for more ONE UN data-based visibility and impactful advocacy based on UN Info presentation of results, making annual reports more results than activity-oriented Elevate the UN communication strategy by including output and outcome-level results-based information for more evidence-based communication messages that conveys the concrete results of the UN altogether, to the public, to donors and to institutions, underlining the contribution of the UN to SDG, and the contribution of institutions, respectively. Improve annual result reports by presenting more achievement of results than activities. |  |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  |  | n/a |  |  |  |  |  |
| Key action(s) |  |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RC |  |  |  |
|  |  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 8.1 | Organize RBM training for PMT members to improve reporting on contributions to outcome-level changes, focusing on results rather than activities. |  | Every 2 years |  |  | Ongoing as expected | January |  |
| 8.2 | Organize capacity building for UNINFO reporting to ensure accurate and high-quality data, particularly in terms of SDG contributions, reporting against indicators, showcasing all geographical locations of interventions, and including implementing and contributing partners to better demonstrate results. |  | Annually | RCO |  | Ongoing as expected | December |  |
| 8.3 | Develop a communications strategy for the CF, in line with annual reporting processes, ensuring the presentation of output and outcome-level results and effectively communicating the UN’s contributions to SDGs to donors, institutions, and the public. |  | Q4 2025 | UNICEF/ UNCG |  | Ongoing as expected | January | 2026 |

| Recommendation 9: Further Improve Monitoring and Indicator Framework for Effectiveness and Accountability To streamline the next Indicators Framework, it should focus on fewer, more targeted indicators. These indicators should align with the SDG Framework for BiH and Growth Plan, UN agencies' monitoring frameworks, and, wherever possible, use domesticated SDG indicators. It’s essential to ensure these indicators are tightly linked to official statistics, with clearly established baselines and consistency with agency-level reporting. The framework should prioritize indicators that are realistic, achievable, and directly connected to tangible outcomes. Further, output level indicators should be more coherent and better linked with outcome level indicators, enabling not only the measurement of results achieved at output levels but also contribution of these results to the higher-level changes in line with the ToC. This way it would be possible to more realistically measure achievements and UN contribution and better plan future interventions. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  | n/a |  |  |  |  |  |
| Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT |  |  |  |
|  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 9.1 | Develop the outcome indicators framework for the next UNSDCF to focus on a smaller set of more targeted indicators that align with the SDG Framework and Growth Plan, ensuring these indicators are linked to official statistics, with clear baselines and achievable targets. | Q1 2025 | PMT |  | Ongoing as expected | April | 2025 |
| 9.2 | Ensure output-level indicators are coherent, directly linked to outcome-level indicators, and consistent with UN agency-level reporting, enabling the measurement of results at the output level and assessing how these results contribute to higher-level changes in alignment with the theory of change. | Q2 2025 | PMT |  | Ongoing as expected | September | 2025 |
| Recommendation 10: Increase coherence through effective resource mobilization A resource mobilisation effort is effective when it is fully coherent, deriving and supportive of the UNSDCF. More than just a framework, the UNSDCF needs a Resource Mobilisation Strategy that derives from the UNSDCF identified outcomes and output priorities and that is logically developed right after the UNSDCF is formulated, as an annex to the key UN strategic document. Such a document will provide strong evidence for donor of UN agencies’ intention to approach donors as ONE coherent UN. It will also provide clarity about UN’s fundraising strategic priorities and underline the fact that fundraising efforts are supporting the UNDSCF priorities before single UN agencies priorities. |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  | n/a |  |  |  |  |  |
| Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT |  |  |  |
|  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 10.1 | Conduct a mapping of potential donors, strategic partners, and financing sources, including the EU, bilateral donors, foundations, and other non-traditional funding channels, to align resource mobilization efforts with UNSDCF priorities. | Q4 2025 | RCO/ UNCT |  | Ongoing as expected | January | 2026 |
| 10.2 | Develop a Resource Mobilisation Strategy that aligns with the UNSDCF’s identified outcomes and output priorities, ensuring that fundraising efforts are coherent, and strategic, and fully support UNSDCF priorities over individual agency goals. | Q4 2025 | PMT |  | Ongoing as expected | January | 2026 |
| Recommendation 11: Plan and implement longer-term, synergetic interventions As evaluation demonstrated, the impact is stronger when there is continuity in implemented projects allowing for local stakeholders to learn, increase capacities, and take ownership over proposed solutions/models. Plan and implement interventions that mutually reinforce changes, such as through coordinated education and employment interventions, social protection and employment, education and digitalization, etc. Also, identify critical geographical areas that can be used as epicenters of changes from which the changes can further expand to other geographical areas and focus interventions on such communities by implementing joint programming, interlinked changes that have potential to generate stronger and wider impact. |  |  |  |  |  |  |  |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  | n/a |  |  |  |  |  |
| Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT |  |  |  |
|  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 11.1 | Identify critical geographical areas that can serve as epicentres of change, and concentrate interventions in those areas to create synergistic impacts that can later be expanded to other regions. | Annually | UNCT |  | Ongoing as expected | January |  |
| 11.2 | Plan and implement long-term, synergistic interventions and joint programmes that mutually reinforce changes across various sectors, such as education and employment, social protection and employment, and education and digitalization, with a focus on collaborative design, targeted implementation in identified areas, and effective cross-sectoral coordination, to build local capacity for sustained change and ensure direct involvement of stakeholders in achieving shared development goals. | Annually | UNCT |  | Ongoing as expected | January |  |

| Recommendation 12: Continue to invest in capacity building of governmental institutions Investing in the capacity building of governmental institutions and local partners is crucial for the successful implementation of development initiatives creating space for stronger impact. Providing technical assistance, training, and resources will improve their operational and managerial capacities, making them more effective in sustaining development efforts. This is particularly important in the areas related to major transitions, such as green just transition, digitalization, education, but also in area of human rights and gender equality as major cross-cutting aspects of transformations. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Management response - Accepted/Partially Accepted/rejected: |  |  |  |  | Accepted |  |  |
| If rejected or partially accepted, please provide an explanation: |  | n/a |  |  |  |  |  |
| Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by UNCT |  |  |  |
|  |  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring |
| 12.1 | Develop tailored capacity-building programmes targeting key areas such as green transition, digitalization, education, and human rights and gender equality, focusing on equipping government institutions with the tools necessary to support transformational changes and ensure the sustainability of new norms and practices. | Annually | UNCT |  | Ongoing as expected | January |  |