## Armenia CF Management Response
Armenia: CF 2021 - 2025 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: Final Evaluation of 2021-2025 UNSDCF for Armenia / 2025 • Preparation of the management response: RCO, UN Armenia Monitoring and Evaluation Group, UNCT • Approval of the management response: UNCT • Follow-up monitoring and updating of the management response’s implementation: RCO, UN Armenia Monitoring and Evaluation Group • Frequency of monitoring and updating: Semi-Annual
Overarching Recommendation
The next cycle of the UNSDCF should focus on improving the United Nations’ ability to adapt quickly to changing circumstances (‘agility’), enhancing coordination and coherence among agencies, and ensuring that its interventions are responsive, integrated and aligned with Armenia’s evolving development needs, including preparedness for potential shocks. This overarching recommendation provides the foundation for the detailed recommendations that follow, aiming to operationalize these principles to enable the United Nations to adapt to changing conditions, foster cross-agency collaboration, and deliver meaningful results that support the country's long-term development priorities.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Recommendation 1: The next UNSDCF should build on the inclusive planning process of 2020 by ensuring even deeper engagement with diverse stakeholders, and by incorporating lessons learned from the previous cycle to further enhance strategic alignment and responsiveness to evolving development needs. The next UNSDCF should aim to enhance the United Nations’ agility and coherence to deliver more responsive and effective results, aligned with country's evolving development context. This can be achieved by: a) deepening the involvement of national stakeholders and development partners, b) streamlining outcome areas, and c) refining coordination structures.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Deepen the involvement of national stakeholders and development partners: Align UNSDCF implementation with key national strategies and commitments. Hold multistakeholder consultations, including with underrepresented groups (e.g., women’s organizations, youth, persons with disabilities) as part of the CCA and UNSDCF design and reviews. | 2025: CCA and CF design completed 2026–2030: Consultations as part of annual reviews | UN RCO (Lead: RC and Head of Office), UNSDCF RG Chairs, Government counterparts (DPM Office, MFA, Line Ministries) |  | completed | December | 2025
1.2 | Streamline outcome areas: Cluster outcome areas effectively. Integrate cross-cutting issues (gender, LNOB, etc.) within all relevant strategic outcomes. | 2025-2026: Coordination structure established, cross-cutting markers integrated in JWPs |  |  |  | December | 2026
1.3 | Refine coordination structures: Simplify the coordination structure from three tiers to two: the JSC and Results Groups (RGs), co-led by UN agency heads and government counterparts. Set up cross-cutting coordination mechanisms—such as an LNOB group and revitalized gender thematic group—to strengthen the UNCT’s normative work. | 2026–2030: Annual Monitoring & Reporting
Recommendation 2: Foster coordination and flexibility to respond to emerging needs and priorities. To improve the United Nations’ capacity to respond to unforeseen challenges and emergencies, the next UNSDCF should integrate a more systemic approach that links development, humanitarian and peacebuilding efforts. This should include the following: a) Fostering sustainable resource mobilization, b) Risk mitigation, c) Contingency planning, d) Strengthening the Humanitarian-Development-Peace Nexus, e) Simplify administrative and procedural requirements.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Partially accepted
If rejected or partially accepted, please provide an explanation: …… |  | All recommendations are accpeted except for sub-recommendation c (Simplify administrative and procedural requirements). The UNCT will address this as part of the UNCT contingency plan and through agency specific protocols.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Foster resource mobilization: (included under partnerships below). | 2025: Strategy finalized 2026–2030: Annual donor roundtables & resource mapping 2026–2030: Annual financial risk reviews | UN RCO (Lead: RCO Partnerships Officer), UNCT, agency partnership officers, RG chairs |  |  | December | 2026
2.2 | Risk mitigation in financial planning: (included under partnerships below).
2.3 | Contingency planning: Incorporate lessons learnt from previous inter-agency emergency responses and regularly update the UNCT contingency plan to strengthen emergency preparedness. | 2025: Contingency plan updated with lessons learnt. 2026–2030: Annual simulations & reviews | UN RCO (Lead: RC, Head of Office and Livelihoods coordination Officer), UNCT
2.4 | Strengthen the HDP Nexus: Strengthen collaboration between humanitarian, development, and peace actors through joint analysis and action. Ensure prevention and disaster risk reduction are integrated into relevant sectors.
Recommendation 3: Develop a unified partnership strategy The next Cooperation Framework should include an elaborated strategy that clearly outlines how the United Nations will engage with various stakeholders, including international financial institutions (e.g. World Bank, International Monetary Fund), bilateral donors, civil society organizations and the private sector.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Develop a UNCT Partnership and Resource Mobilization Strategy. Set clear objectives for each partner type- IFIs, donors, CSOs, private sector Define measurable goals and indicators to track financial and non-financial contributions, including technical support and capacity-building. Strengthen communication to showcase partnership successes. | 2025: Strategy design & consultations completed, risk framework integrated 2026–2030: Annual monitoring and & partnership reviews | UN RCO (Lead: RCO Partnerships Officer), UNCT, agency partnership officers |  |  | December | 2026
3.2 | Hold regular dialogues with private sector and government partners to explore joint funding opportunities.
3.3 | Incorporate risk assessments into annual financial planning.
3.4 | Expand pooled funding mechanisms and joint programming.
Recommendation 4: Strengthen conflict sensitivity in strategic engagement The United Nations should more systematically integrate conflict sensitivity into its development and humanitarian programming. This would entail conducting targeted conflict analyses to tailor interventions that address key challenges while safeguarding its role as a neutral and trusted partner. Leveraging existing mechanisms such as the Peacebuilding Fund can support efforts in dialogue, trust-building and capacity strengthening where appropriate. The Resident Coordinator’s leadership will be key in ensuring that these efforts are coherent, contextually appropriate, and aligned with the country's development and humanitarian needs while advancing the United Nations’ commitment to leaving no one behind and protecting the rights of the most vulnerable.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Integrate conflict analysis into the CCA and UNSDCF design and reviews to ensure programming is sensitive to conflict dynamics and include solid prevention mechanisms. | 2025: Hate Speech Action Plan developed 2026–2027: PBF and/or other peacebuilding funding mobilized | UN RCO (Lead: Head of Office, Partnerships Officer and PDA), CF RG Chairs |  |  | December | 2026
4.2 | Use funding tools like the Peacebuilding Fund (PBF) to support dialogue, trust-building, capacity development and prevention, where appropriate.
4.3 | Mainstream conflict sensitivity across programming by making conflict analysis part of project design.
4.4 | Offer training on conflict sensitivity and Do No Harm principles for UN staff and implementing partners at least once in the CF cycle.
4.5 | Link peace dividends to broader development goals through RC public engagements, knowledge products, and UNCT initiatives.
4.6 | Strengthen UN work on hate speech, as linked to conflict prevention, through the development of a UNCT Action Plan on Hate Speech and carry out activities related to hate speech (capacity development and awareness raising among staff, stakeholders and the general public, strengthen hate speech monitoring and response, develop key messages for UNCT and address root causes such as discrimination).
Recommendation 5: The next UNSDCF should include a strong and comprehensive monitoring and evaluation framework To promote sustainable and adaptive programming, the next UNSDCF should focus on enhancing monitoring and evaluation (M&E) mechanisms at the UNSDCF level as a foundation for United Nations agency specific processes, focusing on clear, actionable key performance indicators. The M&E group should be empowered to effectively monitor data processes, track progress on UNSDCF outcomes and the SDGs, and demand course corrections as needed throughout the programme cycle. This will enhance accountability and learning, improving the United Nations’ ability to adapt to changing contexts. The work of the joint working groups (mentioned in Recommendation 1 above) will also help boost the M&E approaches, learning and accountability.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Develop M&E framework under the next UNSDCF to ensure collaborative monitoring, reporting, and evaluation. | 2026: M&E framework finalized; co-leads and focal points (re)nominated 2026–2030: Annual extended M&E Group meetings with ArmStat & stakeholders | UN RCO (Lead: Data and Results Management Officer), UN Inter-Agency M&E Group, ArmStat and other national data stakeholders1 |  |  | December | 2026
5.2 | Co-lead the M&E Group through the RCO and a UN agency with strong M&E expertise to promote shared ownership.
5.3 | Task M&E Group to develop guidance and tools for learning processes—such as annual reviews. M&E group to nominate focal points to RGs to ensure consistent M&E support.
5.4 | Provide capacity-building opportunities for M&E Group members, especially those without formal M&E expertise.
5.5 | Hold at least annual extended M&E Group meeting—bringing together Armstat, UN agency focal points, and key national data stakeholders (e.g., ArmStat)—around SDG data and national monitoring system strengthening.
5.6 | Support key national data stakeholders (e.g., ArmStat) in addressing SDG data gaps.
Recommendation 6: The United Nations should advance a cohesive, cross-sectoral capacity-building strategy. It should focus on promoting local ownership, continually shifting away from capacity substitution towards capacity building, and enabling institutions to independently lead and sustain reforms in alignment with national priorities. To ensure effectiveness and sustainability of its interventions, the United Nations should prioritize aligning capacity-building efforts with national strategies, fostering long-term institutional resilience. This requires a more decisive shift from capacity substitution to genuine capacity building, transitioning the United Nations’ role from direct implementation to empowering local institutions to take full ownership of reforms.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Develop a UNCT-wide capacity-building strategy that maps institutional needs across sectors and includes an M&E framework to track progress. | 2025-2026: Strategy designed & endorsed by UNCT & Government 2026–2027: Capacity-building and M&E framework operationalized; national needs mapped 2028–2029: Annual reporting on capacity-building results; sustainability plans integrated 2030: Evaluation of capacity-building impact | UN RCO (Lead head of Office), UNSDCF RG Chairs, Capacity-Building Thematic Group (if established), Government focal point |  |  | December | 2026
6.2 | Ensure that the technical expertise is of high quality: - Ensure all technical assistance and skills transfer is tailored to partner institutions’ needs, with national actors setting the agenda. - Systematically measure the results of all capacity-strengthening efforts. Use the findings to inform adjustments and enhance impact over time.
6.3 | Include sustainability and exit strategies in all UN-supported interventions.
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSS-CUTTING ISSUES
Recommendation 7: Apply a gender, disability and human rights lens across throughout programming and policy interventions The UNSDCF has made significant strides in embedding gender, human rights and equity considerations, which should be further strengthened across all programmes and reform interventions. Future efforts could include: 1. Expanding gender-responsive and inclusive programming and budgeting to support the Government to advance mechanisms that not only prioritize gender equality but also address the specific needs of marginalized groups such as persons with disabilities, through targeted resource allocation. 2. More consistently incorporating a gender lens, disability inclusion and human rights-based approaches into monitoring and evaluation systems by embedding indicators that track progress on equality and inclusion. Ensure that these frameworks capture intersectional dimensions of marginalization, providing actionable insights to drive accountability and improve outcomes for women, persons with disabilities and other marginalized groups.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by RCO, M&E Group
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Expand gender-responsive and inclusive programming and budgeting: - Agree on targeted resource allocation within UNSDCF to address the needs of marginalized groups, including women, persons with disabilities, older persons, and other groups. - Track LNOB and related markers (e.g. gender marker, HR marker) using UNINFO and integrate this tracking into regular CF reviews. - Where needed, ensure capacity building for UN staff, including staff with M&E functions, on normative topics, and the use of UN tools, such as LNOB and other markers. - Support the Government in strengthening gender-responsive and disability-inclusive budgeting as part of broader capacity-building efforts (referenced in Recommendation 6). | 2025: UNINFO tracking mechanisms operationalized 2026–2030: Annual tracking & integration into CF reviews | UN RCO (Lead: Gender & LNOB Focal Point, Data and Results Management Officer), Gender Theme Group (GTG), LNOB Group, UN Women, UNFPA, CF RG chairs Results Groups, MoF (for gender budgeting), ArmStat (for disaggregated data). |  |  | December | 2026
7.2 | Strengthen integration of gender, disability, and human rights: - Include gender, disability, and human rights-sensitive indicators into the UNSDCF results framework and agency M&E systems. - Work with the M&E Group, LNOB Group, GTG and RGs, to strengthen national data systems, especially in areas lacking (disaggregated) data. - Support national partners to strengthen data collection, analysis, and use. - Strengthen collaboration with civil society organizations, including LGBTQI+ groups, to leverage their specialized knowledge and community-based data collection efforts, particularly in areas with under-reporting, ensuring that this data complements and enriches official statistics for CF monitoring and reporting.

## Sheet2 (hidden)
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030