## Sheet1
Country ERITREA : UNSDCF 2022-2026 EVALUATION MANAGEMENT RESPONSE
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1: Deepen National Ownership and Institutionalization of Cooperation Framework Priorities.
Management response - Accepted/Partially Accepted/rejected : The UNCT fully accepts this recommendation. The evaluation confirms that strong government ownership was the single most important enabler of results in the 2022–2026 cycle. In the next CF, the UNCT will ensure that CF priorities are directly derived from and aligned with Eritrea's National Development Plan and sector strategies, and that Joint Work Plans serve as the primary operational instruments for translating those priorities into action. Government institutions will progressively take the lead in coordination, monitoring, and reporting throughout the 2027–2031 cycle. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Integrate national development priorities, including the National Development Plan, into the CF 2027–2031, ensuring UNSDCF outcomes are fully aligned with and derived from national priorities. | Next CF | RCO,PMT, MoFND |  |  | December | 2026
1.2 | Joint Work Plans will be redesigned as rolling plans with a minimum three-year horizon, aligned with national planning cycles and updated annually only as required. This addresses the current model in which annual renegotiation consumes an estimated half of the implementation period, reducing delivery efficiency. Multi-year JWPs will provide greater predictability, implementation continuity, and lower transaction costs for both Government and UN entities while remaining the primary operational instrument for delivery of UNSDCF priorities. | Next CF | RCO,PMT, MoFND |  |  | December | 2026
…
Recommendation 2: Strengthen the Leave No One Behind (LNOB) Agenda with Dedicated, Resourced Programmes
Management response - The UNCT fully accepts this recommendation. The evaluation identifies gender inequality as a major systemic weakness that continues to constrain progress across multiple development outcomes, particularly for women and girls facing intersecting forms of exclusion. In the 2027–2031 CF, gender equality will be treated as a core accelerator integrated across all outcomes, alongside dedicated LNOB interventions for persons with disabilities, remote rural communities, climate-affected households, and other populations at risk of being left behind. This approach will be informed by disaggregated data from EPHS-2025 and reflected in programme design, budgeting, monitoring, and accountability mechanisms. This will also be tracked through the UNCT Gender Equality Marker and backed by expanded social protection coverage. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.1 | Design targeted programme outputs for women, youth, persons with disabilities, and climate-affected communities in the 2027–2031 CF results framework, with dedicated budget allocations in multi-year JWPs. Gender equality will be integrated across all outcomes and treated as a strategic accelerator of progress in health, education, livelihoods, food systems, climate resilience, and governance rather than as a stand-alone thematic area. | 2027-2031 | RCO,PMT, MoFND |  |  | December | 2027
2.2 | Continue to support Government to invest in disaggregated data systems (by sex, age, disability, and location) using EPHS-2025 as the baseline, and expand social protection measures to cushion vulnerable groups from climate and economic shocks | 2027-2031 | RCO,PMT, MoFND |  |  | December | 2027
2.3 | Institutionalize LNOB and gender-responsive programming standards across all UNSDCF outcomes, supported by measurable indicators, disaggregated data, and annual performance reviews. Monitoring frameworks will track both inclusion outcomes and the extent to which gender-related barriers are addressed across sectors. | 2027-2031 | RCO,PMT, MoFND |  |  | December | 2027
Recommendation 3: Scale Up Integrated and Multi-Sectoral Approaches
Management response -The UNCT fully accepts this recommendation. The evaluation and Government consultations point to the need for an integrated development planning approach that moves beyond isolated joint programmes toward geographically coordinated, multi-sector interventions delivering convergent results at community level. Past constraints included sectoral silos, limited spatial planning, fragmented implementation arrangements, and insufficient convergence of interventions within the same localities. The next CF will prioritize integrated area-based programming that aligns investments across sectors, agencies, and government institutions within shared geographic priorities. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
3.1 | Develop integrated area-based programmes in priority geographic locations that combine interventions across food systems, health, WASH, education, livelihoods, energy, and climate resilience under a single results framework. Building on lessons from previous joint initiatives, the focus will shift from standalone sector programmes to coordinated interventions planned, implemented, and monitored jointly at community level through shared geographic targeting and delivery platforms. | Q1–Q2 2027 | All UNCT Agencies, RCO |  |  | June | 2027
3.2 | Establish a geographical planning and coordination mechanism to map agency investments, identify convergence opportunities, and sequence interventions within the same communities. Joint planning will prioritize integrated delivery and community-level results rather than parallel implementation of sector-specific projects. | Q1–Q2 2027 | All UNCT Agencies, RCO
RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 4: Embed Resilience and Climate Adaptation Across All Outcomes
Management response - The UNCT fully accepts this recommendation. Eritrea's vulnerability to climate shocks including desertification, erratic rainfall, and regional instability, makes climate resilience an imperative programming principle. The evaluation confirms that resilience-focused interventions (solar-powered water systems, climate-smart agriculture, dam construction) proved most impactful and sustainable. The next CF will explicitly incorporate climate and disaster risk component in all outcome areas, with system-wide application of crisis-sensitive programming standards and early warning systems. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
4.1 | Embed resilience and climate adaptation across the UNSDCF reasults areas by integrating climate risk analysis and early warning into outcomes, JWPs, and development–emergency preparedness linkages. | 2027–2031 | UNCT, PMT |  |  | December | 2028
4.2 | Ensure climate resilience and adaption considerations across interventions as well as targetted intervention to scale up resilience-building, adaptation measures, anticipatory action, underpinning longer term sustainability. | 2027–2031 | UNCT, PMT
Recommendation 5: Expand Partnerships and Diversify Resource Mobilization
Management response - The UNCT partially reframes this recommendation. While financing constraints affected implementation, the evaluation also highlights that a major challenge was the limited delivery of available resources, with implementation rates frequently reaching only 50–60 per cent of planned expenditures. In the next Cooperation Framework, the UNCT will therefore pursue a more comprehensive approach to resource mobilisation and financing. This will include improving absorptive capacity by addressing implementation bottlenecks, streamlining approval and delivery processes, and increasing programmatic efficiency; supporting a strategic shift from a traditional funding perspective to a broader financing approach that leverages a more diversified range of financing sources aligned with national priorities and UN comparative advantages; and strengthening partnerships that can unlock additional development financing opportunities. The UNCT will continue engagement with development financing institutions, including through South-South cooperation and, where appropriate, institutions such as AfDB, while ensuring that efforts to mobilise additional resources are accompanied by stronger delivery systems and improved utilisation of available resources.. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
5.1 | Undertake a joint Government–UNCT review of implementation bottlenecks, expenditure performance, and absorptive capacity across the UNSDCF portfolio, and agree corrective measures to improve delivery rates and utilization of existing resources. Resource planning for the next CF will prioritize implementation efficiency and realistic delivery targets. | 2027 | UNCT,MoFND |  |  | December | 2027
5.2 | Improve the quality and readiness of programme pipelines so that financing efforts are linked to demonstrable implementation capacity, results delivery, and government ownership. | 2027 | UNCT,MoFND |  |  | December | 2027
5.3 | Diversify financing by developing a targeted financing and partnership map for the 2027–2031 CF, focused on funding windows realistically accessible to Eritrea: vertical funds (especially climate finance), innovative and blended finance (e.g., small de-risking grants), Multilateral Development Bank financing (e.g., AfDB/regional grants and concessional finance), pooled UN funds, private sector finance mechanisms (e.g., PPPs and FDI), and South-South cooperation, alongside select technical partnerships subject to Government consultation and approval. Use the map to focus coordinated UNCT engagement on a limited set of priority opportunities suited to Eritrea's operating context, without assuming broad traditional donor re-engagement. | 2027 | UNCT,MoFND
Recommendation 6: Invest in Data, Monitoring, and Accountability Systems
Management response - The UNCT fully accepts this recommendation. The evaluation identifies weak M&E systems and data gaps as a foundational constraint that limited the UNCT's ability to track equity outcomes, demonstrate attribution, and course-correct during implementation. The absence of disability-disaggregated data and the incomplete operationalization of results-based management are particularly noted. The UNCT will invest in data and accountability systems as a core priority throughout the 2027–2031 cycle, and will build a clear pathway toward nationally-led M&E by the cycle's end. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
6.1 | Strengthen UNSDCF Results & Resources Framework with clearer outcome-level indicators | 2027 | PMT, MoFND |  |  | December | 2027
6.2 | Strengthen data‑driven decision‑making by operationalizing EPHS 2025 data and embedding evidence‑based reviews in Joint Performance Review Meetings. | 2027 | PMT, MoFND |  |  | December | 2027
6.3 | Continue to support national systems that produce disaggregated data (sex, age, disability, geography) to track equity-focused results | 2027 | PMT, MoFND |  |  | December | 2027
6.4 | Explore joint interventions and collaborations across sectors, stakeholders, and entitites to strengthen data collection, information management and analysis, for cost-effective solutions that will underpin results-based management, monitoring and reporting for results. | 2027 | PMT, MoFND
6.5 | Strengthen joint review mechanisms (e.g., joint annual reviews, CF results groups) where national counterparts co-lead monitoring, not just consult on it. | 2027 | PMT, MoFND |  |  | December | 2027
Recommendation 7: Advance Gender Equality and Human Capital Development
Management response - The UNCT fully accepts this recommendation. While gains in FGM abandonment, girls’ education, maternal health, and women’s wellbeing will be sustained, the next CF will position gender equality as a system-wide transformation lever for accelerating SDG progress. Programming will focus on increasing women’s economic participation, strengthening institutional inclusion and leadership, expanding access to productive assets and services, and integrating gender-responsive approaches across agriculture, energy, livelihoods, health, education, and climate resilience. Human capital development and gender equality will be pursued as mutually reinforcing strategic priorities. The scope of gender programming will further expand to include women's economic rights and financial inclusion, including by building on existing priorities such as early childhood development and investment in care infrastructure, GBV prevention and response, and youth employment pathways and digital skills. Gender equality will be positioned as a strategic priority in its own right, and not solely as an enabler of other development results and resources will be tracked for their impact on all, supported by the UNCT Gender Equality Marker. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
7.1 | Consolidate gains in FGM reduction, maternal health, and girls’ education while advancing gender equality as a system-wide accelerator of development outcomes. The 2027–2031 CF will include measurable actions to increase women’s economic participation, strengthen institutional inclusion and leadership, improve access to productive resources, and integrate gender-responsive approaches across agriculture, energy, livelihoods, climate resilience, health, and education. Strategic pathways for greater impact on women's rights through existing priorities will be sought - for example in connecting investment in early childhood development with women's labor force participation. | 2027 | UNCT |  |  | December | 2027
7.2 | Expand youth-focused, market-linked skills programmes to translate human capital gains into employment and economic participation with sex-disaggregated targets and dedicated outputs in the 2027–2031 CF results framework | 2027 | UNCT |  |  | December | 2027

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030