## Sheet1
Country _____Sierra Leone_________; UNDAF / CF 2020 - 2024 EVALUATION MANAGEMENT RESPONSE
Evaluation Title/Year: -EVALUATION OF THE UNITED NATIONS SUSTAINABLE DEVELOPMENT COOPERATION FRAMEWORK (UNSDCF) 2020-2024 END OF CYCLE, SIERRA LEONE-------------------------------------------- / 2023 • Preparation of the management response: UNCT and Evaluation Steering Committee • Approval of the management response: UNCT and the Joint Steering Committee • Follow-up monitoring and updating of the management response’s implementation: -M&E Group and RCO---------------------- • Frequency of monitoring and updating: Semi-Annual
RECOMMENDATIONS TO IMPROVE FORMULATION AND GOVERNANCE OF THE NEW CF
Recommendation 1) In the next CF, strengthen the integration of the following aspects within the document and then, ensure sufficient funding and implement the aligned activities:  Climate Change  Youth unemployment  Fiscal space (i.e., ensure enhanced GoSL’ revenue mobilization and fiscal management capacities)  Mental health/drug use  The Blue Economy  Digital inclusion In addition, it is also recommended to mainstream the concept of adaptation within the relevant components of the next CF, as a lesson learned from the pandemic.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Inclusion of institutions whose mandate relates to climate change, mental health, blue economy, digitalization, youth employment and fiscal management in the national consultation for the CF design. | 7th February 2024 | RCO,PMT |  | completed | June | 2024
1.2 | Inclusion of Climate change, mental health, blue economy, digitalization, youth unemployment and fiscal management into the result framework of the new CF | 30th May 2024 | RCO,UNDP,FAO, UNIDO,UNOPS,IOM, IFAD |  | ongoing as expected | December | 2024
…
Recommendation 2) Accentuate more effective and efficient collaboration and communication with key stakeholders, especially the private sector, mainly after the initial consultations of the design phase of the CF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Collaborate with stakeholders, especially the private sector in popularising the new CF | 2024-12-30 | RCO, UNDP, UNICEF, UNFPA, UNIDO, IOM |  | ongoing as expected | June | 2025
1.2
…
Recommendation3) The indicators in the Results Matrix should be made SMART i.e. Specific, Measurable, Achievable, Relevant, Timely with strengthen harmonization with Agency M&E frameworks to ensure they are effectively and efficiently used for decision-making purposes.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Develop SMART indicators for the next CF | 2024-05-31 | UNICEF, UNDP, UNFPA, IOM |  | ongoing as expected | December | 2024
Recommendation : 4) The new CF should take centralized data generation, management and harvesting as a flagship programme by strengthening the capacity of the newly established National Monitoring and Evaluation Directorate (NaMED), Statistics Sierra Leone and other government data institutions to contribute to data availability and use for effective decision making. 6) The next CF should increase joint monitoring programmes between the government and the UN, as a complementary exercise to the UN and MoPED SDG platform currently being established.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Develop flagship programmes around data generation by supporting national data institutions | 2025-12-31 | All UN agencies |  | ongoing as expected | June | 2026
1.2 | Conduct a joint monitoring exercise (government and UN) for effective programme monitoring | 2025-12-31 | RCO, All UN Agencies |  | ongoing as expected | June | 2026
1.3
… | RECOMMENDATIONS TO IMPROVE COHERENCE AND COORDINATION OF THE NEW CF
Recommendation 5) The UNCT needs to address the issue of low participation rates and enhance collaboration among agencies. This could involve consolidating overlapping groups or creating mechanisms for sharing information and updates between groups.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | Develop work plan for working Groups | 2025-09-30 | RCO, All Agencies |  | ongoing as expected | December | 2026
1.2 | Commit Agencies to fully participate in working Groups through UNCT resolution. | 2025-04-30 | RCO |  | ongoing as expected | December | 2025
1.3 | Dedicated UNCT meetings on the periodic reporting of activities by working groups. | 2025-12-31 | RCO, All Agencies |  | ongoing as expected | June | 2026
Recommendation 6)The next CF should encourage more joint programmes among UN Agencies through established system for annual joint monitoring that provides UNCTwith up-to-date information on the ongoing status of joint programmes (more than what has been done in the annual reports) to enhance collaboration and transparency.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1 | At least one joint program developed per pillar | 2025-12-31 | RCO ,All Agencies |  | ongoing as expected | June | 2026
1.2 | Integrate joint programmes reporting in the CF monitoring and reporting | 2025-12-31 | RCO,UNCT |  | ongoing as expected | June | 2026
Recommendation 7) The UN Sustainable Development Group platform (UNINFO) should be reviewed and optimized for greater effectiveness and efficiency in M&E by highlighting clear targets (particularly for SDGs), achievements, and narrative documentation for each indicator, at every level, for every year of the UNSDCF.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Rejected
If rejected or partially accepted, please provide an explanation: …… |  | This is a global platform that is operated by DCO, reviewing UNINFO is not withoin the power at country level. UNIFO platform already have narrative for every indicator.
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
1.1
1.2
…
Recommendation 8)The next CF should prioritize the development of flagship programmes, leveraging the RCO's strong convening influence particularly in areas where there is a high degree of national attention, such as nutrition, health, or data collection, as demonstrated by the past success in promoting SDGs.
Management response - Accepted/Partially Accepted/rejected : …….. |  |  |  |  | Accepted
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
| Develop flagship programme on food and nutrition security, health, including drug abuse | 2025-12-31 | All Agencies |  | ongoing as expected | June | 2026
1.2
RECOMMENDATIONS TO IMPROVE SUPPORT FOR TRANSFORMATION CHANGE AND CROSSCUTTING ISSUES
Management response - Accepted/Partially Accepted/rejected : ……..
If rejected or partially accepted, please provide an explanation: ……
Key action(s) |  | Time frame (or deadline) | Responsible agency (ies) / unit(s) | Monitored by …….
|  |  |  | Comments (or action taken) | Status of implementation | Month of monitoring | Year of monitoring
2.2

## Sheet2
cancelled | June | 2022 | Rejected
delayed | December | 2023 | Partially accepted
ongoing as expected |  | 2024 | Accepted
completed |  | 2025
2026
2027
2028
2029
2030